Source:	Ericsson LM

Title:	On the status of the BASOP conversion

Document for:	Discussion and Agreement

Agenda Item:	1.5

## Introduction

The conversion of the IVAS floating point code to BASOP code is being done by Ittiam, under a contract issued by ETSI. The organization of this conversion is outlined in [1], which is also attached to the contract. Upon delivery of the code to ETSI, SA4 is expected to verify that the delivery meets the FL-to-FX requirements. The verification relies on objective measurement to cover a large set of operating points within a limited time but needs to be complemented with subjective listening tests. This document presents a time plan for this verification and attempts to summarize the current status.

## Time plan

The time plan is outlined in [2], where the delivery is done in four steps. The first part (D1), comprising the decoder and renderer, was delivered by Ittiam as planned on August 31 [3]. The encoder is scheduled to be delivered in three parts, targeting different input formats. An encoder supporting mono, ISM, stereo and MCT (D2) is to be delivered September 30, followed by an encoder also supporting MASA, SBA and Parametric modes (D3) by October 31. The final delivery, including Combined formats and any remaining operating points (D4) is to be delivered by November 30. To complement the delivery plan a verification time plan is outlined in [4], also illustrated in Figure 1, and in table format in Table 1.

At the start of each delivery D1 through D4, a pre-test phase starts. The pre-testing is a combination of objective testing on new material, selected informal and formal listening, complexity measurement and inspection of the code. Issues that are found during the pre-test period may lead to updates of the code, where the latest code always can be found in the main branch of the BASOP repository [5]. The updates of the code may continue until the end of the pre-test phase, when the code is frozen and a new release is issued in [5].

The subjective test phase starts when the pre-test phase ends. The subjective test of D1 is set to start on October 15, covering the D1 delivery. This phase also includes a summarizing report on delivery D1, which is to be submitted to SA4#130 at the latest on the submission deadline on November 12. The subjective test phase of deliveries D2-D4 starts on January 13th 2025, which also marks the code freeze of these deliveries and the end of the corresponding pre-test phases. This phase runs until February 11th, when the results are to be submitted in a report to SA4#131.

Figure 1: Gant chart of Verification time plan

Table 1: Verification time plan in table format. SA4 milestones in italics, verification milestones in bold.

| Date | Milestone |
| --- | --- |
| 31st August 2024 | - D1: Delivery of IVAS fixed-point Decoder and Renderer by Ittiam to SA4, fulfilling the FL-to-FX requirements |
| 1st September - 15th October | - Pre-testing phase D1: Decoder and Renderer - Testing starts in parallel on all formats. There may be "inter-format impact" from resolved issues. Fixes with wide impact need to be integrated for further testing. - Pre-testing may entail both objective and subjective testing, on a need basis. Objective testing may filter out critical cases to listen to. |
| Audio SWG telco (Sept. 13) | - Review progress of the fixed-point code conversion |
| 30th September 2024 | - D2: Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - Mono (EVS) - ISM (core coder) - Stereo - MCT |
| 1st October - 13th January | - Pre-testing phase D2 Encoder for Mono, ISM, Stereo and MCT |
| Audio SWG telco (Oct. 18) | - Review progress of the fixed-point code conversion |
| 15th October – 12th November | - Subjective test phase of Decoder and renderer - Code freeze Decoder and renderer |
| 31st October 2024 | - D3: Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - MASA - SBA - Parametric modes |
| Audio SWG telco (Nov. 4) | - Review progress of the fixed-point code conversion |
| 1st November - 13th January | - Pre-testing phase D3: encoder for MASA, SBA and Parametric modes |
| 12th November | - SA4#130 submission deadline, test report for Decoder and Renderer uploaded |
| SA4#130 (18th – 22nd November 2024) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements |
| 30th November 2024 | - D4: Delivery of complete IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, including the following operation modes: - Combined formats |
| 1st December - 13th January | - Pre-testing phase D4: Encoder for Combined formats and remaining functionality |
| Audio SWG telco (date TBD) | - Review progress of the fixed-point code conversion |
| TSG SA#106 (10th – 12th December 2024) | - Approval by TSG SA (SA#106) of Delivery of IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements, based on agreement in SA4 |
| 13th January 2025 - 11th February 2025 | - Subjective test phase D2-D4: Encoder - Code freeze of Encoder |
| 11th February 2025 | - SA4#131 submission deadline, test report for Encoder uploaded |
| SA4#131 (17th – 21st February 2025) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Encoder, fulfilling the FL-to-FX requirements |
| TSG SA#107 (12th – 14th March 2025) | - Approval by TSG SA (SA#107) of Delivery of IVAS fixed-point Encoder, fulfilling the FL-to-FX requirements, based on agreement in SA4 |

## Status – objective measures

The status of the D1 delivery was summarized in [3], including the performance on the automated test in the BASOP repository [5]. There are 562 tests based on the short test vector (STV) set, and 1216 tests based on the long test vector set. The tests are repeated with a pre-scaling of the input audio with -10 dB, 0 dB and +10 dB, resulting in 3*(562+1216) = 5334 tests. The objective measures in [1] states that the SSNR should be above [60 dB] and the Maximum Loudness Difference (MLD) scores below 5. In total, 4553 tests produce MLD<5, corresponding to 85% of the tests. Based on results from September 10 and 11, the number has improved to 86%. There are a number of challenges to improve the performance, listed in the following clause.

The complexity measurements have so far not been included in the assessment. Automated tests measuring the IVAS floating point code is available, while the automated BASOP complexity measurements are just about to be activated. The complexity goal is stated in [1] is:

- Complexity (WMOPS) ratio between IVAS FX and IVAS FL should be no worse than the complexity ratio between EVS FX and EVS FL; the goal is that the design constraints are met with the FX code.

Preliminary measurements on fixed rate, error free operation at 32 kHz sample rate suggests that the target complexity ratio between EVS FX and EVS FL is in the range of 0.58-0.79.

## Challenges

### Down-mix scaling issue

For input formats comprising multiple audio channels, e.g. Ambisonics, ISM and MASA and Multichannel loudspeaker layouts, the IVAS codec typically reduces the number of channels by applying a down-mix operation. The down-mix aims to compact the representation for encoding. The resulting down-mix channels are input to the IVAS core coder for encoding into the bitstream format. The core coder is based on the EVS codec and expects an input signal within the 16-bit range, -215,215-1=[-32768, 32767]. It was found that the down-mix procedure however may produce signal for the core coder that exceeds the expected input by a factor of ~2.5 at the maximum. Since the IVAS core coder is based on EVS, and the EVS BASOP TS 26.452 was assumed to be used as basis for the IVAS BASOP code, this presents a problem. A proposed solution is being developed for the IVAS floating point code, where the down-mix will be complemented with a scaling factor to ensure that the core coder receives signals within the supported dynamic range.

In addition, Ittiam has conducted an experiment [7] using the floating-point reference code, where saturation to [-32768, 32767] was applied at a number of places within the core coder where out-of-range values were observed. The outcome was a distortion in MLD which is comparable to the problematic cases in the BASOP test results, and several test cases were also overlapping.

### Jitter Buffer Manager objective measurement issue

The Jitter Buffer Manager (JBM) handles the varying arrival times of a packet-based network by storing the decoded audio in a buffer before playback. To keep the delay at a minimum, the JBM adaptively adjusts the playout time by applying time-scaling operations to the decoded audio. The JBM operation depends on calculations on the decoded audio and is inherently affected by the difference in arithmetic precision between the floating-point and fixed-point implementations. As a consequence, the output of the floating-point and fixed-point JBM may differ in time alignment, which has a negative impact on the objective measures such as MLD and PEAQ. An update of the MLD tool is being developed, where only the time-aligned segments of the decoded audio are included in the comparison. For the segments where objective tools cannot be used, the performance needs to be verified by subjective listening.

### Objective verification of encoder

Both the IVAS codec and the EVS codec which it is based on, uses several encoding modes and signal processing tools in a signal adaptive fashion. It is foreseen that the difference in arithmetic precision between the floating-point code and the fixed-point code may trigger different usage patterns of these modes and tools. Hence, the operating mode may differ between the implementations and lead to large differences on the decoded audio signals. Such differences may have a negative impact on the objective measures. This does not necessarily correlate with a degradation in the perceived performance. Two activities are ongoing to try to perform objective assessment of the encoder performance:

- Output of selected encoder parameters for comparison, statistics etc.

- Decoding the IVAS FX bitstream with IVAS FL decoder and comparing to the IVAS FL bitstream decoded with the IVAS FL decoder. This will be compared to the same setup using the EVS FX and EVS FL to check the current objective measures MLD, segmental signal-to-noise ratio (SSNR) and PEAQ. This could offer some guidance on setting a reasonable target in objective measures for the IVAS BASOP encoder.

### Wide range of operating points

The IVAS codec supports a variety of input and output formats and can handle several operating modes including packet loss concealment, DTX, rate switching, bandwidth switching, JBM, etc. This gives a large set of operating points to be tested, which is challenging within the given time. An attempt to document the test points and allocate responsible companies can be found in the Verification assignment table [6].

## Proposal

It is proposed to document the progress of the BASOP verification in a new permanent document, e.g. IVAS-10, containing as a starting point the verification time plan and the verification assignment table. Further details on the verification methods used may also be documented here. The document may serve as a starting point for the report to be submitted to SA4 on the BASOP verification.

## References

- SA4aA240038, Organization of IVAS Characterization Phase rev 1, https://www.3gpp.org/ftp/TSG_SA/WG4_CODEC/3GPP_SA4_AHOC_MTGs/SA4_Audio/Docs/SA4aA240038.zip

- S4-241690, Timeplan for IVAS_Codec_Ph2 Work Item v0.1.0, https://www.3gpp.org/ftp/TSG_SA/WG4_CODEC/TSGS4_129-e/Docs/S4-241690.zip

- IVAS_BASOP_Release_Notes_31082024.pdf, https://forge.3gpp.org/rep/sa4/audio/ivas-basop/-/releases/20240831_Ittiam_fixed_point_decoder_renderer_release (also attached)

- Verification time plan, https://forge.3gpp.org/rep/sa4/audio/ivas-basop/-/wikis/Verification-time-plan

- BASOP repository on 3GPP Forge, https://forge.3gpp.org/rep/sa4/audio/ivas-basop

- Verification assignment table, https://forge.3gpp.org/rep/sa4/audio/ivas-basop/-/wikis/Verification-Assignment-table

- Experiments related to saturation with floating point code (ivas-float-update), https://forge.3gpp.org/rep/sa4/audio/ivas-basop/-/issues/864