3GPPSA4-3GPPSA4-(AH) Video SWG post 128	S4aV240050

online, 25 June 2024

Agenda item: 	3.6

Source: 	Qualcomm Incorporated

Title: 	[FS_FGS] Proposed Completion of Study

Document for	Discussion and Agreement

# Introduction

The time plan of the FS_FGS study item in S4-240460 says:

| SA4 #128 (20-24 May, 2024, Jeju, South Korea) | - Monitor status and new developments of the ISO/IEC JTC1 SC29 JVET Film Grain Synthesis AhG - Communicate with DVB CM about their FGS study mission status |
| --- | --- |
| MPEG/JVET #147 (15-19 July 2024, Sapporo Japan) |  |
| SA4 #129-e (19-23 August 2024, Online) | - Monitor status and new developments of the ISO/IEC JTC1 SC29 JVET Film Grain Synthesis AhG - Communicate with DVB CM about their FGS study mission status |
| MPEG/JVET #148 (4-8 November 2024, Antalya Turkey) | <This is when the new FGS test results from MPEG AG5 / JVET FGS AhG TR may be expected to be available> |
| SA4 #130 (18-22 November 2024, Orlando USA) | - Monitor status and new developments of the ISO/IEC JTC1 SC29 JVET Film Grain Synthesis AhG - Communicate with DVB CM about their FGS study mission status - Progress work on evaluation using HEVC of the benefits or drawbacks of corresponding solutions, including film grain characteristics SEI message (ITU-T H.274) including performance results, complexity and implementation aspects, interoperability, system integration, etc. following the example in TR26.955 based on selected scenarios - Study and identify relevant UE requirements, conformance criteria for consistent usability of the technology |
| MPEG/JVET #149 (20-14 January 2025, Geneva Switzerland) | <This is when the new draft of JVET FGS AhG TR may be expected to be available> |
| SA4 #131 (18-22 February 2025, Geneva, Switzerland) | - Complete all remaining open issues raised for completion of CR to TR 26.955 - Document the agreements into the draft CR to TR26.955 - Communicate with other 3GPP working groups and external organizations, if necessary |
| SA #107 (11-14 March 2025, TBD Korea) | - Present CR to TR 26.955 for approval |

However, from the JVET discussions, it is also observed that there will be a document issued in

| JVET-AI2022 | m69402 | 2024-07-20 07:42:44 |  |  | Plan for subjective quality testing of the FGC SEI message | P. de Lagrange, W. Husak, M. Radosavljević, M. Wien |
| --- | --- | --- | --- | --- | --- | --- |

The time plans of the efforts are unclear. Also the outcome is unclear.

A permanent document (S4-240502) is available. During SA4#127, two option were considered:

- Wait for JVET completion and then resume work

- Close the study (migrate PD to TR) and only restart once JVET has completed.

At any point in time we expressed preference of the second option.

In light of the new developments, that the video SWG is asked to absorbe two new study items, making it in total possibly 8 study and work items in Video SWG, we prefer to come back to the above discussion and close the study by converting to the PD to a TR, and update the work study item accordingly.

# Proposal

It is proposed to:

- Not start any new study or work in Video SWG before FS_FGS is not completed

- To complete FS_FGS at the next SA4#128 by

  - Updating the work item to complete the work

  - Add an internal TR to the be produced

  - Migrate the PD information to the new TR

  - Write conclusions that includes that the subjective tests are carried out in JVET and once completed, SA4 is encouraged to revisit the discussion and start new work if considered suitable.

If the proposal is agreed in principle, we will submit an update to the study item as well as a draft TR to the upcoming SA4#128 meeting.