## Feuil1
Open issue # | Title | Description | Criticality | Status | Action point on | Action point description | Solution | Comment | Source
1 | Test material selection for Test 1 and Test 2 | Proponents have to check the validity of the test sequences selected for Test 1 and Test 2 | High | Not resolved | Qualcomm, Dolby, Xperi, Fraunhofer | Check the validity of the test material |  |  | Gilles
2 | Bit rates for Test 1 and Test 2 | No formal agreement on the bitrates to be tested on Test 1 and Test 2 | High | Not resolved | SA4 | Need agreement on the number of bitrates to be tested. 128, 256, 384 and 512kbps relevance |  | o Should we stick with those 4 initial bitrates? o Should we allow different bitrates to be selected by proponents? o Should we mandate the use of 4 bitrates in total? (e.g. If the quality is saturated at 256kbps, is it needed to test 384 and 512kbps?) | Gilles
3.1 | Test methodology for Test 3 | Test methodology still in square brackets | High | Not resolved | SA4 | Need agreement on the test methodology, Clause 6 of TS 26.259 |  | • 4 to 6 weeks were required so as to check the methodology for binaural test with Reference and Common Informative renderers o Can we consider that the test methodology is valid? o If not what does need to be changed? | Gilles
3.2 | GUI implementation for Test 3 | It would ease the work of cross-check labs and potentially other proponents if an existing GUI could be share among Proponents and Test labs | Low | Not resolved | Qualcomm, Dolby, Xperi, Fraunhofer | Check if possibile to share GUI implementation with at least cross-check labs, ideally with other proponents |  | Has anyone already implemented the GUI for assessing the rendering comparisons and would be ok to share it exclusively to all the proponents and cross-check labs? Note that the issue is not only the GUI but the complete listening system for test 3 | Gilles
3.3 | Listening system for Test 3 | Need to ensure that the configuration of headphone with head-tracking is well understood and the same for all the proponents and cross-check labs | Medium | Not resolved | Qualcomm, Dolby, Xperi, Fraunhofer, Ericsson, Nokia, Philips, Wilus | Confirm that the same understanding is shared among the proponents and Xcheck labs on the listening system configuration for test 3 |  | • Has everyone (within proponents and cross-check labs) the clear understanding on how to implement the listening system, i.e. Headphone-based with head-tracking? | Gilles
3.4 | FOA | Test 1 caters for testing of an FOA option at 128 kbps | High | Not resolved | SA4 | Clarify test methodology if a candidate provides an FOA option |  | There may be various possibilities: - the FOA option is tested along with the non-FOA operation points - the FOA option is tested in a separate test Note: the acceptance criteria for FOA are unclear and the test methodology should test the criteria. | Dolby
3.5 | Shortcuts to make test effort manageable | Test 3 is designed following an unproven test methodology. At the same time it is the biggest hurdle in the VRStream audio profile characterization process | High | Not resolved | SA4 | Discuss if tests 1 and 2 can be (re)designed such that test 3 can be down-prioritized and carried out at a later stage. |  |  | Dolby
4 | Media Profile characterization | Decision on Audio profile not supporting any of the Channel, Object or Scene based representation | Medium | Not resolved | SA4 | Decide if an Audio profile not supporting the 3 representations is eligible to VRStream. If so, agree on the required tests to be run (limited to the supported formats) |  | o Gilles suggests the proponent clearly mentions the supported representation formats o In this case only the compliant test material is to be tested (no conversion considered as pre-processing) o This needs to be reflected at least in the permanent document, potentially in 26.259. | Gilles
5 | Test results from Test 1a,1b,2a,2b | Test 1 and 2 are split due to the number of configuration to assess into sub-test a and b. Need agreement on the merge of the subtest results | Low | Not resolved | SA4 | Decide if results from Test 1a and Test 1b can be merged Decide if results from Test 2a and Test 2b can be merged |  | Should be easy to resolve, only difference is test material so should be merged | Gilles
6 | Test methodology for Test 2 | The test methodology is undefined | Medium | Not resolved | SA4 | Decide which test methodology to reference for running Test 2 |  | TBD in the permanent document | Gilles
7.1 | Cross-check Labs - full or partial test | Does a cross-check Lab has to run the full test or only part of it? | Medium | Not resolved | SA4 | Decide the amount of work cross-check Labs have to prepare |  | Does a cross-check Lab has to run all the test from scratch (meaning running the full subjective test)? Does a cross-check Lab just need to randomly select a limited number of bitstreams (let’s say half of them) and run the test with a limited number of assessors (say half of the required number)? | Gilles
7.2 | Cross-check Labs - access to Proponent's results | Does a cross-check Lab publish the tests independently or (in)validate the proponent's results? | Medium | Not resolved | SA4 | Agree on the procedure of crosschecking an audio profile |  | • Does the cross-check Lab publish its own results without any view on the proponent’s results or the crosscheck lab verify the validity of the proponent’s results (time dependency if the latter case)? | Gilles
7.3 | Cross-check Labs - access to original test material | Do the cross-check Labs need to get access to the source material? | Medium | Not resolved | SA4 | Decide on what the proponents need to deliver to cross-check Labs |  | • Do the cross-check Labs need to get access to the source material? o Yes, if they need to encode the bitstreams, and they need to check the encoding complexity. o No, if they are provided with bitstreams and decoders | Gilles
7.4 | Cross-check Labs - Assess the amount of work | Proponents need to indicate if they will run the optional test 2 and how many profiles they are willing to submit | High | Not resolved | Qualcomm, Dolby, Xperi, Fraunhofer | Indicate the number of profiles that need to be cross-checked Indicate if Test 2 will be run |  | • Proponents need to indicate ASAP if they will run Test 2 before SA4#99 o There is no need for cross-check Labs to run a test that is not conducted by the proponent. | Gilles
7.5 | Legal framework between proponent and cross-check companies | It is not clear if proponents will require an NDA with cross-check companies. | High | Not resolved | Qualcomm, Dolby, Xperi, Fraunhofer | Proponents to indicate NDA needs |  | The NDA needs may depend on the specific proponent/cross-checker pairs | Dolby
7.5 | Cross-check Labs - Who cross-checks who? | Need to agree on who crosschecks who by potentially defining a rule if needed. | High | Not resolved | Qualcomm, Dolby, Xperi, Fraunhofer, Ericsson, Nokia, Philips, Wilus, SA4 | Based on the number of audio candidates, identify who is ready to cross-check which profile. Wish for a balanced distribution of crosschecks. |  | • How do we agree on who cross-checks what? o 8 cross-check Labs for 4 proponents  Do we need to differentiate cross-check Labs that are proponents from those that are not? I don’t think so…  4 cross-check Labs are not proponents (just a fact, don’t know if it’s helpful)  Of course, a proponent can submit more than 1 audio profile but I wish we could agree that any audio profile shall be cross-checked by at least 2 cross-check Labs. o Proponents need to be transparent on the number of profiles they are willing to submit  Based on this list of candidate audio profiles, cross-check labs should indicate what media profile they want to cross-check  What to do in case of audio profiles with not enough cross-checkers? Need to avoid the perception of a club between proponent and crosscheckers. Proposal: All candidate solutions shall be accessible to any of the declared crosscheckers. | Gilles
8.1 | Qualification and Selection Criteria - Audio representation support | Section 5 in square braquets in permanent document. Same Issue as Issue #4 | Medium | Not resolved | SA4 | Decision on any potential candidate that doesn't support any of the 3 representation formats (scene,channel, object based) |  | Shall an audio candidate support the 3 representation formats, namely scene, object and channel based? | Gilles
8.2 | Qualification and Selection Criteria - Performance requirements | Section 5 in square braquets in permanent document. Need to agree on relevance of performance requirements as a selection condition for VRStream Audio profiles | Low | Not resolved | SA4 | Decide, based on the test results how to select audio profiles for VRStream |  | Performance requirements Setting the bar to Excellent may be challenged Same for the reference renderer minimum audio quality (TBD in permanent document) Gilles: Generally speaking, I’m not in favour of defining entry conditions to the specification as we may end up with many solutions not representative of the indsutry interest and support. I would rather state that these qualities will be used in order to select the audio profile(s) for VR Streaming services. Then the 3GPP rules will apply: Group consensus, no more, no less. Acceptance criteria for FOA option missing | Gilles
8.3 | Qualification and Selection Criteria - Documentation of test results | Section 5 in square braquets in permanent document. Need to decide if/where we document the test results of all the candidates | Low | Not resolved | SA4 | Decide if/where audio profiles description and characterization results are documented |  | Gilles: need to identify a placeholder for documenting all the test results for all the candidates: I would propose to create an annex on the VR technical report TR 26.918. | Gilles
8.4 | Qualification and Selection Criteria - Complexity evaluation | Need to decide how complexity evaluation is done | Low | Not resolved | SA4 | Specify a common complexity evaluation method in case this is possible. |  |  | Dolby