**Source: Rapporteurs (HEAD acoustics GmbH, Orange)**

**Title:** **Time Plan for HInT**

**Version: 0.5**

**Agenda Item: 9.7, 15.4**

# **1. Introduction**

This document describes the time plan for the work item “Extension for headset interface tests of UE” (HInT). This document will be continuously updated as necessary.

The work item has the following objectives:

* Update clause 4 (“Interface definition”) of TS 26.131 to include standardized analogue (wired) and digital (wired and wireless) headset interfaces.
* Update clause 5 ("Test configurations") and/or clause 6 ("Test conditions") of TS 26.132 for setup of headset interface testing.
* Updates clauses 7-10 (NB/WB/SWB/FB test methods) of TS 26.132 for new headset interface tests.
* Updates clauses 6-9 (NB/WB/SWB/FB performance) of TS 26.131 for new requirements and objectives of headset interface tests.

Whenever possible, existing tests and requirements of specifications like e.g., 3GPP TR 26.954 and Recommendation ITU-T P.381 and P.382 should be considered/referenced.

# **2. Schedule**

|  |  |  |
| --- | --- | --- |
| Month | Meeting / date | Activity |
| May-20 | SA4#109-e | Proposal and agreement of Work Item (S4-200918) |
| Jun-20 | SA#88-e | Approval of HInT Work Item at SA plenary (SP-200398) |
| Aug-20 | SA4#110-e | Initial inputs for TS 26.132 (description of analogue/digital interface)  Initial inputs for TS 26.131 (proposals for tests and requirements to be added) |
| Sep-20 | SA#89-e |  |
| Sep-20 | Telco (Sep 14th, 16:00-17:30 CEST; Submission Deadline: Sep 11th 23:59 CEST; Host: HEAD acoustics GmbH) | dCR to TS 26.131 and 26.132 discussed (S4aQ200148, S4aQ200149) |
| Oct-20 | Telco (Oct 19th, 16:00-17:30 CEST; Submission Deadline: Oct 16th 23:59 CEST; Host: HEAD acoustics GmbH) | dCR to TS 26.131 and 26.132 agreed as basis for further editing (S4aQ200151, S4aQ200153) |
| Nov-20 | SA4#111-e | dCR to TS 26.131 and 26.132 agreed (S4-201482, S4-201614) |
| Dec-20 | Telco (Dec. 7th, 16:00-17:30 CET; Submission Deadline: Dec. 4th 23:59 CET; Host: HEAD acoustics GmbH) | dCR to TS 26.132 agreed as basis for further editing (S4aQ200156) |
| Dec-20 | SA#90-e |  |
| Jan-21 | Telco (Jan. 18th, 16:00-17:30 CET; Submission Deadline: Jan. 15th 23:59 CET; Host: Qualcomm Incorporated) | no inputs |
| Feb-21 | SA4#112-e | dCR to TS 26.131 and 26.132 agreed as basis for further editing (S4-210040, S4-210169) |
| Mar-21 | Telco (March 15th, 16:00-17:00 CET; Submission Deadline: March 12th 23:59 CET; Host: HEAD acoustics GmbH) | Review additional inputs |
| Mar-21 | SA#91-e |  |
| Apr-21 | SA4#113-e | dCR to TS 26.131 and 26.132 agreed as basis for further editing (S4-210652, S4-210651) |
| Apr-21 | Telco (April 23rd, 16:00-17:00 CEST; Submission Deadline: April 22nd 23:59 CEST; Host: HEAD acoustics GmbH) | dCR to TS 26.131 (S4aQ210164), review of additional input (S4aQ210163) |
| May-21 | SA4#114-e | dCR to TS 26.131 and 26.132 agreed as basis for further editing (S4-210948, S4-210945), review of additional input (S4-210825) |
| Jun-21 | SA#92-e |  |
| Jul-21 | Telco (July 30th, 16:00-17:00 CEST; Submission Deadline: July 29th 23:59 CEST; Host: HEAD acoustics GmbH) |  |
| Aug-21 | SA4#115 | Review additional inputs  Discuss/Agree on CR to TS 26.131 and/or TS 26.132 |
| Sep-21 | SA#93 | Approval of CR to TS 26.131 on requirements for headset interface tests  Approval of CR to TS 26.132 on description & tests for headset interface tests |