3GPP TSG SA WG4#116-e meeting	S4-211399

10th-19th Novemer 2021

Agenda item: 	8.8

Source: 	TELUS (Rapporteur)

Title: 	Updated Work and Time Plan for 5MBUSA

Version:	0.0.2

Document for	Agreement

# Introduction

The New Work Item 5MBUSA on “5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions” was agreed in S4aI211195 and afterwards approved in SA plenary #92-e in SP-210376.

The objective on architectural work are as follows:

1.	Specify the 5MBS User Service architecture, including the following reference points/interfaces and entities:

- New entities MBSF, MBSTF, 5MBS Client, and 5MBS AS.

- The northbound reference points Nmb6 and Nmb4.

- The reference point Nmb2 between the MBSF and the MBSTF.

- The interfaces between the 5MBS Client and 5MBS network functions: MBS-4-UC, MBS-4-MC and MBS-5.

- The 5MBS Client reference points MBS-6 and MBS-7.

2.	Define relevant call flows and procedures to support

a.	5GMS over 5MBS.

b.	5GMS hybrid unicast/broadcast services.

c.	5MBS usage independent of 5GMS.

3.	Extend the 5G Media Streaming architecture by providing a general description and architecture of:

a.	5GMS via 5MBS.

b.	5GMS hybrid unicast/broadcast services.

c.	5GMS via eMBMS.

d.	Multicast ABR with 5GMS and 5MBS.

Note that there is a dependency on SA2’s work on Rel-17 TS 23.247.

# Proposed Time and Work Plan

| Meeting | 5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions - #920010 |
| --- | --- |
| SA#92-e (15 – 21 June 2021) | - Approve work item in SP-210376 |
| 3GPP SA4-e (AH) MBS SWG post 114-e | - Agree skeleton TS 26.502 |
| SA4#115-e (18 – 27 August 2021) | - Agree time and work plan v0.0.1 - Progress draft CRs on 5MBS User Service architecture, reference points/interfaces and entities |
| 3GPP SA4 MBS SWG AH post 115-e Date: Oct 7, 2021, 15:30 – 18:00 CEST Host: Qualcomm Document Submission deadline: Oct 6, 2021, 12:00pm CEST | - Progress draft CRs on 5MBS User Service architecture, reference points/interfaces and new entities |
| 3GPP SA4 MBS SWG AH post 115-e Date: Oct 21, 2021, 15:30 – 18:00 CEST Host: Qualcomm Document Submission deadline: Oct 20, 2021, 12:00pm CEST | - Progress draft CRs on 5MBS User Service architecture, reference points/interfaces and new entities |
| 3GPP SA4 MBS SWG AH post 115-e Date: Oct 28, 2021, 15:30 – 18:00 CEST Host: Qualcomm Document Submission deadline: Oct 27, 2021, 12:00pm CEST | - Progress draft CRs on 5MBS User Service architecture, reference points/interfaces and new entities |
| SA4#116-e (10 – 19 November 2021) | - Agree updated time and work plan v0.0.2 - Progress draft CRs on 5MBS User Service architecture, reference points/interfaces and new entities |
| 3GPP SA4 MBS SWG AH post 116-e Date: Dec 2, 2021, 156 :00-178 00 T Host: Qualcomm Document Submission deadline: Dec 1, 2021, 12:00pm CET | - Progress draft CRs on 5MBS User Service architecture, reference points/interfaces and new entities |
| 3GPP SA4 MBS SWG AH post 116-e Date: Dec 9, 2021, 15 :0-18 :00 CET Host: Qualcomm Document Submission deadline: Dec 8, 2021, 12:00pm CET | - Progress draft CRs on procedures for 5G Multicast-Broadcast User Services - Progress draft CRs on Object Delivery method and transparent delivery method |
| 3GPP SA4 MBS SWG AH post 116-e Date: Dec 16, 2021, 22:00-00:00 CET Host: Qualcomm Document Submission deadline: Dec 15, 2021, 12:00pm CET | - Progress draft CRs on procedures for 5G Multicast-Broadcast User Services - Progress draft CRs on Object Delivery method and transparent delivery method |
| 3GPP SA4 MBS SWG AH post 116-e Date: Jan 13, 2022, 15:00130–18:00 CT Host: Qualcomm Document Submission deadline: Jan 12, 2022, 12:00pm CET | - Progress draft CRs on procedures for 5G Multicast-Broadcast User Services - Progress draft CRs on Object Delivery method and transparent delivery method |
| 3GPP SA4 MBS SWG AH post 116-e Date: Feb 3, 2022, 15:00 – 17800 CET Host: Qualcomm Document Submission deadline: Feb 2, 2022, 12:00pm CET | - Progress draft CRs on procedures for 5G Multicast-Broadcast User Services - Progress draft CRs on Object Delivery method and transparent delivery method |
| SA4#117-e (14-18 February 2022 or, E-meeting:14-23 February 2022) | - Progress draft CRs on procedures for 5G Multicast-Broadcast User Services - Progress draft CRs on Object Delivery method and transparent delivery method |
| SA#95-e (March 16 – 18, 2022) | - Present TS 26.502 v1.0.0 for information |
| SA4#118-e (6-14 April 2022) | - Progress draft CRs on extended 5G Media Streaming architecture with a general description and architecture of: a. 5GMS via 5MBS b. 5GMS hybrid unicast/broadcast services c. 5GMS via eMBMS d. Multicast ABR with 5GMS and 5MBS |
| SA4#119/-e (May 16-20 2022 OR, E-Meeting: 11-20 May 2022) | - Progress draft CRs on extended 5G Media Streaming architecture with a general description and architecture of: a. 5GMS via 5MBS b. 5GMS hybrid unicast/broadcast services c. 5GMS via eMBMS d. Multicast ABR with 5GMS and 5MBS - Finalize TS 26.502 - Agree on TS 26.502 v 2.0.0 for approval |
| SA#96-e (June 8-10, 2022) | - Present TS 26.502 v2.0.0 for approval |