**Source: eUET Co-Rapporteurs (Orange, HEAD acoustics GmbH)**

**Title: Draft time plan for eUET, v0.3**

## Document for: Agreement

## Agenda Item: 14.6

## Introduction

This document presents the time plan for the Enhancements to UE Testing (eUET) work item in 3GPP SA4. This document will be updated as necessary.

## Schedule of eUET work

The tentative schedule for the eUET work is outlined in the table below.

|  |  |  |
| --- | --- | --- |
| **Month** | **Meeting / date** | **Activity** |
| Aug-2022  | SA4#120-e | Initial discussions on:* Existing tests: vehicle-handsfree tests (S4-221011), initial measurement results (S4-221019)
* RTP payload conformance (S4-221029, S4-221030)
* JBM performance tests (S4-221031, S4-221032) with dCRs (S4-221033, S4-221034)

Initial draft TS 26.130 (S4-221028), updated in S4-221189 |
| Oct-2022 | Telco (October 17, 16:00-18:00 CEST; Submission deadline: October 14, 23:59 CEST; Host: HEAD acoustics GmbH) | Initial proposals for impairment profiles for JBM performance tests (S4aA220012) |
| Nov-2022 | SA4#121 | Progress on:* Removal of vehicle-mounted hands-free UE:CR to TS 26.131 (S4-221522)CR to TS 26.132 (S4-221523)
* Clarifications on impairments profiles for JBM performance tests (S4-221445)
* Report on measurement results for headset & desktop hands-free (S4-221419)
 |
| Jan-2023 | Telco (Jan. 30, 16:00-18:00 CET; Submission deadline: Jan. 27, 14:00 CET; Host: HEAD acoustics GmbH) |  Discussion of S4aA230014 on JBM tests and S4aA230015 on RTP conformance tests. |
| Feb-2023  | SA4#122 | Discussion of JBM performance tests and requirements (S4-230236) and RTP conformance tests (S4-230237) |
| Mar-2023 | Telco (March 27, 16:00-18:00 CET; Submission deadline: March 24, 16:00 CET; Host: HEAD acoustics GmbH) | Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801) |
| Apr-2023  | SA4#123-e | Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801) |
| May-2023  | SA4#124 | Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801) |
| Aug-2023  | SA4#125 | Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801) |
| Nov-2023 | SA4#126 | **Agreement on sending to SA*** **TS 26.130 on Speech/Audio Codec RTP Payload Format Conformance for UE Testing**
* **CR to TS 26.131 on performance requirements and 26.132 on test methods**
* **CR to TR 26.801 on relevant test results**
 |
| Dec-2023  | SA#102 (Dec 2023)  | **TSG-SA approval of*** **TS 26.130 on Speech/Audio Codec RTP Payload Format Conformance for UE Testing**
* **CR to TS 26.131 on performance requirements and 26.132 on test methods**
* **CR to TR 26.801 on relevant test results**
 |