Source:	Xiaomi

Title:	Work Plan for the study on DaCED V0.1

Agenda Item:	15.7

Document for:	Agreement

- Introduction

# During SA4#121 meeting, the new study item on “Diverse audio Capturing system for End-user Devices” in S4-221623 was agreed and then approved in SA#98-e in SP-221330. The output of the study item will be TR 26.933 specification. this is the work plan for the project.

- Proposed Time and Work Plan

| Meeting | Diverse audio Capturing system for End-user Devices - #980008 |
| --- | --- |
| SA4#121 (14 – 18Nov 2022 Toulouse) | - Agree New Study Item “Diverse audio Capturing system for End-user Devices” in S4-221623 |
| SA#98-e (13 - 19 Dec 2022) | - Approve New Study Item “Diverse audio Capturing system for End-user Devices” in SP-221330 |
| SA4#122 (20 – 24 Feb 2023 Athens) | - Agree TR skeleton for TR 26.933 - Agree Work Plan v0.1 - Start work on the UE categories determination: |
| Joint telco on ATIAS/FS_DaCED: 24 March 2023, 16:00 – 18:00 CET, submission deadline: 23 March 2023, 16:00 CET, host: Dolby | - Continue to work on: - UE categories determination; - Start work on components used in audio capture: - Documentation of components may be used in diverse audio capture. |
| SA4#123-e (17 – 21 Apr 2023, e-meeting) | - Continue to work on: - UE categories determination; - Documentation of components may be used in diverse audio capture. |
| SA4#124 (22 May – 26 Mar 2023, Berlin) | - Continue to work on: - UE categories determination; - Components used in audio capture. - Start work on: - Acoustic design including acoustic structure, microphone array design, etc. - Signal processing Including necessary relevant processing for audio format, enhancement solution for immersive, speech enhancement, etc |
| SA4#125 (21 – 25 Aug 2023, Goteborg) | - Continue to work on: - Components used in audio capture. - Acoustic design including acoustic structure, microphone array design, etc. - Signal processing Including necessary relevant processing for audio format, enhancement solution for immersive, speech enhancement, etc - Start work on: - Characterization of the audio capture performance - Complete work on: - UE categories determination; |
| SA4#126 (13 – 17 Nov 2023, Chicago) | - Continue to work on: - Signal processing Including necessary relevant processing for audio format, enhancement solution for immersive, speech enhancement, etc; - Characterization of the audio capture performance - Start work on: - Example audio capture processing solutions; - Complete work on: - Components used in audio capture; - Acoustic design including acoustic structure, microphone array design, etc; |
| SA4#127 (29 Jan – 2 Feb 2024, Sophia Antipolis) | - Continue to work on: - Signal processing Including necessary relevant processing for audio format, enhancement solution for immersive, speech enhancement, etc; - Characterization of the audio capture performance; - Example audio capture processing solutions; |
| SA4#128 (20 – 24 May 2024, Korea) | - Continue to work on: - Example audio capture processing solutions; - Complete work on: - Signal processing Including necessary relevant processing for audio format, enhancement solution for immersive, speech enhancement, etc; - Characterization of the audio capture performance; - Agree on Draft TR 26.933 v1.0.0 to be sent to SA plenary for information |
| SA#104 (18 – 21 June 2024, China) | - Present Draft TR 26.933 v1.0.0 for information |
| SA4#129 (22 – 26 July 2024) | - Complete work on: - Example audio capture processing solutions; - Remaining issues - Provide recommendation on potential work for DaCED based on the findings in this study. - Agree on TR 26. 933 v2.0.0 to be sent to SA plenary for approval |
| SA#105 (10 – 13 Sep 2024, Australia) | - Present TR 26.933 v2.0.0 for approval |

- Proposal

Propose 1: SA4 to agree on the Work Plan for the study on DaCED v0.1.