## Slide 1: Brief report from SA#99 on SA4 topics
Frédéric Gabin, SA4 Chair, Dolby Laboratories Inc. (ETSI)
SA4#123-e, Online meeting, 17-21 April 2023
Tdoc: S4-230445

## Slide 2: Outline
General information
Outcome of SA4 submissions
SA4 Calendar
Planning

## Slide 3: General information - 1
Elections
  Mr. Puneet JAIN (Intel (ATIS)) was elected as TSG SA Chair.
  Dr. Mustapha (Apple France (ETSI)), Mr. Nagata (NTT DOCOMO INC. (ARIB)) and, Mr. Younge (T-Mobile USA Inc. (ATIS)) were elected as SA#99 Vice Chairs.
Inputs
  The SA#99 documents: https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_99_Rotterdam_2023-03/Docs
Reports
  SA#99 report: https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_99_Rotterdam_2023-03/Report
  SA4 report to SA: SP-230310
  RAN report to SA: SP-230381
  CT report to SA: SP-230355
  Workplan: SP-230382

## Slide 4: Outcome of SA4 submissions
All SA4 documents to SA#99 were noted or approved as requested.
There were a few questions and comments on the Chair’s report:
  SP-230310 (REPORT) SA WG4 Chair Status Report to TSG SA#99 (Source: SA WG4 Chair) Document for: Presentation Abstract: SA WG4 Chair Status Report to TSG SA#98-e.
  Questions and comments:
  Slide 7 AT&T asked whether the meeting locations for 2024 had been confirmed. The SA WG4 Chair clarified that ETSI offered to host the January meeting, but it is misaligned with other WGs. Korea is expected for the May meeting.
  General: Deutsche Telekom asked that the references used in the SA WG4 specifications need to be verified in order to ensure that they remain valid and stable in the future.
  General The TSG SA Chair thanked SA WG4 for their good work and coordination. The TSG SA Chair thanked the SA WG4 Chair for his support over his 2 terms as TSG SA Chair.
  The SA WG4 Chair was thanked for this report, which was noted.
  Status: Noted.

## Slide 5: Other aspects – SA4 calendar - 2023
Meetings in 2023 | Dates | Venue and Host
SA4#123-e | E-meeting: 17-21 April 2023 | Host: MCC, Electronic meeting
SA4#124 | F2F: 22-26 May 2023 | Host: E3MAG, Venue: Berlin, Germany
SA4#125 | F2F: 21-25 August 2023 | Host: EF3, Venue: Gothenburg, Sweden
SA4#126 | F2F: 13-17 November 2023 | Host: ATIS, Venue: Chicago, USA

## Slide 6: Other aspects – SA4 calendar - 2024
Meetings in 2024 | Dates | Venue and Host
SA4#127 | F2F: 29 January - 2 February 2024 | Host: ETSI, Venue: Sophia-Antipolis, France
SA4#127bis-e | E-meeting: 8-12 April 2024 | Host: MCC, Electronic meeting
SA4#128 | F2F: 20-24 May 2024 | Host: TBD, Venue: Korea
SA4#129-e | E-meeting: 19-23 August 2024 Note: agreement to have NO SA4 meetings in August 2025 | Host: MCC, Electronic meeting
SA4#130 | F2F: 18-22 November 2024 | Host: TBD, Venue: North-America

## Slide 7: Planning – Rel-18
Release 18 planning
  SA Rel-18 Workshop September 2021 - completed
  Rel-18 Stage 1 100% complete by December 2021 (TSG#94) (with 80% completion at TSG#93)
  Rel-18 Stage 2 freeze June 2023 (TSG#100)
    Stage 2 studies progress = 99%
    Stage 2 normative work progress = 67%
  Rel-18 Stage 3 freeze (CT & SA WGs) March 2024 (TSG#103)
    CT, SA3, SA4 and SA5 studies progress = 66%
    CT, SA3, SA4 and SA5 normative work progress = 25%
  Rel-18 Protocol coding Freeze (ASN.1, OpenAPI), June 2024 (TSG#104)

## Slide 8: Timeline – Rel-18
TSG#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN Content def.
RAN Completion (RAN2/3/4core)
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review

## Slide 9: Planning – Rel-19 - 1/3
Release 19 planning
  June 2023: RAN and SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103):
    RAN4 Content Definition
  Dec 2024 (TSG#106):
    Stage 2 functional freeze (working assumption)
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)

## Slide 10: Planning – Rel-19 - 2/3
Rel-19 Stage 1:
  Stage 1 studies :
    14 SA1 studies in total – one new one at this meeting (FS_ISN)
    OCI (St.1 Studies) = 71 % (number not recorded at previous TSG).
    1 SA4 study (FS_DaCED), 5% complete
  Stage 1 normative :
    8 “miniWIDs” items in total – three new ones at this meeting
      Reminder: in SA1 terminology, a “miniWID” is a WID without prior study and completed within one TSG cycle
    Overall progress of normative items not representative since only “miniWIDs” handled
    Normative work from ongoing studies have started only for one item (RVAS)
The more significant Features, including the one resulting from studies, will be completed by Stage 1 Rel-19 freeze
Rel-19 Stage 2 & 3:
  Not started

## Slide 11: Planning – Rel-19 - 3/3
Inputs to 13&14 June 2023 TSG SA Workshop on Rel-19 (source SP-230383 endorsed by SA#99)
  SA1 input on Rel-19 status
  3GPP Member/MRP/other contributions on Rel-19 views/priority.
  SA WG inputs on TU Budget for Rel-19, Max SIDs/WIDs, Max size per SID/WID.
    Note: as response to an SA#98-e AP, SA4 Chair indicated that SA4 can execute up to 16 concurrent SIs/WIs in addition to maintenance work.
Output:
  High level summary report from the WS.
  Identify the Core and Miscellaneous Rel-19 items/direction.
  Guidance to the WGs.

## Slide 12: Timeline – Rel-19
TSG#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
RAN Content def.
RAN Completion (RAN2/3/4core)
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review

## Slide 13: Timeline - overall
TSG#96
Release 19
Release 18
Note: All starting dates are indicative
TSG#98e
TSG#100
TSG#102
TSG#104
TSG#106
TSG#108
TSG#110
TSG#112
TSG#114
2022
2023
2025
Now
*: +3 months for RAN4
**: - 3 months for RAN1, + 3 months for RAN4 perf
SA1 Stage 1
Stage 3 (CT & SA)
Stage 2 Normative
RAN Content def.*
RAN Completion**
Maint.*
ASN.1 & Open APIs
ASN.1
1st review
TSG#99
TSG#101
TSG#103
TSG#107
TSG#109
TSG#111
TSG#113
2024
2026
SA1 Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1 & Open APIs
Stage 2 Normative
TSG#105
TSG#97
RAN Content Def*
SA St.2 Content Def
See Rel-19 timing slide
2021
TSG#92
TSG#94
TSG#95
TSG#93

## Slide 14: Thank You!
Frédéric Gabin
3GPP SA4 Chair
mail: frederic.gabin@dolby.com
phone: +33 678448575