**Source: eUET Co-Rapporteurs (Orange, HEAD acoustics GmbH)**

**Title: Time plan for eUET, v0.5**

## Document for: Agreement

## Agenda Item: 14.6

## Introduction

This document presents the time plan for the Enhancements to UE Testing (eUET) work item in 3GPP SA4. This document will be updated as necessary.

## Schedule of eUET work

The tentative schedule for the eUET work is outlined in the table below.

|  |  |  |
| --- | --- | --- |
| **Month** | **Meeting / date** | **Activity** |
| Aug-2022 | SA4#120-e | Initial discussions on:   * Existing tests: vehicle-handsfree tests (S4-221011), initial measurement results (S4-221019) * RTP payload conformance (S4-221029, S4-221030) * JBM performance tests (S4-221031, S4-221032) with dCRs (S4-221033, S4-221034)   Initial draft TS 26.130 (S4-221028), updated in S4-221189 |
| Oct-2022 | Telco (October 17, 16:00-18:00 CEST; Submission deadline: October 14, 23:59 CEST; Host: HEAD acoustics GmbH) | Initial proposals for impairment profiles for JBM performance tests (S4aA220012) |
| Nov-2022 | SA4#121 | Progress on:   * Removal of vehicle-mounted hands-free UE: CR to TS 26.131 (S4-221522) CR to TS 26.132 (S4-221523) * Clarifications on impairments profiles for JBM performance tests (S4-221445) * Report on measurement results for headset & desktop hands-free (S4-221419) |
| Jan-2023 | Telco (Jan. 30, 16:00-18:00 CET; Submission deadline: Jan. 27, 14:00 CET; Host: HEAD acoustics GmbH) | Discussion of S4aA230014 on JBM tests and S4aA230015 on RTP conformance tests. |
| Feb-2023 | SA4#122 | Discussion of JBM performance tests and requirements (S4-230236) and RTP conformance tests (S4-230237) |
| Mar-2023 | Telco (March 27, 16:00-18:00 CEST; Submission deadline: March 24, 16:00 CET; Host: HEAD acoustics GmbH) | No Tdoc. |
| Apr-2023 | SA4#123-e | Discussion of one Tdoc providing a status update on JBM performance tests. |
| May-2023 | SA4#124 | Presentation of updated SWB measurement results for eUET results. Discussion of draft changes to TS 26.131 and 26.132 for JBM performance testing.. |
| Aug-2023 | SA4#125 | Proposal of custom format for delay profiles. Status update on JBM performance tests. |
| Oct-2023 | Telco: (13 October 2023, 16:00 – 18:00 CEST, submission deadline: 12 October 2023, 16:00 CEST, host: HEAD acoustics) | No Tdoc. |
| Oct-2023 | Telco: (23 October 2023, 16:00 – 18:00 CEST, submission deadline: 20 October 2023, 16:00 CEST, host: HEAD acoustics) | No Tdoc. |
| Nov-2023 | SA4#126 | **Agreement on CR on TR 26.801 with HaNTE round robin test results (S4-231922).**  Review of CR on TS 26.131 on SWB performance requirements for desktop hands-free UE, headset UE, and handheld hands-free UE (S4-231974). Review of updated proposal for delay & loss profile and draft CRs on TS 26.131/132 (S4-231946).. |
| Dec-2023 | Telco: (4 December 2023, 16:00 – 18:00 CET, submission deadline: 1 December 2023, 16:00 CET, host: HEAD acoustics) | Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801) |
| Dec-2023 | SA#102 (Dec.. 2023) | **TSG-SA approval of CR on TR 26.801** **with HaNTE round robin test results** |
| Jan-2023 | Telco: (12 January 2024, 16:00 – 18:00 CET, submission deadline: 11 January 2024, 16:00 CET, host: HEAD acoustics) | Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801) |
| Feb-2024 | SA4#127 | **Agreement on sending to SA**   * **TS 26.130 on Speech/Audio Codec RTP Payload Format Conformance for UE Testing** * **CR to TS 26.131 on performance requirements and 26.132 on test methods** |
| Mar-2024 | SA#103 (Mar. 2024) | **TSG-SA approval of**   * **TS 26.130 on Speech/Audio Codec RTP Payload Format Conformance for UE Testing** * **CR to TS 26.131 on performance requirements and 26.132 on test methods** |