## 3GPP SA4 Rel-19 Planning
Date of SA4 meeting | 2024-01-01 | 2024-04-01 | 2024-05-01 | 2024-07-01 | 2024-11-01 | 2025-02-01 | 2025-04-01 | 2025-05-01 | 2025-07-01 | 2025-11-01
SA meeting -> | SA#103 Rel-18 Stage 3 |  | SA#104 | SA#105 | SA#106 Rel-19 Stage 2 | SA#107 |  | SA#108 | SA#109 Rel-19 stage 3 | SA#110
SA4 Meeting-> | SA4#127 | SA4#127bis-e | SA4#128 | SA4#129 | SA4#130 | SA4#131 | SA4#131bis-e | SA4#132 | SA4#133 | SA4#134
Audio SWG | 2024-01-01: IVAS_Codec; 2024-04-01: IVAS_Codec; 2024-05-01: IVAS_Codec
Audio SWG | 2024-01-01: ATIAS; 2024-04-01: ATIAS; 2024-05-01: ATIAS
Audio SWG | 2024-01-01: ISAR; 2024-04-01: ISAR; 2024-05-01: ISAR
Audio SWG | 2024-01-01: eUET; 2024-04-01: FS_ACAPI; 2024-05-01: FS_ACAPI; 2024-07-01: ACAPI; 2024-11-01: ACAPI
Audio SWG | FS_DaCED | FS_DaCED | FS_DaCED | FS_DaCED | DaCED stage 3 | DaCED stage 3 | DaCED stage 3 | DaCED stage 3 | DaCED stage 3
MBS SWG | 2024-01-01: SR_MSE; 2024-04-01: SR_MSE; 2024-05-01: SR_MSE
MBS SWG | PROMISE | FS_MeMe2 | FS_MeMe2 | FS_MeMe2 | FS_MeMe2 | MeMe2_Stage 3 | MeMe2_Stage 3 | MeMe2_Stage 3 | MeMe2_Stage 3
MBS SWG | 5GMS_Pro_Ph2 | 5GMS_Pro_Ph2 | 5GMS_Pro_Ph2 | FS_AMD | FS_AMD | AMD Stage 3 | AMD Stage 3 | AMD Stage 3 | AMD Stage 3
MBS SWG | n/a | FS_AMD | FS_AMD | FS_AMD | FS_AMD | AMD Stage 3 | AMD Stage 3 | AMD Stage 3 | AMD Stage 3
MBS SWG | n/a | FS_MediaGREEN | FS_MediaGREEN | FS_MediaGREEN | FS_MediaGREEN | FS_MediaGREEN
Video SWG | 2024-01-01: FS_AI4Media; 2024-04-01: FS_AI4Media; 2024-05-01: FS_AI4Media; 2024-07-01: FS_AI4Media
Video SWG | FS_HEVC_Profiles | VOPS | VOPS | VOPS | VOPS | VOPS
Video SWG | 2024-01-01: FS_AVATAR; 2024-04-01: FS_AVATAR; 2024-05-01: FS_AVATAR; 2024-07-01: FS_AVATAR; 2024-11-01: FS_AVATAR
Video SWG | FS_FGS | FS_FGS | FS_FGS | FS_FGS | FS_FGS | FS_FGS
Video SWG | MeCAR | FS_B2DV | FS_B2DV | FS_B2DV | FS_B2DV | FS_B2DV | FS_B2DV | FS_B2DV
Video SWG | 2024-01-01: FS_ARMRQoE
RTC SWG | 2024-01-01: iRTCW; 2024-04-01: iRTCW; 2024-05-01: iRTCW
RTC SWG | 2024-01-01: IBACS; 2024-04-01: IBACS; 2024-05-01: IBACS
RTC SWG | 5G_RTP | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2
RTC SWG | MP_RTT | SR_IMS | SR_IMS | SR_IMS | SR_IMS | SR_IMS
RTC SWG | 2024-01-01: FS_eiRTCW
Total # SID/WID | 21 | 19 | 19 | 13 | 12 | 10 | 6 | 6 | 5 | 0
Endorsed
Agreed
Exception requeted
TBD
Completed