Source:	Audio SWG

Title:	Status of IVAS fixed-point conversion

Document for:	Agreement

Agenda Item:	14.3

# Introduction

The floating-point code of the IVAS codec was standardized in Rel-18 in TS 26.258 [1]. The task to convert the floating-point implementation to fixed-point code using Basic Operators (BASOP) is being done by Ittiam, under a contract issued by ETSI. The organization, including floating-point to fixed-point (FL-to-FX) conversion requirements, of this conversion is outlined in [2], which is also attached to the contract.

The current milestones include:

- SA4#130, Nov 18-22, 2024: Agreement by TSG SA WG 4 (SA4) on Delivery of Decoder and Renderer, fulfilling the FL-to-FX requirements

- Nov 30, 2024: Delivery of complete IVAS fixed-point Encoder to SA4, fulfilling the FL-to-FX requirements

- SA#106, Dec 10-13, 2024: Approval by TSG SA of Delivery of Decoder and Renderer, fulfilling the FL-to-FX requirements, based on agreement in SA4

- SA4#131, Feb 17-21, 2025: Agreement by TSG SA WG 4 (SA4) on Delivery of Encoder, fulfilling the FL-to-FX requirements

- Feb 28, 2025: Delivery of maintenance for IVAS fixed-point Encoder/Decoder/Renderer

- SA#107, Mar 12-14, 2025: Approval by TSG SA of Delivery of Encoder, fulfilling the FL-to-FX requirements, based on agreement in SA4

- Jun 2025: Approval by TSG SA on TS 26.251 and TR 26.997

An extensive verification of the decoder and renderer delivery has been carried out, as reported in [3]. The report includes a summary on fulfilment of formal requirements in clause 4.2, observations on the source code in clause 5 and a summary of the main problematic areas identified from objective and subjective evaluations. Because of delayed verification of the Decoder and Renderer, the verification of IVAS fixed-point Encoder has so far been very limited. The initial evaluations however show that the first deliveries are not yet fulfilling the requirements [4].

# Conclusions and proposals

Overall, the fixed-point Decoder/Renderer delivered by Ittiam serves as a decent baseline for the IVAS fixed-point code, although as reported in [3] there are several problematic areas that would need further work in order for the requirements to be fulfilled. It is assumed that the present Decoder/Renderer deliverable fulfils the requirements at a level of 90%. However, the delivery of the fixed-point Encoder is considered of higher priority than further corrections and optimizations of the Decoder and Renderer.

It is therefore proposed to:

- Split the fixed-point Decoder and Renderer deliverable into two parts, where the first part corresponds to the current deliverable constituting 90% of the requirements and where the remaining work addressing the problematic areas in the maintenance phase constitutes 10% of the requirements.

- Ask SA4 for agreement on the 90% portion of the Delivery of the Decoder and Renderer, which TSG-SA is asked to approve.

- Extend the term of the contract to allow more time for:

  - Encoder development (priority one)

  - Maintenance (further corrections and optimizations) to Encoder, Decoder and Renderer (priority two)

It is further suggested to split the fixed-point Encoder deliverable into two parts, where the first part corresponds to the deliverable of IVAS Encoder v3 constituting 90% of the Encoder requirements and where the remaining work addressing problematic areas in IVAS Encoder v3 in the maintenance phase constitutes 10% of the Encoder requirements. Thus, 10% of the funds currently allocated to decoder/renderer deliverable and 10% of the funds currently allocated to the Delivery of the Encoder would be allocated to the work on Maintenance (further corrections and optimizations) of the Encoder, Decoder and Renderer.

Note: There is nothing preventing earlier completion of the milestones, which would allow for earlier payments.

It is proposed to update the time plan as follows:

- SA4#130, Nov 18-22, 2024: Agreement by TSG SA WG 4 (SA4) on Delivery of Decoder and Renderer, fulfilling FL-to-FX requirements

- Nov 30, 2024: Delivery of IVAS fixed-point Encoder v1 to SA4, targeting fulfilment of FL-to-FX requirements

- SA#106, Dec 10-13, 2024: Approval by TSG SA of Delivery of Decoder and Renderer, fulfilling FL-to-FX requirements, based on agreement in SA4

- Jan 31, 2025: Delivery of the Encoder v2, targeting fulfilment of FL-to-FX requirements, as basis for subjective verification

- Audio SWG Telco, Mar 14: Verification by TSG SA WG 4 (SA4) on Encoder v2 (with potential additional bugfixes)

- Mar 31, 2025: Delivery of the Encoder v3 (addressing most severe issues identified by the verification)

- SA4#132, May 19-23, 2025: Agreement by TSG SA WG 4 (SA4) on Delivery of Encoder, fulfilling FL-to-FX requirements

- TSG SA#108, Jun 10-13, 2025: Approval by TSG SA of Delivery of Encoder, fulfilling FL-to-FX requirements, based on agreement in SA4

- Jun 30, 2025: Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer

- SA4#133-e, Jul 21-25, 2025: Agreement by TSG SA WG 4 (SA4) on Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer

- TSG SA#109, Sep 16-19, 2025: Approval on Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer

Finally, ETSI is kindly asked to amend their contract with Ittiam to reflect the extended term of the contract, with the updated milestones and allocation of funds.

References

- 3GPP TS 26.258, Codec for Immersive Voice and Audio Services (IVAS); C code (floating-point)

- SA4aA240038, Organization of IVAS Characterization Phase rev 1

- S4-242054, Verification of IVAS BASOP code, Decoder and Renderer

- S4-241866, Report on Audio SWG Call 18 October 2024