3GPP TSG-SA WG4 Meeting #131-bis-e	S4-250563

Online, 11 – 17 April 2025

Source:	Fraunhofer IIS, China Mobile, Qualcomm Incorporated

Title:	[FS_ULBC] Analysis of ULBC Dependencies

Agenda item:	7.9

Document for:	Discussion

1. Introduction

The new “Study on Ultra Low Bitrate Speech Coding” has been approved at the SA#107 plenary meeting [1]. The study item has a targeted completion date of June 2026 (SA#112 plenary). Multiple objectives have to be completed within this time frame. These objectives have firstly interdependencies and secondly are also dependent on the input from other 3GPP working groups.

This contribution provides an analysis of these dependencies and proposes measures to successfully complete the study item within the given time frame.

2. Analysis of Dependencies

In the following section, dependencies and interdependencies of the study item objectives are analyzed. This analysis is based on experience from previous voice codec standardizations in 3GPP.

The source sees the individual design constraints (DC) as one of the crucial parts of this study, and they exhibit various interdependencies. For this reason, the individual design constraints are listed separately. In contrast to this, the other individual work item objectives are for reasons of simplicity not further broken down.

The analysis distinguishes between interdependencies within the study item and dependencies on other groups. The dependencies on other groups are highlighted in red. Also, major dependencies are marked by bold arrows.

Figure 1 provides a graphical analysis of the study item objective dependencies. Based on previous work, the definition of the design constraints and performance requirements are seen as most work intense part of this study item. Out of this, the following design constraints are key elements:

- Bitrates (Dependencies from other 3GPP groups)

- Sample rate, audio bandwidth

- Complexity, Memory demand

Unfortunately, these requirements have large mutual interdependencies. For example:

- Audio bandwidth and bitrate – typically, a higher audio bandwidth requires also a higher bitrate

- Audio bandwidth and complexity/memory – typically, a higher audio bandwidth/sampling rate requires also higher complexity and memory demands

- Bitrate and complexity with respect to audio quality – typically, a decrease in bitrate can (up to a certain degree) be compensated by higher complexity

In addition, these design constraints have a significant impact also on the performance requirements. Experience from previous standardization efforts is that the design constraints have the be defined before the performance requirements can be agreed. This critical interdependency is depicted in the center of Figure 1, highlighted in orange.

Figure 1: Graphical Analysis of Dependencies on Study Item Objectives

3. Conclusion

The ULBC study item exhibits a significant number of project interdependencies and dependencies on other 3GPP working groups for completing the study item objectives. In the proposed time plan, the following considerations have been taken into account:

- Objectives which aren’t dependent on others should be addressed and finalized early

- For objectives with multiple dependencies, sufficient time to resolve all dependencies should be reserved; this applies also to dependencies on other 3GPP working groups

- Especially for the critical interdependency between bitrates - sample rate/audio bandwidth – complexity/memory and performance requirements a sufficient amount of time was foreseen

- It is expected that the performance requirements are finalized last: sufficient time between completion of the preceding objectives and the performance requirements needs to be reserved in order to make ensure that performance requirements can be fulfilled given the outlined design constraints.

In addition, it is proposed to

- keep track of the status of the individual study item objectives. This could be done by the work-item rapporteur for example in a spreadsheet or a project management tool

- enforce the project timeline – finalization dates as in the agreed time plan shouldn’t be considered as non-binding proposals, but as ultimate completion date (earlier completion always possible)

[1] Tdoc SP-250378, “Study on Ultra Low Bitrate Speech Codec”