## Slide 1: Guidelines for 3GPP SA4 planning of Release 20 5G Advanced and 6G
Gilles Teniou
3GPP SA WG4 Vice-Chair
3GPP TSG SA4#131-bis-e
Online, 11-18 April 2025
S4-250587

## Slide 2: Context
3GPP Release 19 is to be finalized in September 2025.
3GPP Release 20 will be two-fold:
  5G Advanced studies and normative work.
  6G Studies.

## Slide 3: From the dedicated offline session this week
It is anticipated that 5G Advanced topics may be proposed as a follow-up of Release19 activities or as a request to implement stage 3 from other 3GPP WGs (or any new topic).
There is a wish to not only initiate 6G studies but also to build up a global vision on what 6G means in terms of media experience.
On the requested work split from SA, it is foreseen to start Release 20 with 75% of 5GA and 25% of 6G.

## Slide 4: Proposed next steps on the 3GPP SA4 Release 20 planning in 2025
It is proposed to organize dedicated SA4 WG Ad’hoc calls between SA4 meetings to review/agree Release 20 study and work item proposals.
  SA4 WG Ad’hoc group calls will have decision power.
  SID and WID are expected to be submitted with a companion document including:
    draft work plan
    Indication of any normative expectation as a follow up.
    Plans for usage of software and evaluation tools…
Only SA4 meetings #132 in May and #134 in November will have a dedicated agenda item on Release new work/studies (SA4#133 will be focused on Rel19 completion).
Beyond the already agreed new activities at this meeting, it is expected to provide SA with a first package of topics in September and a second package in December (eventually a third one in 2026).

## Slide 5: Proposed next steps on the Release 20 planning in SA4 in 2025
Proposal:
  Agree on a template companion document for Rel20 proposals during SA4#131-bis-e
  Add an agenda item on new work/studies for SA4#132 in May
    Review and decision to include new study/work items into the 1st package, considering the SA4 workload.
  If needed, agree on 1 SA4 call prior to SA4#133-e for reviewing 5GA/FS_6G topics
    Review and decision on new study/work proposals for the 1st package, considering the SA4 workload.
  Send a first package Release 20 activities to SA#109 plenary in September
  Agree on 1 SA4 call in October/November for reviewing additional 5GA/FS_6G topics
    Review and decision new study/work proposals, considering the SA4 workload.
  Add an agenda item on new work/studies for SA4#134 in November
    Review and decision new study/work proposals, considering the SA4 workload.
  Send a second package Release 20 activities to SA#110 plenary in December
NOTE: A third package is expected in 2026, details TBD

## Slide 6
Thank you!

## Slide 7
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
#116
RAN4 C.def.
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
St.3 SID def. TBD
Release 20 5GA-FS_6G timeline
Note: All starting dates are indicative
Workshop 5GA RAN
Workshop 5GA SA
RAN WG SID def.
St.2 SID def.
Workshop 6G TSGs
CT & St. 3 6G SID def.
SA1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
or
TBD
SA3/4/5/6 6G Study(ies)TBD