## Slide 1: Release-18/19 Time Plan Proposal for OAM SA5#147, 27 February – 3 March, 2023
Zou Lan, SA5 Vice-Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Chair, ERICSSON

## Slide 2: Background
Rel-18 and Rel-19 release schedule was discussed in SA and RAN plenary in Dec. 2022. We need to align the SA5 work plan with the overall 3GPP release schedule.
This tdoc uses the following references:
  SA#98e: 3GPP Work Plan review at Plenary #98e (SP-221352)
  SA#98e: 3GPP SA, RAN, CT Rel-18 Timeline (SP-221317 endorsed)
  SA#98e: Rel-19 Planning (SP-221353 endorsed)
  SA#86 3GPP Newcomer Orientation.pdf

## Slide 3: Background information from latest 3GPP Work Plan review at Plenary #98e (1/2)
Ref: SP-221352_SP-221285_rev2.ppt
So far SA5 Rel-18 time plan is not specifically shown in the latest 3GPP work plan, chair has started communication with MCC.

## Slide 4: Background information from latest 3GPP Work Plan review at Plenary #98e (2/2)
Ref: SP-221352_SP-221285_rev2.ppt

## Slide 5
TSG#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN Content def.
RAN Completion (RAN2/3/4core)
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
Release 18 timeline– figure with SA5 OAM
Studies (SA5 OAM)
Stage 1 (SA5 OAM)
Stage 2 Functional and stage 3 work (OAM/CN related),
provide inputs to CT
Stage 2 Functional and stage 3 work (RAN related)
SA5 OAM Rel-18 Timeline

## Slide 6: Release 18 timelines – with SA5 OAM text
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content
    SA2 Work Items prioritization
    RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96), Sept 2022 (#97) and Dec 2022 (#98): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work Freeze
  Sep 2023 (TSG#101): RAN1 freeze before maintenance
  Dec 2023 (TSG#102):
    RAN1 freeze after maintenance
    RAN2, RAN3, RAN4Core freeze before maintenance
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (CT&SA) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs
Updated at TSG#98
SA5 OAM Release 18 Freezes and other milestones, sorted by dates :
  Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
  Mar 2023 (SA#99) and Jun 2023(SA#100): SA5 SID concluded and Rel-18 WID started if needed
  Sep 2023 (TSG#101): Stage 1 work freeze
  Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to CT
  Mar 2024 (TSG#103): Stage 2 Functional work Freeze and stage 3 (RAN related)
Updated at SA5#146bis-e
Support of SA2, provide inputs to CT
Support of RAN

## Slide 7: Background information from endorsed Rel-19 planning at Plenary #98e
Ref: SP-221353

## Slide 8
TSG#93-e
SA1 Stage 1 80%
100%
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN4
content def.
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
RAN Rel-19 workshop
SA Rel-19
Workshop (TBC)
Note: Other Rel-19 milestones/timelines to be specified (latest June 2023 for SA/CT)
SA St.2 Content approval
Rel-19 planning
Release 19 timeline– figure with SA5 OAM
SA Rel-19 workshop
SA stage2
1st package
SA stage2
final package
SA5 OAM Rel-19 planning
SA5 will collect the potential work area and provide inputs to SA workshop in Jun, September and December based on group agreement.

## Slide 9: Leaders’ recommendation for SA5 OAM time planning for endorsement
SA5 OAM Release 18 planning：
Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
Mar 2023 (SA#99) and Jun 2023(SA#100): SA5 SID concluded and Rel-18 WID started if needed
Sep 2023 (TSG#101): Stage 1 work freeze
Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to SA2 and CT
Mar 2024 (TSG#103): Stage 2 Functional work Freeze and stage 3 (RAN related)
SA5 OAM Release 19 planning：
June 2023 SA Rel-19 workshop: Provide SA5 relevant Rel-19 inputs/planning to Jun SA workshop
Sep 2023 (TSG#101): Submit Rel-19 1st package following 3GPP timelines
Dec 2023 (TSG#102): Submit Rel-19 final package following 3GPP timelines
Note:
We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
For the CT related features, we need to provide inputs to CT as early as possible.
Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
Avoid exception requests as much as possible, and in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.

## Slide 10: Update History
S5-231032 | SA5#146Bis-e | Endorsed in SA5#146Bis-e
S5-232446 | SA5#147 | Editorial update and add provide inputs to SA2 in slide 9
S5-232763 | SA5#147 | Update slide 8

## Slide 11: Thank you!

## Slide 12: Consideration on SA5 OAM R18&R19 time planning(1/2)
General considerations as agreed in S5-221173:
1. We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
2. For the CT related features, we need to provide inputs to CT as early as possible.
3. Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
4. Avoid exception requests as much as possible, in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.
Concrete time planning consideration:
Rel-18 studies:
  For the topics which target to start corresponding work items in Rel-18, the studies need to be closed and corresponding work items be initiated no later than Jun, 2023. This is to leave enough time to produce high quality standardization specification within Rel-18 timeframe. For the leftover work which could not be finalized in the study, it could be considered for potential Rel-19 work.
  It’s also allowed to use the full Rel-18 time for the approved study items if there is no plan for standardization in Rel-18.
Rel-18 work items: all the work items are to be finished strictly following the 3GPP overall time schedule. Rapporteurs are requested to consider reasonable Rel-18 scope and coordinate the work with best utilizing the time.
Rel-19 studies/work items: closely following the SA Rel-19 discussion and provide SA5 relevant inputs if they are available.

## Slide 13: Consideration on SA5 OAM R18&R19 time planning(2/2)
Mar.2023&Jun.2023
(check point-1 for SA R19 preparation activities)
Dec.2023
(check point-2)
Now
A. Rel-18 approved SIs
A-1: Keep study only in Rel-18
A-2: Close study and Initiate Rel-18 corresponding WI
A-2: Rel-18 corresponding WI starts
A-3: Close study with no Rel-18 corresponding WI
B. Rel-18 approved WIs
B-1. Objectives which reached consensus, produce Rel-18 specifications, Rel-18 closed
C. Potential Rel-19 topics
B-2.Objectives which need more time for discussion
C. New ideas for Rel-19
potential R19 topics and join the SA R19 workplan
①
②
③

## Slide 14
Ref: SA#86 3GPP Newcomer Orientation.pdf

## Slide 15: Detailed view of SA5 OAM relation with other groups
SA1
Requirements
SA2
Architecture
SA3
Security
SA4
Media
SA5 OAM
Stage 3
SA6
Apps/MC
RAN
Radio Access
CT – Protocols & Coding
Stage 1
Stage 2
Stage 3
time
SA5 OAM
Stage 1
SA5 OAM
Stage 2
O-RAN
ONAP
GSMA GST
ETSI ZSM
1
2
1. SA1 Management requirements refer to SA5 specifications.
2. Take GSMA GST deliverables as input
3. Align the MnS with ZSM
4. ONAP reuses SA5 MnS
5. Collaboration with SA2 on architecture and CN management
6. Collaboration with SA4 on QoE
7. O-RAN reuse SA5 MnS
8. Provide inputs to CT
9. Collaboration with RAN on RAN management
10. Collaboration with SA6 on exposure and edge computing
11. Collaboration with SA3 on security aspects
3
4
5
6
7
8
9
Note: To be updated with working progress in Rel-18
10
11
Ref: SA5#141e S5-221173

## Slide 16: Change History
SA5 #141e | S5-221173 SA5 Rel-18 time plan proposal for OAM
SA5 #146 | S5-226377 Rel-18&Rel-19 Time Plan Proposal for OAM
SA5#146bis-e | S5-231032 Rel-18&Rel-19 Time Plan Proposal for OAM