## Slide 1: SA5 OAM&P Exec Report SA5#150, 21 – 25 August, 2023 Goteborg, Sweden
Zou Lan, SA5 Chair, HUAWEI
Thomas Tovinger, SA5 Vice-Chair, ERICSSON
Anatoly Andrianov, SA5 Vice-Chair, NOKIA
Mirko Cano Soveri, MCC

## Slide 2: Incoming LSs – OAM SWG level (1/2)
Tdoc | Title | Source | Decision | Reply In
S5-235024 | Reply LS on 3GPP work on Energy Efficiency | C4-232465 | Noted | 
S5-235025 | LSout to 3GPP SA5 about status of FEAT24 ^VNF-OAM" development by ETSI NFV | ETSI ISG NFV | Replied To | S5-235771
S5-235026 | Reply LS on Approval of eQoE CRs for NR | R2-2304401 | Replied To | S5-235772
S5-235027 | LS on area scope for QoE measurements | R2-2306569 | Replied To | S5-235782
S5-235028 | LS on the feasibility of introducing assistance information for handling of QoE reporting during RAN overload | R3-232047 | Replied To | S5-235542
S5-235029 | LS on NCR Solutions | R3-225253 | Postponed | 
S5-235030 | LS on MDT measurements collection in MR-DC | R3-232070 | Postponed | 
S5-235031 | LS on collecting QoE measurements per MBS service area and MBS session ID | R3-232079 | Replied To | S5-235781
S5-235032 | Response to Reply LS on Support of network slices which have area of service not matching deployed tracking areas | R3-233432 | Replied To | S5-235774
S5-235033 | LS on QoE measurement collection for application sessions delivered via MBS broadcast or multicast | R3-233457 | Postponed | 
S5-235034 | Reply LS on RAN UE Id optionality | R3-233476 | Postponed | 
S5-235035 | LS on Multiple Trace/MDT configurations | R3-233481 | RepliedTo | S5-235775
S5-235036 | LS on AI/ML for NG-RAN Energy Saving Energy Cost index | R3-233515 | Replied To | S5-235777
S5-235037 | LS on cell ID (re)configuration for mobile IAB cell | R3-233516 | Replied To | S5-236128
S5-235038 | Reply LS on customer acceptance of limited QoS degradation to save energy in the network | S1-231468 | Replied To | S5-235364
S5-235039 | Reply LS on Reply LS on DN energy efficiency | S1-231469 | Noted | 
S5-235040 | Reply LS on 3GPP work on Energy Efficiency | S1-231805 | Noted | 

## Slide 3: Incoming LSs – OAM SWG level (2/2)
Tdoc | Title | Source | Decision | Reply In
S5-235041 | LS for improved KPIs involving end-to-end data volume transfer time analytics | S2-2304067 | Replied To | S5-235454
S5-235043 | LS on OAM input data for QoS Sustainability Analytics | S2-2306095 | Replied To | S5-235776
S5-235044 | LS on MDAF discovery mechanisms | S2-2308078 | Replied To | S5-235729
S5-235045 | LS to SA5 on NFc registration using OAM | S3-233351 | Noted | 
S5-235046 | LS on 3GPP work on Energy Efficiency | S4-231111 | Replied To | S5-235778
S5-235047 | LS to GSMA on publication of GSMA OPG and OPAG documents | S6-232145 | Noted | 
S5-235048 | LS on REl-18 work on architecture for enabling Edge Applications | S6-232197 | Postponed | 
S5-235049 | LS for clarification on EAS instantiation duration time | S6-232198 | Replied To | S5-236127
S5-235050 | LS/r on initiation of new work item ITU-T Q.PMEE ""Protocol for managing energy efficiency with AI-assisted analysis in IMT-2020 networks and beyond"" (SG5-LS54) [to ITU-T SG5, SG13, and 3GPP SA5] | ITU-T | Replied To | S5-235779
S5-235051 | LS on initiation of draft new Recommendation ITU-T Y.IMT2020-MEVE-req-frame ""Future networks including IMT-2020: requirements and framework for measurement of effectiveness and value evaluation of autonomous networks"" | ITU-T | Noted | 
S5-235053 | ZSM work on AI enablers and intent-driven autonomous networks | ETSI ISG ZSM | Postponed | 
S5-235056 | LSout reply to ITU-T SG13 LSin on the NWI "Requirements and framework on network function enhancements of IMT-2020 networks and beyond from the energy efficiency perspective" | ETSI ISG NFV | Noted | 
S5-235057 | Liaison Statement to 3GPP SA5 | ETSI TC EE | Postponed | 
S5-235109 | LS/r on consideration of a new work item “Requirements and framework of network function enhancements of IMT-2020 networks and beyond from the energy efficiency perspective” (reply to SG13-LS78) | ITU-T | Noted | 

## Slide 4: Outgoing LSs – OAM SWG level
Tdoc | Title | To | Cc | Reply To
NGMN/GSMA/O-RAN/ITU-T/ETSI NFV |  |  |  | 
S5-235771 | LS reply to LSout to 3GPP SA5 about status of FEAT24 “VNF-OAM” development by ETSI NFV | ETSI ISG NFV |  | S5-235025
S5-235779 | Reply to LS on initiation of new work item ITU-T Q.PMEE “Protocol for managing energy efficiency with AI-assisted analysis in IMT-2020 networks and beyond” | ITU-T |  | S5-235050
RAN2/RAN3/SA1/SA2/SA4/SA6 |  |  |  | 
S5-235772 | Reply LS on Approval of eQoE CRs for NR | RAN2 |  | S5-235026
S5-235782 | Reply to: LS on area scope for QoE measurements | RAN2 |  | S5-235027
S5-235542 | Reply LS on the feasibility of introducing assistance information for handling of QoE reporting during RAN overload | RAN3 |  | S5-235028
S5-235781 | Reply to: LS on collecting QoE measurements per MBS service area and MBS session ID | RAN3 |  | S5-235031
S5-235774 | Reply to: Response to Reply LS on Support of network slices which have area of service not matching deployed tracking areas | RAN3 |  | S5-235032
S5-235775 | Reply LS on Multiple TraceMDT configurations | RAN3 |  | S5-235035
S5-235777 | Reply to LS on AI/ML for NG-RAN Energy Saving Energy Cost index | RAN3 |  | S5-235036
S5-236128 | LS reply to LS on Cell ID (re)configuration for mobile IAB cell | RAN3 |  | S5-235037
S5-235364 | Reply to LS on customer acceptance of limited QoS degradation to save energy in the network | SA1 |  | S5-235038
S5-235454 | Reply LS to SA2 on improved KPIs involving end-to-end data volume transfer time analytics | SA2 |  | S5-235041
S5-235776 | Reply LS on OAM input data for QoS Sustainability Analytics | SA2 |  | S5-235043
S5-235729 | Reply LS MDAF service discovery by NWDAF | SA2 |  | S5-235044
S5-235778 | Reply to LS on 3GPP work on energy efficiency | SA4 |  | S5-235046
S5-236127 | Reply to S6_on_clarification on EAS instantiation duration | SA6 |  | S5-235049

## Slide 5
New Rel-18 Work Items
Tdoc | Type | Release | Title | Source | Potential related groups
Intelligence and Automation |  |  |  |  | 
Management Architecture and Mechanisms |  |  |  |  | 
Support of New Services |  |  |  |  | 
No New Work Item at this meeting

## Slide 6
Revised Rel-18 Study / Work Items
Tdoc | Type | Release | Title | Source | Potential related groups
S5-235870 | WID Revised | Rel-18 | Revised WID on Service Based Management Architecture (SBMA) | Nokia, Nokia Shanghai Bell | 

## Slide 7
Documents endorsed by OA&M
TDoc | Title | Source | Potential related topics and related groups
S5-236126 | SA5 Collection of Rel-19 potential topics | SA5 Vice chair (Huawei) | 
S5-235690 | Service Management | Ericsson | 
S5-235453 | DP on SA2 LS for improved KPIs involving end-to-end data volume transfer time analytics | Intel, Verizon | 
S5-235145 | Discussion paper on Using Forge-Git as the primary storage for Code | Ericsson | CT WGs
S5-235664 | Discussion paper on GST version and Release | L.M. Ericsson Limited, Deutsche Telekom, Telefonica, Huawei | 
S5-235370 | Living document on 3GPP work on energy efficiency | Huawei, Deutsche Telekom | All 3GPP WGs
S5-235814 | DP on discovery and retrieval of stored management data | Microsoft | 

## Slide 8
OAM General Topics information
Forge related:
S5‑235145 Discussion paper on Using Forge-Git as the primary storage for Code
S5‑236113 Add Forge as a potential normative storage for Code
S5‑236114 Add Forge as a potential normative storage for Stage 3 OpenAPI code
Rel-18&Rel-19 time plan
S5‑235580 Rel-18 & Rel-19 time plan proposal for OAM
Latest WoP:
S5‑235015 Collection of Rel-18 3GPP SA5 OAM WoP
Rel-19 topics:
S5‑236126 SA5 Collection of Rel-19 potential topics
S5‑236129 Rel-19 topic OAM moderator list

## Slide 9: Incoming LSs (SA5 level)
Tdoc | Title | Source | Decision | Reply In
S5-235020 | Reply LS on having OpenAPI changes only in GitLab | C1-234390 | Noted | 
S5-235022 | LS on having OpenAPI changes only in GitLab | C3-232461 | Noted | 
S5-235023 | LS on having OpenAPI changes only in GitLab | C4-232464 | Noted | 
S5-235052 | Reply LS on GSMA requirements regarding intermediaries in the roaming ecosystem and related LSs | SP-230763 | Noted | 
S5-235215 | LS on GSMA OPG PRDs publication and document name change | GSMA | Noted | 

## Slide 10: Outgoing LSs (SA5 level)
Tdoc | Title | To | Cc | ReplyTo
None at this meeting

## Slide 11: Overview of Rel-18 SA5 OAM ongoing WIs/SIs
Altogether 49 WIs/SIs, including 7 ongoing SIs and 21 ongoing WIs, 19 studies are finished, 2 work items are finished.
Rel-18 OAM&P Studies |  |  |  | 
Intelligence and Automation |  |  |  | 
1 | Study on enhancement of autonomous network levels | China Mobile, Huawei | FS_eANL | SP-211446
2 | Study on evaluation of autonomous network levels | China Mobile, Huawei | FS_ANLEVA | SP-211445
3 | (finished) Study on enhanced intent driven management services for mobile networks | Huawei, Ericsson | FS_eIDMS_MN | SP-211450
4 | Study on intent-driven management for network slicing | Ericsson, Huawei | FS_NETSLICE_IDMS | SP-220278
5 | (finished) Study on AI/ ML management | Intel, NEC | FS_AIML_MGMT | SP-211443
6 | (finished) Study on Enhancement of the management aspects related to NWDAF | China Telecom | FS_MANWDAF | SP-211435
7 | Study on Fault Supervision Evolution | China Mobile, Huawei | FS_FSEV | SP-220153
8 | (finished)Study on measurement data collection to support RAN intelligence | Intel, China Mobile | FS_MEDACO_RAN | SP-220488
Management Architecture and Mechanisms |  |  |  | 
9 | (finished) Study on Enhancement of service based management architecture | Huawei, Ericsson | FS_eSBMA | SP-211451
10 | (finished) Study on Basic SBMA enabler enhancements | Nokia | FS_eSBMAe | S5-221506
11 | (finished) Study on Management Aspects of URLLC | China Unicom | FS_URLLC_Mgt | SP-220146
12 | (finished) Study on Management Aspects of 5GLAN | China Mobile | FS_5GLAN_Mgt | SP-220324
13 | (finished) Study on Management of Cloud Native Virtualized Network Function | China Mobile | FS_MCVNF | SP-220150
14 | (finished) Study on Management Aspects of 5G MOCN Network Sharing Phase2 | China Unicom | FS_MANS_ph2 | SP-220151
15 | (finished) Study on continuous integration continuous delivery support for 3GPP NFs | Lenovo | FS_CICDNS | SP-211427
16 | (finished) Study on Management of Trace/MDT phase 2 | Nokia | FS_5GMDT_Ph2 | SP-220152
17 | (finished)Study on YANG PUSH (stopped at SA5#144e) | Ericsson | FS_YANG | SP-200765
18 | Study on Management Aspects of IoT NTN Enhancements | China Unicom | FS_IOT_NTN | SP-220490
19 | Study on Data management phase 2 | Nokia | FS_MADCOL_ph2 | SP-220842
Support of New Services |  |  |  | 
20 | (finished)Study on enhancement of management of non-public networks | Huawei | FS_OAM_eNPN | SP-211436
21 | (finished) Study on new aspects of EE for 5G networks Phase 2 | Huawei | FS_EE5G_Ph2 | SP-211440
22 | (finished) Study on Network and Service Operations for Energy Utilities | Samsung | FS_NSOEU | SP-211622
23 | Study on Key Quality Indicators(KQIs)for 5G service experience | Huawei | FS_KQI_5G | SP-211433
24 | Study on Deterministic Communication Service Assurance | Huawei | FS_DCSA | SP-211442
25 | (finished) Study on management aspects of network slice management capability exposure | Alibaba | FS_NSCE | SP-220142
26 | (finished) Study on alignment with ETSI MEC for Edge computing management | Huawei | FS_MEC_ECM | SP-220147
Rel-18 Operations, Administration, Maintenance and Provisioning (OAM&P) |  |  |  | 
Intelligence and Automation |  |  |  | 
1 | Self-Configuration of RAN NEs | China Mobile, Huawei | RANSC | SP-211431
2 | Management Data Analytics phase 2 | Intel, NEC | eMDAS_Ph2 | SP-220981
3 | AI/ML management | Intel, NEC | AIML_MGT | SP-230335
4 | Intent driven Management Service for Mobile Network phase 2 | Huawei, Ericsson | IDMS_MN_ph2 | SP-230180
Management Architecture and Mechanisms |  |  |  | 
5 | Service based management architecture | Huawei, Ericsson, Nokia | eSBMA | SP-230174
6 | Network slicing provisioning rules | Ericsson | NSRULE | SP-211449
7 | Network slice provisioning enhancement | Samsung | eNETSLICE_PRO | SP-211434
8 | Management of Trace/MDT phase 2 | Nokia | 5GMDT_Ph2 | SP-221163
9 | 5G performance measurements and KPIs phase 3 | China Telecom, Intel | PM_KPI_5G_Ph3 | SP-220489
10 | (finished) Enhancement of QoE Measurement Collection | Ericsson | eQoE | SP-200193
11 | Additional NRM features phase 2 | Nokia | AdNRM_ph2 | SP-220351
12 | Management Aspects related to NWDAF | China telecom | MANWDAF | SP-230181
13 | Enhanced Edge Computing Management | Samsung, Intel | eECM | SP-220154
14 | Management Aspect of 5GLAN | China Mobile Com. Corporation | 5GLAN_Mgt | SP-230175
15 | Management Aspects of NTN | China Unicom,CATT | OAM_NTN | SP-230183
16 | (finished) methodology for deprecation | Ericsson | OAM_MetDep | SP-220843
17 | Management of cloud-native Virtualized Network Functions | China Mobile,Huawei,AsiaInfo | MCVNF | SP-230764
18 | Management Aspect of 5G Network Sharing Phase2 | China Unicom, Ericsson | MANS_ph2 | SP-230629
19 | Management Aspects of URLLC | China Unicom | URLLC_Mgt | SP-230631
Support of New Services |  |  |  | 
20 | Access control for management service | Nokia | MSAC | SP-210859
21 | Enhancements of EE for 5G Phase 2 | Huawei | EE5GPLUS_Ph2 | SP-211441
22 | Management of non-public networks phase 2 | Huawei | OAM_NPN_Ph2 | SP-230184
23 | Network and Service Operations for Energy Utilities | Samsung | NSOEU | SP-230632

## Slide 12: Summary - SA5 Rel-18 WI progress (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
990119 | AI/ML management | AIML_MGT | 2023/12/12 | 20% | SP-230335 | 35% |  | SA2, RAN3 | 0->20->35% | 28.105; 28.552; 32.425; 28.554; 28.541 | Yao, Yizhi, Intel Hassan Al-kanani, NEC
940045 | Network slicing provisioning rules | NSRULE | 2023/6/9 ->SA#102 (Dec 2023) | 60% | SP-211449 | 70% |  |  | 0->15->35->45->55->60->60->70% | 28.531; 28.541 | Robert Petersen, Ericsson
990030 | Intent driven Management Service for Mobile Network phase 2 | IDMS_MN_ph2 | 2023/12/12 | 40% | SP-230180 | 75% |  | SA2, RAN3, ETSI ZSM, TM Forum | 0->40->75% | 28.312 | Xu Ruiyue, Huawei Mark Scott, Ericsson
970031 | Management Data Analytics phase 2 | eMDAS_Ph2 | 2023/12/12 | 25% | SP-220981 | 50% |  | SA2,RAN3,RAN2 | 0->5->15->25->50% | 28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 | Yao, Yizhi, Intel Hassan, NEC
950031 | Additional NRM features phase 2 | AdNRM_ph2 | 2023/3/3 ->SA#103(Mar 2024) | 80% | SP-220351 | 88% |  |  | 0->5->7->10 -> 30->55->65->80->88% |  | Sean Sun, Nokia
940030 | Self-Configuration of RAN NEs | RANSC | 2023/12/12 | 55% | SP-211431 | 65% |  |  | 0->5->5->5->45->50->55->65% | 28.313; ; 28.317 | Hu, Yaxi, China Mobile Xu Ruiyue, Huawei
980029 | Management of Trace/MDT phase 2 | 5GMDT_Ph2 | 2023/12/12 ->SA#103(Mar 2024) | 0% | SP-221163 | 40% |  | SA2,RAN2,RAN3 | 0->40% | 28.621; 28.622; 28.623; 32.421; 32.422; 32.423 | Swaminathan, Sivaramakrishnan, Nokia
940037 | Enhancements of EE for 5G Phase 2 | EE5GPLUS_Ph2 | 2023/12/12 | 35% | SP-211441 | 55% |  | SA2,RAN2,RAN3 | 0->0->0->10->25->30->35->55% | 28.310; 28.552; 28.554; 28.541 | Cornily Jean-Michel, Orange
960025 | 5G performance measurements and KPIs phase 3 | PM_KPI_5G_Ph3 | 2023/12/12 | 70% | SP-220690 | 80% |  | RAN2/RAN3/SA4/CT1/CT4 | 0 -> 5->15->50->60->70->80% | 28.552; 32.425; 28.554; 28.550 | Chen, Xiumin, China Telecom Yao, Yizhi, Intel
870027 | Enhancement of QoE Measurement Collection | eQoE | 2023/12/12 | 100% | SP-200193 |  |  |  | 95->95->70->95 ->100% | 28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 | Bagher Zadeh, Ericsson
950036 | Enhanced Edge Computing Management | eECM | 2023/12/12 | 50% | SP-220154 | 50% |  |  | 0->5->10->20-> 35->50->50% | 28.541; 28.538; 28.552; 28.554; 28.531; 28.532 | Deepanshu Gautam , Samsung
930010 | Access control for management service | MSAC | 2023/12/12 | 72% | SP-210859 | 73% |  | SA3 | 67->67->67%->68->69->72->73% | 28.533; 28.540; 28.622; 28.623; 28.532; | Jing Ping, Nokia
940033 | Network slice provisioning enhancement | eNETSLICE_PRO | 2023/12/12 | 90% | SP-211434 | 100% |  |  | 85->85 ->85%->90->100% | 28.531; 28.541 | Deepanshu Gautam , Samsung
990026 | Service based management architecture | eSBMA | 2023/12/12 | 0% | SP-230174 | 10% |  |  | 0->10% | 32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.158; 28.111 | Lan Zou, Huawei Robert Peterson, Ericsson Pollakowski,Nokia
990031 | Management Aspects related to NWDAF | MANWDAF | 2023/12/12 | 50% | SP-230181 | 75% |  |  | 0->50->75% | 28.541; 28.552; 28.554 | Niu, Yuxia, China Telecom
990027 | Management Aspect of 5GLAN | 5GLAN_Mgt | 2023/12/12 | 45% | SP-230175 | 90% |  | SA2 | 0->45->90% | 28.541; 28.552; 28.554 | Yushuang Hu, CMCC
970030 | Methodology for deprecation | OAM_MetDep | 2023/3/10 | 100% | SP-220843 |  |  |  | 95->100% | 32.156; 32.160 | Lengyel, Balázs, Ericsson
990033 | Management Aspects of NTN | OAM_NTN | 2023/12/12 | 0% | SP-230183 | 30% |  |  | 0->30% | 28.541; 28.552; 28.554; 28.658 | Sun Mingrui, China Unicom
990034 | Management of non-public networks phase 2 | OAM_NPN_Ph2 | 2023/12/12 | 0% | SP-230184 | 40% |  | SA1, SA2, RAN3 | 0->10->40% | 28.557; 28.541; 28.531; 28.533; 28.552 | ZHANG, Kai, Huawei

## Slide 13: Summary - SA5 Rel-18 WI progress (2/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
1000007 | Management of cloud-native Virtualized Network Functions | MCVNF | 2024/3/3 | 0% | SP-230764 | 30% |  | ETSI NFV | 0->30% |  | China Mobile Guangjing Cao
1000012 | Management Aspects of 5G Network Sharing Phase2 | MANS_ph2 | 2024/3/3 | 0% | SP-230629 | 30% |  | RAN3 | 0->30% |  | Wang Zhaoning, China Unicom,
1000013 | Management Aspects of URLLC | URLLC_Mgt | 2024/3/3 | 0% | SP-230631 | 10% |  | RAN3 | 0->10% |  | Wang Zhaoning, China Unicom,
1000014 | Network and Service Operations for Energy Utilities | NSOEU | 2024/3/3 | 0% | SP-230632 | 30% |  | SA1 | 0->30% | 28.318, 28.522, 28.554, 28.622 | Erik Guttman, Samsung

## Slide 14: Rel-18 WI - Intelligence and Automation
RANSC:
Progress at SA5#150:
The MnS model (Type B) and procedure for self-configuration
management have been discussed, only procedure has been agreed. The topic for configuration data handling is discussed again but no agreement achieved due to Nokia’s objection, which need further discussion.
Impacts and dependencies on other WGs: none identified
Next steps:
The MnS definition (type A and type B) of self-configuration management;
The concept, use case and requirement for configuration data handling
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
940030 | Self-Configuration of RAN NEs | RANSC | 2023/12/12 | 55% | SP-211431 | 65% |  |  | 0->5->5->5->45->50->55->65% | 28.313; ; 28.317 | Hu, Yaxi, China Mobile Xu Ruiyue, Huawei
970031 | Management Data Analytics phase 2 | eMDAS_Ph2 | 2023/12/12 | 25% | SP-220981 | 50% |  | SA2,RAN3,RAN2 | 0->5->15->25->50% | 28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 | Yao, Yizhi, Intel Hassan, NEC
990119 | AI/ML management | AIML_MGT | 2023/12/12 | 20% | SP-230335 | 35% |  | SA2, RAN3 | 0->20->35% | 28.105; 28.552; 32.425; 28.554; 28.541 | Yao, Yizhi, Intel Hassan Al-kanani, NEC
990030 | Intent driven Management Service for Mobile Network phase 2 | IDMS_MN_ph2 | 2023/12/12 | 40% | SP-230180 | 75% |  | SA2, RAN3, ETSI ZSM, TM Forum | 0->40->75% | 28.312 | Xu Ruiyue, Huawei Mark Scott, Ericsson
eMDAS_Ph2：
Progress at SA5#150:
Discussion at SA5#150 evolved around several documents including the following: Adding enabling data for Coverage and SLS use cases for PM predictionsresource analytics use case with correlation across NFsMDA RecommendationsSupport in stage 2 for cross domain MDAAdd recommended actions for non-3GPP operationsAdd MDA capability for resource utilization analysisAdd use case of MDA assisted control plane congestion analysis.
The discussion led to the approval of the following documents as input to the Draft CR: Adding enabling data for Coverage and SLS use cases for PM predictions.Filtering MDA Recommendations.Enhancing resource analytics use case with correlation across NFs.Add recommended actions for non-3GPP operations.Add MDA capability for resource utilization analysis.Add use case of MDA assisted control plane congestion analysis.
Impacts and dependencies on other WGs: SA2
Next steps: Continue the work according to the objectives
AI/ML management：
Progress at SA5#150:
With the discussions focused on AI/ML management for ML training phase, AI/ML emulation phase, and ML deployment phase in SA5#150, the contributions related to the following topics were agreed as inputs to the Draft CR:
- Use case, requirements and NRMs for ML training and testing performance management
- Modelling of ML Entity
- NRM for ML entities grouping
- NRMs for ML entities joint training
- NRMs for ML entities joint testing
- NRMs for ML entity update
- AI/ML management capabilities
- Rapporteur clean-up
Impacts and dependencies on other WGs: SA2, RAN3
Next steps: Continue the work according to the objectives
IDMS_MN_ph2：
Progress at SA5#150:
  Following solutions for new scenarios are discussed and agreed: Intent driven approach for RAN energy saving, Intent driven approach for radio capacity assurance, intent driven approach for 5GC network delivering and intent driven approach for E2E network optimization;
  Following solutions for generic intent capabilities are discussed and agreed: Intent report, intent handling capability obtaining, intent feasibility check, intent conflict
Impacts and dependencies on other WGs; SA2, RAN3
Next steps: deployment scenarios for intent interface

## Slide 15: Rel-18 WI - Management Architecture and Mechanisms (1/4)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
990026 | Service based management architecture | eSBMA | 2023/12/12 | 0% | SP-230174 | 10% |  |  | 0->10% | 32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111 | Lan Zou, Huawei Robert Peterson, Ericsson Pollakowski,Nokia
940045 | Network slicing provisioning rules | NSRULE | 2023/6/9 ->SA#102 (Dec 2023) | 60% | SP-211449 | 70% |  |  | 0->15->35->45->55->60->60->70% | 28.531; 28.541 | Robert Petersen, Ericsson
940033 | Network slice provisioning enhancement | eNETSLICE_PRO | 2023/12/12 | 90% | SP-211434 | 100% |  |  | 85->85 ->85%->90%->100% | 28.531; 28.541 | Deepanshu Gautam , Samsung
eNETSLICE_PRO:
Progress at SA5#150:
  This WID is completed.
Impacts and dependencies on other WGs:
  None identified
Next steps:
  None
eSBMA：
Progress at SA5#150: The following topics were agreed:
  28.111 skeleton
  Rel-18 pCR 28.111 FM service first draft
  Rel-18 pCR 28.111 FM service, definition updates
  Introduction of SBMA in 32.300
  Introduction of SBMA in 32.404
  Rel-18 Input to DraftCR,32.158 Add design pattern for error responses,Deprecate FM subscribe-unsubscribe,Introduce MnS Producer Notification Capabilility
Impacts and dependencies on other WGs: N/A
Next steps:examples of using SBMA for deployment needs further discussion.
NSRULE：
Progress at SA5#150:
  The solution description has been discussed however more discussion is needed to further align the solution described the technical specifications
Impacts and dependencies on other WGs:
  None identified
Next steps:
  Explore alternative solutions

## Slide 16: Rel-18 WI - Management Architecture and Mechanisms (2/4)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
980029 | Management of Trace/MDT phase 2 | 5GMDT_Ph2 | 2023/12/12 ->SA#103(Mar 2024) | 0% | SP-221163 | 40% |  | SA2,RAN2,RAN3 | 0->40% | 28.621; 28.622; 28.623; 32.421; 32.422; 32.423 | Swaminathan, Sivaramakrishnan, Nokia
960025 | 5G performance measurements and KPIs phase 3 | PM_KPI_5G_Ph3 | 2023/12/12 | 70% | SP-220690 | 80% |  | RAN2/RAN3/SA4/CT1/CT4 | 0 -> 5->15->50->60->70->80% | 28.552; 32.425; 28.554; 28.550 | Chen, Xiumin, China Telecom
950031 | Additional NRM features phase 2 | AdNRM_ph2 | 2023/3/3 ->SA#103(Mar 2024) | 80% | SP-220351 | 88% |  |  | 0->5->7->10 -> 30->55->65->80->88% |  | Sean Sun, Nokia
PM_KPI_5G_Ph3：
Progress at SA5#150:
  Total of 14 contributions regarding to PM&KPI new measurement and streaming format enhancing were discussed at this meeting, eight of which (CRs focus on TS 28.552 and TS 28.554) were agreed. And one LS out may potentially involve this WID.
Impacts and dependencies on other WGs: Measurements for RAN depends on the progress in RAN WGs. Some LSs may be involved.
Next steps:
  Continue the WID per the WoPs.
5GMDT_Ph2：
Progress at SA5#150: The discussion at SA5#150 was focused on the below topics:
  Report Amount in LTE.
  Name containment of Trace job in signaling based activation.
  Stage 1 requirements for TraceMDT in NPN networks.
  Per drb measurements in stage 3 schema.
  Trace job restructuring
Impacts and dependencies on other WGs: N/A
Next steps: Continue the work according to the objectives.
AdNRM_ph2：
Progress at SA5#150:
Second phase of NRM enhancement for NRF agreed. NRM enhancement for BSF, AANF, TSCTSF, 5G GMLC agreed.
Improvments to LogicalInterfaceInfo model , Non IP Support stage2/3 agreed.
TS structure proposal for generic NRM Fragment discussed but not agreed, alternative solution discussed
A few CR related to NROperatorCellDU, feasibility check, BWP configuration agreed.
User Data Access stage2/3 and adding slice validity info to ServiceProfile discussed but not
pursued.
  Impacts and dependencies on other WGs: Yes
Next steps: Next step is for phase 3 of NRF enhancement, and remaining Core NF NRM enhancement

## Slide 17: Rel-18 WI - Management Architecture and Mechanisms (3/4)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
990031 | Management Aspects related to NWDAF | MANWDAF | 2023/12/12 | 50% | SP-230181 | 75% |  |  | 0->50->75% | 28.541; 28.552; 28.554 | Niu, Yuxia, China Telecom
950036 | Enhanced Edge Computing Management | eECM | 2023/12/12 | 50% | SP-220154 | 50% |  |  | 0->5->10->20-> 35->50->50->50% | 28.541; 28.538; 28.552; 28.554; 28.531; 28.532 | Deepanshu Gautam , Samsung
990027 | Management Aspect of 5GLAN | 5GLAN_Mgt | 2023/12/12 | 45% | SP-230175 | 90% |  | SA2 | 0->45->90% | 28.541; 28.552; 28.554 | Yushuang Hu, CMCC
990033 | Management Aspects of NTN | OAM_NTN | 2023/12/12 | 0% | SP-230183 | 30% |  |  | 0->30% | 28.541; 28.552; 28.554; 28.658 | Sun Mingrui, China Unicom
eECM：
  Progress since SA5#150:
  Requirement for Federation Management got agreed. Solution for EAS Relocation got agreed
  Impacts and dependencies on other WGs:
  No Impact
MANWDAF：
Progress at SA5#150: following CRs were agreed:
  S5-235566 Rel-18 CR 28.552 Add use case on monitoring of machine learning model provisioning at NWDAF
  S5-235644 Rel-18 CR 28.552 Add measurements related to NWDAF ML model provision service; S5
Impacts and dependencies on other WGs:
  No
Next steps:
  Continue the work per WoP and update the wording in TS.
5GLAN_Mgt：
Progress at SA5#150: following CRs were agreed:
  S5-235936 (revision of S5-235667) Rel-18 CR 28.554 Add Accessibility KPIs for 5G VN group measurements
  S5-235937(revision of S5-235669) Rel-18 CR 28.554 Add Integrity KPIs for 5G VN group measurements
  S5-235938 (revision of S5-235670) Rel-18 CR 28.554 Add Utilization KPIs for 5G VN group measurements
  And one LS out to CT4 and SA2 for aligning: S5-235780 LS on Enhancement on the attribute for 5GLAN management
Impacts and dependencies on other WGs: SA2,CT4
Next steps: waiting the feedback from SA2/CT4 and continue to finish this WID.
OAM_NTN：
Progress at SA5#150: The following topics were agreed
  Rel-18 CR 28.541 NTN Location Restriction Stage-2&Stage3
  Rel-18 CR TS 28.541 Add NRM Info Model definitions for NTN management(stage2)&(stage3)Rel-18 CR 28.541 NTN Coverage Availability Information Configuration Stage 2&Stage3
Impacts and dependencies on other WGs: N/A
Next steps: specify appropriate performance measurements and KPIs for NTN

## Slide 18: Rel-18 WI - Management Architecture and Mechanisms (4/4)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
1000007 | Management of cloud-native Virtualized Network Functions | MCVNF | 2024/3/3 | 0% | SP-230764 | 30% |  | ETSI NFV | 0->30% |  | 
1000012 | Management Aspects of 5G Network Sharing Phase2 | MANS_ph2 | 2024/3/3 | 0% | SP-230629 | 30% |  | RAN3 | 0->30% |  | Mingrui,sun, China Unicom
1000013 | Management Aspects of URLLC | URLLC_Mgt | 2024/3/3 | 0% | SP-230631 | 10% |  | RAN3 | 0->10% |  | Mingrui,sun, China Unicom
MCVNF：
Progress at SA5#150: Adding the interactions with NFV-MANO in NF instance creation and deletion procedure on TS 28.531
Impacts and dependencies on other WGs: No
Next steps: Based on the conclusions of 28.834, we continue to enhance TS 28.531 and 28.533
MANS_ph2：
Progress at SA5#150: The following three CRs were agreed on this meeting: Add new requirements for management support for NG-RAN MOCN network sharing scenario; Update recommended QoS model usage for Shared RAN; Update NRM for operator specific QoS model for RAN Sharing.
Impacts and dependencies on other WGs: no changes
Next steps: Continue to update requirements, IOC and measuremnets for MOCN..
URLLC_Mgt：
Progress at SA5#150: Two CRs are submitted and one CR of UL and DL reliability configuration in slice and subnet profiles has approved on this meeting. The other CR adding new KPI on DL reliability with delay threshold in RAN will be discussed on the next meeting
Impacts and dependencies on other WGs: N/A
Next steps: Continue to way forward the performance and configuration management of URLLC

## Slide 19: Rel-18 WI - Support of New Services
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TS | Rapporteur
930010 | Access control for management service | MSAC | 2023/12/12 | 72% | SP-210859 | 73% |  | SA3 | 67->67->67%->68->69->72->73% | 28.533; 28.540; 28.622; 28.623; 28.532; | Jing Ping, Nokia
990034 | Management of non-public networks phase 2 | OAM_NPN_Ph2 | 2023/12/12 | 10% | SP-230184 | 40% |  | SA1, SA2, RAN3 | 0->10->40% | 28.557; 28.541; 28.531; 28.533; 28.552 | ZHANG, Kai, Huawei
940037 | Enhancements of EE for 5G Phase 2 | EE5GPLUS_Ph2 | 2023/12/12 | 35% | SP-211441 | 55% |  | SA2,RAN2,RAN3 | 0->0->0->10->25->30->35->55% | 28.310; 28.552; 28.554; 28.541 | Cornily Jean-Michel, Huawei
1000014 | Network and Service Operations for Energy Utilities | NSOEU | 2023/12 | 0% | SP-230632 | 30% |  | SA1 | 0->30% | 28.318, 28.522, 28.554, 28.622 | Erik Guttman, Samsung
MSAC：
Progress at SA5#150:
  Approved Input to Draft CR(S5-235947) co-signed with Deutsche Telekom, Telefonica New Baseline Draft CR – S5-235998 approval ongoing with consolidation of previously approved baseline Draft CRs(S5-234845)·
SA/RAN/CT impacts and dependencies: yes
Next steps:
  Complete Stage 2 and Stage 3 of Management Service Access controlAdd use cases and requirements for management service access control if required
OAM_NPN_Ph2:
Progress at SA5#150:
  The group agreed the solution for management of NPN service customer and the solution for NPN fault management.
Impacts and dependencies on other WGs
Next steps:
  continue discussion
EE5GPLUS_Ph2:
Progress at SA5#150:
  Two CRs have been agreed (one (for TS 28.554) introducing new metrics for estimating the energy consumption of VNF/VNFCs, and one (for TS 28.310) introducing roles involved in EE KPI building). Two CR proposals for a EE KPI definition of URLLC network slice based on reliability have been discussed but not agreed. The two contributing companies will try to converge for the next meeting.
Impacts and dependencies on other WGs:
  SA2, RAN WGs
Next steps:
  Try to converge for the definition of a unique URLLC network slice EE KPI based on reliability.
NSOEU：
Progress at SA5#150:
  Began TS, added general information
  Progress on specifying requirements and procedures for performance measurement exposure
Impacts and dependencies on other WGs: None
Next steps:
  Complete performance measurement exposure and energy recovery coordination exposure functionality

## Slide 20: Summary - Rel-18 SI - Intelligence and Automation
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
940042 | Study on enhancement of autonomous network levels | FS_eANL | SA#100 (Jun.2023)->->SA#102(Dec 2023) | 75% | SP-211446 | 85% |  | SA2, RAN3 and ETSI ZSM | 0->10->25->25->30->30%->70% with WA->75%->75->85% | 28.910 | China Mobile, Huawei
940041 | Study on evaluation of autonomous network levels | FS_ANLEVA | SA#102 (Dec.2023)->->SA#103(Mar 2024) | 60% | SP-211445 | 70% | update TR title to align with SA5 official title | SA2, RAN3 and ETSI ZSM | 0->10->10->10->10->10%->60% with WA->60->70% | 28.909 | China Mobile, Huawei
940046 | Study on enhanced intent driven management services for mobile networks | FS_eIDMS_MN | SA#100(June 2023) | 100% | SP-211450 |  |  | SA2, RAN3, ETSI ZSM, TM Forum | 0->15->40->65 ->80->90->98->100% | 28.912 | Huawei, Ericsson
950039 | Study on intent-driven management for network slicing | FS_NETSLICE_IDMS | SA#100 (Jun 2023) -> SA#101 (Sep 2023) | 70% | SP-220278 | 85% |  |  | 0->10->20->35-> 40->50->60->70->85% | 28.836 | Huawei, Ericsson
940039 | Study on AI/ML management | FS_AIML_MGMT | SA#100(June 2023) | 100% | SP-211443 |  |  | SA1, SA2, RAN3,RAN2 | 0->5->10->30 ->55%->85%->95->100% | 28.908 | Intel, NEC
940034 | Study on Enhancement of the management aspects related to NWDAF | FS_MANWDAF | SA#100(June 2023) | 100% | SP-211435 |  |  | SA2 | 0->5->30->60-> 65->75->95->100% | 28.864 | China Telecom
950035 | Study on Fault Supervision Evolution | FS_FSEV | SA#100 (Jun 2023) ->SA#103(Mar 2024) | 30% | SP-220153 | 40% |  |  | 0->10->10->15 ->20%->20->30->30->30->40% | 28.830 | China Mobile, Huawei
960024 | Study on measurement data collection to support RAN intelligence | FS_MEDACO_RAN | SA#98(Dec. 2022) | 100% | SP-220488 |  |  | RAN2,RAN3 | 0->10->10->100 % | 28.838 | Intel, China Mobile

## Slide 21: Rel-18 SI - Intelligence and Automation (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
940042 | Study on enhancement of autonomous network levels | FS_eANL | SA#100 (Jun.2023) ->SA#102(Dec 2023) | 75% | SP-211446 | 85% |  | SA2, RAN3 and ETSI ZSM | 0->10->25->25->30->30%->70% with WA->75%->75->85% | 28.910 | China Mobile, Huawei
940041 | Study on evaluation of autonomous network levels | FS_ANLEVA | SA#102 (Dec.2023)->->SA#103(Mar 2024) | 60% | SP-211445 | 70% | update TR title to align with SA5 official title | SA2, RAN3 and ETSI ZSM | 0->10->10->10->10->10%->60%->70% | 28.909 | China Mobile, Huawei
FS_eANL：
Progress at SA5#150:
  add recommendation for KI#5.1b: RAN UE throughput optimization
  add potential solutions for KI#6-1: RAN energy saving
  add use cases and requirements for management of ANL.
Impacts and dependencies on other WGs:
  None identified
Next steps:
  add potential solution for KI #6.2, discuss management of ANL, make conclusion and recommendation for the rest of the KIs and present Draft TR to SA for approval.
FS_ANLEVA：
Progress at SA5#150:
  update concept for key effectiveness indicator, add conclusion and recommendation for generic methodology for autonomous network levels evaluation.
  Impacts and dependencies on other WGs:
  None identified
Next steps:
  add potential solution for KEI of fault management and other use cases defined in Rel-17, analyse and discuss the conclusion and recommendation for the KIs without conclusion yet.

## Slide 22: Rel-18 SI - Intelligence and Automation (2/2)
FS_NETSLICE_IDMS：
Progress since SA5#150:
  Four of ten contributions where agreed, and good discussions on expectation and expectation object where had, but not yet completed. The main outstanding question is the definition of the object type
Impacts and dependencies on other WGs:
  not identified
Next steps:
  Complete solution descriptions, conclusions and recommendations.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
950039 | Study on intent-driven management for network slicing | FS_NETSLICE_IDMS | SA#100 (Jun 2023) -> SA#102 (Dec 2023) | 70% | SP-220278 | 85% |  |  | 0->10->20->35-> 40->50->60->70->85% | 28.836 | Huawei, Ericsson
950035 | Study on Fault Supervision Evolution | FS_FSEV | SA#100 (Jun 2023) ->SA#103(Mar 2024) | 30% | SP-220153 | 40% |  |  | 0->10->10->15 ->20%->20->30->30->30->40% | 28.830 | China Mobile, Huawei
FS_FSEV：
Progress at SA5#150:
  5 contributions were discussed
  1 contribution S5‑236079 about failure prediction was approved
  Others were noted, the topics are about performance KPI related analysis, performance related alarm analysis, root cause analysis and description for relation with MDA and close loop control.
  Impacts and dependencies on other WGs:
  Not identified yet
Next steps:
  To discuss performance related alarm analysis and try to conclude some issues such as concepts, failure prediction, relation with MDA and closed loop control etc.

## Slide 23: Summary Rel-18 SI - Management Architecture and Mechanisms
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
910031 | Study on Enhancement of service-based management architecture | FS_eSBMA | SA#100(Jun 2023) | 100% | SP-211451 |  |  |  | 45->50->60->65->75%->80%->85->100% | 28.925 | Huawei, Ericsson
950027 | Study on Basic SBMA enabler enhancements | FS_eSBMAe | SA#100(Jun 2023) | 100% | SP-220145 |  |  |  | 0->5->10->15->25->35 ->70->100% | 28.831 | Nokia
950028 | Study on Management Aspects of URLLC | FS_URLLC_Mgt | SA#100(June 2023) | 100% | SP-220146 |  |  |  | 0->10->15->15->40->60->62->80->100% | 28.832 | China Unicom
950030 | Study on Management Aspect of 5GLAN | FS_5GLAN_Mgt | SA#99 (Mar. 2023) | 100% | SP-220324 |  |  | SA2 | 0->10->25->45 ->65%->98%->100% | 28.833 | China Mobile
950032 | Study on Management of Cloud Native Virtualized Network Functions | FS_MCVNF | SA#100(June 2023) | 100% | SP-220150 |  |  |  | 0->0->5->15-> 30->70%->95% | 28.834 | China Mobile
950033 | Study on Management Aspects of 5G MOCN Network Sharing Phase2 | FS_MANS_ph2 | SA#100(Jun 2023) | 100% | SP-220151 |  |  |  | 0->10->30->40-> 75->90->94->100% | 28.835 | China Unicom
950034 | Study on Management of Trace/MDT phase 2 | FS_5GMDT_Ph2 | SA#100(Jun 2023) | 100% | SP-220152 |  |  |  | 0->10->15->20->25->35->60% | 28.837 | Nokia
960026 | Study on Management Aspects of IoT NTN Enhancements | FS_IoT_NTN | SA#100(Jun 2023) | 100% | SP-220490 |  |  |  | 0->20->30->75->95->100% | 28.841 | China Unicom
970029 | Study on Data management phase 2 | FS_MADCOL_ph2 | SA#100 (Jun 2023) | 25% | SP-220842 | 45% |  |  | 0->5->10->15->25->45% |  | Nokia

## Slide 24: Rel-18 SI - Management Architecture and Mechanisms
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
970029 | Study on Data management phase 2 | FS_MADCOL_ph2 | SA#100 (Jun 2023) | 25% | SP-220842 | 45% |  |  | 0->5->10->15->25->45% |  | Nokia
FS_MADCOL_ph2：
Progress since SA5#150:
  It was agreed that the 3GPP system shall have a capability allowing MnS consumers to discover MnS producers that support retrieval of historical data. Furthermore, the “DataCollectionRequest” was identified as one method for retrieving historical data when the consumer is unaware of managed objects. It was agreed that it must be possible to discover which data reporting methods a MnS producer supports. The understanding of what a “harmonized data model” means was progressed.
Impacts and dependencies on other WGs:
  Not identified
Next steps:
  Continue the work on the SID objectives

## Slide 25: Summary - Rel-18 SI - Support of New Services
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
940035 | Study on enhancement of management of non-public networks | FS_OAM_eNPN | SA#99(Mar 2023) | 100% | SP-220152 |  | ready for SA Information approval |  | 0->10->40->60->80->90->100% | 28.907 | Huawei
940036 | Study on new aspects of EE for 5G networks Phase 2 | FS_EE5G_Ph2 | SA#100(June 2023) | 100% | SP-211440 |  |  | SA, SA2, RAN WGs | 0->10->10->15->25->50->50->100% | 28.913 | Huawei
940040 | Study on Network and Service Operations for Energy Utilities | FS_NSOEU | SA#100(Jun 2023) | 100% | SP-211622 |  |  |  | 0->10->15->35->45->55->79->100% | 28.829 | Samsung
940032 | Study on Key Quality Indicators (KQIs) for 5G service experience | FS_KQI_5G | SA#100(June 2023) ->SA#103(Mar 2024) | 55% | SP-211433 | 65% |  | SA4,RAN2,RAN3 | 0->5->10->10 ->20->20->35->55->55->65% | 28.863 | Huawei
940038 | Study on Deterministic Communication Service Assurance | FS_DCSA | SA#100(June 2023) ->SA#103(Mar 2024) | 45% | SP-211442 | 60% |  | SA2, SA6, RAN2, SA4 | 0->5->30->32 ->32->32->45->60% | 28.865 | Huawei
910026 | Study on network slice management capability exposure | FS_NSCE | SA#100(June 2023) | 100% | SP-220350 |  |  | SA3, SA, RAN | 70->75->80->82->83%->90%->92>98->100% | 28.824 | Alibaba
950029 | Study on alignment with ETSI MEC for Edge computing management | FS_MEC_ECM | SA#100(June 2023) | 100% | SP-220147 |  |  | SA6, ETSI MEC | 0->5->15->40 ->50->50->70->100% | 28.903 | Huawei

## Slide 26: Rel-18 SI - Support of New Services
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment | Related groups | SA5 Progress | TR | Rapporteur
940032 | Study on Key Quality Indicators (KQIs) for 5G service experience | FS_KQI_5G | SA#100(June 2023) ->SA#103(Mar 2024) | 55% | SP-211433 | 65% |  | SA4,RAN2,RAN3 | 0->5->10->10 ->20->20->35->55->65% | 28.863 | Huawei
940038 | Study on Deterministic Communication Service Assurance | FS_DCSA | SA#100(June 2023) ->SA#103(Mar 2024) | 45% | SP-211442 | 60% |  | SA2, SA6, RAN2, SA4 | 0->5->30->32 ->32->32->45->60% | 28.865 | Huawei
FS_KQI_5G：
Progress at SA5#150:
  The correction of the KQI definition in 3GPP and other standard organizations has been approved.
Impacts and dependencies on other WGs:
  Not identified
Next steps:
  Continue to push the KQI for video uploading and remote control based on the 3GPP service.
FS_DCSA：
Progress at SA5#150:
  No contribution at this meeting
Impacts and dependencies on other WGs:
  No impacts and dependencies on SA/RAN/CT
Next steps:

## Slide 27: List of latest DraftCRs
Tdoc# Tdoc# for latest DraftCR | Title | Source Company | Rapporteur | Agenda | Latest approved DraftCR from previous meeting(s) | Approved Input(s) to DraftCR at this meeting
S5‑235998 | DraftCR 28.533 on Access control for management service | Nokia, Deutsche Telekom | Nokia | 6.6.1.3 | S5-234845 | S5-235947
S5-235762 | Draft CR eMDAS_Ph2 – TS28.104; Further enhancements into the Management Data Analytics (Phase 2). | NEC | Intel, NEC | 6.4.2.1 | S5-235733 | S5-235207 S5-235820 S5-235821 S5-235819 S5-236093 S5-235942
S5-235988 | Draft CR AIML_MGMT – TS28.105; Enhancements for AI-ML management. S5-234593 converted from CR to draft CR, and using it as baseline of skeleton. | Intel | Intel, NEC | 6.4.3.1 | S5-235139 | S5‑235827 S5‑235828 S5‑236075 S5‑235837 S5‑235838 S5‑235839 S5‑235840 S5‑235999
S5-235989 (email approval) | Draft CR 28.538 Revise EAS VNF instantiation and termination procedures | Intel | Samsung | 6.5.8.1 | S5-233152 (SA5#147) | S5-233152 S5-235916 S5-235917 S5-235920 S5-235921 S5-235922 S5-235923
S5-235869 | DraftCR eSBMA- TS32.300; Introduction of SBMA in 32.300 | Ericsson | Ericsson | 6.5.1.4 | NA | First Draft CR without any other input contribution: S5-235869
S5-235871 | DraftCR eSBMA- TS32.158 | Nokia | Nokia | 6.5.1.6 | NA | First Draft CR without any other input contribution: S5-235871
S5‑236113 | Add Forge as a potential normative storage for Code | Ericsson | Ericsson | 6.3.1 | NA | No need more actions.
S5‑236114 | Add Forge as a potential normative storage for Stage 3 OpenAPI code | Ericsson | Ericsson | 6.3.1 | NA | No need more actions.

## Slide 28: New action items from this meeting
Item | Description | Rel. | Owner | Status | Target
150.1 | Check SA2 and SA5 working progress on network provisioning, network performance analysis and identify the relation. (S5-235650/S5 233550/S5-232774) | Rel-18 | SA5 leaders, Yizhi Yao, Zhaosong | Open | SA5#152
150.2 | Need a way to clearly distinguish MnS specification which is not for MnS(S5-235419) | Rel-18 | Olaf, Mark | Open | SA5#152

## Slide 29: TRs / TSs to be sent to SA#101
Tdoc | Title | Source | Sent for
S5-234082 | Presentation of Specification/Report to TSG: TR 28.925, Version 1.0.0 | Ericsson | Information and approval

## Slide 30: TRs / TSs to be sent to Edithelp
Tdoc | Title | Source

## Slide 31: Rapporteur calls (draft plan after SA5#150)
Rapporteur calls | DateTime | Potential Topics
#150.1 | 29 June 13:00 ~15:00 UTC | Open
#150.2 | 3 August 13:00 ~15:00 UTC | Open
Latest update on the rapporteur call agenda in : https://www.3gpp.org/ftp/Email_Discussions/SA5/OAM%20rapporteur%20calls/Rapporteur%20call%20%23147

## Slide 32: Thank you!

## Slide 33: Leaders’ recommendation for SA5 OAM time planning in S5‑232763 Rel-18&Rel-19 time plan proposal for OAM (Endorsed)
SA5 OAM Release 18 planning：
Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
Mar 2023 (SA#99) and Jun 2023(SA#100): SA5 SID concluded and Rel-18 WID started if needed
Sep 2023 (TSG#101): Stage 1 work freeze
Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to SA2 and CT
Mar 2024 (TSG#103): Stage 2 Functional work Freeze and stage 3 (RAN related)
SA5 OAM Release 19 planning：
June 2023 SA Rel-19 workshop: Provide SA5 relevant Rel-19 inputs/planning to Jun SA workshop
Sep 2023 (TSG#101): Submit Rel-19 1st package following 3GPP timelines
Dec 2023 (TSG#102): Submit Rel-19 final package following 3GPP timelines
Note:
We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
For the CT related features, we need to provide inputs to CT as early as possible.
Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
Avoid exception requests as much as possible, and in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.

## Slide 34
TSG#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN Content def.
RAN Completion (RAN2/3/4core)
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
Release 18 timeline– figure with SA5 OAM
Studies (SA5 OAM)
Stage 1 (SA5 OAM)
Stage 2 Functional and stage 3 work (OAM/CN related),
provide inputs to CT
Stage 2 Functional and stage 3 work (RAN related)
SA5 OAM Rel-18 Timeline
Ref: S5-232763 updated

## Slide 35
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content; SA2 Work Items prioritization; RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96) till March 2023 (#99): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work (SA2 and SA6) Freeze
  Sep 2023 (TSG#101):
    RAN1 freeze before maintenance
    Freeze for SA3
  Dec 2023 (TSG#102):
    RAN1 freeze after maintenance
    RAN2, RAN3, RAN4Core freeze before maintenance
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs
Now
Release 18 timelines – with SA5 OAM text
SA5 OAM Release 18 Freezes and other milestones, sorted by dates :
  Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
  Mar 2023 (TSG#99) and Jun 2023(TSG#100): SA5 SID concluded and Rel-18 WID started if needed
  Sep 2023 (TSG#101): Stage 1 work freeze
  Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to CT
  Mar 2024 (TSG#103): Stage 2 Functional work Freeze and stage 3 (RAN related)
Updated at SA5#146bis-e
Support of SA2, provide inputs to CT
Support of RAN
Now
Ref: updated of S5-232763 according to SA#99 inputs

## Slide 36
TSG#93-e
SA1 Stage 1 80%
100%
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN4
content def.
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
RAN Rel-19 workshop
SA Rel-19
Workshop (TBC)
Note: Other Rel-19 milestones/timelines to be specified (latest June 2023 for SA/CT)
SA St.2 Content approval
Rel-19 planning
Release 19 timeline– figure with SA5 OAM
SA Rel-19 workshop
SA stage2
1st package
SA stage2
final package
SA5 OAM Rel-19 planning
SA5 will collect the potential work area and provide inputs to SA workshop in Jun, September and December based on group agreement.

## Slide 37
TSG#101
Note: All starting dates are indicative
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
RAN Rel-19 workshop
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
SA Rel-19
Workshop
TSG#100
June
2023
Now
NEW at TSG#99 - Working assumption for SA, endorsed for RAN
100%
SA1 Stage 1 80%
Release 19 timeline– figure with SA5 OAM (considering of sync with SA1/SA2/SA6/RAN/CT)
Studies (SA5 OAM)
Stage 1 (Standalone OAM –part 2/SA5 RAN related OAM)
Stage 2 Functional and stage 3 work (standalone OAM part 2/RAN related OAM)
SA5 OAM Rel-19 Timeline
SA5#151~152:New Rel-19 SIDs
SA5#155~156:New WIDs
package 2
Studies (SA5 OAM)
Stage 1 (Standalone OAM-part 1/SA2/SA6 related OAM)
Stage 2 Functional work (SA2/6 related OAM) and CT related stage3 work, Stage2/stage3 for standalone OAM-part1
Categorization of SA5 work:
Standalone OAM (part 1 and part 2)
  Part1: work related to Rel-18 study with no Rel-18 WI and other potential high priority WIs.
  Part2: other potential rel-19 SIs/WIs.
SA1 related OAM
SA2/6 related OAM
RAN/CT related OAM
Key sync periods and potential sync consideration:
① Jun (SA5#150) ~Dec.2023 (SA5#152/ TSG#102) follow SA1 discussion with DP
② Oct (SA5#151) ~Dec.2023 (SA5#152/TSG#102): Rel-19 SIs discussion time window. All SIs are to be ready in TSG#102.
③ Jan (SA5#153) ~Jun. 2024 (SA5#155/TSG#104): WID package 1(Standalone OAM part1 and SA2/SA6 related OAM) discussion time window. Standalone OAM part 1 and SA2/SA6 related Wis should be ready in TSG#104, to be able to sync with SA2/SA6 discussion.
④ Jun (SA5#155)~Sep. 2024 (SA5#156/TSG#105): WID package 2 (standalone OAM part 2 and RAN/CT related OAM) discussion time window. Standalone OAM part 2 and RAN related SIs are to be ready in TSG#105, to be able to sync with RAN/CT.
⑤Jun (SA5#150) ~Dec.2023 (SA5#152/ TSG#102) potential sync time window with SA1(6 months).
⑥ Apr (SA5#154)~Dec,2024 (SA5#158): potential sync time window with SA2/SA6(9 months).
⑦Oct,2024(SA5#157)~Sep,2025 (TSG#109): potential sync time window with RAN/CT (12 months).
②
⑥ 9 months SA2/6 sync
⑦ 12 months RAN/CT sync
Work item 15 months
Studies 6 months
SA5#150~152:Follow SA1 discussion with DP
①
④
⑤ 6 months SA1 sync
Studies (SA5 OAM) (standalone OAM-part2)
③
SA5#153~155: New WIDs package 1

## Slide 38
OAM General Topics (Rel-18 prioritization and Work Package)
Info about WoP:
  We need to start the Rel-18 work at SA5#142e – all SA-approved Rel-18 WI/SIs should be on the agenda.
  Definition of the complete set of WoPs for each Rel-18 WID/SID should be proposed by the work item rapporteurs as input contributions to SA5#142e and agreed there, which means that the WoPs can and should then be used as basis for selection of subsets of the WoPs on the agenda for SA5#143e.
  Therefore we need some other less formal way of reducing the agenda for SA5#142e, if we want that – like a leaders recommendation of what to focus on, e.g. initial skeleton proposals and/or DPs. Maybe this will come natural anyway for a first Rel-18 meeting, so we did not decide on any such leaders recommendation yet (but I still ask everyone to consider that, to avoid a huge overload of Rel-18 contributions at the same time as we need to finish the Rel-17 work items with approved exceptions as well as the earlier Rel-17 studies that continue into Rel-18).
  The WoPs shall in no way modify the content or meaning of the objectives in the approved WID/SIDs – they are only allowed to identify clearly defined subsets of the objectives, typically one WoP per “main bullet” in the WID/SID Objectives, or in some cases subsets of a bullet if it’s clearly separable.
  The SA5#142e-agreed complete set of WoPs for each Rel-18 WID/SID should be documented as an “SA5-local WID/SID update with WoPs” (no need to send them to SA for approval).
  Then we ask the rapporteurs to propose a subset of all agreed WoPs to be recommended to the leaders to be put on the agenda for next meeting, which means that contributions to the next meeting (143e) are only allowed to address the selected WoPs. We don’t spend time on this selection during the meeting, as the agreed WoPs are not known until the end of the meeting but also to save time for the tdoc discussions and conclusions in the meeting.
  We will add the selection of subsets of WoPs to the real meeting agenda as “level 4 (or 5)” agenda item (e.g. 6.3.4.1 for WoP no. 1 in agenda 6.4.3) so that this has to be used for tdoc agenda allocation in 3GU. This is possible in 3GU according to Mirko. The next meeting’s draft agenda shall be sent out for email review asap after the meeting, and then it will be decided by the leaders after any comments have been considered. Thus the WoP selection for SA5#143e should be known soon after SA5#142e finished, for everyone to be able to plan and prepare contributions for SA5#143e as early as possible.
  This also means that the leaders have “full control” to decide about the WoP selection in the agenda for next meeting (like we always have for the agenda), and it is not possible to contribute to any other WoPs than the selected ones.
  This also has the big advantage that we can follow the “statistics of number of tdocs for every WoP” at every meeting to see an indication of the progress for each WoP and at the end of the release check if all objectives (WoPs) have been addressed with some contributions (and how many were agreed).
Latest version of WoP is captured in S5‑232012 Collection of Rel-18 3GPP SA5 OAM WoPs
  We ask every rapporteur to provide proposal to update the WoP if needed, the latest version will be updated in S5-226xyz.