## Slide 1: FS_Metaverse_App Work plan
Sapan Shah
Rapporteur, Samsung

## Slide 2: Contents
TU Status and plan
TR Status and plan

## Slide 3: FS_Metaverse_App (SID/WID) Status
Meeting | TUs Planned |  | Work Planned | TUs Consumed | Work Completed
 | SID | WID |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval | - | SID Approval completed
SA6#58 (Nov-23) | 2.0 TUs | - | Skeleton, Scope, Key Issues | 1 (SID) | Skeleton, scope and 2 Key issues agreed
SA6#59 (Feb-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions | 2 (SID) | 1 Architecture option, 3 new KIs, 2 Solutions
SA6#60 (Apr-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions | 2 (SID) | Definitions, 2 new KIs, 5 Sol Update, 6 new solutions, 2 KI updates, 1 architecture option
SA6#61 (May-24) | 2.0 TUs | - | Key Issues (Freeze), Solutions, Start Solution Conclusions. Send for Information. WID Approval | 2 TUs? | New Solutions (with Sol. Evaluation), Solution evaluations, Architecture requirements, Deployment scenarios, Business relationships (if any).
SA6#62-Adhoc-e (Jul-24) (10 – 18 July 2024 - TBD) | 2.0 TUs | 1.0 TUs | Finish Solution Conclusions, Send TR for Approval Begin Normative work (architecture impacts) |  | 
SA6#62 (Aug-24) | - | 2.0 TUs | Architecture and Solutions, Business Relationships |  | 
SA6#63 (Oct-24) | - | 3.0 TUs | Architecture and Solutions, Deployment models |  | 
SA6#64 (Nov24) | - | 3.0 TUs | Complete unfinished work, WID complete / Send for Approval. |  | 
Total | 10 TUs | 9 TUs |  | 5 TUs | 

## Slide 4: TR Status and plan (1/2)
Content | Current Status | Remark
Scope | Completed | 
Reference | On going | 
Definitions of terms, symbols and abbreviations | On going | If new term is introduced, it needs to be defined.
Key issues | Key issue #1: Enabler support for managing spatial anchors Key Issue #2: Exposure of user sensitive information Key issue #3: Digital avatars support Key issue #4: Spatial mapping Key issue #5: Support for avatar discovery and QoS control Key issue #6: Support device discovery to offload task for metaverse services Key issue #7: Support for metaverse services requiring multiple devices Key issue #8: Enabler support for spatial anchors based services | If companies are planning to bring new KIs, bring with solution. Resolve ENs.
Application enablement architecture requirements | Not present | Recommended to complete by SA6#61
Application enablement architecture for metaverse services | Option #1: On-network mobile metaverse application layer architecture Option #2: A-DACM architecture to support Metaverse services | - Need to resolve ENs - Need to evaluate the architecture

## Slide 5: TR Status and plan (2/2)
Content | Current Status | Remark
Solutions | Solution #1: Spatial anchor discovery Solution #2: Support for spatial anchor management Solution #3: Spatial anchor subscription Solution #4: Support for spatial anchor analytics information Solution #5: Support for digital avatars Solution #6: Avatar support using Metaverse Digital Representation Block (MDRB) Solution #7: Digital avatar support by A-DACM Solution #8: Support for spatial map management | - Solutions for KI 2, 5, 6 and 7 are not present, recommended to give preference and bring solutions for these KIs.
Deployment scenarios | Not present | Recommended to complete by SA6#61
Business Relationships | Not present | Recommended to complete by SA6#61
Overall evaluation | Not present | Need to start working on this
Conclusions | Not present | Need to start working on this