## Slide 1: SA6#45-e Work Plan Review
Suresh Chitturi
SA6 Chairman
SAMSUNG

## Slide 2: Overview: Rel-17 Work Items – 1/2
Work Item | WI Code | WID Approved | SA#92-e | SA6#44-e | SA6#45-e | Target Completion | Remarks
Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 | eMONASTERY2 | SA#84 (06/2019) | 100% | 100% | 100% | SA#89 (09/2020) | 
MC services support on IOPS mode of operation | MCIOPS | SA#84 (06/2019) | 100% | 100% | 100% | SA#89 (09/2020) | 
Enhanced Mission Critical Push-to-talk architecture phase 3 | enh3MCPTT | SA#87 (03/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Enhancements for functional architecture and information flows for Mission Critical Data | eMCData3 | SA#86 (12/2019) | 100% | 100% | 100% | SA#92 (06/2021) | 
Architecture for enabling Edge Applications | EDGEAPP | SA#86 (12/2019) | 98% | 99% | 99% | SA#90 (12/2020) | 

## Slide 3: Overview: Rel-17 Work Items – 2/2
Work Item | WI Code | WID Approved | SA#92-e | SA6#44-e | SA6#45-e | Target Completion | Remarks
Enhanced application layer support for V2X services | eV2XAPP | SA#89 (09/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Application Architecture for MSGin5G Service | 5GMARCH | SA#89 (09/2020) | 75% | 80% | 90% | SA#92 (06/2021) | TS for approval at SA#93-e. Exception sheet to be prepared.
Mission Critical Services over 5GS | MCOver5GS | SA#89 (09/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Enhanced Service Enabler Architecture Layer for Verticals | eSEAL | SA#90 (12/2020) | 80% | 90% | 100% | SA#92 (06/2021) | 
Application layer support for Uncrewed Aerial System (UAS) | UASAPP | SA#90 (12/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 

## Slide 4: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#92-e | SA6#44-e | SA6#45-e | Target Completion | Remarks
Study on application layer support for Factories of the Future in 5G NW | FS_FFAPP | SA#82 (12/2018) | 98% | 100% | 100% | SA#93 (09/2021) | TR for approval at SA#93-e (agreed at SA6#44)
Study on Mission Critical Services support over 5G System | FS_MCOver5GS | SA#80 (06/2018) | 80% | 85% | 87% | SA#93 (09/2021) | Revised SID with new date (June 2022)
Study of Gateway UE function for Mission Critical Communication | FS_MCGWUE | SA#88 (06/2020) | 60% | 80% | 100% | SA#93 (09/2021) | TR for approval at SA#93-e
Study of Interconnection and Migration Aspects for Railways | FS_IRail | SA#88 (06/2020) | 30% | 50% | 60% | SA#93 (09/2021) | Revised SID with new dates (Dec 2021). TR for information at SA#93-e
Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | SA#91 (03/2021) | 0% | 10% | 25% | SA#95 (03/2022) | 

## Slide 5: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#92-e | SA6#44-e | SA6#45-e | Target Completion | Remarks
Study on application enablement aspects for subscriber-aware northbound API access | FS_SNAAPP | SA#92 (06/2021) | 0% | 10% | 20% | SA#95 (03/2022) | 
Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | SA#92 (06/2021) | 0% | 10% | 15% | SA#95 (03/2022) | 
Study on enhanced Application Architecture for enabling Edge Applications | FS_eEDGEAPP | SA#92 (06/2021) | 0% | 5% | 10% | SA#95 (03/2022) | 
Study on 5G-enabled fused location service capability exposure | FS_5GFLS | SA#92 (06/2021) | 0% | 5% | 20% | SA#95 (03/2022) | 

## Slide 6: Overview: New Rel-18 Work-Items
Study Item | WI Code | SID Approved | SA#92-e | SA6#44-e | Target Completion | Remarks
Mission Critical Services over 5MBS | MCOver5MBS | New WID | - | 0% | SA#95 (03/2022) | Work to begin in Q4/2021

## Slide 7: Conference calls and other items
Pre-SA6#45-BIS-e conference calls
  5GMARCH – 1 (date TBD)?
  MCX – 1 (date TBD)?
  New WID/SIDs – 1 (date TBD)?
  EDGEAPP – 1 (TBD)?
  FS_NSCALE – 1 (TBD)?
R18 SA WS on Sep 09-10
Q1/2022 SA6 meeting dates to be e-meetings
Rapporteurs to make the draft TRs/TSs available within one week!
All revisions MUST be in the inbox folder!

## Slide 8: Thank You!