## Slide 1: Discussion on guidelines for SA6 WIs management
Niranth, Yanmei (Huawei)

## Slide 2: Background
For S6-220997 (Revised WID proposal for MCOver5MBS), several discussions are held.
  The only change in the Revised WID is to the planned end date.
Different viewpoints have been shared about such a change.
  Analysis of the objectives have shown there is no left over work. Some corrections are on-going which is normal and does not impact the timeline for the WID.
  Dependency on SA2 R18 work has been cited with unknown impact, whereas the WID is based on R17 normative work of SA2 and the concluded R18 study.
  There is time for stage 2 freeze, so let us extend the WID time.
The decisions on the WID and the WI progress does impact WG project management and IM understanding of the work to be completed for which IMs can plan contributions for subsequent meetings. So, some guidelines are necessary for SA6 WIs management.
The following questions arise:
  Managing WI with dependencies on other WGs?
  What should be the guidelines to assess the progress of a WI?
  What should be the guidelines to assess whether WID update is required?

## Slide 3: Managing WI with dependencies on other WGs?
The following aspects need attention:
  Release mapping with other WGs - SA6 R18 should be based on which release of SA2/RAN?
  If SA6 Rel18 is based on the completion of Rel18 in SA2,RAN, then how to make that possible since the timeline of SA6 Rel18 is the same as other WGs?
Based on the above aspects WIDs can have the following dependencies with other WG work (e.g. SA2).
  R18 WID with dependency on SA2 for 5GC architecture of R17 and earlier.
  R18 WID with dependency on SA2 for 5GC architecture for R18 itself.
Regarding (a), there are clear timelines for the work completion and can be fulfilled without any coordination with SA2.
  There is no impact due to on-going R18 work in SA2.
Regarding (b), SA6 should propose a completion time later to the work completion time of SA2. Example: SA6 completion time should be at least 1 quarter after SA2 completion time.
  A problem may arise when SA2 completion time is the release freeze time. Then SA6 completion time will be beyond release freeze time.

## Slide 4: What should be the guidelines to assess the progress of a WI?
Suggestions for guidelines to assess WI progress
  The progress should be assessed based on the completion of WID objectives.
    Outstanding ENs related features corresponding to the objectives contribute to the assessment of an objective.
  Outstanding issues based on objectives should be identified if the WI does not complete in time as per the approved WID.
    If WI is dependent on other WG, then clear evidence of other WG work impacting SA6 work should be identified.
    These will serve as the necessary justification for revising the WI timeline or the objectives.
  WIs should be progressed as complete, if the WI objectives have been met.
    There is always maintenance TUs which may be due to FASMO, alignment asked by other WGs which does not impact the progress of the WI.
  Subjective opinions without evidence of any outstanding issues should not be considered towards assessment of WI progress.

## Slide 5: What should be the guidelines to assess whether WID update is required?
Suggestions for guidelines to assess whether WID update is required:
  SA6 R18 work dependent on R17 work of other WGs, Change in objectives which result in either delaying the timeline or to meet the timeline.
  SA6 R18 work dependent on R18 work of other WGs, Change in objectives to meet the timeline. Some work may not get included in R18 and hence should be considered for future release.
  All WIDs does not require to have the completion time to be the release freeze time for stage 2. (This situation is usually a project management nightmare)

## Slide 6: Summary
Discuss and agree a mechanism for managing WI with dependencies on other WGs
  SA6 WIs based on previous release work of other WGs can be completed as per the time plan.
  SA6 WIs based on current release work of other WGs can impact the completion time.
Discuss and agree some draft guidelines in slide 4 for assessing the WI progress.
Discuss and agree some draft guidelines in slide 5 for assessing whether WID update is required.
Suggestions are welcome!