## Slide 1: ICC 8 Feb 2023 Work Plan Review
Alan Soloway (Qualcomm)
SA6 Chair

## Slide 2: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Study on sharing of administrative configuration between interconnected MC service systems | FS_MCShAC | SA#94 (12/2021) | 65% | 65% | SA#99 (03/2023) | 
Study on Mission Critical Ad hoc Group Communications Support for Mission Critical Services | FS_MCAHGC | SA#94 (12/2021) | 95% | 100% | SA#97 (09/2022) | We didn’t receive any TDocs for this meeting.
Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | SA#91 (03/2021) | 100% | 100% | SA#96 (06/2022) | 
Study on application enablement aspects for subscriber-aware NB API access | FS_SNAAPP | SA#92 (06/2021) | 100% | 100% | SA#96 (06/2022) | 

## Slide 3: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | SA#92 (06/2021) | 85% | 85% | SA#97 (09/2022) | 
Study on 5G-enabled fused location service capability exposure | FS_5GFLS | SA#92 (06/2021) | 100% | 100% | SA#97 (09/2022) | 
Study on enhanced Application Architecture for enabling Edge Applications | FS_eEDGEAPP | SA#92 (06/2021) | 100% | 100% | SA#96 (06/2022) | 
Study on enhanced architecture for UAS Applications | FS_eUASAPP | SA#93 (09/2021) | 100% | 100% | SA#97 (09/2022) | 

## Slide 4: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Study on SEAL data delivery enabler for vertical applications | FS_SEALDD | SA#93 (09/2021) | 100% | 100% | SA#97 (09/2022) | 
Study on enhancements to application layer support for V2X services; Phase 2 | FS_eV2XAPP2 | SA#93 (09/2021) | 100% | 100% | SA#97 (09/2022) | 
Study on Application Data Analytics Enablement Service | FS_ADAES | SA#94 (12/2021) | 100% | 100% | SA#97 (09/2022) | 
Study on Application layer support for Personal IoT and Residential Networks | FS_PINAPP | SA#94 (12/2021) | 90% | 100% | SA#97 (09/2022) | Progress since SA#98-e: 2 pCRs for draft TR 23.700-78 were approved; Add requirements and supplement of PIN create

## Slide 5: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Mission Critical Services over 5MBS | MCOver5MBS | SA#93 (09/2021) | 100% | 100% | SA#95 (03/2022) | 
Mission Critical Services over 5GProSe | MCOver5GProSe | SA#94 (12/2021) | 100% | 100% | SA#99 (03/2023) | 
Gateway UE function for Mission Critical Communication | MCGWUE | SA#93 (09/2021) | 100% | 100% | SA#96 (06/2022) | 
Enhanced Mission Critical Push-to-talk architecture phase 4 | enh4MCPTT | SA#94 (12/2021) | 65% | 70% | SA#99 (03/2023) | 
Interconnection and Migration Aspects for Railways | IRail | SA#95 (03/2022) | 75% | 75% | SA#98 (12/2022) | No paper was agreed
Application layer support for Factories of the Future (FF) | FFAPP | SA#93 (09/2021) | 65% | 75% | SA#99 (03/2023) | 

## Slide 6: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Enhanced Service Enabler Architecture Layer for Verticals Phase 2 | eSEAL2 | SA#94 (12/2021) | 60% | 80% | SA#98 (12/2022) | 
New WID on support of the MSGin5G Service phase 2 | 5GMARCH_Ph2 | SA#95 (03/2022) | 70% | 75% | SA#99 (03/2023) | We have covered most objective of the WID, but we agreed that many issues are needed to be re-visited, e.g. bulk-registration/de-registration solutions, Proxy/Relay UEs etc.
Application enablement aspects for subscriber-aware northbound API access | SNAAPP | SA#96 (06/2022) | 55% | 85% | SA#99 (03/2023) | We have covered all the study solutions/conclusions.

## Slide 7: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Network Slice Capability Exposure for Application Layer Enablement | NSCALE | SA#96 (06/2022) | 30% | 55% | SA#99 (03/2023) | 3 services, part of deployment and business relationship were approved
Application Architecture for enabling Edge Applications Phase 2 | EDGEAPP_Ph2 | SA#97 (09/2022) | 30% | 45% | SA#99 (03/2023) | - Total 24 KIs were studied. - There is a progress in normative work related to 14 KIs - Among remaining 10 KIs – there were contributions related to 7 KIs, while 3 KIs had no contributions.

## Slide 8: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Edge Application Standards in 3GPP and alignment with External Organizations | EDGEAPP_EXT | SA#96 (06/2022) | 5% | 5% | SA#100 (06/2023) | No contribution in this meeting. Status remains the same.
Architecture for UAS Applications, Phase 2 | UASAPP_Ph2 | SA#97 (09/2022) | 25% | 35% | SA#99 (03/2023) | multi-USS almost completed, solutions from InterDigital & Lenovo included in flows, IEs and API DAA barely started, no solutions Coordination between Uu and PC5, nothing done

## Slide 9: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
SEAL data delivery enabler for vertical applications | SEALDD | SA#97 (09/2022) | 60% | 75% | SA#99 (03/2023) | Progress since SA#98-e: 9 pCRs for draft TS 23.433 were approved ; 1 CR for TS 23.434 was agreed; and 1 CR for TS 23.558 was agreed.
Application layer support for V2X services; Phase 3 | V2XAPP_Ph3 | SA#97 (09/2022) | 45% | 45% | SA#99 (03/2023) | Progress since SA#98-e: None

## Slide 10: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
Application Data Analytics Enablement Service | ADAES | SA#97 (09/2022) | 45% | 60% | SA#99 (03/2023) | SA6#52-Bis-e outcomes: 1 new feature added on service API analytics, and common identities clause was filled. Architecture aspects moved from 23.434 to 23.436 Remaining work (40%): • 3/9 solutions still missing (1 from Convida, 1 from Samsung, 1 from Lenovo); however there was some discussion on Convida/Samsung proposed features. (expected effort 25-30%) • API clause and remaining requirements to be added from the TR (5%) • Possible architecture enhancement for data collection based on E/// DP related to NSCALE (5-10%)

## Slide 11: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#98-e | Post SA6#52-Bis-e | Target Completion | Remarks
5G-enabled fused location service capability exposure | 5GFLS | SA#98 (12/2022) | 0% | 40% | SA#99 (03/2023) | 
Mission Critical ad hoc group Communications | MC_AHGC | SA#98 (12/2022) | 35% | 70% | SA#99 (03/2023) | 
Application layer support for Personal IoT Network | PINAPP | SA#98 (12/2022) | 0% | 25% | SA#99 (03/2023) | Progress since SA#98-e: 23 pCRs are approved, including skeleton PIN create/delete, PIN server discovery, PIN profile, multiple PEMC/PEGCs, service switch, service continuity start the normative work.
Technical Enhancements and Improvements for Release 18 | TEI18 | SA6#52 (Agreed) | NA | NA | SA#100 (06/2023) | 

## Slide 12: Thank You!

## Slide 13: Backup

## Slide 14: 2.4) Rel-18 Study/Work (xx/yy)
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
970037 | SEAL data delivery enabler for vertical applications | SEALDD | Rel-18 | S6 | Mar-2023 | 60% | 75% | 
Progress since SA#98-e:
  9 pCRs for draft TS 23.433 were approved ; 1 CR for TS 23.434 was agreed; and 1 CR for TS 23.558 was agreed.
RAN impacts and dependencies:
  None identified
Clause 9.6 – Updates to Information flows, APIs and Resolve ENs
Clause 9.7 – Resolve ENs
Annex A - Deployment models for SEALDD (Objective 1 of WID)
New proposals for the features (mostly which are postponed).
Next steps: (Aspects to progress in SA6#53)
  Clause 4 - Functionalities overview (Editorial work – Summary of SEALDD capabilities)
  Clause 7 - Architecture Cardinality rules and Resolve ENs
  Clause 9.2 – Information flows and Resolve ENs
  Clause 9.3 – Resolve ENs
  Clause 9.4 – Information flows, APIs and Resolve ENs
Features outlined in the WID objectives are mostly addressed.

## Slide 15: 2.4) Rel-18 Study/Work (xx/yy)
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
970039 | Application layer support for V2X services; Phase 3 | V2XAPP_Ph3 | Rel-18 | S6 | Mar-2023 | 45% | 45% | 
Progress since SA#98-e:
  None
RAN impacts and dependencies:
  None identified
3 features outlined in the WID objectives are addressed.
Next steps: Address the following aspects
  APIs for the new procedures.
  Update the procedures for “network monitoring” and “monitoring and control of QoS for eV2X” with the usage of network analytics
  Monitor the progress in SA2 and RAN2 for the capabilities related to VAE layer support for energy efficient V2P communications

## Slide 16: 2.4) Rel-18 Study/Work (xx/yy)
Progress since SA#98-e:
  2 pCRs for draft TR 23.700-78 were approved ;
  Add requirements and supplement of PIN create
RAN impacts and dependencies:
  None identified
Next steps: (Aspects to progress in SA6#53 or SA6 54e)
  Security related issues clarification
  Ens in conclusion to resolve
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
940021 | Study on Application layer support for Personal IoT Networks | FS_PINAPP | Rel-18 | S6 | Dec-2022 | 90% | 98% | 

## Slide 17: 2.4) Rel-18 Study/Work (xx/yy)
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
980052 | Application layer support for Personal IoT Network | PINAPP | Rel-18 | S6 | Mar-2023 | 0% | 25% | 
Progress since SA#98-e:
  23 pCRs are approved, including skeleton
  PIN create/delete, PIN server discovery, PIN profile, multiple PEMC/PEGCs, service switch, service continuity start the normative work.
RAN impacts and dependencies:
  None identified
Next steps: Address the following aspects
  PINAPP supports the 5GS communication
  PINAPP supports the application server discovery
  PINAPP service continuity that changes the communication to 5GS
  Some of the information flow and APIs should be added