## Slide 1: FS_XRApp: TU planning and TU Estimation Update
Apr, 2024
Shaowen Zheng (CMCC)

## Slide 2: FS_XRApp(SID) TU planning
Meeting | TUs Planned |  | Work Planned | Completion rate | TUs Consumed | Work Completed
 | SID | WID |  |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval |  | - | SID Approval completed
SA6#58 (Nov-23) | 0.5 TU | - | Skeleton, introduction, scope and Key Issues | SID: 10% | 0.5 (SID) | Skeleton, introduction, scope, and 2 Key issues agreed
SA6#59 (Feb-24) | 1.0 TUs | - | Key Issues, Architecture Requirements, Architecture , Business Models, Solutions | SID:20% | 1.5 TU(SID) | Key Issues, Architecture Requirements, Architecture , Business Models
SA6#60 (Apr-24) | 1.0 TUs | - | Key Issues (Freeze), Architecture, Architecture Requirements, Solutions, Solution evaluation | SID:50%? |  | 
SA6#61 (May-24) | 1.0 TUs | - | Solutions, Solution evaluation and Conclusions. Send for Information. WID proposal | SID:80%? |  | 
SA6#62-Adhoc-e (Jul-24) | 0.5 TUs | 1.0 TUs | Finish Solution Conclusions, Send for Approval Begin Normative work (Architecture and Solutions, Business Relationships) | SID:100%? WID:10%? |  | 
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions | WID:40%? |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions | WID:70%? |  | 
SA6#64 (Nov24) | - | 1.0 TUs | Complete unfinished work, Send for Approval. | WID:100%? |  | 
Total | 4 TUs | 4 TUs |  |  | 1.5 TUs | 

## Slide 3: Updated TU Estimation
template
 | Original TU Plan |  | Updated TU Plan | 
Meeting | FS_XRApp (SID) | XRApp(WID) | FS_XRApp (SID) | XRApp(WID)
SA6#58 (Nov-23) | 0.5 TU | - | 0.5 TU | 
SA6#59 (Feb-24) | 1.0 TUs | - | 1.0 TUs | 
SA6#60 (Apr-15) | 1.0 TUs | - | 2.0 TUs | -
SA6#61 (May-20) | 1.0 TUs | - | 2.0 TUs | -
SA6#62-Adhoc-e (Jul-10)(TBD) | 0.5 TUs | 1.0 TUs | 1.0 TUs | 1.0 TUs
SA6#62 (Aug-19) | - | 1.0 TUs | - | 1.5 TUs
SA6#63 (Oct-14) | - | 1.0 TUs | - | 1.0 TUs
SA6#64 (Nov-18) | - | 1.0 TUs | - | 1.0 TUs
Total | 4TUs | 4 TUs | 6.5TUs | 4.5TUs
 | 8TU |  | 11 TUs | 

## Slide 4: Summary
  TU Estimation Updated
  More Key Issues and solutions are welcomed.
Suggested Work Plan
  SA6#60 (target: 50% complete)
    Get Key Issues freezed.
    As many solutions approved as possible.