## Slide 1
Rel-19 Status and Plan
SA6 Chair, Vice Chairs & Rel-19 Rapporteurs

## Slide 2: 5GSAT_Ph3_App (SID/WID) Status untill SA6#63 (Rapporteur: Basu Pattan)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#57 (Oct-23) | - | - | SID Approval
SA6#58 (Nov-23) | 1.0 TU | - | Skeleton, Scope, Key Issues
SA6#59 (Feb-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions
SA6#60 (Apr-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions
SA6#61 (May-24) | 2.0 TUs | - | Key Issues (Freeze), Solutions, Start Solution Conclusions. Send for Information. WID Approval
SA6#62-Adhoc-e (Jul-24) | 2.0 TUs | 2.0 TUs | Finish Solution Conclusions, Send TR for Approval Begin Normative work (architecture impacts)
SA6#62 (Aug-24) | - | 2.0 TUs | Architecture and Solutions, Business Relationships
SA6#63 (Oct-24) | - | 2.5 TUs | Architecture and Solutions, Deployment models
SA6#64 (Nov24) | - | 2.5 TUs | Complete unfinished work
Total | 9 TUs | 9 TUs | 
SID/WID Current Status | 
SID Status: 100% complete and approved | WID Status: 40% complete
Remaining work for SID: None. Remaining ENs planned to be addressed in normative. | 
Remaining work for WID: EDGEAPP, SEALDD, ADAE Architecture requirements AE#2 and AE#7 solution aspects for edge computing on-board the satellite AE#3 solution aspects for Discontinuous satellite coverage MC#1 solution for Mission Critical using satellite | 
Expected completion at SA6#64 At the end of SA6#64, it might be difficult to achieve 100% completion | 
May need Exception? If needed, what is the scope: Exception may be needed, if SA#64 does not complete all of the remaining work identified above and especially if 2 to 4 are not completed. | 

## Slide 3: enhMC(WID) Status untill SA6#63 (Rapporteur: Harish Negalaguli)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#55 (Oct-23) | - | - | WID Approval
SA6#56 (Nov-23) | - | - | Enhancements/corrections to MC Specs
SA6#57 (Oct-23) | - | 1.0 TU | Solutions/Enhancements
SA6#58 (Nov-23) | - | 1.0 TU | Solutions/Enhancements
SA6#59 (Feb-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures)
SA6#60 (Apr-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures)
SA6#61 (May-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures)
SA6#62-Adhoc-e (Jul-24) | - | 0 | Solutions & Architecture(flows, Procedures)
SA6#62 (Aug-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures)
SA6#63 (Oct-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures)
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work
Total | - | 8 TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 85% complete
Remaining work for SID: Not applicable | 
Remaining work for WID: Completion & cleanup Logging/Recording Arch details & procedures MC Location enhancements completion MCX Services improvements from deployment experiences. Message store coverage for MCPTT/MCVideo Discreet Listening | 
Expected completion at SA6#64 100% | 
May need Exception? If needed, what is the scope: No exception anticipated, as #1,#2,#3 are expected to complete in SA6#64. All other remaining items likely to be moved to Rel-20. | 

## Slide 4: eMMTelAPP (SID/WID) Status untill SA6#63 (Rapporteur: Yue Liu)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#55 (May-23) | - | - | SID Approval
SA6#56 (Aug-23) | 1.0 TU | - | Skeleton, Scope, Key Issues
SA6#57 (Oct-23) | 1.0 TU | - | Key Issues, Architecture Requirements
SA6#58 (Nov-23) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions
SA6#59 (Feb-24) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions
SA6#60 (Apr-24) | 1.0 TU |  | Key Issues (Freeze), Solutions, Start Solution Conclusions.
SA6#61 (May-24) | 1.0 TU |  | Solutions, send TR for Information. WID Approval
SA6#62-Adhoc-e (Jul-24) | - | 1.0 TU | Begin Normative work (architecture impacts), Deployment model
SA6#62 (Aug-24) | - | 1.0 TU | Architecture and Solutions, Deployment models
SA6#63 (Oct-24) |  | 1.0 TU | Finish TR Solution Conclusions based on two LSs replied from SA2. Architecture and Solutions
SA6#64 (Nov24) |  | 1.0 TU | Architecture and Solutions, send TS for Approval.
Total | 6 TUs | 4 TUs | 
SID/WID Current Status | 
SID Status: 95% | WID Status: 20% complete
Remaining work for SID: Clean-up the TR, e.g. solve necessary ENs adn editorials | 
Remaining work for WID: 1. service enabler layer APIs and IEs used in the mmtel calling 2. the application layer architecture and procedures and IEs for controlling the downloading of data channel applications on UE 3. multiple call control handling coordination among different Application Servers 4. the necessary value added services provided by eMMTel Enabler, e.g. virtual number etc. | 
Expected completion at SA6#64 50% | 
May need Exception? If needed, what is the scope: Yes. See bullet 1, 3, 4 above. | 

## Slide 5: CAPIF_Ph3 (SID/WID) Status until SA6#63 (Rapporteur: Diego Preciado Rojas)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA#102 (Dec-23) | - | - | SID Approval
SA6#59 (Feb-24) | 0.5 TUs | - | Skeleton, Scope, Key Issues
SA6#60 (Apr-24) | 0.5 TUs | - | Key Issues, Architecture Requirements, Solutions
SA6#61 (May-24) | 0.5 Tus | - | Key Issues, Architecture Requirements, Solutions
SA6#62-Adhoc-e (Jul-24) | 0.5 Tus |  | Key Issues (Freeze), Solutions, Solution evaluations/Overall evaluation. WID agreement
SA6#62 (Aug-24) | 1.0 Tus | 1.0 TUs | Solutions, Overall evaluation, Begin Normative work (based on agreed WID)
SA6#63 (Oct-24) | 0.5 TUs | 1.0 TUs | Solutions, Overall evaluation, Conclusions, Normative Architecture and Solutions
SA6#64 (Nov24) |  | 1.0 TUs | Architecture and Solutions (remaining),
Total | 3.5 TUs | 3 TUs | 
SID/WID Current Status | 
SID Status: 98% | WID Status: 30% complete
Remaining work for SID: Final conclusions and send the TR for Approval | 
Remaining work for WID: CRs based on SID conclusion CRs based on coordination with other groups (SA3, SA5) | 
Expected completion at SA6#64 70% | 
May need Exception? If needed, what is the scope: CRs based on coordination with other groups (SA3, SA5) | 

## Slide 6: Metaverse_App (SID/WID) Status untill SA6#63 (Rapporteur: Sapan Shah)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#57 (Oct-23) | - | - | SID Approval
SA6#58 (Nov-23) | 2.0 TUs | - | Skeleton, Scope, Key Issues
SA6#59 (Feb-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions
SA6#60 (Apr-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions
SA6#61 (May-24) | 2.0 TUs | - | Key Issues (Freeze), Solutions, Start Solution Conclusions. Send for Information. WID Approval
SA6#62-Adhoc-e (Jul-24) | 2.0 TUs | 1.0 TUs | Finish Solution Conclusions, Send TR for Approval Begin Normative work (architecture impacts)
SA6#62 (Aug-24) | - | 2.0 TUs | Architecture and Solutions, Business Relationships
SA6#63 (Oct-24) | - | 3.0 TUs | Architecture and Solutions, Deployment models
SA6#64 (Nov24) | - | 3.0 TUs | Complete unfinished work, WID complete / Send new TSs for Approval.
Total | 10 TUs | 9 TUs | 
SID/WID Current Status | 
SID Status: 100% | WID Status: 60% complete
Remaining work for SID: None | 
Remaining work for WID: To bring Solution#19 (for KI#9) into normative (Support for permission control of digital assets) To bring Solution#13 (for #7) to normative (Support for metaverse services requiring multiple devices) Discovery of VAL server with SM capability Layers details and Media aspects for Digital assets Specifying APIs | 
Expected completion at SA6#64 100% (*) | 
May need Exception? If needed, what is the scope: Possible Exception (Depending on progress during SA6#64) Scope: Based on the remaining work for WID. | 

## Slide 7: FRMCS_Ph5(WID) Status untill SA6#63 (Rapporteur: Martin Oettl)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#56 (Aug) | - | - | WID Approval
SA6#57 (Oct-09) | - | 1.0 TU | Solutions
SA6#58 (Nov-13) | - | 1.0 TU | Solutions
SA6#59 (Feb-24) | - | 1.0 TU | Solutions
SA6#60 (Apr-24) | - | 1.0 TU | Solutions
SA6#61 (May-24) | - | 1.0 TU | Solutions
SA6#62-Adhoc-e (Jul-24) (TBC) | - |  | -
SA6#62 (Aug-24) | - | 1.0 TU | Solutions
SA6#63 (Oct-24) | - | 1.0 TU | Solutions
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work
Total |  | 8TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 85% complete
Remaining work for SID: Not applicable | 
Remaining work for WID: Interworking with GSM-R to support an automatic subsequent MCPTT ad hoc group calls following an ad hoc group emergency alert. Support of MC gateway UEs, e.g., multicast/broadcast, location, migration and interconnection. Separation of the signaling and the media paths within an MC system. | 
Expected completion at SA6#64 Separation of the signaling and the media paths MC gateway UE broadcast and location support | 
May need Exception? If needed, what is the scope: No exception, remaining work will be shifted to Rel-20. | 

## Slide 8: XRApp (SID/WID) Status untill SA6#63 (Rapporteur: Shaowen Zheng)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#57 (Oct-23) | - | - | SID Approval
SA6#58 (Nov-23) | 0.5 TU | - | Skeleton, introduction, scope and Key Issues
SA6#59 (Feb-24) | 1.0 TUs | - | Key Issues, Architecture Requirements, Architecture , Business Models, Solutions
SA6#60 (Apr-24) | 1.0 TUs | - | Key Issues (Freeze), Architecture, Architecture Requirements, Solutions, Solution evaluation
SA6#61 (May-24) | 1.0 TUs | - | Solutions, Solution evaluation and Conclusions. Send for Information. WID proposal
SA6#62-Adhoc-e (Jul-24) | 0.5 TUs | 1.0 TUs | Finish Solution Conclusions, Send TR for Approval Begin Normative work (Architecture and Solutions, Business Relationships)
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions
SA6#64 (Nov24) | - | 1.0 TUs | Complete unfinished work
Total | 4 TUs | 4 TUs | 
SID/WID Current Status | 
SID Status: 100% | WID Status: 60% complete
Remaining work for SID: KI#6 conclusion, which has dependency on SA2’s working progress | 
Remaining work for WID: EN resolutions at existing features Remaining features based on concluded TR solutions (solutions related to KI#6 and QoS coordination/guarantee) | 
Expected completion at SA6#64 90% for WID | 
May need Exception? If needed, what is the scope: No exception, remaining work will be shifted to Rel-20. | 

## Slide 9: Generic_IOPS(WID) Status until SA6#63 (Rapporteur: Mark Lipford)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA#104 |  |  | SID Agreed
SA6#62 adhoc-e | .5 |  | SID skeleton, Introduction and Scope agreed
SA6#62 | 2 |  | SID KIs agreed, SA6 agreed WID
SA#105 |  |  | WID Agreed
SA6#63 | 3 |  | Solutions for KI#1 agreed, update to KI#2
SA6#64 | 1 | 2 | Agreed CR’s based on KI#1 solutions, this will complete the scope of the WID. Clean up SID sections Discuss and possible agree solution for KI#2
SA#106 |  |  | Present WID CRs for approval (WID – 100%) Depending on status of solution(s) for KI#2 in SID may have an exception sheet, but note KI#1 is 100% and overall will be >90%
SID/WID Current Status | 
SID Status: 90% | WID Status: 0% complete
Remaining work for SID: Possibly include a solution for KI#2, and some minor clean up work. | 
Remaining work for WID: Agree CRs to match KI#1 solutions that were agreed at SA6#63 | 
Expected completion at SA6#64 Both SID and WID should be completed | 
May need Exception? If needed, what is the scope: Possibly work on KI#2 solution depending on level of agreement at SA6#64. | 

## Slide 10: FS_SEAL_Ph4(SID) Status untill SA6#63 (Rapporteur: Yanmei Yang)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#63 (Oct-24) | 2.0 TUs | -- | Skeleton, Gaps, solutions
SA6#64 (Nov24) | 2.0TUs | -- | Gaps, Architecture Requirements,Solutions TR for information, WID proposal
SA6#65 (Feb25) | 2.0TUs | -- | Gaps(Freeze), Architecture Requirements,Solutions Send for approval. WID Approval
SID/WID Current Status | 
SID Status: 10% | WID Status: --
Remaining work Solutions to SEAL services technical gap#1 More Solutions to for SEAL services adoption gap (generic Gap 2,3,4 ) More Gaps(SEAL services technical and adoption) and related solutions are to be added | 
Remaining work for WID: --- | 
Expected completion at SA6#64 45% | 
May need Exception? If needed, what is the scope: Yes Solutions to SEAL services technical gap#1 More Solutions to for SEAL services adoption gap (generic Gap 2,3,4 ) More Gaps(SEAL services technical and adoption) and related solutions are to be added | 

## Slide 11: EDGEAPP_Ph3 (WID) Status untill SA6#63 (Rapporteur: Hyesung)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#57 (Oct-23) | - | 2 | Normative work for new or enhanced feature
SA6#58 (Nov-23) | - | 1.5 | Normative work for new or enhanced feature
SA6#59 (Feb-24) | - | 1.5 | Normative work for new or enhanced feature
SA6#60 (Apr-24) | - | 2.5 | Normative work for new or enhanced feature
SA6#61 (May-24) | - | 1.5? | Normative work for new or enhanced feature
SA6#62-Adhoc-e (Jul-24) | - | 0 | Only LS related issue?
SA6#62 (Aug-24) | - | 0.5 | Addressing the remaining issues/inconsistency
SA6#63 (Oct-24) | - | 0.25 | Addressing the remaining issues/inconsistency
SA6#64 (Nov24) | - | ? | Focus on the remaining issues/inconsistency Complete unfinished work
Total | 0 TUs | 9 TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 95%
Remaining work for SID: Not applicable | 
Remaining work for WID: EN resolution and fixing inconsistency | 
Expected completion at SA6#64 96-100% is expected by SA#106 | 
May need Exception? If needed, what is the scope: No Exception expected | 

## Slide 12: UASAPP_Ph3(WID) Status untill SA6#63 (Rapporteur: Michel Roy)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA#99 (Sept-23) |  |  | WID Approved
SA6#57 (Oct-23) | - | 0.5 | Improved redundancy for C2 traffic
SA6#58 (Nov-23) | - | 0.5 | Real-time UAV connection status monitoring
SA6#59 (Feb-24) | - | 0.5 | Resolve ENs
SA6#60 (Apr-24) | - | 0.5 | Real-time UAV connection status monitoring
SA6#61 (May-24) | - | 0.5 | Communications to support PC5 in addition to Uu
SA6#62-Adhoc-e (Jul-24) | - | 0.5 | Resolve ENs
SA6#62 (Aug-24) | - | 0.5 | Possible aspects to SEAL Resolve ENs
SA6#63 (Oct-24) | - | 1.0 | Remaining topics identified and started
SA6#64 (Nov24) | - | 0.5 | Remaining topics resolved Work completed
Total | - | 5 TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 90% complete
Remaining work for SID: Not applicable | 
Remaining work for WID: Expected: Editorial, alignments and corrections. | 
Expected completion at SA6#64 On track | 
May need Exception? If needed, what is the scope: None expected. | 

## Slide 13: 5GMARCH_Ph3 (WID) Status untill SA6#63 (Rapporteur: Yue Liu)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#55 (May-23) | - | - | WID Approval
SA6#56 (Aug-23) |  | 0 TU | No contribution
SA6#57 (Oct-23) |  | 1.0 TU | solutions
SA6#58 (Nov-23) |  | 0 TU | No contribution
SA6#59 (Feb-24) |  | 1.0 TU | solutions
SA6#60 (Apr-24) |  | 1.0 TU | solutions
SA6#61 (May-24) |  | 1.0 TU | solutions
SA6#62-Adhoc-e (Jul-24) |  | - | 
SA6#62 (Aug-24) |  | 1.0 TU | solutions, Complete unfinished work
Total | 0 TUs | 5 TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 90% complete
Remaining work for SID: Not applicable | 
Remaining work for WID: Clean-up the TS, e.g. solve necessary ENs and editorials | 
Expected completion at SA6#64 100% | 
May need Exception? If needed, what is the scope: No | 

## Slide 14: CAPIF_EXT(WID) Status untill SA6#63 (Rapporteur: Junpei Uoshima)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#56 (Aug-30) | - | - | WID Approval
SA6#57 (Oct-23) | - | 0.5 TU | Skeleton, Scope
SA6#58 (Nov-23) | - | 0.5 TU | References, Definitions, Overview of CAPIF
SA6#59 (Feb-24) | - | 0.5 TU | Role of Stakeholders for API Exposure, Exemplary Use Cases and Adoption, Summary
SA6#60 (Apr-24) | - | 0.5 TU | Exemplary Use Cases and Adoption
SA6#61 (May-24) | - | 0.2TU | Exemplary Use Cases and Adoption
SA6#62-Adhoc-e (Jul-24) | - | - | Exemplary Use Cases and Adoption
SA6#62 (Aug-24) | - | 0.3 TU | Exemplary Use Cases and Adoption
SA6#63 (Oct-24) | - | 0.3 TU | Exemplary Use Cases and Adoption, Annex
SA6#64 (Nov24) | - | 0.2 TU | Complete unfinished work, Send for Approval.
Total | - | 3 TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 95% complete
Remaining work for SID: Not applicable | 
Remaining work for WID: In the revised WID, the scope is set to Rel-18 and an agreement is formed within SA6#64 meeting. After the CAPIF_PH3 discussion is complete, and the specification is finalized, the updates will be merged into CAPIF_EXT. | 
Expected completion at SA6#64 Plans to achieve 100% progress. Target to send TR 23.946 for approval at SA#106 | 
May need Exception? If needed, what is the scope: No | 

## Slide 15: SEALDD_Ph2(WID) Status untill SA6#63 (Rapporteur: Cuili Ge)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#56 (Aug) | - | - | WID Approval
SA6#57 (Oct-09) | - | 1.0 TU | Solutions
SA6#58 (Nov-13) | - | 1.0 TU | Solutions
SA6#59 (Feb-24) | - | 1.0 TU | Solutions
SA6#60 (Apr-24) | - | 1.0 TU | Solutions
SA6#61 (May-24) | - | 1.0 TU | Solutions
SA6#62-Adhoc-e (Jul-24) | - |  | Solutions
SA6#62 (Aug-24) | - | 1.0 TU | Solutions
SA6#63 (Oct-24) | - | 1.0 TU | Solutions
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work
Total |  | 8TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 90%
Remaining work for SID: Not applicable | 
Remaining work for WID: Cleanups and alignments | 
Expected completion at SA6#64 100% | 
May need Exception? If needed, what is the scope: No | 

## Slide 16: eLSAPP (SID/WID) Status until SA6#63 (Rapporteur: Liping Wu)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#55 (May-23) | - | - | SID Approval
SA6#56 (Aug-23) | 0.5TU | - | Skeleton, Scope, Key Issues
SA6#57 (Oct-23) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions
SA6#58 (Nov-23) | 1.0 TU | - | Key Issues, Solutions
SA6#59 (Feb-24) | 1.0 TU |  | Key Issues, Solutions
SA6#60 (Apr-24) | 1.0 TU | - | Key Issues(Freeze), Solutions, Start Solution Conclusions. Send for information, WID proposal
SA6#61 (May-24) | 0.5 TU | - | Solutions(Freeze), Finish Solution Conclusions. Send for Approval, WID Approval
SA6#62-Adhoc-e (Jul-24) |  | 0.5 TUs | Begin Normative work
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions
SA6#64 (Nov24) | - | 0.5 TUs | Complete unfinished work
Total | 5 TUs | 3 TUs | 
SID/WID Current Status | 
SID Status: 100% | WID Status: 80% complete
Remaining work for SID: None. | 
Remaining work for WID: EN for multiple UEs sharing the same location EN for UE obtaining the location via SL/Ranging positioning EN for Geofencing monitoring list IE Clean-ups and alignments | 
Expected completion at SA6#64 Resolve the left ENs Complete the normative work to 100% | 
May need Exception? If needed, what is the scope: No. | 

## Slide 17: AIMLAPP (SID/WID) Status until SA6#63 (Rapporteur: Manos Pateromichelakis)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#56 (Aug-23) | - | - | SID Approval
SA6#57 (Oct-09) | 2.0 TU |  | Skeleton, Scope, Key Issues, Solutions
SA6#58 (Nov-13) | 1.0 TU |  | Key Issues, Architecture Requirements, Solutions, Background Analysis
SA6#59 (Feb-24) | 1.0 TU |  | Key Issues (Freeze), Solutions and solution updates
SA6#60 (Apr-24) | 1.0 TU |  | Stable Architecture, Solutions (Freeze), Solution Updates and Evaluations, Deployment/ Business Models
SA6#61 (May-24) | 1.0 TU |  | Overall Evaluation and Conclusions. SID send for Approval. WID Approval
SA6#62-Adhoc-e (Jul-24) | - | 1.0 TU | Architecture, Deployments and Features (procedures and flows)
SA6#62 (Aug-24) | - | 1.0 TU | Features (procedures and flows) and APIs
SA6#63 (Oct-24) | - | 1.0 TU | Features (procedures and flows) and APIs
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work, Send for Approval.
Total | 6 TUs | 4 TUs | 
SID/WID Current Status | 
SID Status: 100% | WID Status: 75% complete
Remaining work for SID: No remaining work | 
Remaining work for WID: EN resolutions at existing features Remaining features based on concluded TR solutions (couple solutions related to AIMLE and ADAES) Finalization of API clause | 
Expected completion at SA6#64 On track. 95-100% is expected by SA#106, depending on progress. No controversial topics. Target to send TS 23.482 for approval at SA#106 | 
May need Exception? If needed, what is the scope: No | 

## Slide 18: MCShAC (WID) Status until SA6#63 (Rapporteur: Andreas Flander)
Meeting | TUs Planned |  | Work Planned
 | SID | WID | 
SA6#55 (May-23) | - | - | WID Approval
SA6#56 (Aug-23) | - | 0.6 TUs | Begin normative work
SA6#57 (Oct-13) | - | 0.6 TUs | Architecture and Functional
SA6#58 (Nov-23) | - | 0.6 TUs | Architecture and Solutions
SA6#59 (Feb-24) | - | 0.6 TUs | Architecture and Solutions
SA6#60 (Apr-24) | - | 0.6 TUs | Architecture and Solutions
SA6#61 (May-24) | - | 0.6 TUs | Architecture and Solutions
SA6#62-Adhoc-e (Jul-24) | - | 0.6 TUs | None as of this meeting is about Rel-19 studies only
SA6#62 (Aug-24) | - | 0.6 TUs | Corrections, miscellaneous
SA6#63 (Oct-24) | - | 0.6 TUs | Corrections, miscellaneous
SA6#64 (Nov24) | - | 0.6 TUs | Closing
Total | - | 6 TUs | 
SID/WID Current Status | 
SID Status: Not applicable | WID Status: 100% complete
Remaining work for SID: Not applicable | 
Remaining work for WID: No work left. WID is 100 % completed | 
Expected completion at SA6#64 WID 100 % completed since SA6#62 | 
May need Exception? If needed, what is the scope: No |