## dinu
ID | UID | Name | Acronym | Lev | Release | Resource | Start | Finish | Compl | Hyperlink | SR | Rapporteur | WI_rapporteur_Email | Notes | TS_TR | Special_Focus_Doc
1 | 0 | Release 13 Features | - | 1 | Rel-13 | SP,RP,CP,GP | 2015-04-14 15:00 | 2015-12-25 17:00 | 0% | - | - | - | - | - | -
2 | 611000 | Stage 1 - ONLY Features | - | 1 | Rel-13 | SP | 2013-09-12 08:00 | 2015-12-25 17:00 | 0% | - | - | - | - | - | -
3 | 600045 | RAN Sharing Enhancements | RSE | 1 | Rel-13 | S1 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | SP#62 completed. Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | 22.101
4 | 610030 | Service Exposure and Enablement Support | SEES | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 89% | SP-130505 | - | KPN | toon.norp@tno.nl | SP#62 completion 06/14=>09/14. Linked to Rel-12 Study TR 22.888 (FS_MTCe) and to Features Rel-11 SIMTC & Rel-12 MTCe and MOSAP | 22.368 | MTC, M2M
5 | 610130 | TR on Stage 1 for Service Exposure and Enablement Support | - | 2 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130505 | - | KPN | toon.norp@tno.nl | SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements) | New TR 22.853 | MTC, M2M
6 | 610230 | Stage 1 for Service Exposure and Enablement Support | - | 2 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 80% | SP-130505 | - | KPN | toon.norp@tno.nl | SP#62 completion 06/14=>09/14 | 22.368, TBD | MTC, M2M
7 | 620063 | Service Requirements Maintenance for Machine-Type Communications (MTC) | SRMMTC | 1 | Rel-13 | S1 | 2013-12-12 08:00 | 2014-12-10 17:00 | 0% | SP-130600 | - | KPN | toon.norp@tno.nl | Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13. | 22.368 | MTC, M2M
8 | 630015 | Isolated E-UTRAN Operation for Public Safety | IOPS | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 60% | SP 140232 | - | General Dynamics | paul.piggin@gd-broadband.com | SP#64 updated WID SP-140167=>SP 140232. Triggered by Rel-13 TR 22.897 Study on Isolated E-UTRAN Operation for Public Safety (FS_IOPS) | New TS 22.346 | Public Safety (A-A)
9 | 640042 | Service Requirements Maintenance for Group Communication System Enablers for LTE | SRM_GCSE_LTE | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140228 | - | NSN | Juergen.Merkel@nsn.com | Some Rel-12 service reqs have no Stage 2/3 implementation. These are taken up in Rel-13 (add. aspect of Geographic Scope, Floor Control, User Interaction, UE to Network Relay, I/W with non-3GPP networks, UE-AS Open I/F). No new service reqs introduced | 22.468 | Public Safety (A-A)
10 | 640044 | Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140235 | - | Intel | Eric.siow@intel.com | Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO) | 22.101
11 | 640052 | Application specific Congestion control for Data Communication | ACDC | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 90% | SP-140234 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | Triggered by Rel-13 Study TR 22.806 | 22.011
12 | 620999 | SA1/SA2 Features | - | 1 | Rel-13 | SP,RP,CP,GP | 2013-12-11 08:00 | 2015-12-25 17:00 | 0% | - | - | - | - | - | -
13 | 570029 | User Plane Congestion management | UPCON | 1 | Rel-13 | S1,S2 | 2012-02-02 08:00 | 2015-06-17 17:00 | 48% | SP-140153 | - | KDDI | John Visser (jvisser@rogers.com) | SP#63 moved to Rel-13 updated WID SP-120890=>SP-140114. SP#62 Rel-12 stopped. Triggered by Rel-12 TR 22.805 Study on User Plane Congestion management (FS_UPCON) | Stage 1/2
14 | 570129 | Stage 1 for User Plane Congestion management | - | 2 | Rel-13 | S1 | 2012-02-02 08:00 | 2013-03-06 17:00 | 100% | SP-140153 | - | KDDI | John Visser (jvisser@rogers.com) | SP#63 moved to Rel-13 updated WID SP-120890=>SP-140114. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101 | 22.101
15 | 580057 | TR on Stage 2 for User Plane Congestion management | - | 2 | Rel-13 | S2 | 2012-12-12 08:00 | 2014-12-10 17:00 | 85% | SP-140153 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | - | new TR 23.705
16 | 580058 | Deleted - Stage 2 for User Plane Congestion management | - | 2 | Rel-13 | S2 | 2012-12-19 08:00 | 2013-12-11 17:00 | 100% | SP-140153 | - | NEC | andreas.maeder@neclab.eu | SP#62 stopped at 0% completion | TBD
17 | 630019 | BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2015-06-17 17:00 | 0% | SP-140153 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | Includes: RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control | 23.060, 23.203, 23.401
18 | 630020 | BB2: Application and Content Prioritization | UPCON-CON | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2015-06-17 17:00 | 0% | SP-140153 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | Includes: Content specific UP prioritization (Video), Application specific UP prioritization | TBD
19 | 630021 | BB3: Uplink traffic and attended/unattended traffic | UPCON-TRAF | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2015-06-17 17:00 | 0% | SP-140153 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | Includes: Uplink Congestion Management, Un/Attended UE Information | TBD
20 | 620064 | Mission Critical Push To Talk over LTE | MCPTT | 1 | Rel-13 | S1,S2 | 2013-12-11 08:00 | 2015-06-17 17:00 | 21% | SP-140276 | - | NIST | david.cypher@nist.gov | SP#64 updated WID SP-130728=>SP-14027 (added SA2 part). Complements Rel-12 FS_ProSe/ProSe and GCSE_LTE. External requirements: FIRSTNET (US), UK Home Office, OMA, TCCA (TETRA and Critical Communications Association) | Stage 1 | Public Safety (A-A)
21 | 620164 | Stage 1 for Mission Critical Push To Talk over LTE | - | 2 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-12-10 17:00 | 50% | SP-140276 | - | NIST | david.cypher@nist.gov | SP#64 completion 09/14=>09/14. LS received from ETSI TCCE S1-141225 and OMA S1-141227 with their PTT requirements (Reply to OMA S1-141590) | new TS 22.179 | Public Safety (A-A)
22 | 640142 | TR on Stage 2 for Mission Critical Push To Talk over LTE | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-10 17:00 | 4% | SP-140276 | - | U.S. Department of Commerce | Randy Bloomfield (randy@its.bldrdoc.gov) | SP#64 updated WID SP-130728=>SP-14027 (added SA2 part) | New TR 23.779 | Public Safety (A-A)
23 | 640042 | Stage 2 for Mission Critical Push To Talk over LTE | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140276 | - | U.S. Department of Commerce | Randy Bloomfield (randy@its.bldrdoc.gov) | SP#64 updated WID SP-130728=>SP-14027 (added SA2 part) | New TS 23.179 | Public Safety (A-A)
24 | 630014 | Enhancements to WEBRTC interoperability | eWebRTCi | 1 | Rel-13 | S1,S2 | 2014-03-07 08:00 | 2015-06-17 17:00 | 21% | SP-140286 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#64 updated WID SP-140166=>SP-140286 (added SA2 part). Add enhanced interoperability support for WebRTC to Rel-12 Web Real Time Communication (WebRTC) Access to IMS. | Stage 1/2
25 | 630114 | Stage 1 for Enhancements to WEBRTC interoperability | - | 2 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 90% | SP-140286 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | - | 22.228
26 | 640138 | TR on Stage 2 for Enhancements to WEBRTC interoperability | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 0% | SP-140286 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#64 updated WID SP-140166=>SP-140286 (added SA2 part | New TR 23.706
27 | 640038 | Stage 2 for Enhancements to WEBRTC interoperability | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140286 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#64 updated WID SP-140166=>SP-140286 (added SA2 part | 23.228
28 | 630016 | Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord | 1 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-12-10 17:00 | 30% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios | Stage 2
29 | 630116 | TR on Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | - | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-12-10 17:00 | 60% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | SP#64 TR 23.704v100 for Information | New TR 23.704
30 | 630216 | Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | - | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-12-10 17:00 | 0% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | - | 23.216, 23.251, 23.272
31 | 640040 | Enhancements to Proximity-based Services | eProSe | 1 | Rel-13 | S1,S2 | 2014-06-18 08:00 | 2015-06-12 17:00 | 0% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced. | Stage 1 | Public Safety (A-A)
32 | 640140 | Stage 1 for Enhancements to Proximity-based Services | - | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced. | 22.115, 22.278 | Public Safety (A-A)
33 | 640141 | TR on Stage 2 for Enhancements to Proximity-based Services - Extensions | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-13 17:00 | 0% | SP-140385 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | - | New TR 23.713 | Public Safety (A-A)
34 | 640041 | Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-12 17:00 | 0% | SP-140385 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | - | 23.303, TBD | Public Safety (A-A)
35 | 640045 | voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD | 1 | Rel-13 | S1,S2 | 2014-06-16 08:00 | 2014-12-10 17:00 | 2% | SP-140394 | - | Alcatel-Lucent | (betsy.covell@alcatel-lucent.com) | Specify requirements to allow a differentiated E-UTRAN paging policy for voice compared with non-voice IMS services | Stage 1
36 | 640145 | Stage 1 for voice over E-UTRAN Paging Policy Differentiation | - | 2 | Rel-13 | S1 | 2014-06-16 08:00 | 2014-06-18 17:00 | 100% | SP-140394 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#64 approved WID & completed | 22.228, 22.278
37 | 640245 | Stage 2 for voice over E-UTRAN Paging Policy Differentiation | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-10 17:00 | 0% | SP-140287 | - | Alcatel-Lucent | laurent.thiebaut@alcatel-lucent.com | Architectural enhancements allowing a differentiated paging policy for IMS voice calls over E-UTRAN | 23.228, 23.401
38 | 640046 | Dedicated Core Networks | DECOR | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 4% | SP-140395 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | Enable deployment of dedicated CNs to UEs sharing the same characteristics. The specific dedicated CN that serves a UE is selected based on subscription info and operator config, without requiring UEs to be modified. | Stage 2
39 | 640146 | TR for Dedicated Core Networks | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-10 17:00 | 10% | SP-140395 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | - | New TR 23.707
40 | 640246 | Stage 2 for Dedicated Core Networks | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 0% | SP-140395 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | - | 23.060, 23.401
41 | 640047 | IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 2% | SP-140279 | - | ZTE | Tricci So (tso@zteusa.com) | - | Stage 2
42 | 640147 | TR for IP Flow Mobility support for S2a and S2b Interfaces | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-13 17:00 | 5% | SP-140279 | - | ZTE | Tricci So (tso@zteusa.com) | Revived the Rel-12 DRAFT TR 23.861 stopped at SP#59 (at 40% completion) | New TR 23.861
43 | 640247 | Stage 2 for IP Flow Mobility support for S2a and S2b Interfaces | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140279 | - | ZTE | Tricci So (tso@zteusa.com) | - | 23.402, TBD
44 | 640048 | Architecture Enhancements for Service capability Exposure | AESE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 2% | SP-140301 | - | Intel | puneet.jain@intel.com | - | Stage 2
45 | 640148 | TR for Architecture Enhancements for Service capability Exposure | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 10% | SP-140301 | - | Intel | puneet.jain@intel.com | - | New TR 23.708
46 | 640248 | Stage 2 for Architecture Enhancements for Service capability Exposure | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140301 | - | Intel | puneet.jain@intel.com | - | TBD
47 | 640348 | TR on Security for Architecture Enhancements for Service capability Exposure | - | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140301 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. | New TR 33.889
48 | 640448 | Security for Architecture Enhancements for Service capability Exposure | - | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 0% | SP-140301 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | - | 33.187
49 | 640049 | Monitoring Enhancements | MONTE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 3% | SP-140302 | - | Intel | puneet.jain@intel.com | Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs | Stage 2
50 | 640149 | TR for Monitoring Enhancements | - | 2 | Rel-13 | S2 | 2014-09-17 08:00 | 2015-06-17 17:00 | 15% | SP-140302 | - | Intel | puneet.jain@intel.com | - | New TR 23.789
51 | 640249 | Stage 2 for Monitoring Enhancements | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140302 | - | Intel | puneet.jain@intel.com | - | 23.682, TBD
52 | 640349 | TR on Security for Monitoring Enhancements | - | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140302 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. | New TR 33.889
53 | 640449 | Security for Monitoring Enhancements | - | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 0% | SP-140302 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | - | 33.187
54 | 640050 | Group based Enhancements | GROUPE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 2% | SP-140305 | - | Huawei | ZhangWanqiang@huawei.com | - | Stage 2
55 | 640150 | TR for Group based Enhancements | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 10% | SP-140305 | - | Huawei | ZhangWanqiang@huawei.com | - | New TR 23.769
56 | 640250 | Stage 2 for Group based Enhancements | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140305 | - | Huawei | ZhangWanqiang@huawei.com | - | 23.682, TBD
57 | 640350 | TR on Security for Group based Enhancements | - | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140305 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. | New TR 33.889
58 | 640450 | Security for Group based Enhancements | - | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 0% | SP-140305 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | - | 33.187
59 | 640051 | Enhanced CS Fallback (CSFB) | eCSFB | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 0% | SP-140285 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB) | Stage 2
60 | 640151 | TR for Enhanced CS Fallback (CSFB) | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-10 17:00 | 0% | SP-140285 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | CSFB is important in LTE networks. Compared to native calls starting in 2G or 3G CS domain, CSFB has longer call setup time (LTE->UMTS, LTE->GSM CSFB) esp. if standardized solutions (RIM) to optimize callsetup time are not possible to deploy | New TR 23.772
61 | 640251 | Stage 2 for Enhanced CS Fallback (CSFB) | - | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 0% | SP-140285 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | - | 23.272
62 | 640053 | Double Resource Reuse for Multiple Media Sessions | DRuMS | 1 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 20% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | - | Stage 2
63 | 640153 | Stage 2 for Double Resource Reuse for Multiple Media Sessions | - | 2 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 20% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | - | 23.203, 23.228
64 | 620062 | Security Assurance Specification for 3GPP network products | SCAS | 1 | Rel-13 | S3 | 2013-12-09 08:00 | 2015-03-18 17:00 | 34% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | Triggered by Rel-12 TR 33.805 Study on Security Assurance Methodology for 3GPP Network Elements (FS_SECAM) | -
65 | 620162 | TR on Pilot development of Security Assurance Specification for MME network product class | - | 2 | Rel-13 | S3 | 2013-12-09 08:00 | 2014-12-10 17:00 | 45% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR collects input for the new TS 33.116 | New TR 33.806
66 | 620262 | Security Assurance Specification for 3GPP network product classes | - | 2 | Rel-13 | S3 | 2013-12-10 08:00 | 2015-03-18 17:00 | 0% | SP-130718 | - | China Mobile | Judy Zhu (zhuhongru@chinamobile.com) | This TS contains results of the first WID objective | New TS 33.116
67 | 620362 | TR on Security Assurance scheme for 3GPP network products | - | 2 | Rel-13 | S3 | 2013-12-09 08:00 | 2014-12-10 17:00 | 65% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR contains results of the second WID objective | New TR 33.916
68 | 640056 | Lawful Interception in the 3GPP Rel-13 | LI13 | 1 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-12-09 17:00 | 0% | SP-140400 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com |  | 33.106, 33.107, 33.108
69 | 590044 | End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI | 1 | Rel-13 | S4,C3,C1,C4 | 2013-03-06 08:00 | 2015-03-13 17:00 | 26% | SP-130670 | - | Ericsson | tomas.frankkila@ericsson.com | SP#64 moved to Rel-13. Co-ordinate with SA2, CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | -
70 | 620068 | TR on Study on improved end-to-end QoS handling for MTSI | - | 2 | Rel-13 | S4 | 2013-12-11 08:00 | 2015-03-13 17:00 | 55% | SP-130670 | - | Ericsson | tomas.frankkila@ericsson.com | SP#64 completion 12/14=>03/15 | new TR 26.924
71 | 590144 | SA4 part of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | - | 2 | Rel-13 | S4 | 2013-03-06 08:00 | 2015-03-13 17:00 | 55% | SP-130670 | - | Ericsson | tomas.frankkila@ericsson.com | SP#64 completion 12/14=>03/15. Stage 1 in TS 22.173. No impact on service reqs or architecture | 26.114
72 | 600007 | CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 2 | Rel-13 | C3,C1,C4 | 2013-06-20 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | Stage 2/3 | Stage 2/3
73 | 600107 | CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | - | 3 | Rel-13 | C3 | 2013-06-20 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | - | 29.162, 29.163, 29.213, 29.214
74 | 600207 | CT1 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | - | 3 | Rel-13 | C1 | 2013-06-20 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14 | 24.229
75 | 600307 | CT4 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | - | 3 | Rel-13 | C4 | 2013-06-20 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14 | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334
76 | 640058 | Video enhancements by Region-Of-Interest information signalling | ROI | 1 | Rel-13 | S4 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140219 | - | Intel | ozgur.oyman@intel.com | Standardize the signalling of region-of-interest (ROI) information and associated capability negotiation mechanisms for MTSI in TS 26.114 | 26.114
77 | 630010 | Rel-13 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM13 | 1 | Rel-13 | S5 | 2014-09-17 08:00 | 2015-12-11 17:00 | 0% | - | - | - | - | OAM13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | - | SON
78 | 630110 | Rel-13 Self-Organizing Networks (SON) - OAM aspects | OAM13-SON | 2 | Rel-13 | S5 | 2014-09-17 08:00 | 2015-12-11 17:00 | 0% | - | - | - | - | OAM13-SON is an umbrella BB also for SON related TEI13 type of changes that are not part of any other dedicated feature/WI | - | SON
79 | 560132 | Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | SON-NM-CCO | 3 | Rel-13 | S5 | 2014-09-17 08:00 | 2015-12-11 17:00 | 0% | SP-140060 | - | Ericsson | robert.petersen@ericsson.com | SP#64 work not started. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060) | 28.627, 28.628, 32.103, 32.422, 32.425, 32.442 | SON
80 | 641000 | Rel-13 Charging | CH13 | 1 | Rel-13 | S5 | 2014-06-18 08:00 | 2015-12-09 17:00 | 0% | - | - | - | - | CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | -
81 | 640059 | Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 2 | Rel-13 | S5 | 2014-06-18 08:00 | 2015-12-09 17:00 | 0% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Study and specify Gy Reference Point “service data flows based online charging” for inter-PLMN situations | Stage 2/3
82 | 640159 | TR on Inter-PLMN PS domain online charging | - | 3 | Rel-13 | S5 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | - | New TR 32.843
83 | 640259 | Specification of Inter-PLMN PS domain online charging | - | 3 | Rel-13 | S5 | 2014-06-18 08:00 | 2015-12-09 17:00 | 0% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | - | 32.251, 32.299
84 | 550017 | LTE in the 1670-1675 MHz Band for US | LTE_FDD_1670_US | 1 | Rel-13 | R4,R2,R3 | 2012-03-05 08:00 | 2015-06-12 17:00 | 8% | RP-121397 | - | LightSquared | masoud.olfat@lightsquared.com | RP#63 moved to Rel-13 | LTE
85 | 550117 | Core part: LTE in the 1670-1675 MHz Band for US | LTE_FDD_1670_US-Core | 2 | Rel-13 | R4,R2,R3 | 2013-08-06 14:12 | 2015-03-13 17:00 | 15% | RP-121397 | RP-140797 | LightSquared | masoud.olfat@lightsquared.com | RP#64 completion 12/14=>03/15 | 25.101, 25.104, 25.113, 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, new TR 36.832
86 | 550217 | Perf. Part: LTE in the 1670-1675 MHz Band for US | LTE_FDD_1670_US-Perf | 2 | Rel-13 | R4 | 2012-03-05 08:00 | 2015-06-12 17:00 | 5% | RP-121397 | RP-140797 | LightSquared | masoud.olfat@lightsquared.com | RP#64 completion 03/15=>06/15 | 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.113, 36.124, 36.133, 36.141, 36.307
87 | 640019 | Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig | 1 | Rel-13 | R3 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-141032 | - | Samsung | sunghwan.won@samsung.com | Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015) | LTE
88 | 640119 | Core part: Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig-Core | 2 | Rel-13 | R3 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-141032 | - | Samsung | sunghwan.won@samsung.com | - | 36.300, 36.423
89 | 640036 | 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1 | 1 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-141009 | - | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | Triggered by TR 37.846 Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) FS_UTRA_LTE_1980_2170_REG1 | LTE
90 | 640136 | Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)" | LTE_1980_2170_REG1-Core | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-141009 | - | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL), New TR 36.862 (Technical Report for 2 GHz Band in Region 1)
91 | 640236 | Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)" | LTE_1980_2170_REG1-Perf | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-141009 | - | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, 36.862
92 | 621000 | Rel-13 LTE Carrier Aggregation | LTE_CA_Rel-13 | 1 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-06-12 17:00 | 8% | - | - | - | - | LTE_CA_Rel-13 | LTE | CA
93 | 630033 | LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 5% | RP-140094 | - | Orange, Ericsson | erika.tejedor@ericsson.com | Inter-band CA 2DL | LTE | CA
94 | 630133 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140094 | RP-140569 | Orange, Ericsson | erika.tejedor@ericsson.com | - | 36.101, 36.104, 36.133, generic TR 36.851 (2 Band CA with 1UL), | CA
95 | 630233 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 0% | RP-140094 | RP-140569 | Orange, Ericsson | erika.tejedor@ericsson.com | - | 36.141, 36.307 | CA
96 | 630034 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 15% | RP-140169 | - | Intel | xinrong.wang@intel.com | Inter-band CA 2DL | LTE | CA
97 | 630134 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140169 | RP-140569 | Intel | xinrong.wang@intel.com | - | 36.101, 36.104, 36.133, generic TR 36.851 (2 Band CA with 1UL) | CA
98 | 630234 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140169 | RP-140569 | Intel | xinrong.wang@intel.com | - | 36.101, 36.133, 36.141, 36.307 | CA
99 | 630035 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 0% | RP-140987 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band CA 2DL | LTE | CA
100 | 630135 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 0% | RP-140987 | RP-140569 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#64 updated WID RP-140449=>RP-140987 | 36.101, generic TR 36.850 | CA
101 | 630235 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 0% | RP-140987 | RP-140569 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#64 updated WID RP-140449=>RP-140987 | 36.307 | CA
102 | 630037 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140116 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band CA 3DL | LTE | CA
103 | 630137 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140116 | RP-140569 | T-Mobile USA | nelson.ueng@t-mobile.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL) | CA
104 | 630237 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 0% | RP-140116 | RP-140569 | T-Mobile USA | nelson.ueng@t-mobile.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
105 | 630038 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140117 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | Inter-band CA 3DL | LTE | CA
106 | 630138 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140117 | RP-140569 | T-Mobile USA | nelson.ueng@T-Mobile.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL) | CA
107 | 630238 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 0% | RP-140117 | RP-140569 | T-Mobile USA | nelson.ueng@T-Mobile.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
108 | 630039 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 15% | RP-140165 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE | CA
109 | 630139 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140165 | RP-140569 | Intel | peiling.zhang@intel.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
110 | 630239 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140165 | RP-140569 | Intel | peiling.zhang@intel.com | - | 36.101, 36.133, 36.141, 36.307 | CA
111 | 630040 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 15% | RP-140166 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE | CA
112 | 630140 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140166 | RP-140569 | Intel | peiling.zhang@intel.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
113 | 630240 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140166 | RP-140569 | Intel | peiling.zhang@intel.com | - | 36.101, 36.133, 36.141, 36.307 | CA
114 | 630041 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 15% | RP-140167 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE | CA
115 | 630141 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140167 | RP-140569 | Intel | xinrong.wang@intel.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
116 | 630241 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140167 | RP-140569 | Intel | xinrong.wang@intel.com | - | 36.101, 36.133, 36.141, 36.307 | CA
117 | 630042 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 15% | RP-140168 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE | CA
118 | 630142 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 20% | RP-140168 | RP-140569 | Intel | xinrong.wang@intel.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
119 | 630242 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 10% | RP-140168 | RP-140569 | Intel | xinrong.wang@intel.com | - | 36.101, 36.133, 36.141, 36.307 | CA
120 | 630043 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 40% | RP-140194 | - | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | Inter-band CA 3DL | LTE | CA
121 | 630143 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 40% | RP-140194 | RP-140569 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
122 | 630243 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-05 17:00 | 40% | RP-140194 | RP-140569 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | - | 36.141, 36.307 | CA
123 | 630044 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 10% | RP-140451 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL | LTE | CA
124 | 630144 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 20% | RP-140451 | RP-140569 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
125 | 630244 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 0% | RP-140451 | RP-140569 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307 | CA
126 | 640022 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140647 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | 3DL/1UL | LTE | CA
127 | 640122 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140647 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL) | CA
128 | 640222 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140647 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
129 | 640023 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140661 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | 3DL/1UL | LTE | CA
130 | 640123 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140661 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.101, 36.104, 36.133, 36.307, generic TR 36.851 (2 Band CA with 1UL), generic TR 36.853 (3 Band CA with 1UL) | CA
131 | 640223 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140661 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.133, 36.141 | CA
132 | 640024 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140662 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | 3DL/1UL | LTE | CA
133 | 640124 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140662 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.101, 36.104, 36.133, 36.307, generic TR 36.853 (3 Band CA with 1UL) | CA
134 | 640224 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140662 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.133, 36.141 | CA
135 | 640025 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-140692 | - | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | 3DL/1UL | LTE | CA
136 | 640125 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-140692 | - | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | - | 36.101, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
137 | 640225 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-140692 | - | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | - | 36.307 | CA
138 | 640026 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140708 | - | China Mobile | PAN Qun (panqun@chinamobile.com) | 3DL/1UL | LTE | CA
139 | 640126 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140708 | - | China Mobile | PAN Qun (panqun@chinamobile.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
140 | 640226 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140708 | - | China Mobile | PAN Qun (panqun@chinamobile.com) | - | 36.141, 36.307 | CA
141 | 640032 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140974 | - | Huawei | leo.liuye@huawei.com | 3DL/1UL | LTE | CA
142 | 640132 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140974 | - | Huawei | leo.liuye@huawei.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
143 | 640232 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140974 | - | Huawei | leo.liuye@huawei.com | - | 36.141, 36.307 | CA
144 | 640033 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140963 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | 3DL/1UL | LTE | CA
145 | 640133 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140963 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
146 | 640233 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140963 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307 | CA
147 | 640034 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41 | 2 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140964 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | 3DL/1UL | LTE | CA
148 | 640134 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Core | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140964 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
149 | 640234 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140964 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307 | CA
150 | 610034 | (Small) Technical Enhancements and Improvements for Rel-13 | TEI13 | 1 | Rel-13 | SP,CP,RP,GP | 2013-09-18 08:00 | 2015-12-24 17:00 | 0% | - | - | - | - | - | -
151 | 0 | Release 13 Studies | - | 1 | Rel-13 | SP,RP | 2014-07-31 13:00 | 2015-12-25 17:00 | 0% | - | - | - | - | - | -
152 | 570034 | Study on Application specific Congestion control for Data Communication | FS_ACDC | 1 | Rel-13 | S1 | 2012-09-13 08:00 | 2014-09-17 17:00 | 90% | SP-130415 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#64 completion 06/14=>09/14. TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion) | 22.806
153 | 600046 | Study on Isolated E-UTRAN Operation for Public Safety | FS_IOPS | 1 | Rel-13 | S1 | 2013-06-21 08:00 | 2014-06-18 17:00 | 100% | SP-130596 | - | General Dynamics | paul.piggin@gd-broadband.com | SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and Features: ProSe, GCSE_LTE | 22.897 | Public Safety (A-A)
154 | 610031 | Study on enhancements for Infrastructure based data Communication Between Devices | FS_eICBD | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 70% | SP-130418 | - | KPN | toon.norp@tno.nl | SP#64 TR 22.807v100 for Information | 22.807 | MTC, M2M
155 | 610032 | Study on need for Multiple Access Point Names | FS_MAPN | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-12-10 17:00 | 58% | SP-130416 | - | Giesecke & Devrient | Ilario.macchi@gi-de.com | SP#64 completion 09/14=>12/14. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM | 22.802
156 | 610033 | Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO | FS_CSIPTO | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130417 | - | Intel | Eric.siow@intel.com | SP#64 completed. TR 22.828v200 for Approval. Linked to Features: Rel-10 LIPA_SIPTO & Rel-12 LIMONET | 22.828
157 | 620069 | Study on Flexible Mobile Service Steering | FS_FMSS | 1 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-09-17 17:00 | 70% | SP-130597 | - | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#64 TR 22.808v100 for Information. Study supporting traffic classification and service chain selection capabilities per operator’s policy in order to realize efficient and flexible mobile service steering in the Gi-LAN network | 22.808
158 | 620070 | Study on Enhanced Calling Information Presentation | FS_ECIP | 1 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-09-17 17:00 | 70% | SP-130598 | - | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#64 completion 06/14=>09/14. TR 22.810v100 for Information. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067 | 22.810
159 | 620071 | Study on Multimedia Broadcast Supplement for Public Warning System (PWS) | FS_MBSP | 1 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-09-17 17:00 | 59% | SP-130599 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | Study the case where a public safety agency needs to distribute on a large scale timely multimedia public safety information to the public. Linked to Rel-9 Feature PWS | 22.815 | Public Safety (I-A)
160 | 630017 | Study on RAN Sharing Enhancements on GERAN and UTRAN | FS_GUSH | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 80% | SP-140073 | - | Telefónica | chris.friel@telefonica.com | Update on GERAN and UTRAN of Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | 22.852 updates
161 | 630018 | Study on service aspects for dealing with User Control over spoofed calls | FS_UC_SPOOF | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-12-10 17:00 | 15% | SP-140074 | - | Sprint | Gregory.schumacher@sprint.com | Linked to SA3 Rel-11 TR 33.838 Protection against Unsolicited Communications in IMS (PUCI) and Rel-12 ongoing study TR 33.831 Study on Security on spoofed call detection and prevention - Stage 2 (FS_SPOOF) Caller identity verification | 22.898
162 | 640060 | Study on User Location Reporting Support enhancements | FS_eULRS | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2015-06-17 17:00 | 0% | SP-140402 | - | China Unicom | Zhuoyun Zhang ( zhangzy910@chinaunicom.cn) | Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES) | 22.899
163 | 640061 | Study on Control of Applications when Third party Servers encounter difficulties | FS_CATS | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-12-10 17:00 | 0% | SP-140246 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | Linked to Rel-13 Feature Service Exposure & Enablement Support (SEES) and Rel-13 TR 22.806 Study on Application specific Congestion control for Data Communication (FS_ACDC) | 22.818
164 | 520035 | Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group | FS_UMONC_sas | 1 | Rel-13 | S2 | 2011-06-08 08:00 | 2014-12-10 17:00 | 0% | SP-140403 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Added to the Title "for Service, Application and Subscriber Group", Changed Acronym: FS_UMONC=>FS_UMONC_sas | 23.858
165 | 520335 | Deleted - SA1 part of Study on Usage Monitoring Control PCC Enhancement | - | 2 | - | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 0% | SP-120554 | - | ZTE | Li.Mian@zte.com.cn | SP#56 completed | 23.858
166 | 520135 | SA2 part of Study on Usage Monitoring Control PCC Enhancement | - | 2 | Rel-13 | S2 | 2013-06-02 08:00 | 2014-12-10 17:00 | 0% | SP-140403 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Updated WID SP-120554=>SP-140403. Changed Justification/objectives/Rapporteut ZTE=>China Unciom. SP#58 SA2 stopped (at 70% completion) | 23.858
167 | 520235 | Deleted - SA5 part of Study on Usage Monitoring Control enhancement | - | 2 | - | S5 | 2012-03-02 08:00 | 2012-09-12 17:00 | 0% | SP-120554 | - | Huawei | Hui Cai (Sarah.Cai@huawei.com) | SP#57 stopped | 32.858
168 | 640055 | Study on Lawful Interception Service Evolution | FS_LISE | 1 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-12-09 17:00 | 0% | SP-140303 | - | Alcatel-Lucent | terry.jacobson@alcatel-lucent.com | Linked to LI13 which defines existing LI service requirements in TS 33.106 as well as existing HI1, HI2 & HI3 reference points | 33.826
169 | 560435 | Study on Compliance of 3GPP SA5 specifications to the NGMN NGCOR | FS_OAM_NGMN_NGCOR | 1 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-09-16 17:00 | 30% | SP-140349 | - | Huawei | zoulan@huawei.com | SP#64 updated WID SP-120350=>SP-140349. Completion 06/14=>09/15. TR 32.837 moved out of Rel-12 BB as a stand-alone Rel-13 Study. Completion 50%=>30% (added NGCOR phase II in the scope) | 32.837
170 | 610045 | Study on Enhancements of OAM aspects of Distributed Mobility Load Balancing (MLB) SON function | FS_D_MLB_SON_OAM | 1 | Rel-13 | S5 | 2013-09-12 08:00 | 2014-12-10 17:00 | 20% | SP-130430 | - | Cisco | Vladimir Yanover (vyanover@cisco.com) | SP#64 updated WID SP-130430=>SP-140321. Completion 06/14=>12/14 | 32.860 | SON
171 | 620059 | Study on Application and Partitioning of Itf-N | FS_OAM_AP_Itf-N | 1 | Rel-13 | S5 | 2013-12-11 08:00 | 2014-12-10 17:00 | 10% | SP-130681 | - | China Mobile | Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com) | - | 32.861
172 | 620060 | Study on Charging aspects on Roaming End-to-end scenarios with VoLTE IMS and interconnecting networks | FS_REVOLTE_IMS_CH | 1 | Rel-13 | S5 | 2013-12-11 08:00 | 2014-12-10 17:00 | 30% | SP-130609 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | SP#64 moved to Rel-13. Completion 06/14=>12/14. Linked to CT3/CT1 draft TR 29.949 Study on Technical Aspects on Roaming End-to-end scenarios with VoLTE IMS and other networks (FS_REVOLTE_IMS) UID_610010 | 32.849
173 | 640054 | Study on Network Management of Virtualized Networks | FS_OAM_VIRNET | 1 | Rel-13 | S5 | 2014-06-06 08:00 | 2015-06-17 17:00 | 0% | SP-140398 | - | China Mobile, Huawei | xuehaiqiang@chinamobile.com, zoulan@huawei.com | Linked to ETSI Network Functions Virtualisation (NFV) ISG. Objective 1: Scenario, use cases & concepts for network management of Virtualized Networks. Objective 2: Recommend potential solutions supporting management of Virtualized Networks | 32.842
174 | 590034 | Study on Downlink MIMO | FS_DOMIMO | 1 | Rel-13 | G1,G2 | 2013-08-20 08:00 | 2015-02-20 17:00 | 45% | GP-130288 | - | NSN | Khairul Hasan | GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID | 45.8xy
175 | 620012 | Study on Power saving for Machine-Type Communications (MTC) devices | FS_uPoD | 1 | Rel-13 | G2,G1 | 2014-06-18 16:36 | 2015-02-20 17:00 | 15% | GP-131136 | - | China Mobile | Jing Han (hanjing@chinamobile.com) | GP#60 approved WID. Linked to Rel-12 Feature MTCe, Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP) | 43.869
176 | 620013 | Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO) | FS_UL_MU_MIMO | 1 | Rel-13 | G1,G2 | 2014-04-17 11:12 | 2015-02-20 17:00 | 15% | GP-131131 | - | Huawei | Chao Luo (chluo@huawei.com) | GP#62 completion 11/14=>02/15. GP#60 approved WID. Triggered by increase in UL connections to be served by PS domain in GSM networks (scenarios: GSM frequencies refarming to other RATs, emergence of MTC services over mobile radio networks) | 45.876
177 | 640001 | Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things | FS_IoT_LC | 1 | Rel-13 | G1,G2 | 2015-01-14 08:00 | 2015-08-28 17:00 | 0% | GP-140421 | - | Vodafone | chris.pudney@vodafone.com | GP#62 approved WID | 45.8xy | MTC, M2M
178 | 620045 | Study on Multi-RAT joint coordination | FS_MultiRAT_JC | 1 | Rel-13 | R3 | 2013-12-06 08:00 | 2014-12-05 17:00 | 30% | RP-132086 | RP-140605 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | Identify general scenarios and requirements for Multi-RAT (LTE/UMTS/GSM/CDMA/WLAN) coordination and study candidate solutions | UTRA, LTE 37.870 | WLAN
179 | 640016 | Study on Advanced Wireless Services (AWS) - Extension band for LTE | FS_LTE_AWS_EXT | 1 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 0% | RP-141037 | - | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | - | LTE 36.8xy
180 | 640017 | Study on MIMO OTA antenna test function for LTE | FS_LTE_MIMO_OTA_ATF | 1 | Rel-13 | R5 | 2013-03-15 08:00 | 2014-12-05 17:00 | 0% | RP-140985 | - | Agilent | Moray_Rumney@agilent.com | Linked to Rel-12 TR 37.977 under WI Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS, adding the radiated two-stage MIMO OTA test method, which now requires the definition of an antenna test function. | UTRA, LTE 37.9xy
181 | 640018 | Study on Indoor Positioning Enhancements for UTRA and LTE | FS_UTRA_LTE_iPos_enh | 1 | Rel-13 | R1,R4 | 2014-06-13 08:00 | 2015-09-17 17:00 | 0% | RP-141003 | - | NextNav | Vogedes Jerome (jvogedes@NextNav.com) | Study techniques for indoor positioning (RAT-dependent, e.g. OTDOA, UTDOA, E-CID, RFPM, and RAT-independent systems, e.g. A-GNSS, Terrestrial Beacon Systems). Study potential 3GPP positioning enh. in indoor/other challenging envir. (e.g. urban canyons) | UTRA, LTE 37.8xy
182 | 0 | Release 12 Features | - | 1 | Rel-12 | SP,CP,RP,GP | 2013-10-14 08:00 | 2014-12-10 17:00 | 65% | - | - | - | - | - | -
183 | 581000 | Stage 1 - ONLY Features | - | 1 | Rel-12 | SP,CP | 2011-09-27 08:00 | 2014-03-05 17:00 | 0% | - | - | - | - | - | -
184 | 490030 | SIPTO Service Continuity of IP Data Session | SIPTO_SC | 1 | Rel-12 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-100589 | - | Vodafone | mona.mustapha@vodafone.com | SP#57 moved to Rel-12 (Reason: Stage 2 for requirements in TS 22.101 clause 4.3.5 have not been implemented in Rel-11). Linked to Rel-10 Local IP Access and Selected Internet IP Traffic Offload (LIPA_SIPTO) | Stage 1 | HNB
185 | 490130 | Stage 1 for SIPTO Service Continuity of IP Data Session | - | 2 | Rel-12 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-100589 | - | Vodafone | mona.mustapha@vodafone.com | SP#57 moved to Rel-12. SP#53 completed | 22.101, 22.220 | HNB
186 | 500031 | Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers | MOSAP | 1 | Rel-12 | S1,S2 | 2010-12-16 08:00 | 2013-12-11 17:00 | 100% | SP-120427 | - | Cisco | Vojislav Vucetic (vvucetic@cisco.com) | SP#58 Stage 2 stopped (TR only, no normative work done) | Stage 1
187 | 500131 | Stage 1 for MOSAP | - | 2 | Rel-12 | S1 | 2010-12-16 08:00 | 2011-09-21 17:00 | 100% | SP-120427 | - | Cisco | Vojislav Vucetic (vvucetic@cisco.com) | SP#53 completed | 22.278
188 | 520025 | TR on Stage 2 for MOSAP | - | 2 | Rel-12 | S2 | 2011-06-06 08:00 | 2013-12-11 17:00 | 100% | SP-120427 | - | Intel | chang.hong.shan@intel.com | SP#62 completed. TR 23.862v200 for Approval. SP#58 frozen as v100. | new TR 23.862
189 | 520026 | Deleted - Stage 2 for MOSAP | - | 2 | Rel-12 | S2 | 2011-06-14 08:00 | 2012-12-12 17:00 | 100% | SP-120427 | - | Intel | chang.hong.shan@intel.com | SP#58 stopped (no normative work done) | TBD
190 | 520027 | IMS Network-Independent Public User Identities | INIPUI | 1 | Rel-12 | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-120425 | - | Vodafone | mona.mustapha@vodafone.com | Triggered by Rel-11 TR 22.894 (FS_INIPUI) | Stage 1
191 | 520127 | Stage 1 for IMS Network-Independent Public User Identities | - | 2 | Rel-12 | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-120425 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 re-completed. Updated WID SP-110381=>SP-120425 (Re-opened & moved to Rel-12 by adding new reqs & removing reqs from Rel-11). SP#53 Rel-11 Stage 1 completed | 22.115, 22.228
192 | 530043 | Service and Media Reachability for Users over Restrictive Firewalls | SMURFs | 1 | Rel-12 | S1 | 2011-09-21 08:00 | 2012-06-20 17:00 | 100% | SP-110653 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 Stage 1 completed | Stage 1
193 | 530143 | Stage 1 for Service and Media Reachability for Users over Restrictive Firewalls | - | 2 | Rel-12 | S1 | 2011-09-21 08:00 | 2012-06-20 17:00 | 100% | SP-110653 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 completed | 22.278
194 | 550024 | Advanced IP Interconnection of Services (IPXS) for national interconnect | IPXSNAT | 1 | Rel-12 | S1 | 2012-03-06 08:00 | 2012-09-12 17:00 | 100% | SP-120428 | - | KPN | toon.norp@tno.nl | SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051. | Stage 1
195 | 550124 | Stage 1 for Advanced IP Interconnection of Services (IPXS) for national interconnect | - | 2 | Rel-12 | S1 | 2012-03-06 08:00 | 2012-09-12 17:00 | 100% | SP-120428 | - | KPN | toon.norp@tno.nl | SP#57 completed | 22.228 CR#0161
196 | 550025 | Integration of Single Sign-On (SSO) frameworks with 3GPP networks | SSO_Int | 1 | Rel-12 | S1 | 2012-03-08 08:00 | 2012-09-12 17:00 | 100% | SP-120184 | - | InterDigital | christopher.wallace@interdigital.com | SP#57 Stage 1 completed. Triggered by Rel-12 TR 22.895. Linked to SA3 33.8xy (Study on Security aspects of SSO_Int), 33.914 (SSO application security for common IMS based on SIP Digest), 33.924 (i/w GBA and OpenID), 33.980 (i/w GBA and Liberty Alliance) | Stage 1
197 | 550125 | Stage 1 for Integration of Single Sign-On (SSO) frameworks with 3GPP networks | - | 2 | Rel-12 | S1 | 2012-03-08 08:00 | 2012-09-12 17:00 | 100% | SP-120184 | - | InterDigital | christopher.wallace@interdigital.com | SP#57 completed | 22.101
198 | 560019 | Explicit Communication Transfer Blind (ECT Blind) service interactions | ECTB | 1 | Rel-12 | S1 | 2012-06-18 08:00 | 2012-06-20 17:00 | 100% | SP-120301 | - | Orange | philippe.lottin@orange.com | SP#56 WID approved & Stage 1 completed | Stage 1
199 | 560119 | Stage 1 for Explicit Communication Transfer Blind (ECT Blind) service interactions | - | 2 | Rel-12 | S1 | 2012-06-18 08:00 | 2012-06-20 17:00 | 100% | SP-120301 | - | Orange | philippe.lottin@orange.com | SP#56 new WID approved & work completed. Clarify the service interactions between ECT Blind and other MMTEL Supplementary Services | 22.173
200 | 570027 | IMS access via Digital Video Broadcast - Return Channel via Satellite (DVB-RCS2) | IMSSat | 1 | Rel-12 | S1 | 2012-02-02 08:00 | 2012-09-12 17:00 | 100% | SP-120543 | - | KPN | toon.norp@tno.nl | SP#57 Stage 1 completed. Integrate Satcom access with IMS. Specify DVB-RCS2 as an IP Connectivity Access Network for IMS | Stage 1
201 | 570127 | Stage 1 for IMS access via DVB-RCS2 | - | 2 | Rel-12 | S1 | 2012-02-02 08:00 | 2012-09-12 17:00 | 100% | SP-120543 | - | KPN | toon.norp@tno.nl | SP#57 completed. Definition of DVB-RCS2 as a non-3GPP IP Connectivity Access Network for IMS | 22.228
202 | 580060 | Sequential Flexible Alerting | SEQ_FA | 1 | Rel-12 | S1 | 2012-12-10 08:00 | 2012-12-12 17:00 | 100% | SP-120895 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#58 approved WID & Stage 1 completed. Currently Flexible Alerting (FA) group members are simultaneously alerted by the incoming call. Add the possibility to alert FA group members sequentially. | Stage 1
203 | 580160 | Stage 1 for Sequential Flexible Alerting | - | 2 | Rel-12 | S1 | 2012-12-10 08:00 | 2012-12-12 17:00 | 100% | SP-120895 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#58 approved WID & Stage 1 completed | 22.173
204 | 580061 | Language and Modality Information for communications | LangInfo | 1 | Rel-12 | S1 | 2012-12-11 08:00 | 2013-03-06 17:00 | 100% | SP-130108 | - | Orange | philippe.lottin@orange.com | SP#59 Stage 1 completed. Triggered by Rel-11 Study on Non Voice Emergency Services (FS_NOVES) TR 22.871 use case 10 | Stage 1
205 | 580161 | Stage 1 for Language and Modality Information for communications | - | 2 | Rel-12 | S1 | 2012-12-11 08:00 | 2013-03-06 17:00 | 100% | SP-130108 | - | Orange | philippe.lottin@orange.com | SP#59 completed. Updated WID SP-120937=>SP-130108 | 22.228
206 | 590040 | Emergency Session Identification | ESID | 1 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130126 | - | Telecom Italia | carmen.catalano@telecomitalia.it | SP#59 Stage 1 completed. | Stage 1
207 | 590140 | Stage 1 for Emergency Session Identification | - | 2 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130126 | - | Telecom Italia | carmen.catalano@telecomitalia.it | SP#59 completed (22.101 CR#0445) | 22.101
208 | 590041 | Deleted - Application and Service Access Control | ASAC | 1 | Rel-12 | S1 | 2013-03-06 08:00 | 2013-06-19 17:00 | 100% | SP-130124 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#60 stopped and Rel-13 FS_ACDC continues. Triggered by TR 22.806 Study on Application specific Congestion control for Data Communication (FS_ACDC) UID_570034 | Stage 1
209 | 590141 | Deleted - Stage 1 for Application and Service Access Control | - | 2 | Rel-12 | S1 | 2013-03-06 08:00 | 2013-06-19 17:00 | 100% | SP-130124 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#60 stopped and Rel-13 FS_ACDC contd. Allow/prohibit for E-UTRAN idle mode UE initiation of particular applications defined by operator and subject to regional regulations. Prevent/mitigate overload of AN/CN defined by operator (congestion or disaster) | 22.011
210 | 590042 | Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode | PMOC | 1 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130111 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#59 Stage 1 completed | Stage 1
211 | 590142 | Stage 1 for Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode | - | 2 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130111 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#59 completed | 22.011
212 | 561000 | SA1/SA2 Features | - | 1 | Rel-12 | SP,CP,RP | 2013-05-17 08:00 | 2014-03-07 17:00 | 0% | - | - | - | - | - | -
213 | 500028 | LIPA Mobility and SIPTO at the Local Network | LIMONET | 1 | Rel-12 | S2,C4,C1,R3 | 2010-10-15 08:00 | 2014-03-06 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | CP#63 completed. SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility). Linked to UID_450035 Local IP Access and Selected IP Traffic Offload (LIPA_SIPTO) | Stage 2/3 | HNB
214 | 500128 | TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network | - | 2 | Rel-12 | S2 | 2010-10-15 08:00 | 2013-03-06 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#59 completed. TR 23.859 v100 for Information and Approval | new TR 23.859 | HNB
215 | 500328 | BB1: SIPTO at the Local Network | LIMONET-SIPTO | 2 | Rel-12 | S2 | 2010-10-22 08:00 | 2014-03-05 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#60 completed | 23.060, 23.401 | HNB
216 | 501328 | Stage 2 for SIPTO at the Local Network | - | 3 | Rel-12 | S2 | 2010-10-22 08:00 | 2013-06-19 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#60 completed | 23.060, 23.401 | HNB
217 | 530015 | Stage 3 CN aspects of SIPTO at the Local Network | - | 3 | Rel-12 | C4,C1 | 2011-09-24 08:00 | 2014-03-05 17:00 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#63 completed | Stage 3 | HNB
218 | 530115 | CT4 part of Stage 3 CN aspects of SIPTO at the Local Network | - | 4 | Rel-12 | C4 | 2011-09-24 08:00 | 2013-09-06 17:00 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#61 completed | 23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.303 | HNB
219 | 530215 | CT1 part of Stage 3 CN aspects of SIPTO at the Local Network | - | 4 | Rel-12 | C1 | 2011-09-24 08:00 | 2014-03-05 17:00 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#63 completed | 24.008, 24.301 | HNB
220 | 590020 | RAN aspects for SIPTO at the Local Network | LIMONET-RAN | 2 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-130372 | - | Huawei | zheng.zhou@huawei.com | - | UTRA, LTE | HNB
221 | 590120 | Core part: RAN aspects for SIPTO at the Local Network | LIMONET-RAN-Core | 3 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-130372 | RP-131512 | Huawei | zheng.zhou@huawei.com | RP#62 completed | 25.401, 25.413, 25.423, 25.467, 25.469, 36.300, 36.413, 36.423 | HNB
222 | 501228 | Deleted - BB2: Stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network | LIMONET-LIPA | 2 | Rel-12 | S2 | 2010-10-22 08:00 | 2012-12-12 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility) | 23.060, 23.401 | HNB
223 | 500228 | Deleted - Stage 2 for stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network | - | 3 | Rel-12 | S2 | 2010-10-22 08:00 | 2012-12-12 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility) | 23.060, 23.401 | HNB
224 | 530016 | Deleted - Stage 3 CN aspects of LIPA Mobility | - | 3 | Rel-12 | C1,C4 | 2011-09-24 08:00 | 2012-12-12 17:00 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | Stage 3 | HNB
225 | 530116 | Deleted - CT1 part of CN aspects of LIPA Mobility | - | 4 | Rel-12 | C1 | 2011-09-24 08:00 | 2012-12-12 17:00 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | 24.008, 24.301 | HNB
226 | 530216 | Deleted - CT4 part of CN aspects of LIPA Mobility | - | 4 | Rel-12 | C4 | 2011-09-24 08:00 | 2012-12-12 17:00 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | 29.060, 29.274, 29.281, 29.303, 29.002, 29.272, 29.275, 29.282, 29.305 | HNB
227 | 510049 | Operator Policies for IP Interface Selection | OPIIS | 1 | Rel-12 | S2,C1 | 2011-03-23 08:00 | 2013-12-06 17:00 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | Linked to Rel-10 IFOM IP Flow Mobility and seamless WLAN offload (non-seamless WLAN offload aspects) & Rel-11 LIMONET (support traffic offload at local network) | Stage 2/3
228 | 510149 | TR on Stage 2 for Operator Policies for IP Interface Selection | - | 2 | Rel-12 | S2 | 2011-03-23 08:00 | 2012-12-12 17:00 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | SP#58 completed | new TR 23.853
229 | 510249 | Stage 2 for Operator Policies for IP Interface Selection | - | 2 | Rel-12 | S2 | 2011-04-04 08:00 | 2013-03-06 17:00 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | SP#59 completed (23.402 CR#152: Introduction of Inter-APN Routing Policies) | 23.402
230 | 600047 | Stage 3 for Operator Policies for IP Interface Selection | OPIIS-CT | 2 | Rel-12 | C1 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130215 | - | LG Electronics | Jaehyun Kim (jaehyun7.kim@lge.com) | CP#62 completed. Specify Inter-APN Routing Policies for selecting an IP interface to route IP flows among a choice of available interfaces in both 3GPP and non-3GPP accesses | 24.302, 24.312
231 | 520029 | Short Message Service (SMS) submit and delivery without MSISDN in IMS | SMSMI | 1 | Rel-12 | S2,C1,C4 | 2011-06-08 08:00 | 2013-12-06 17:00 | 100% | SP-120321 | - | NSN | curt.wong@nsn.com | Linked to Rel-7 SMSIP (Support of SMS over generic 3GPP IP access), Rel-11 SIMTC, Rel-12 TR 22.988 SA1 Study on alternatives to E.164 for MTC | Stage 2/3
232 | 520129 | TR on Stage 2 for SMS submit and delivery without MSISDN in IMS | - | 2 | Rel-12 | S2 | 2011-06-08 08:00 | 2012-12-12 17:00 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | SP#58 completed | new TR 23.863
233 | 520229 | Stage 2 for SMS submit and delivery without MSISDN in IMS | - | 2 | Rel-12 | S2 | 2011-06-13 08:00 | 2012-12-12 17:00 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | SP#58 completed | 23.204, 23.682
234 | 590013 | Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 2 | Rel-12 | C1,C4 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS | Stage 3
235 | 590113 | CT1 part of Stage 3 for SMS submit and delivery without MSISDN in IMS | - | 3 | Rel-12 | C1 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#62 completed | 23.040, 24.341
236 | 590213 | CT4 part of Stage 3 for SMS submit and delivery without MSISDN in IMS | - | 3 | Rel-12 | C4 | 2013-03-01 08:00 | 2013-09-06 17:00 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#61 completed | 23.008, 29.002, 29.305, 29.328, 29.338
237 | 530042 | IMS-based Telepresence | IMS_TELEP | 1 | Rel-12 | S1,C1,C3,C4,IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 15% | SP-110588 | - | Orange | bruno.tossou@orange-ftgroup.com | This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified | Stage 1/2/3
238 | 530142 | Stage 1 for IMS-based Telepresence | - | 2 | Rel-12 | S1 | 2011-09-22 08:00 | 2012-06-20 17:00 | 100% | SP-110588 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#56 completed | 22.228
239 | 580001 | CT part for IMS Telepresence (Stage 2/3) | - | 2 | Rel-12 | C1,C3,C4,IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 12% | CP-140196 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | - | Stage 2/3
240 | 580002 | TR on CT part of IMS Telepresence (Stage 2/3) | - | 3 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-06-13 17:00 | 100% | CP-140196 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#64 completed | New TR 24.803
241 | 580003 | CT1 part of IMS Telepresence (Stage 3) | - | 3 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-12 17:00 | 70% | CP-140196 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#63 completion 06/14=>09/14 (added new TS) | 24.147, 24.166, 24.229, New TS 24.103
242 | 641001 | (IETF) CT1 part of IMS Telepresence (mmusic-sctp-sdp) | - | 3 | Rel-12 | C1-IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 0% | CP-140196 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-mmusic-sctp-sdp
243 | 641002 | (IETF) CT1 part of IMS Telepresence (clue-framework ) | - | 3 | Rel-12 | C1-IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 0% | CP-140196 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-clue-framework
244 | 641003 | (IETF) CT1 part of IMS Telepresence (clue-datachannel) | - | 3 | Rel-12 | C1-IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 0% | CP-140196 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-clue-datachannel
245 | 641004 | (IETF) CT1 part of IMS Telepresence (clue-signaling) | - | 3 | Rel-12 | C1-IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 0% | CP-140196 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-clue-signaling
246 | 641005 | (IETF) CT1 part of IMS Telepresence (clue-data-model-schema) | - | 3 | Rel-12 | C1-IETF | 2010-03-19 13:00 | 2014-12-05 17:00 | 0% | CP-140196 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-clue-data-model-schema
247 | 580004 | CT3 part of IMS Telepresence (Stage 3) | - | 3 | Rel-12 | C3 | 2012-12-07 08:00 | 2014-09-12 17:00 | 0% | CP-140196 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#64 completion 06/14=>09/14 | 29.165
248 | 610011 | CT4 part of IMS Telepresence (Stage 2/3) | - | 3 | Rel-12 | C4 | 2013-09-10 08:00 | 2014-09-12 17:00 | 0% | CP-140196 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | - | 23.333, 29.333
249 | 560020 | Group Communication System Enablers for LTE | GCSE_LTE | 1 | Rel-12 | S1,S2,S3,C3,C4,R3 | 2012-06-18 08:00 | 2014-09-17 17:00 | 86% | SP-140113 | - | NSN | Juergen.Merkel@nsn.com | Linked to Rel-12 FS_ProSe TR 22.803 Study on Proximity-based Services. External requirements: NIST, MESA, APCO Global Alliance, TCCA. Specify 3GPP system enablers to support group communication over LTE for Public Safety | Stage 1/2/3 | Public Safety (A-A)
250 | 560120 | Stage 1 for Group Communication System Enablers for LTE | - | 2 | Rel-12 | S1 | 2012-06-18 08:00 | 2013-06-19 17:00 | 100% | SP-140113 | - | NSN | Juergen.Merkel@nsn.com | SP#60 completed. TS 22.468 v100 for 1-step approval | New TS 22.468 | Public Safety (A-A)
251 | 590037 | TR on Architecture enhancements to support Group Communication System Enablers for LTE | - | 2 | Rel-12 | S2 | 2013-03-07 08:00 | 2014-03-07 17:00 | 100% | SP-140113 | - | NSN | curt.wong@nsn.com | SP#63 completed. Updated WID SP-130397=>SP-140113. TR 23.768v200 for Approval | New TR 23.768 | Public Safety (A-A)
252 | 590038 | Stage 2 for Group Communication System Enablers for LTE | - | 2 | Rel-12 | S2 | 2013-03-12 08:00 | 2014-09-17 17:00 | 95% | SP-140113 | - | NSN | curt.wong@nsn.com | SP#64 completion 06/14=>09/14. QCI agreed for handling of special bearer(s) for public safety, details added. SP#63 TS 23.468 v100 for 1-step Approval | New TS 23.468 | Public Safety (A-A)
253 | 610135 | TR on Security for Group Communication System Enablers for LTE (Stage 2) | - | 2 | Rel-12 | S3 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-140113 | - | NSN | anja.jerichow@nsn.com | SP#64 completed. TR 33.888 v100 for 1-step Approval | New TR 33.888 | Public Safety (A-A)
254 | 610035 | Security for Group Communication System Enablers for LTE (Stage 2) | - | 2 | Rel-12 | S3 | 2013-09-13 08:00 | 2014-06-18 17:00 | 100% | SP-140113 | - | NSN | anja.jerichow@nsn.com | SP#64 completed. | 33.246 | Public Safety (A-A)
255 | 640010 | CT aspects of Group Communication System Enablers for LTE | GCSE_LTE-CT | 2 | Rel-12 | C3,C4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140452 | - | NSN | thomas.belling@nsn.com | - | Stage 3
256 | 640110 | CT3 part of Group Communication System Enablers for LTE | - | 3 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140452 | - | NSN | thomas.belling@nsn.com | - | 29.061, 29.212, 29.213, 29.214, 29.274, New TS 29.468
257 | 640210 | CT4 part of Group Communication System Enablers for LTE | - | 3 | Rel-12 | C4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140452 | - | NSN | thomas.belling@nsn.com | - | 23.007, 23.008
258 | 640037 | Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM | 2 | Rel-12 | R3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141035 | - | Alcatel-Lucent | hakon.helmers@alcatel-lucent.com | - | LTE
259 | 640137 | Core part: Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM-Core | 3 | Rel-12 | R3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141035 | - | Alcatel-Lucent | hakon.helmers@alcatel-lucent.com | - | 36.413
260 | 560022 | Machine-Type and other mobile data applications Communications enhancements | MTCe | 1 | Rel-12 | S2,S1,S3,C1,C3,C4,C6,R2,R3 | 2009-12-10 08:00 | 2014-09-12 17:00 | 94% | SP-130327 | - | Intel | puneet.jain@intel.com | - | Stage 1/2/3 | MTC, M2M
261 | 560021 | Stage 1 for Support for Interworking with M2M Service Enablement | MTCe-SIMSE | 2 | Rel-12 | S1 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120436 | - | KPN | toon.norp@tno.nl | SP#59 completed. Define requirements for interworking with M2M service enablement layer specified by ETSI TC M2M in TS 102 689 ( specification for Service Enablement layer) | 22.368 | MTC, M2M
262 | 570030 | Stage 1 for Machine-Type and other mobile data applications Communications – Service Requirement Maintenance | MTCe-SRM | 2 | Rel-12 | S1 | 2012-09-13 08:00 | 2013-03-06 17:00 | 100% | SP-130105 | - | KPN | toon.norp@tno.nl | SP#59 completed. Updated WID SP-120541=>SP-130105 | 22.101, 22.368 | MTC, M2M
263 | 560722 | TR on Security aspects of Machine-Type Communications | - | 2 | Rel-12 | S3 | 2009-12-10 08:00 | 2014-03-07 17:00 | 100% | SP-130327 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#63 completed. TR 33.868v100 for 1-step Approval. Was Rel-10 UID_460023 (Security for NIMTC). Was Rel-11 UID_490028 (TR on Security aspects of MTC). SP#56 activity transferred to Rel-12 Feature MTCe | New TR 33.868 | MTC, M2M
264 | 560522 | Security and Privacy aspects for Machine-Type and other mobile data applications Communications enhancements (Stage 2) | - | 2 | Rel-12 | S3 | 2012-06-22 08:00 | 2014-03-07 17:00 | 100% | SP-130327 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#63 completed. TS 33.187v100 for 1-step Approval | New TS 33.187 | MTC, M2M
265 | 560122 | BB1: Small Data and Device Triggering Enhancements (SDDTE) | MTCe-SDDTE | 2 | Rel-12 | S2,C4,C3 | 2012-06-18 08:00 | 2014-09-12 17:00 | 99% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 Stage 2 completed | - | MTC, M2M
266 | 560622 | TR on Stage 2 BB1: Small Data and Device Triggering Enhancements | - | 3 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-12-11 17:00 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 completed. TR 23.887v200 for Approval | New TR 23.887 | MTC, M2M
267 | 562122 | Stage 2 for BB1: Small Data and Device Triggering Enhancements | - | 3 | Rel-12 | S2 | 2012-06-26 08:00 | 2013-12-11 17:00 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 completed | 23.682 | MTC, M2M
268 | 630001 | Stage 3 for BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE-CT | 3 | Rel-12 | C4,C3 | 2014-03-05 08:00 | 2014-09-12 17:00 | 93% | CP-140272 | - | Huawei | peter.schmitt@huawei.com | - | Stage 3 | MTC, M2M
269 | 630101 | CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement | - | 4 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 90% | CP-140272 | - | Huawei | peter.schmitt@huawei.com | CP#64 updated WID CP-140100=>CP-140272. Completion 06/14=>09/14 | 29.002, 29.336, 23.008, 29.337, 29.338, 29.230 | MTC, M2M
270 | 630201 | CT3 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement | - | 4 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 100% | CP-140272 | - | Huawei | peter.schmitt@huawei.com | CP#64 completed | 29.368 | MTC, M2M
271 | 560222 | Deleted - BB2: Monitoring Enhancements (MONTE) | MTCe-MONTE | 2 | Rel-12 | S2 | 2012-06-18 08:00 | 2012-12-12 17:00 | 100% | SP-120438 | - | Intel | puneet.jain@intel.com | SP#58 stopped (at 20% completion) | 23.682 | MTC, M2M
272 | 560322 | BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 2 | Rel-12 | S2,C1,C4,C6 | 2012-06-18 08:00 | 2014-09-12 17:00 | 83% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 Stage 2 completed | - | MTC, M2M
273 | 561622 | TR on Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP) | - | 3 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-12-11 17:00 | 100% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 completed. TR 23.887v200 for Approval | New TR 23.887 | MTC, M2M
274 | 562322 | Stage 2 for BB3: UE Power Consumptions Optimizations (UEPCOP) | - | 3 | Rel-12 | S2 | 2012-06-26 08:00 | 2013-12-11 17:00 | 100% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 completed | 23.060, 23.401, 23.682 | MTC, M2M
275 | 620007 | Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT | 3 | Rel-12 | C1,C4,C6 | 2013-12-06 08:00 | 2014-09-12 17:00 | 62% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | - | Stage 3 | MTC, M2M
276 | 620107 | CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | - | 4 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-09-12 17:00 | 90% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#64 completion 06/14=>09/14 | 24.008, 24.301 | MTC, M2M
277 | 620207 | CT4 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | - | 4 | Rel-12 | C4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#64 completion 06/14=>09/14 | 29.274, 29.060, 23.008 | MTC, M2M
278 | 620307 | CT6 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | - | 4 | Rel-12 | C6 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#64 completion 06/14=>09/14 | 31.101, 31.102, 31.111 | MTC, M2M
279 | 560422 | Deleted - BB4: Group based MTC feature (GROUP) | MTCe-GROUP | 2 | Rel-12 | S2 | 2012-06-20 08:00 | 2012-12-12 17:00 | 100% | SP-120267 | - | KPN | Annemieke Kips | SP#58 stopped (at 25% completion) | 23.682 | MTC, M2M
280 | 620043 | RAN enhancements for Machine-Type and other mobile data applications Communications | MTCe-RAN | 2 | Rel-12 | R2,R3 | 2014-02-03 15:24 | 2014-09-12 17:00 | 90% | RP-140752 | - | ZTE | sergio.parolari@zte.com.cn | Triggered by TR 23.887 Machine Type and other mobile data applications Communications Enhancements (MTCe), TR 37.869 Study on Enhancements MTC and other Mobile Data Applications; RAN aspects (FS_MTCe_RAN), Rel-11 TR 23.888 SIMTC | UTRA, LTE | MTC, M2M
281 | 620143 | Core part: RAN enhancements for Machine-Type and other mobile data applications Communications | MTCe-RAN-Core | 3 | Rel-12 | R2,R3 | 2014-02-03 15:24 | 2014-09-12 17:00 | 90% | RP-140752 | RP-140750 | ZTE | sergio.parolari@zte.com.cn | RP#64 updated WID RP-132053=>RP-140752 (impacted specs). Completion 06/14=>09/14 | 25.300, 25.304, 25.413, 36.300, 36.304, 36.413, 36.423 | MTC, M2M
282 | 560024 | Policy and Charging Control for supporting fixed broadband access networks | P4C | 1 | Rel-12 | S2,S1,S5,C3,C1,C4 | 2012-06-20 08:00 | 2014-09-17 17:00 | 97% | SP-120443 | - | Huawei | marco.spini@huawei.com | Linked to BBF, IETF work. SP#58 stopped BB3 to BB6. Split BB1 and BB2 into TR and Stage 2 work | Stage 1/2/3
283 | 570031 | Stage 1 for Policy and Charging Support for Fixed Mobile Convergence | P4C-FMC | 2 | Rel-12 | S1 | 2012-09-10 08:00 | 2012-09-12 17:00 | 100% | SP-120542 | - | Huawei | amar.deol@huawei.com | SP#57 completed | 22.278
284 | 560124 | BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO (Non Seamless WLAN Offload) traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F | 2 | Rel-12 | S2,S5,C3,C1,C4 | 2012-06-20 08:00 | 2014-09-17 17:00 | 95% | SP-120275 | - | Huawei | marco.spini@huawei.com | - | - | WLAN
285 | 560724 | TR on Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | - | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2014-09-17 17:00 | 90% | SP-120275 | - | Huawei | marco.spini@huawei.com | SP#64 TR 23.896 was never sent for approval due to incomplete P4C BBs | new TR 23.896 | WLAN
286 | 562124 | Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | - | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-12-11 17:00 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | SP#62 completed | 23.139, 23.203 | WLAN
287 | 610012 | Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 3 | Rel-12 | C3,C1,C4 | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#64 completed | 29.212, 29.213, 29.215, 29.219 | WLAN
288 | 610112 | CT3 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | - | 4 | Rel-12 | C3 | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | - | 29.212, 29.213, 29.215, 29.219 | WLAN
289 | 620009 | CT1 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | - | 4 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-03-05 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#63 completed | 24.302 | WLAN
290 | 620010 | CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | - | 4 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#64 completed | 29.273 | WLAN
291 | 600042 | Policy and Charging Enforcement Function (PCEF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3) | P4C-F-CH_P | 3 | Rel-12 | S5 | 2013-06-21 08:00 | 2014-09-17 17:00 | 90% | SP-130261 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#64 completion 06/14=>09/14 | Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299) | WLAN
292 | 600043 | Traffic Detection Function (TDF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3) | P4C-F-CH_T | 3 | Rel-12 | S5 | 2013-06-24 08:00 | 2014-06-18 17:00 | 100% | SP-130262 | - | Openet Telecom | alan.mcnamee@openet.com | SP#64 completed | Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299) | WLAN
293 | 560224 | BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI | 2 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | - | -
294 | 560824 | TR on Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | - | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | SP#60 completed | new TR 23.839
295 | 562224 | Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | - | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | SP#60 completed | 23.139, 23.203
296 | 560324 | Deleted - BB3: Policy and Charging Control for 3GPP UEs connected to fixed broadband access network via S2b and S2c reference points for EPC routed traffic (P4C-S2bc) | P4C-S2bc | 2 | Rel-12 | S2 | 2012-06-21 08:00 | 2012-12-12 17:00 | 100% | SP-120445 | - | ZTE | Tricci So (tso@zteusa.com) | SP#58 stopped (at 0% completion) | 23.139, 23.203, new TR 23.896
297 | 560424 | Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB) | P4C-HeNB | 2 | Rel-12 | S2 | 2012-06-21 08:00 | 2012-12-12 17:00 | 100% | SP-120278 | - | NEC | Stefan.Schmid@neclab.eu | SP#58 stopped (at 0% completion) | 23.139, 23.203, new TR 23.896
298 | 560524 | Deleted - BB5: Policy and Charging Control for supporting Layer 2 traffic in fixed broadband access network (P4C-FL2) | P4C-FL2 | 2 | Rel-12 | S2 | 2012-06-21 08:00 | 2012-12-12 17:00 | 100% | SP-120279 | - | Huawei | marco.spini@huawei.com | SP#58 stopped (at 0% completion) | 23.139, 23.203, new TR 23.896
299 | 560624 | Deleted - BB6: Policy and Charging Control for 3GPP UEs connected to fixed broadband access networks via S2a reference point for EPC routed traffic in convergence (P4C-TC) | P4C-TC | 2 | Rel-12 | S2 | 2012-06-20 08:00 | 2012-12-12 17:00 | 100% | SP-120280 | - | ZTE | Tricci So (tso@zteusa.com) | SP#58 stopped (at 30% completion) | 23.139, 23.203, new TR 23.896
300 | 560025 | IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI | 1 | Rel-12 | S2,S1,C1,C3 | 2011-09-28 16:12 | 2014-09-12 17:00 | 96% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | Linked to Rel-11 IPXS Feature UID_470051 Advanced IP Interconnection of Services. This WI defines a generic framework for interconnecting with any type of IMS based network including IP-PBXs. | Stage 1/2/3
301 | 560325 | Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation | - | 2 | Rel-12 | S1 | 2011-09-28 16:12 | 2012-09-12 17:00 | 100% | SP-120862 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | SP#57 completed. 22.228CR#0171 | 22.228
302 | 560125 | TR on IMS Business Trunking for IP-PBX in Static Mode of Operation | - | 2 | Rel-12 | S2,S1 | 2012-06-18 08:00 | 2013-06-19 17:00 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#60 completed | new TR 23.897
303 | 560225 | Stage 2 for IMS Business Trunking for IP-PBX in Static Mode of Operation | - | 2 | Rel-12 | S2 | 2012-06-25 08:00 | 2013-06-19 17:00 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#60 completed | 23.228
304 | 610007 | CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 2 | Rel-12 | C1,C3 | 2013-09-06 08:00 | 2014-09-12 17:00 | 91% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | CP#63 updated WID CP-130476=>CP-140110 | Stage 3
305 | 610107 | CT1 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | - | 3 | Rel-12 | C1 | 2013-09-06 08:00 | 2014-09-12 17:00 | 85% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | CP#63 updated WID CP-130476=>CP-140110. Completion 03/14=>09/14. Added New TS 24.525 (transfer of ETSI TS 182 025) | 23.218, 24.229, New TS 24.525 (transfer of ETSI TS 182 025)
306 | 610207 | CT3 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | - | 3 | Rel-12 | C3 | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | CP#64 completed | 29.165
307 | 560026 | WLAN Network Selection for 3GPP Terminals | WLAN_NS | 1 | Rel-12 | S2,S1,S3,C1 | 2012-06-18 08:00 | 2014-09-12 17:00 | 97% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 Stage 2 completed. Evaluate and if needed enhance existing 3GPP solutions for WLAN network selection taking into account WFA Hotspot 2.0 solutions | Stage 1/2/3 | WLAN
308 | 560126 | TR on Stage 2 for WLAN Network Selection for 3GPP Terminals | - | 2 | Rel-12 | S2,S1 | 2012-06-18 08:00 | 2013-12-11 17:00 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 completed | New TR 23.865 | WLAN
309 | 560226 | Stage 2 for WLAN Network Selection for 3GPP Terminals | - | 2 | Rel-12 | S2 | 2012-06-22 08:00 | 2013-12-11 17:00 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 completed | 23.402, 23.865 | WLAN
310 | 580055 | Deleted - TR on Security Aspects of WLAN Network Selection for 3GPP Terminals | - | 2 | Rel-12 | S3 | 2012-12-13 08:00 | 2014-03-07 17:00 | 100% | SP-120847 | - | Huawei | Lydia Xu (xuyixian@huawei.com) | SP#63 stopped (84% complete) | New TR 33.865 | WLAN
311 | 620005 | CT aspects of WLAN Network Selection for 3GPP Terminals (Stage 3) | WLAN_NS-CT | 2 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-09-12 17:00 | 80% | CP-130712 | - | Qualcomm | Amer Catovic, amerc@qualcomm.com | CP#64 completion 06/14=>09/14. Modify ANDSF MO to include TS 23.402 types of information. Define: 1) selection procedure for active ANDSF rule, 2) UE behaviour on interaction between different ANDSF policies | 24.302, 24.312 | WLAN
312 | 570028 | Deleted - IMS Registration Control | IMS_RegCon | 1 | Rel-12 | S1,S2,C1,C4 | 2012-01-31 08:00 | 2013-12-11 17:00 | 100% | SP-120735 | - | China Mobile | lulu@chinamobile.com | SP#62 stopped. Specify for fixed line the requirement of controlling user registration to IMS based on network information related to user location (e.g. IP address, DSLAM information) | Stage 1/2/3
313 | 570128 | Deleted - Stage 1 for IMS Registration Control | - | 2 | Rel-12 | S1 | 2012-01-31 08:00 | 2012-09-12 17:00 | 100% | SP-120735 | - | China Mobile | lulu@chinamobile.com | SP#57 completed | 22.228
314 | 580056 | Deleted - Stage 2 for IMS Registration Control | - | 2 | Rel-12 | S2 | 2012-12-13 08:00 | 2013-12-11 17:00 | 100% | SP-120735 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 stopped at 50% completion | 23.228
315 | 600016 | Deleted - CT aspects of IMS registration control | IMS_RegCon-CT | 2 | Rel-12 | C1,C4 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | Stage 2/3
316 | 600116 | Deleted - CT1 aspects of CT aspects of IMS registration control (Stage 2/3) | - | 3 | Rel-12 | C1 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | 23.218, 24.229
317 | 600216 | Deleted - CT4 aspects of CT aspects of IMS registration control (Stage 3) | - | 3 | Rel-12 | C4 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | 29.228, 29.229, 23.008
318 | 580059 | Proximity-based Services | ProSe | 1 | Rel-12 | S1,S2,S3,C1,C3,C4,C6,R1,R2,R4 | 2012-12-13 08:00 | 2015-03-13 17:00 | 70% | SP-140300 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#64 SA3 updated the SA-wide WID SP-130715=>SP-140300. Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044 | Stage 1/2 | Public Safety (A-A)
319 | 580159 | Stage 1 for Proximity-based Services | - | 2 | Rel-12 | S1 | 2012-12-13 08:00 | 2013-06-19 17:00 | 100% | SP-140300 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#60 completed | 22.115, 22.278 | Public Safety (A-A)
320 | 580259 | TR on Stage 2 for Proximity-based Services | - | 2 | Rel-12 | S2 | 2012-12-13 08:00 | 2014-03-07 17:00 | 100% | SP-140300 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#63 completed. TR 23.703v200 for Approval | New TR 23.703 | Public Safety (A-A)
321 | 580359 | Stage 2 for Proximity-based Services | - | 2 | Rel-12 | S2 | 2012-12-19 08:00 | 2014-06-18 17:00 | 100% | SP-140300 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#64 completed open issue/alignment to RAN/SA3 decisions. SP#63 TS 23.303v100 for 1-step Approval | New TS 23.303 | Public Safety (A-A)
322 | 590035 | TR on Security for Proximity-based Services | - | 2 | Rel-12 | S3 | 2013-03-07 08:00 | 2014-09-17 17:00 | 95% | SP-140300 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#64 updated WID SP-130715=>SP-140300. Completion 06/14=>09/14. TR 33.833 v100 for Information | New TR 33.833 | Public Safety (A-A)
323 | 590036 | Security for Proximity-based Services | - | 2 | Rel-12 | S3 | 2013-03-13 08:00 | 2014-06-18 17:00 | 100% | SP-140300 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#64 completed. Updated WID SP-130715=>SP-140300. TS 33.303 v100 for 1-step Approval | New TS 33.303 | Public Safety (A-A)
324 | 640039 | Charging Aspects of Proximity-based Services | ProSe-CH | 2 | Rel-12 | S5 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140401 | - | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | Study&define CH arch for one-to-many ProSe Direct Communication for ProSe-enabled Public Safety UE, define CH arch for ProSe Discovery for ProSe-enabled UE, define triggers for on/offline CH events, specify content&format of CDR & Diameter apps | Stage 2/3
325 | 640139 | Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use | - | 3 | Rel-12 | S5 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140401 | - | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | - | New TR 32.844
326 | 640239 | Specification of Charging Aspects of Proximity-based Services | - | 3 | Rel-12 | S5 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140401 | - | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | - | 32.240, 32.297, 32.298, 32.299, New TS 32.277
327 | 630006 | CT aspects of Proximity-based Services (Stage 3) | ProSe-CT | 2 | Rel-12 | C1,C3,C4,C6 | 2014-03-05 08:00 | 2014-09-12 17:00 | 36% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#64 updated WID CP-140194=>CP-140290 | Stage 3 | Public Safety (A-A)
328 | 630106 | CT1 part of CT aspects of Proximity-based Services | - | 3 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-09-12 17:00 | 60% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#64 TS 24.333, 24.334v100 for Information | 24.301, 23.122, New TSs (24.333, 24.334) | Public Safety (A-A)
329 | 630206 | CT3 part of CT aspects of Proximity-based Services | - | 3 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-09-12 17:00 | 25% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | - | New TS 29.343 | Public Safety (A-A)
330 | 630306 | CT4 part of CT aspects of Proximity-based Services | - | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 50% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | - | 29.272, 23.008, 23.003, New TSs (29.344, 29.345) | Public Safety (A-A)
331 | 630406 | CT6 part of CT aspects of Proximity-based Services | - | 3 | Rel-12 | C6 | 2014-03-06 08:00 | 2014-09-12 17:00 | 10% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | - | 31.102 | Public Safety (A-A)
332 | 630030 | LTE Device to Device Proximity Services | LTE_D2D_Prox | 2 | Rel-12 | R1,R2,R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 9% | RP-140955 | - | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | follow-up of TR 36.843 FS_LTE_D2D_Prox | LTE | Public Safety (A-A)
333 | 630130 | Core part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Core | 3 | Rel-12 | R1,R2,R4 | 2014-07-11 10:40 | 2014-09-12 17:00 | 61% | RP-140955 | RP-141015 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | RP#64 updated WID RP-140518=>RP-140955 | 36.101, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.306, 36.321, 36.322, 36.323, 36.331, 36.413, 36.423, New TR 36.8xy (LTE Device to Device Proximity Services; User Equipment (UE) radio transmission and reception) | Public Safety (A-A)
334 | 630230 | Perf. part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 0% | RP-140955 | RP-141015 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | - | 36.101, 36.133 | Public Safety (A-A)
335 | 580062 | Web Real Time Communication access to IMS | IMS_WebRTC | 1 | Rel-12 | S1,S2,S3,C1,C4,IETF | 2012-12-14 08:00 | 2014-12-10 17:00 | 60% | SP-130707 | - | China Mobile | lulu@chinamobile.com | IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed. | Stage 1/2
336 | 580162 | Stage 1 for Web Real Time Communication access to IMS | - | 2 | Rel-12 | S1 | 2012-12-14 08:00 | 2013-06-19 17:00 | 100% | SP-130707 | - | China Mobile | lulu@chinamobile.com | SP#60 completed | 22.101, 22.228
337 | 600040 | TR on Stage 2 for Web Real Time Communication access to IMS | - | 2 | Rel-12 | S2 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | SP-130707 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#62 completed. TR 23.701v100 for Information & Approval | New TR 23.701
338 | 600041 | Stage 2 for Web Real Time Communication access to IMS | - | 2 | Rel-12 | S2 | 2013-06-19 08:00 | 2014-03-07 17:00 | 100% | SP-130707 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#63 completed | 23.228
339 | 631001 | (IETF) Web Real Time Communication access to IMS (rtcweb-overview) | - | 2 | Rel-12 | S2-IETF | 2013-06-19 08:00 | 2014-12-10 17:00 | 50% | SP-130707 | - | Uwe Rauschenbach | Uwe Rauschenbach | In WGLC | draft-ietf-rtcweb-overview
340 | 620067 | TR on Security for Web Real Time Communication access to IMS | - | 2 | Rel-12 | S3 | 2013-12-11 08:00 | 2014-09-17 17:00 | 90% | SP-130707 | - | Ericsson | oscar.ohlsson@ericsson.com | SP#64 completion 06/14=>09/14. TR 33.871 v100 for Information | New TR 33.871
341 | 610036 | Security for Web Real Time Communication access to IMS | - | 2 | Rel-12 | S3 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130707 | - | Ericsson | oscar.ohlsson@ericsson.com | SP#64 completed | 33.203, 33.328
342 | 630003 | CT aspects of Web Real Time Communication (WebRTC) Access to IMS | - | 2 | Rel-12 | C1,C4,IETF | 2014-03-05 08:00 | 2014-12-05 17:00 | 18% | CP-140192 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | - | Stage 3
343 | 630103 | CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | - | 3 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-09-12 17:00 | 55% | CP-140192 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | - | 24.229, New TS 24.371
344 | 641006 | (IETF) Web Real Time Communication access to IMS (rtcweb-data-channel) | - | 3 | Rel-12 | C1-IETF | 2014-03-05 08:00 | 2014-12-05 17:00 | 0% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-rtcweb-data-channel
345 | 641007 | (IETF) Web Real Time Communication access to IMS (rtcweb-stun-consent-freshness) | - | 3 | Rel-12 | C1-IETF | 2014-03-05 08:00 | 2014-12-05 17:00 | 0% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-rtcweb-stun-consent-freshness
346 | 630203 | CT4 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | - | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-19 17:00 | 30% | CP-140192 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | CP#64 completion 06/14=>09/14 | 23.334, 29.334
347 | 580063 | Usage Monitoring Control PCC enhancement | UMONC | 1 | Rel-12 | S2,C3 | 2012-12-13 08:00 | 2013-09-06 17:00 | 100% | SP-120928 | - | ZTE | bi.yifeng@zte.com.cn | SP#59 Stage 2 completed. Triggered by Rel-12 TR 23.858 Study on Usage Monitoring Control enhancement (UID_520035) | Stage 2/3
348 | 580163 | Stage 2 for Usage Monitoring Control PCC enhancement | - | 2 | Rel-12 | S2 | 2012-12-13 08:00 | 2013-03-06 17:00 | 100% | SP-120928 | - | ZTE | bi.yifeng@zte.com.cn | SP#59 completed. 23.203 CR#0782 (Time Based Usage Monitoring), CR#0784 (Usage Monitoring via Online Charging System) | 23.203
349 | 600048 | CT3 aspects of Usage Monitoring Control PCC enhancement (Stage 3) | UMONC-CT3 | 2 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-09-06 17:00 | 100% | CP-130396 | - | ZTE | zhou.xiaoyun@zte.com.cn | CP#61 completed | 29.212, 29.214, 29.215
350 | 590039 | Application Based Charging | ABC | 1 | Rel-12 | S2,S5,C3 | 2013-03-07 08:00 | 2014-06-18 17:00 | 100% | SP-130328 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | Triggered by TR 23.800 Study on Application Based Charging (FS_ABC) UID_560038 | Stage 2/3
351 | 590139 | Stage 2 for Application Based Charging | - | 2 | Rel-12 | S2 | 2013-03-07 08:00 | 2013-06-19 17:00 | 100% | SP-130328 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | SP#60 completed | 23.203
352 | 600011 | Charging for Application Based Charging | - | 2 | Rel-12 | S5 | 2013-06-19 08:00 | 2014-06-18 17:00 | 100% | SP-130328 | - | Openet Telecom | alan.mcnamee@openet.com | SP#64 completed | 32.240, 32.251, 32.296, 32.298, 32.299
353 | 600049 | CT3 aspects of Application Based Charging (Stage 3) | ABC-CT3 | 2 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130353 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | CP#62 completed | 29.212, 29.213, 29.214, 29.215, 29.219
354 | 610038 | Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG | 1 | Rel-12 | S2,C1,C4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 88% | SP-130391 | - | ZTE | Tricci So (tso@zteusa.com) | - | Stage 2/3 | WLAN
355 | 610138 | Stage 2 for Enhanced S2a Mobility Over trusted WLAN access to EPC | - | 2 | Rel-12 | S2 | 2013-09-11 08:00 | 2014-03-07 17:00 | 100% | SP-130391 | - | ZTE | Tricci So (tso@zteusa.com) | SP#63 completed | 23.402 | WLAN
356 | 610009 | Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 2 | Rel-12 | C1,C4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 85% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#62 updated WID CP-130580=>CP-130715 | Stage 3 | WLAN
357 | 610109 | CT1 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | - | 3 | Rel-12 | C1 | 2013-09-09 08:00 | 2014-09-12 17:00 | 80% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#64 completion 06/14=>09/14 . CP#63 TS 24.244 v100 for Information | 24.302, New TS 24.244 (WLAN control plane protocol for trusted WLAN access to EPC) | WLAN
358 | 610209 | CT4 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | - | 3 | Rel-12 | C4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 90% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#64 completion 06/14=>09/14 | 29.273, 29.274, 29.275 | WLAN
359 | 610039 | Optimized Offloading to WLAN in 3GPP-RAT Mobility | WORM | 1 | Rel-12 | S2,C1 | 2013-09-12 08:00 | 2014-06-13 17:00 | 100% | SP-130392 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB) | Stage 2/3 | WLAN
360 | 610139 | Stage 2 for Optimized Offloading to WLAN in 3GPP-RAT Mobility | - | 2 | Rel-12 | S2 | 2013-09-12 08:00 | 2013-12-11 17:00 | 100% | SP-130392 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | SP#62 completed | 23.272, 23.401, 23.402 | WLAN
361 | 620003 | CT aspects of Optimized Offloading to WLAN in 3GPP-RAT Mobility (Stage 3) | WORM-CT | 2 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-140109 |  | Intel | Chen-ho Chin (chen-hox.chin@intel.com) | CP#63 updated WID CP-130710=>CP-140109. Completion 03/14=>06/14, Changed Rapp BB=>Intel. Stage 3 enabling differentiation/prioritization of 3GPP RATs relative to WLAN for traffic flow routing based on Inter-System Routing Policies | 24.302, 24.312 | WLAN
362 | 610040 | Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN | 1 | Rel-12 | S2,C3,C1,C4 | 2013-09-12 08:00 | 2014-09-12 17:00 | 67% | SP-130393 | - | Alcatel-Lucent | Laurent.thiebaut@alcatel-lucent.com | Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN | Stage 2/3 | WLAN
363 | 610140 | Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | - | 2 | Rel-12 | S2 | 2013-09-12 08:00 | 2014-03-07 17:00 | 100% | SP-130393 | - | Alcatel-Lucent | Laurent.thiebaut@alcatel-lucent.com | SP#63 completed | 23.203, 23.228, 23.402
364 | 620008 | CT aspects of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case (Stage 3) | NETLOC_TWAN-CT | 2 | Rel-12 | C3,C1,C4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 59% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | - | Stage 3
365 | 620108 | CT3 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | - | 3 | Rel-12 | C3 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#64 completed | 29.212, 29.214
366 | 620208 | CT1 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | - | 3 | Rel-12 | C1 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#64 completion 06/14=>09/14 | 24.229
367 | 620308 | CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | - | 3 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 90% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#64 completion 06/14=>09/14 | 29.273, 29.274, 29.275, 29.328, 29.329
368 | 620061 | Core Network Overload - User Location Information reporting improvement | CNO_ULI | 1 | Rel-12 | S2,C3,C4 | 2013-12-11 08:00 | 2014-09-12 17:00 | 95% | SP-130717 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | - | Stage 2/3
369 | 620161 | Stage 2 for Core Network Overload - User Location Information reporting improvement | - | 2 | Rel-12 | S2 | 2013-12-11 08:00 | 2014-03-07 17:00 | 100% | SP-130717 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#63 completed | 23.060, 23.203, 23.401
370 | 630004 | CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 2 | Rel-12 | C3,C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 93% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | Specify Stage 3 procedures to support the ULI signalling optimizations | Stage 3
371 | 630104 | CT3 part of CT aspects of Core Network Overload – User Location Information reporting improvements | - | 3 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#64 completed | 29.212, 29.213
372 | 630204 | CT4 part of CT aspects of Core Network Overload – User Location Information reporting improvements | - | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 90% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | 23.008, 29.060, 29.274
373 | 560028 | Rel-12 Security small Enhancements | SEC12 | 1 | Rel-12 | S3 | 2011-03-23 08:00 | 2014-06-18 17:00 | 90% | - | - | - | - | SEC12 is an umbrella Feature for Security related TEI12 type of changes that are not part of any other dedicated feature | Stage 2/3
374 | 510054 | Security aspects of Public Warning System | PWS_Sec | 1 | Rel-12 | S3,S1 | 2011-03-23 08:00 | 2014-09-17 17:00 | 97% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | - | - | Public Safety (I-A)
375 | 560029 | Stage 1 for Protection against false PWS Warning Notifications | - | 2 | Rel-12 | S1 | 2012-06-15 08:00 | 2012-09-12 17:00 | 100% | SP-120433 | - | Vodafone | adrian.neal@vodafone.com | SP#57 completed. Specify reqs to protect against false PWS Warning Notifications (Optional as not all regions/countries require this functionality). WID covers all objectives in SA3 PWS_Sec Feature-level WID replacing the original Stage 1 UID_510154 | 22.268 | Public Safety (I-A)
376 | 510354 | TR on SA3 part for Security aspects of Public Warning System | - | 2 | Rel-12 | S3 | 2011-03-23 08:00 | 2014-09-17 17:00 | 90% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#64 completion 06/14=>09/14. Updated WID SP-120434=>SP-140299 | New TR 33.869 | Public Safety (I-A)
377 | 511354 | Deleted - SA3 part for Security aspects of Public Warning System | - | 2 | Rel-12 | S3 | 2011-03-30 08:00 | 2014-06-18 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#64 stopped | New TS 33.269 | Public Safety (I-A)
378 | 510154 | Deleted - Stage 1 for Security aspects of Public Warning System | - | 2 | Rel-12 | S1 | 2011-03-23 08:00 | 2012-06-20 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | Completed in Rel-9 under PWS. SP#55 stopped, Stage 1 requirements removed from Rel-9 onwards (SP-120172). AP 55/1: SA1 to align Stage 1 PWS security for Rel-12. SA1 new WID PWS Security UID_560029. | 22.268 | Public Safety (I-A)
379 | 510254 | Deleted - Stage 2 for Security aspects of Public Warning System | - | 2 | Rel-12 | S2 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#53 work stopped as already done in previous releases | 23.401 | Public Safety (I-A)
380 | 510454 | Deleted - CT1 part for Security aspects of Public Warning System | - | 2 | Rel-12 | C1 | 2011-03-25 08:00 | 2012-06-20 17:00 | 100% | SP-120434 | - | ST-Ericsson | mikael.wass@ericsson.com | TSG#56 work stopped. SP#56 updated WID SP-110223=>SP-120334 (removed all but SA3 impacted specs) | 23.041 | Public Safety (I-A)
381 | 510554 | Deleted - RAN2 part for Security aspects of Public Warning System | - | 2 | Rel-12 | R2 | 2011-03-25 08:00 | 2011-09-16 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | RP#53 work stopped as no WI in RAN | 36.331 | Public Safety (I-A)
382 | 520031 | Security enhancements for usage of Generic Bootstrapping Architecture (GBA) from the browser (Stage 2) | Web_GBA | 1 | Rel-12 | S3 | 2011-06-08 08:00 | 2013-06-19 17:00 | 100% | SP-120890 | - | Nokia | Silke.Holtmanns@nokia.com | SP#60 completed | 33.220, 33.222, New TR 33.823
383 | 560030 | Extended IMS media plane security features | eMEDIASEC | 1 | Rel-12 | S3,C4,C1,C3,IETF | 2012-06-20 08:00 | 2014-12-10 17:00 | 84% | SP-120447 | - | Vodafone | Aguibou.Barry@vodafone.com | Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC) | Stage 2/3
384 | 560130 | SA3 part of Extended IMS media plane security features (Stage 2) | - | 2 | Rel-12 | S3 | 2012-06-20 08:00 | 2014-06-18 17:00 | 100% | SP-120447 | - | Vodafone | Aguibou.Barry@vodafone.com | SP#64 completed | 33.328
385 | 611003 | (IETF) SA3 part of Extended IMS media plane security features (mmusic-udptl-dtls) | - | 2 | Rel-12 | S3-IETF | 2012-06-20 08:00 | 2014-12-10 17:00 | 75% | SP-120447 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Submitted to IESG for Publication | draft-ietf-mmusic-udptl-dtls
386 | 580005 | CT aspects of Extended IMS media plane security features (Stage 2/3) | eMEDIASEC-CT | 2 | Rel-12 | C4,C1,C3,IETF | 2012-12-13 08:00 | 2014-12-05 17:00 | 84% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 updated WID CP-130392=>CP-130597 | Stage 2/3
387 | 600051 | TR on Extended IMS media plane security features and TCP related NAT traversal support; IMS H.248 profiles aspects | - | 3 | Rel-12 | C4 | 2012-12-13 08:00 | 2014-09-12 17:00 | 97% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | New TR 29.828
388 | 580006 | CT4 part of CT aspects of Extended IMS media plane security features | - | 3 | Rel-12 | C4 | 2012-12-19 08:00 | 2014-09-12 17:00 | 60% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | 23.334, 29.334, 29.238, 23.333, 29.333
389 | 621001 | (IETF) CT4 part of Extended IMS media plane security features (mmusic-udptl-dtls) | - | 3 | Rel-12 | C4-IETF | 2012-12-18 08:00 | 2014-12-05 17:00 | 75% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Submitted to IESG for Publication | draft-ietf-mmusic-udptl-dtls
390 | 641009 | (IETF) CT4 part of Extended IMS media plane security features (draft-schwarz-sdp-for-gw) | - | 3 | Rel-12 | C4-IETF | 2014-06-12 08:00 | 2014-12-05 17:00 | 75% | CP-130597 |  | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Submitted to IESG for Publication | draft-schwarz-sdp-for-gw
391 | 580007 | CT1 part of CT aspects of Extended IMS media plane security features | - | 3 | Rel-12 | C1 | 2012-12-13 08:00 | 2014-09-12 17:00 | 95% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#64 reduced completion 100%=>95%. Completion 03/14=>09/14 | 23.218, 24.147, 24.229, 24.247
392 | 621002 | (IETF) CT1 part of Extended IMS media plane security features (mmusic-udptl-dtls) | - | 3 | Rel-12 | C1-IETF | 2014-03-06 08:00 | 2014-12-05 17:00 | 75% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Submitted to IESG for Publication | draft-ietf-mmusic-udptl-dtls
393 | 580008 | CT3 part of CT aspects of Extended IMS media plane security features | - | 3 | Rel-12 | C3 | 2012-12-19 08:00 | 2014-06-13 17:00 | 100% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#64 completed | 29.162
394 | 570032 | Lawful Interception in the 3GPP Rel-12 | LI12 | 1 | Rel-12 | S3 | 2012-09-17 08:00 | 2014-09-12 17:00 | 75% | SP-130650 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | - | 33.106, 33.107, 33.108
395 | 580064 | Tunneling of UE Services over Restrictive Access Networks (Stage 2/3) | TURAN | 1 | Rel-12 | S3,C1 | 2012-12-13 08:00 | 2014-06-18 17:00 | 100% | SP-130245 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | Linked to Rel-12 SMURFs. Related to TS 22.278 (EPS) cl.7.1.8 Service Reachability (Firewall traversal for IP based services for non-3GPP access), TS 22.228 (IMS) cl.5 (support Firewall traversal), TR 33.830 (Study on Firewall traversal) | Stage 2/3
396 | 580164 | SA3 part of Tunneling of UE Services over Restrictive Access Networks (Stage 2/3) | - | 2 | Rel-12 | S3 | 2012-12-13 08:00 | 2014-06-18 17:00 | 100% | SP-130245 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | SP#64 completed | 33.203, 33.402
397 | 600050 | CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3) | TURAN-CT | 2 | Rel-12 | C1 | 2013-06-14 08:00 | 2014-06-13 17:00 | 100% | CP-130716 | - | Huawei | Haitao Wei (weihaitao@huawei.com) | CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1)UE access to PLMN IP-based services via restrictive non-3GPP ANs, 2) UE access to IMS services via restrictive Ans | 24.229, 24.302, New TS 24.322
398 | 620065 | Specification of the TUAK Algorithm Set | STAS | 1 | Rel-12 | S3 | 2013-12-09 08:00 | 2014-06-18 17:00 | 100% | SP-130647 | - | Vodafone | aguibou.barry@vodafone.com | SP#64 completed. Triggered by SP-130602 LS from ETSI SAGE (TUAK as alternative to Milenage) | New TSs (35.231, 35.232, 35.233)
399 | 470030 | Codec for Enhanced Voice Services | EVS_codec | 1 | Rel-12 | S4,S1 | 2010-03-25 08:00 | 2014-12-12 17:00 | 85% | SP-140151 | - | Huawei | lei.miao@huawei.com | Triggered by UID_370045 Study on enhanced voice service requirements for EPS (TR 22.813) | -
400 | 470031 | Stage 1 for Codec for Enhanced Voice Services | - | 2 | Rel-12 | S1 | 2010-03-25 08:00 | 2010-03-25 17:00 | 100% | SP-140007 | - | Huawei | lei.miao@huawei.com | SP#47 completed | 22.173
401 | 470032 | Stage 2/3 for Codec for Enhanced Voice Services | - | 2 | Rel-12 | S4 | 2010-03-25 08:00 | 2014-09-17 17:00 | 85% | SP-140151 | - | Huawei | lei.miao@huawei.com | SP#64 TS 26.441v100 for Information | 26.114, New TS (26.441, 26.442, 26.443, 26.444, 26.445, 26.446, 26.447, 26.448, 26.449, 26.450, 26.451)
402 | 470132 | TR on Performance characterization of Codec for Enhanced Voice Services | - | 2 | Rel-12 | S4 | 2010-03-25 08:00 | 2014-12-12 17:00 | 85% | SP-140151 | - | Huawei | lei.miao@huawei.com | SP#63 updated WID SP-100202=>SP-140151 (added new TR#) | New TR 26.952
403 | 560040 | Coordination of Video Orientation | CVO | 1 | Rel-12 | S4,C4,C1,C3 | 2012-06-07 08:00 | 2013-12-06 17:00 | 100% | SP-120228 | - | Ericsson | frederic.gabin@ericsson.com | CP#62 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering | -
404 | 560140 | SA4 part of Coordination of Video Orientation | - | 2 | Rel-12 | S4 | 2012-06-07 08:00 | 2013-03-06 17:00 | 100% | SP-120228 | - | Ericsson | frederic.gabin@ericsson.com | SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering | 26.114, 26.141, 26.234, 26.346
405 | 600006 | CT aspects of Coordination of Video Orientation | CVO-CT | 2 | Rel-12 | C4,C1,C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | Complete CVO support (both, basic 2 bit orientation and additional option for extra 6 bit granularity) within CN protocols/procedures for IMS nodes, e.g. IMS ALG/AGW,IBCF/TrGW,MRFC/MRFP & add support of CVO-related SDP attributes to be negotiated by UE | Stage 2/3
406 | 600106 | CT4 part of CT aspects of Coordination of Video Orientation | - | 3 | Rel-12 | C4 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334
407 | 600206 | CT1 part of CT aspects of Coordination of Video Orientation | - | 3 | Rel-12 | C1 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 24.229
408 | 600306 | CT3 part of CT aspects of Coordination of Video Orientation | - | 3 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 29.162, 29.163
409 | 570033 | High Efficiency Video Coding | HEVC | 1 | Rel-12 | S4,IETF | 2012-09-12 08:00 | 2014-12-05 17:00 | 81% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | Specify the support of HEVC in 3GPP services (PSS, DASH, MTSI, MMS, MBMS, IMS Messaging and Presence) | -
410 | 570133 | TR on Evaluation of High Efficiency Video Coding for 3GPP Services | - | 2 | Rel-12 | S4 | 2012-09-12 08:00 | 2014-06-19 08:00 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | SP#64 completed. TR 26.906v200 for Approval | New TR 26.906
411 | 570233 | High Efficiency Video Coding in 3GPP services PSS, MBMS, DASH, MMS, MTSI | - | 2 | Rel-12 | S4 | 2012-09-17 08:00 | 2014-06-18 17:00 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | SP#64 completed | 26.114, 26.140, 26.141, 26.234, 26.244, 26.247, 26.346
412 | 631002 | (IETF) High Efficiency Video Coding | - | 2 | Rel-12 | S4-IETF | 2012-09-17 08:00 | 2014-12-05 17:00 | 50% | SP-130569 | - | Thomas Stockhammer | Thomas Stockhammer | Not completed internet-draft | draft-ietf-payload-rtp-h265
413 | 580065 | Mobile stereoscopic 3D services extensions | M3DV_Ext | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2013-09-11 17:00 | 100% | SP-120768 | - | Huawei | lukasz.kondrad@huawei.com | SP#61 completed. Related to Rel-11 Study On Mobile 3D Video Coding (FS_M3DVC) TR 26.905 and Rel-11 Mobile 3D Video Coding (M3DVC) | 26.114, 26.245, 26.247, 26.430
414 | 580066 | IMS-based Streaming and Download Delivery Enhancements | IMS_SDE | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-03-07 17:00 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | Provide an extension of IMS based PSS and MBMS user services | -
415 | 580166 | TR on IMS-based Streaming and Download Delivery Enhancements | - | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-03-07 17:00 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | SP#63 completed. Identify use cases and requirements based on Rel-10/11 PSS and MBMS functionality to be addressed for IMS-based streaming and download enhancements | new TR 26.827
416 | 580266 | Specification on IMS-based Streaming and Download Delivery Enhancements | - | 2 | Rel-12 | S4 | 2012-12-13 08:00 | 2014-03-07 17:00 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | SP#63 completed. Develop procedures towards enabling the IMS-based extensions of the identified use cases in TS 26.237. Refine existing MBMS download procedures to enable IMS-based MBMS file repair with the use of conventional HTTP web servers. | 26.237
417 | 580067 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE | ART_LTE | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-09-17 17:00 | 71% | SP-120769 | - | Qualcomm | Andre Schevciw (aschevci@qualcomm.com) | Triggered by Rel-12 Feature Codec for Enhanced Voice Services (EVS_codec) UID_470030. Need for super wideband acoustic requirements and test methods | Stage 3
418 | 580167 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - NarrowBand and WideBand aspects | ART_LTE-NBWB | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2013-12-11 17:00 | 100% | SP-120771 | - | Sony Mobile Communications | peter.isberg@sonymobile.com | SP#62 completed | 26.131, 26.132
419 | 580267 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - UE Delay aspects | ART_LTE-UED | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-09-17 17:00 | 70% | SP-120770 | - | AT&T, Orange | luisa.marchetto@att.com, stephane.ragot@orange.com | SP#64 completion 06/14=>09/14 | 26.131, 26.132
420 | 580367 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - Super wideband and fullband aspects | ART_LTE-SUPER | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-09-17 17:00 | 55% | SP-120772 | - | Sony Mobile Communications | peter.isberg@sonymobile.com | SP#62 completion 06/14=>09/14 | 26.131, 26.132
421 | 590043 | MBMS Improvements | MI | 1 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-17 17:00 | 70% | SP-130024 | - | Ericsson | eric.turcotte@ericsson.com | Stage 3
422 | 590343 | TR on Enhanced MBMS Operation | - | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-17 17:00 | 75% | SP-140212 | - | Huawei | Zhiming Li (lizhiming@huawei.com) | SP#64 updated WID SP-130574=>SP-140212. Completion 06/14=>09/14. SP#63 TR 26.848v100 for Information | New TR 26.848
423 | 590143 | Enhanced MBMS Operation | MI-EMO | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-17 17:00 | 75% | SP-140212 | - | Huawei | Zhiming Li (lizhiming@huawei.com) | SP#64 updated WID SP-130574=>SP-140212. Completion 06/14=>09/14. Stage 3 based on existing Stage 2 in TS 23.246 MBMS Architecture and functional description | 26.247, 26.346
424 | 590443 | TR on MBMS operation on Demand | - | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-17 17:00 | 65% | SP-130026 | - | Qualcomm | Charles Lo (clo@qti.qualcomm.com) | SP#64 completion 06/14=>09/14. SP#63 TR 26.849v100 for Information | New TR 26.849
425 | 590243 | MBMS operation on Demand | MI-MooD | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-17 17:00 | 65% | SP-130026 | - | Qualcomm | Charles Lo (clo@qti.qualcomm.com) | SP#64 completion 06/14=>09/14. Stage 3 based on existing Stage 2 in TS 23.246 MBMS Architecture and functional description | 26.346
426 | 620066 | Video Coding Enhancements in IMS Messaging and Presence | VCEIMP | 1 | Rel-12 | S4 | 2013-12-11 08:00 | 2014-03-07 17:00 | 100% | SP-130579 | - | Ericsson | frederic.gabin@ericsson.com | SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141 | 26.141
427 | 640057 | Video Telephony Robustness Improvements | VTRI | 1 | Rel-12 | S4 | 2014-06-18 08:00 | 2014-09-17 17:00 | 0% | SP-140218 | - | Qualcomm | Muhammed Coban (mcoban@qti.qualcomm.com) | Linked to E2EMTSI (End-to-End Multimedia Telephony Service for IMS extensions). Add Reqs&guidelines for video telephony robustness to improve service perf. for PLI, Generic NACK, and FIR messages within overall bitrate limit | 26.114
428 | 560031 | Rel-12 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM12 | 1 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-09-17 17:00 | 48% | - | - | - | - | OAM12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | -
429 | 560131 | Rel-12 Self-Organizing Networks (SON) - OAM aspects | OAM12-SON | 2 | Rel-12 | S5 | 2011-09-21 08:00 | 2013-12-11 17:00 | 100% | - | - | - | - | OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI | - | HNB, SON
430 | 560033 | Multi-vendor Plug and Play eNB connection to the network | SON-NM-MUPPET | 3 | Rel-12 | S5 | 2011-09-21 08:00 | 2013-12-11 17:00 | 100% | SP-120777 | - | NSN | anatoly.andrianov@nsn.com | SP#62 completed. TS 32.508v200 for Approval, TS 32.509v100 for 1-step Approval | 32.501, New TSs (32.508, 32.509) | HNB, SON
431 | 560034 | Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 2 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 60% | SP-120349 | - | Huawei | christian.toche@huawei.com | Stage 1/2/3. Source of external requirements: NGMN Top OPE Recommendations 1.0 | -
432 | 560134 | TR on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | - | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 70% | SP-120349 | - | Huawei | christian.toche@huawei.com | SP#64 completion 06/14=>12/14. TR 32.838v100 for Information | New TR 32.838
433 | 560234 | TS work on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | - | 3 | Rel-12 | S5 | 2012-06-25 08:00 | 2014-09-17 17:00 | 50% | SP-120349 | - | Huawei | christian.toche@huawei.com | SP#64 completion 06/14=>12/14 | 32.101/2/3,32.111-1,32.111-2,32.111-6,32.15x,32.401,32.411,32.412,32.421,32.422,32.423,32.431,32.432,32.436,32.441,32.442,32.446,32.500,32.501,32.502,32.506,32.521,32.522,32.526,32.531,32.532,32.536,32.551,32.691,32.692,32.696,32.762
434 | 560035 | Compliance of 3GPP SA5 specifications to the NGMN Next Generation Converged Operations Requirements (NGCOR) | OAM-NGMN_NGCOR | 2 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 45% | SP-140321 | - | Huawei | christian.toche@huawei.com | SP#64 updated WID SP-120350=>SP-140321. Stage 1/2/3 | -
435 | 560135 | Converged Management Model Alignment (Phase 2) | OAM-MODAL | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 45% | SP-140322 | - | NSN | olaf.pollakowski@nsn.com | SP#64 updated WID SP-120351=>SP-140322. Completion 06/14=>09/14 | 32.156, new TR 32.8xy
436 | 560235 | Converged management Performance Management Interface Definitions | OAM-PMID | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 20% | SP-130641 | - | Huawei | christian.toche@huawei.com | SP#64 completion 06/14=>09/14 | new TSs (32.PM1, 32.PM6, 32.PM7)
437 | 560335 | 3GPP Fault Management Solution Profile for NGMN NGCOR | OAM-FMSP | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120778 | - | Ericsson | thomas.tovinger@ericsson.com | SP#60 completed. TS 28.390 v200 for Approval | new TS 28.390
438 | 560036 | WLAN Management | WLAN-OAM | 2 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 35% | SP-130042 | - | Intel | joey.chou@intel.com | - | - | WLAN
439 | 560336 | TR on WLAN impacts to Type-2 management interface to the 3GPP Network Manager | - | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 90% | SP-130042 | - | Intel | joey.chou@intel.com | SP#64 completion 06/14=>09/14 | new TR 32.841 | WLAN
440 | 560136 | WLAN Network Resource Model for Type-2 interface | - | 3 | Rel-12 | S5 | 2012-06-27 08:00 | 2014-09-17 17:00 | 10% | SP-130042 | - | Intel | joey.chou@intel.com | SP#64 completion 06/14=>09/14 | new TS (28.680, 28.682) | WLAN
441 | 560236 | WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface | - | 3 | Rel-12 | S5 | 2012-06-27 08:00 | 2014-09-17 17:00 | 5% | SP-130042 | - | Intel | joey.chou@intel.com | SP#64 completion 06/14=>09/14 | new TS 28.403 | WLAN
442 | 530050 | Network Management for 3GPP Interworking WLAN | OAM-IWLAN | 2 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-06-18 17:00 | 56% | SP-120779 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#62 completed. TSs 28.601/02/06/11/12/16 for Approval. Stage 2 in Rel-6 WLAN-UMTS i/w 23.234, Rel-7 WLAN i/w – Private Network access from WLAN 3GPP IP Access 23.234, Rel-8 Mobility between 3GPP-WLAN i/w and 3GPP Systems 23.327 | 32.632, 32.636, 32.752, 32.756, new TS (28.601, 28.602, 28.606, 28.611, 28.612, 28.616) | WLAN
443 | 530150 | Performance measurements part Network Management for 3GPP Interworking WLAN | - | 3 | Rel-12 | S5 | 2011-09-22 08:00 | 2014-06-18 17:00 | 20% | SP-120779 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | Stage 2 in Rel-6 WLAN-UMTS Interworking 23.234, Rel-7 WLAN Interworking – Private Network access from WLAN 3GPP IP Access 23.234, Rel-8 Mobility between 3GPP-WLAN Interworking and 3GPP Systems 23.327 | new TS (28.401, 28.402) | WLAN
444 | 530250 | NIM part Network Management for 3GPP Interworking WLAN | - | 3 | Rel-12 | S5 | 2011-09-21 08:00 | 2013-12-11 17:00 | 100% | SP-120779 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#62 completed. TSs 28.601/02/06/11/12/16 for Approval. Stage 2 in Rel-6 WLAN-UMTS i/w 23.234, Rel-7 WLAN i/w – Private Network access from WLAN 3GPP IP Access 23.234, Rel-8 Mobility between 3GPP-WLAN i/w and 3GPP Systems 23.327 | 32.632, 32.636, 32.752, 32.756, new TS (28.601, 28.602, 28.606, 28.611, 28.612, 28.616) | WLAN
445 | 580053 | Rel-12 Network Infrastructure Management | OAM12-NIM | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-09-17 17:00 | 29% | - | - | - | - | OAM12-NIM is an umbrella BB also for NIM related TEI12 type of changes that are not part of any other dedicated feature/WI | -
446 | 620056 | Alarm quality improvements | OAM-AMI | 3 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-09-17 17:00 | 25% | SP-130611 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#64 completion 06/14=>09/14. Triggered by Rel-12 TR 32.859 Study on Alarm Management (FS_OAM_AM) | 32.111-1, 32.111-2, 32.111-6
447 | 630012 | Radio Planning Tool (RPT) interface | OAM-RPTi | 3 | Rel-12 | S5 | 2014-03-07 08:00 | 2014-09-17 17:00 | 35% | SP-140026 | - | NSN | olaf.pollakowski@nsn.com | Standardize the interface between an RPT and applications using the site and antenna data held by the RPT. Standardize data (semantics and syntax) to be transferred over the interface in an NRM and on the operations to read access this data. | 32.101, New TSs (28.667, 28.668, 28.669)
448 | 580054 | Rel-12 Performance Management | OAM12-PM | 2 | Rel-12 | S5 | 2013-06-21 08:00 | 2014-09-17 17:00 | 25% | - | - | - | - | OAM12-PM is an umbrella BB also for PM related TEI12 type of changes that are not part of any other dedicated feature/WI | -
449 | 600044 | Energy Efficiency related Performance Measurements | OAM-PM_EE | 3 | Rel-12 | S5 | 2013-06-21 08:00 | 2014-09-17 17:00 | 25% | SP-130263 | - | NSN | Yizhi.yao@nsn.com | ETSI TC EE asked SA5 to identify/define Energy Efficiency related PM for E-UTRAN. Step 1: ETSI EE defines use cases/requirements/global KPIs to measure EE. Step 2: RAN2 crosschecks TS 36.314. Step 3: SA5 provides necessary additions to TS 32.425. | 32.425
450 | 620057 | OAM aspects of Network Sharing | OAM-SHARE | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-09-17 17:00 | 20% | SP-130607 | - | Orange | jeanmichel.cornily@orange.com | Triggered by Rel-12 TR 32.851 Study on OAM aspects of Network Sharing (FS_OAM_SHARE), Rel-6 Network Sharing (NTShar) UID_31018 | Stage 1/2/3
451 | 620157 | OAM aspects of Network Sharing - Concepts and high-level requirements | - | 3 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-09-17 17:00 | 25% | SP-130607 | - | Orange | jeanmichel.cornily@orange.com | SP#64 completion 06/14=>09/14 | new TS 32.130
452 | 620257 | OAM aspects of Network Sharing - Impacts on existing specifications | - | 3 | Rel-12 | S5 | 2013-12-12 08:00 | 2014-09-17 17:00 | 15% | SP-130607 | - | Orange | jeanmichel.cornily@orange.com | SP#64 completion 06/14=>09/14 | TBD
453 | 570037 | Rel-12 Charging | CH12 | 1 | Rel-12 | S5 | 2012-12-12 08:00 | 2014-06-18 17:00 | 100% | - | - | - | - | CH12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | -
454 | 580051 | Short Message Service - Service Center (SMS-SC) Offline Charging | SMS-SC-CH | 2 | Rel-12 | S5 | 2012-12-12 08:00 | 2014-03-07 17:00 | 100% | SP-140027 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027 | 32.240, 32.274, 32.297, 32.298, 32.299
455 | 610041 | Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3) | CHIPS | 2 | Rel-12 | S5 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130642 | - | Ericsson | david.shrader@ericsson.com | SP#64 completed | 32.251, 32.298, 32.299
456 | 610042 | Charging using an Alternative Roaming Provider (Stage 2/3) | CHARP | 2 | Rel-12 | S5 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130428 | - | Ericsson | david.shrader@ericsson.com | SP#64 completed. TS 32.276v200 for Approval, 32.293v100 for 1-step Approval | 32.240, 32.299, New TSs [32.276 (Voice Call Service Charging), 32.293 (Proxy Function)]
457 | 620058 | Charging for IMS centralized service (ICS) control (Stage 2/3) | CHICS | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-06-18 17:00 | 100% | SP-130610 | - | NSN | Gerald.Goermer@nsn.com | SP#64 completed. Align SA5 Charging specifications with Rel-8 Feature IMS Centralized Service control (ICSRA) and subsequent enhancements under TEIx (SA2 23.292 ICSRA Stage 2, CT3 29.292, CT1 24.607, 24.611) | 32.250, 32.298
458 | 530018 | IMS Emergency PSAP Callback (Stage 3) | EMC_PC | 1 | Rel-12 | C1,C3,IETF | 2011-09-21 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls | Stage 3 | Public Safety (I-A)
459 | 530118 | CT1 part of IMS Emergency PSAP Callback | - | 2 | Rel-12 | C1 | 2011-09-22 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | CP#64 completed | 24.229, tied to completion of IETF dependencies: 24.604, 24.605, 24.610, 24.611, 24.629 | Public Safety (I-A)
460 | 531004 | (IETF) CT1 part of IMS Emergency PSAP Callback (RFC 7090) | - | 2 | Rel-12 | C1-IETF | 2011-09-21 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#64 completed | RFC 7090 (was draft-ietf-ecrit-psap-callback | Public Safety (I-A)
461 | 530218 | CT3 part of IMS Emergency PSAP Callback | - | 2 | Rel-12 | C3 | 2011-09-24 08:00 | 2013-09-06 17:00 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | CP#61 completed | 29.163, 29.165 | Public Safety (I-A)
462 | 601001 | (IETF) CT3 part of IMS Emergency PSAP Callback (RFC 7090) | - | 2 | Rel-12 | C3-IETF | 2011-09-21 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#64 completed | RFC 7090 (was draft-ietf-ecrit-psap-callback) | Public Safety (I-A)
463 | 570008 | Interworking between a PLMN with WLAN to access the EPC and a PDN (Stage 3) | SAES_WLAN_EPC_intwk | 1 | Rel-12 | C3 | 2012-09-10 08:00 | 2013-09-06 17:00 | 100% | CP-130395 | - | Huawei | Christian.Herrero@huawei.com | CP#61 completed. Linked to Rel-8 Feature SAES: System Architecture Evolution specification - Evolved Packet System (non RAN aspects) UID_320005 | 29.061 | WLAN
464 | 580009 | Reporting Enhancements in Warning Message Delivery (Stage 2/3) | REP_WMD | 1 | Rel-12 | C1,C4,R3 | 2012-12-07 08:00 | 2014-06-13 17:00 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | Stage 1 for Cell Broadcast does not exist. This WID enhances the reporting capabilities of Warning Message Delivery. Introduce LTE functionality requested by regulators, equivalent to existing 2G/3G functionality. | Stage 2/3 | Public Safety (I-A)
465 | 580010 | CT1 part of Reporting Enhancements in Warning Message Delivery (Stage 2) | - | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-03-04 17:00 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | CP#63 completed | 23.041 | Public Safety (I-A)
466 | 580011 | CT4 part of Reporting Enhancements in Warning Message Delivery (Stage 2/3) | - | 2 | Rel-12 | C4 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | CP#64 completed | 23.007, 29.168 | Public Safety (I-A)
467 | 590021 | Public Warning System - Reset/Failure/Restart in Warning Message Delivery in LTE | REP_WMD-RFR_PWS | 2 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-06-13 17:00 | 100% | RP-130398 | - | one2many, Huawei | peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com) | - | LTE | Public Safety (I-A)
468 | 590121 | Core part: PWS - Reset/Failure/Restart in Warning Message Delivery in LTE | REP_WMD-RFR_PWS-Core | 3 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-06-13 17:00 | 100% | RP-130398 | RP-140637 | one2many, Huawei | peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com) | RP#64 completed | 36.413 | Public Safety (I-A)
469 | 580012 | Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3) | bSRVCC | 1 | Rel-12 | C1,C3,R5 | 2012-12-07 08:00 | 2014-03-06 17:00 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12 | GERAN, UTRA, LTE
470 | 580112 | CT1 part of Single Radio Voice Call Continuity (SRVCC) before ringing | - | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2013-06-14 17:00 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | CP#60 completed | 24.008, 24.237
471 | 600008 | CT3 part of Single Radio Voice Call Continuity (SRVCC) before ringing | - | 2 | Rel-12 | C3 | 2013-06-12 08:00 | 2013-06-14 17:00 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | CP#60 completed | 29.165
472 | 620017 | Test part: Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC-UEConTest | 2 | Rel-12 | R5 | 2013-12-06 08:00 | 2014-03-06 17:00 | 100% | RP-131919 | RP-140422 | NTT DOCOMO | Masahiro.Tamaoki.eu@nttdocomo.com | RP#63 completed. Testing for CT1 TS 24.237 (IMS service continuity Stage 3) | 34.229-1, 34.229-2, 36.523-1, 36.523-2
473 | 580013 | IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 1 | Rel-12 | C1,C3,IETF | 2012-12-07 08:00 | 2014-12-05 17:00 | 68% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | - | Stage 3
474 | 580014 | CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | - | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-12 17:00 | 95% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | 23.218, 24.229, 24.930
475 | 601002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | - | 2 | Rel-12 | C1-IETF | 2013-05-21 08:00 | 2014-12-05 17:00 | 50% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft | draft-holmberg-sipcore-received-realm
476 | 580015 | CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | - | 2 | Rel-12 | C3 | 2014-06-06 08:00 | 2014-09-12 17:00 | 85% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | 29.163, 29.165
477 | 611001 | (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | - | 2 | Rel-12 | C3-IETF | 2013-09-06 08:00 | 2014-12-05 17:00 | 50% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft | draft-holmberg-sipcore-received-realm
478 | 580016 | SAE Protocol Development - Phase 3 | SAES3 | 1 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-12 17:00 | 95% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005 | Stage 2/3
479 | 580017 | SAE Protocol Development (Stage 3) - Phase 3 | - | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-12 17:00 | 95% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#64 completion 06/14=>09/14 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118
480 | 580018 | CS Fallback in EPS - Phase 3 | SAES3-CSFB | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-12 17:00 | 95% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#64 completion 06/14=>09/14 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118
481 | 580019 | SAE for support for non-3GPP accesses - Phase 3 | SAES3-non3GPP | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-12 17:00 | 95% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#64 completion 06/14=>09/14 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118
482 | 580020 | IM-SSF Application Server Service Data Descriptions (Stage 2/3) | IMS_SSFDD | 1 | Rel-12 | C4,C1 | 2012-12-07 08:00 | 2013-06-14 17:00 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#60 completed | Stage 2/3
483 | 580021 | Stage 2 for IM-SSF Application Server Service Data Descriptions | - | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2013-03-01 17:00 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#59 completed | 23.218
484 | 580022 | Stage 3 for IM-SSF Application Server Service Data Descriptions | - | 2 | Rel-12 | C4 | 2012-12-10 08:00 | 2013-06-14 17:00 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#60 completed | 29.328, 29.329, 29.364
485 | 580023 | Diameter based interface between SGSN and SMS central functions (Stage 2/3) | Dia_SGSN_SMS | 1 | Rel-12 | C4,C1 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | Stage 2/3
486 | 590015 | Stage 2 for Diameter based interface between SGSN and SMS central functions | - | 2 | Rel-12 | C1 | 2013-03-07 08:00 | 2013-12-06 17:00 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | 23.040
487 | 580123 | Stage 3 for Diameter based interface between SGSN and SMS central functions | - | 2 | Rel-12 | C4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | 29.002, 29.230, 29.272, 29.305, 29.336, 29.337, 29.338
488 | 580024 | Diameter based interface between SGSN-GMLC (Stage 3) | Dia_SGSN_GMLC | 1 | Rel-12 | C4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | CP-130598 | - | Cisco | Nirav Salot (nsalot@cisco.com) | CP#62 completed. Updated WID CP-130273=>CP-130598. No Stage 2 impact. Define a Diameter variant for the protocol used over existing reference points between SGSN and GMLC for LCS (replace the use of MAP by Diameter protocol) | 29.002, 29.172, 29.173, 29.230, 29.272
489 | 590009 | IMS impacts on UICC Application Aspects (Stage 3) | IMS_UApAs | 1 | Rel-12 | C6 | 2013-03-04 08:00 | 2014-09-12 17:00 | 75% | CP-130169 | - | Giesecke & Devrient | pedro.hernandez@gi-de.com) | CP#64 completion 06/14=>09/14. Linked to Rel-11 CT1 WI ATURI (AT commands for Universal Resource Identifier support) | 31.102, 31.103, 31.111, 31.130
490 | 590012 | eMBMS restoration procedures | eMBMS_Rest | 1 | Rel-12 | C4,C3 | 2013-03-01 08:00 | 2014-06-13 17:00 | 75% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 completed. Linked to Rel-9 MBMS support in EPS (MBMS_EPS). Rel-10 CT Features EPC Node Restoration with/out Idle mode Signalling Reduction (ISR) activated (EPC_NR/EPC_NR_ISR) | Stage 3
491 | 590112 | CT4 part of eMBMS restoration procedures | - | 2 | Rel-12 | C4 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 completed | 23.007, 23.008, 29.274
492 | 610006 | CT3 part of eMBMS restoration procedures | - | 2 | Rel-12 | C3 | 2013-09-04 08:00 | 2014-06-13 17:00 | 50% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#64 updated WID CP-130432=>CP-140271 | 29.061
493 | 590014 | Dual Radio VCC enhancements (Stage 2/3) | eDRVCC | 1 | Rel-12 | S2,C1,C3 | 2012-09-19 08:00 | 2013-12-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed. Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). Stage 3 linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056 (Stage 2 in TS 23.237) | Stage 2/3
494 | 590114 | Stage 2 for Dual Radio VCC enhancements | - | 2 | Rel-12 | S2 | 2012-09-19 08:00 | 2013-03-01 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting) | 23.237
495 | 590214 | Stage 3 for Dual Radio VCC enhancements | - | 2 | Rel-12 | C1,C3 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed | Stage 3
496 | 590314 | CT1 part of Stage 3 for Dual Radio VCC enhancements | - | 3 | Rel-12 | C1 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed | 24.237, 24.292
497 | 590414 | CT3 part of Stage 3 for Dual Radio VCC enhancements | - | 3 | Rel-12 | C3 | 2013-03-01 08:00 | 2013-09-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#61 completed | 29.165
498 | 600009 | CT aspects of Signalling of Image Size (Stage 2/3) | SIS_CT | 1 | Rel-12 | C4,C1,C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included | Stage 2/3
499 | 600109 | CT4 part of Signalling of Image Size | - | 2 | Rel-12 | C4 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334
500 | 600209 | CT1 part of CT Aspects of Signalling of Image Size | - | 2 | Rel-12 | C1 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 24.229
501 | 600309 | CT3 part of CT Aspects of Signalling of Image Size | - | 2 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 29.162, 29.163
502 | 600010 | IMS Centralized Services (ICS) InterWorking Enhancement in Mobile Switching Center Server (MSC-S) | ICS_IWE | 1 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130352 | - | Orange | marianne.mohali@orange.com | CP#62 completed. Stage 3 enhancement interworking between IMS and MSC-S for IMS Centralized Services (ICS) | 29.292
503 | 610002 | GPRS Tunnelling Protocol for the Control plane (GTP-C) Overload Control Mechanisms | GOCMe | 1 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-09-12 17:00 | 90% | CP-130433 | - | Cisco | Nirav Salot (nsalot@cisco.com) | CP#64 completion 06/14=>09/14. CP#63 TR 29.807 v100 for Information | 23.008, 29.274, 29.303, New TR 29.807
504 | 610004 | Proxy Call Session Control Function (P-CSCF) restoration enhancements (Stage 2/3) | PCSCF_RES | 1 | Rel-12 | C4,C3,C1 | 2013-04-03 16:12 | 2014-12-05 17:00 | 17% | CP-140443 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#64 updated WID CP-130435=>CP-140443. Based on latest DRAFT TR 29.806v120, solutions B and D are selected for standardization | Stage 2/3
505 | 610104 | TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements | - | 2 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-09-12 17:00 | 35% | CP-140443 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#64 updated WID CP-130435=>CP-140443. Completion 06/14=>09/14 | New TR 29.806
506 | 610204 | CT4 part of Proxy Call Session Control Function (P-CSCF) restoration enhancements | - | 2 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-12-05 17:00 | 35% | CP-140443 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#64 updated WID CP-130435=>CP-140443. Completion 06/14=>12/14 | Common for HSS & PCRF solutions (23.380, 29.274), HSS solution (29.002, 29.228, 29.229, 29.272, 29.273, 29.305)
507 | 640014 | CT1 part of Proxy Call Session Control Function (P-CSCF) restoration enhancements | - | 2 | Rel-12 | C1 | 2013-04-03 16:12 | 2014-12-05 17:00 | 0% | CP-140443 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#64 updated WID CP-130435=>CP-140443. Added CT1 part | Common for HSS & PCRF solutions (24.008), HSS solution (24.229), PCRF solution (24.229)
508 | 640015 | CT3 part of Proxy Call Session Control Function (P-CSCF) restoration enhancements | - | 2 | Rel-12 | C3 | 2013-05-03 16:12 | 2014-12-05 17:00 | 0% | CP-140443 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#64 updated WID CP-130435=>CP-140443. Added CT3 part | PCRF based solution (29.212, 29.213, 29.214)
509 | 610005 | Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS | RTCP_MUX | 1 | Rel-12 | C4,C1,C3 | 2013-09-09 08:00 | 2014-09-12 17:00 | 4% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | Stage 2/3 | Stage 2/3
510 | 610105 | CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS | - | 2 | Rel-12 | C4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 10% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | 23.334, 29.334
511 | 610205 | CT1 part of Support of RTP / RTCP multiplexing (signalling) in IMS | - | 2 | Rel-12 | C1 | 2013-09-10 08:00 | 2014-09-12 17:00 | 0% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#64 completion 06/14=>09/14 | 24.229
512 | 610305 | CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS | - | 2 | Rel-12 | C3 | 2013-09-10 08:00 | 2014-06-13 17:00 | 0% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#62 completion 12/13=>06/14 | 29.213, 29.214
513 | 610008 | Updating IMS to conform to RFC 6665 (Stage 3) | UP6665 | 1 | Rel-12 | C1,C3 | 2013-09-09 08:00 | 2014-09-12 17:00 | 97% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | Stage 3. Review the references related to RFC 3265 in the 3GPP IMS specifications and determine the impact of the RFC 6665 changes | Stage 3
514 | 610108 | CT1 part of Updating IMS to conform to RFC 6665 | - | 2 | Rel-12 | C1 | 2013-09-09 08:00 | 2014-09-12 17:00 | 96% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | CP#64 completion 06/14=>09/14 | 23.218, 24.141, 24.147, 24.229, 24.237, 24.292, 24.337, 24.341, 24.604, 24.606, 24.623, 24.628, 24.629, 24.642
515 | 610208 | CT3 part of Updating IMS to conform to RFC 6665 | - | 2 | Rel-12 | C3 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | CP#62 completed | 29.163, 29.165
516 | 620004 | IMS Operator Determined Call Barring enhancements (Stage 3) | eIODB | 1 | Rel-12 | C1,C3 | 2013-12-06 08:00 | 2014-06-13 17:00 | 50% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CP#60 decision | Stage 3
517 | 620104 | CT1 part of IMS Operator Determined Call Barring enhancements | - | 2 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | CP#64 completed | 24.229, 24.315
518 | 620204 | CT3 part of IMS Operator Determined Call Barring enhancements | - | 2 | Rel-12 | C3 | 2013-12-09 08:00 | 2014-06-13 17:00 | 0% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | CP#63 completion 03/14=>06/14 | 29.165
519 | 620006 | Signalling Improvements for Network Efficiency (Stage 3) | SINE | 1 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-09-12 17:00 | 70% | CP-130713 | - | Huawei | Lin Shu (shulin@huawei.com) | CP#64 completion 06/14=>09/14. Triggered by C1-134079 LS_in GSMA Terminal Steering Group (TSG): Smartphone Network Efficiency (SNE) work item on "Signalling Loops and Aggressive Retries" issues. | 24.008, 24.301
520 | 630002 | Interactive Connectivity Establishment (ICE, IETF RFC 5245) impacts on IMS H.248 profiles | ICEH248 | 1 | Rel-12 | C4,C3 | 2014-03-05 08:00 | 2014-09-12 17:00 | 93% | CP-140266 | - | NSN | Jan.Kall@nsn.com | Add optional ICE support as defined in Rel-8 TS (23.228, 24.229) to Iq, Ix, Mn, Mp, Mc interfaces. SA2 Rel-12 TS 23.228 requires support for ICE in eP-CSCF, eIMS-AGW for WebRTC | Stage 2/3
521 | 630102 | CT4 part of ICE impacts on IMS H.248 profiles (Stage 2/3) | - | 2 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 90% | CP-140266 | - | NSN | Jan.Kall@nsn.com | CP#64 updated WID CP-140101=>CP-140266. Completion 06/14=>09/14 | 23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334
522 | 630202 | CT3 part of ICE impacts on IMS H.248 profiles (Stage 2) | - | 2 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | CP#64 completed | 29.162, 29.163, 29.292
523 | 630005 | Transfer of ETSI business trunking specifications | IMS_Corp2 | 1 | Rel-12 | C1,S1 | 2014-03-05 08:00 | 2014-09-17 17:00 | 85% | SP-140170 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com, Youssef Chadli | Rel-12 enhancements to business trunking (BusTI). ETSI E2NA(14)000019 asked 3GPP to take responsibility of business communications over IMS: TS 181 019, TS 182 023, TS 182 024, TS 182 025, TR 183 060 | -
524 | 630105 | SA1 part of Transfer of ETSI business trunking specifications | - | 2 | Rel-12 | S1 | 2014-03-05 08:00 | 2014-09-17 17:00 | 95% | SP-140170 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#64 completion 06/14=>09/14. TS 22.519v100 for Information | New TS 22.519 (ETSI TS 181 019)
525 | 630205 | CT1 part of Transfer of ETSI business trunking specifications | - | 2 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-09-12 17:00 | 75% | SP-140170 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com, Youssef Chadli | CP#64 completion 06/14=>09/14. TS 24.523/4 for 1-step Approval, 24.525 for Information. Transfer ETSI TS182023 (Arch scenarios),TS182024 (Hosted Enterprise Services-arch),TS18 025 (Business Trunking–arch&prot),TR183060 (SIP profile for Business Trunking) | New TSs [24.523 (TS 182 023), 24.524 (TS 182 024), 24.525 (TS 182 025)], New TR 24.969 (TR 183 069)
526 | 630007 | IMS Signalling Activated Trace | ISAT | 1 | Rel-12 | C1,C3,C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 0% | CP-140195 | - | Vodafone | peter.dawes @vodafone.com | Linked to Rel-8 OAM8-Trace. Update interface protocols to include the procedures defined in SA5 TS 32.422 for trace activation, and for conveying a signalling activated tracing indicator. | -
527 | 630107 | CT1 part of IMS Signalling Activated Trace | - | 2 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-09-12 17:00 | 0% | CP-140195 | - | Vodafone | peter.dawes @vodafone.com | CP#64 completion 06/14=>09/14 | 24.229, 24.323
528 | 630207 | CT3 part of IMS Signalling Activated Trace | - | 2 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 0% | CP-140195 | - | Vodafone | peter.dawes @vodafone.com | - | 29.165
529 | 630307 | CT4 part of IMS Signalling Activated Trace | - | 2 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 0% | CP-140195 | - | Vodafone | peter.dawes @vodafone.com | CP#64 completion 06/14=>09/14 | 23.008, 29.228, 29.229, 29.328, 29.329
530 | 630008 | Support of ALT-C attribute | ALTC | 1 | Rel-12 | C4,C1,C3 | 2014-03-05 08:00 | 2014-09-12 17:00 | 0% | CP-140191 | - | Orange | lionel.morand@orange.com | SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network. | -
531 | 630108 | CT4 part of Support of ALT-C attribute | - | 2 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-12 17:00 | 0% | CP-140191 | - | Orange | lionel.morand@orange.com | CP#64 completion 06/14=>09/14 | 23.334, 29.238, 29.334
532 | 630208 | CT1 part of Support of ALT-C attribute | - | 2 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-09-12 17:00 | 0% | CP-140191 | - | Orange | lionel.morand@orange.com | CP#64 completion 06/14=>09/14 | 24.229
533 | 630308 | CT3 part of Support of ALT-C attribute | - | 2 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 0% | CP-140191 | - | Orange | lionel.morand@orange.com | - | 29.162
534 | 640003 | Diameter Overload Control Mechanisms | DOCME | 1 | Rel-12 | C4,IETF | 2014-06-13 08:00 | 2014-12-05 17:00 | 33% | CP-140273 | - | Orange | lionel.morand@orange.com | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME) | -
535 | 640103 | CT4 part of Diameter Overload Control Mechanisms | - | 2 | Rel-12 | C4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140273 | - | Orange | lionel.morand@orange.com | - | 29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.344, 29.345
536 | 641010 | (IETF) Diameter Overload Control Mechanisms | - | 2 | Rel-12 | C4-IETF | 2014-06-13 08:00 | 2014-12-05 17:00 | 50% | CP-140273 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-dime-ovli
537 | 640004 | Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 1 | Rel-12 | C1,C3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | IETF updated RFC4244 for History-Info header field to RFC7044. IETF introduced new features which could be useful for 3GPP use cases. | -
538 | 640104 | CT1 part of Impacts of RFC7044 for introduction of the new History-Info header field | - | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | - | 24.229, 24.259, 24.604
539 | 640204 | CT3 part of Impacts of RFC7044 for introduction of the new History-Info header field | - | 2 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | - | 29.163, 29.165, 29.292
540 | 640007 | Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 1 | Rel-12 | C1,C3,IETF | 2014-06-13 08:00 | 2014-12-05 17:00 | 35% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | Triggered by TR 24.802 Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests UID_580025 | -
541 | 640107 | CT1 part of Indication of NNI Routeing scenarios in SIP requests | - | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-09-12 17:00 | 50% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | - | 24.229
542 | 641008 | (IETF) CT1 part of Indication of NNI Routeing scenarios in SIP requests (holmberg-dispatch-iotl) | - | 2 | Rel-12 | C1-IETF | 2014-06-13 08:00 | 2014-12-05 17:00 | 50% | CP-140288 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-holmberg-dispatch-iotl
543 | 640207 | CT3 part of Indication of NNI Routeing scenarios in SIP requests | - | 2 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | - | 29.079, 29.165
544 | 640008 | Unstructured Supplementary Service Data (USSD) method selection (Stage 3) | USSD_MS | 1 | Rel-12 | C1 | 2014-06-11 08:00 | 2014-06-13 17:00 | 100% | CP-140450 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#64 approved WID & completed. Related to R11 USSD simulation service in IMS (delivery of UE originating USSD request using IMS, I.e. introduce 2nd method for delivery of UE originating USSD request to network (additional to USSD using CS domain) | 24.173, 24.390, New TS 24.391
545 | 640009 | Representational State Transfer (REST) reference point between Application Function (AF) and Protocol Converter (PC) | REST_AF_PC | 1 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140451 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | Triggered by TR 29.817 Study on XML based access of the AF to the PCRF UID_590011) | 29.213, 29.214, new TS 29.201
546 | 640011 | Overload Control for PCC based Diameter applications | DOCME-PCC | 1 | Rel-12 | C3,IETF | 2014-06-13 08:00 | 2014-12-05 17:00 | 33% | CP-140405 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME) | -
547 | 640111 | CT3 part of Overload Control for PCC based Diameter applications | - | 2 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140405 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | - | 29.212, 29.213, 29.214
548 | 641011 | (IETF) Overload Control for PCC based Diameter applications | - | 2 | Rel-12 | C3-IETF | 2014-06-13 08:00 | 2014-12-05 17:00 | 50% | CP-140405 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-ietf-dime-ovli
549 | 530002 | Introduction of ER-GSM band for GSM-R | RT_ERGSM | 1 | Rel-12 | G1,C1,G3new | 2011-09-16 08:00 | 2014-02-28 17:00 | 100% | GP-130889 | SP-140137 | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | Use of band 870-876/915-921 MHz for land mobile service on national possibilities/market demand - as per ECC/DEC/(04)06. Introduction of ERGSM band, Performance requirements and Deployment scenarios. | GERAN
550 | 530102 | GERAN1 part of Introduction of ER-GSM band for GSM-R | - | 2 | Rel-12 | G1 | 2011-09-16 08:00 | 2014-02-28 17:00 | 100% | GP-130889 | SP-140137 | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | GP#61 completed. GP#51 approved WID | 45.001, 45.005, 45.008, 45.050
551 | 610016 | Test part: Introduction of ER-GSM band for GSM-R | - | 2 | Rel-12 | G3new | 2013-09-02 08:00 | 2014-02-28 17:00 | 100% | GP-130889 | SP-140137 | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | GP#61 completed | 51.010, 51.021
552 | 530202 | CT1 part of Introduction of ER-GSM band for GSM-R | - | 2 | Rel-12 | C1 | 2011-09-28 08:00 | 2013-12-06 17:00 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | CP#62 completed. Added ERGSM capability indication (24.008 CR#2469R1) | 24.008
553 | 570002 | Downlink Multi Carrier GERAN | DMCG | 1 | Rel-12 | G2,G1,C1,G3new | 2012-09-10 08:00 | 2014-09-12 17:00 | 26% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | Linked to Rel-7 Downlink Dual Carrier UID_50579 (Previous work on multiple carriers on the downlink was limited to two). Ref: TR 45.912 Feasibility study for evolved GERAN, TS 43.064 GPRS Stage 2 | GERAN
554 | 570102 | Core part: Downlink Multi Carrier GERAN | - | 2 | Rel-12 | G2,G1 | 2013-07-22 08:00 | 2014-05-30 17:00 | 100% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | GP#62 completed. GP#55 approved WID | 43.064, 44.004, 44.018, 44.060, 45.002, 45.003, 45.005, 45.008, 48.018
555 | 570202 | CT part: Downlink Multi Carrier GERAN | - | 2 | Rel-12 | C1 | 2012-09-10 08:00 | 2014-09-12 17:00 | 0% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | CP#64 completion 06/14=>09/14 | 24.008
556 | 570302 | Test part: Downlink Multi Carrier GERAN | DMCG-MStest | 2 | Rel-12 | G3new | 2012-09-10 08:00 | 2014-08-29 17:00 | 20% | GP-120930 | - | ST-Ericsson | hakan.e.grunditz@stericsson.com | GP#61 completion 02/14=>08/14 | 51.010-1, 51.010-2
557 | 590033 | Mobile Station Receive Diversity (MSRD) for Voice Services over Adaptive Multi-user channels on One Slot (VAMOS) | MSRD_VAMOS | 1 | Rel-12 | G1,G2,C1,G3new | 2013-03-01 08:00 | 2014-08-29 17:00 | 84% | GP-130849 | - | NSN, Microsoft Europe | Khairul Hasan (NSN), Markku Tarkiainen (Nokia=>Microsoft Europe) | Linked to Rel-7 Mobile Station Receive Diversity (DARP Phase II) UID_50569, Rel-9 Voice Services over Adaptive Multiuser channels on One Slot (VAMOS) UID_420002 | GERAN
558 | 590333 | CT1 introduction of MS capability support for MS supporting MSRD for VAMOS | - | 2 | Rel-12 | C1 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | GP-130849 | - | NSN, Microsoft Europe | Khairul Hasan (NSN), Markku Tarkiainen (Nokia) | CP#62 completed | 24.008
559 | 590133 | MSRD for VAMOS - Performance Requirements | MSRD_VAMOS-PerfReq | 2 | Rel-12 | G1,G2 | 2013-11-28 13:00 | 2014-08-29 17:00 | 85% | GP-130849 | - | NSN, Microsoft Europe | Khairul Hasan (NSN), Markku Tarkiainen (Nokia) | GP#61 completion 05/14=>08/14 | 44.018, 45.001, 45.002, 45.005, 45.008, 45.009
560 | 590233 | MSRD for VAMOS - MS Conformance Test | MSRD_VAMOS-Test | 2 | Rel-12 | G3new | 2013-03-06 08:00 | 2014-08-29 17:00 | 75% | GP-130849 | - | NSN, Microsoft Europe | Khairul Hasan (NSN), Markku Tarkiainen (Nokia) | GP#61 completion 05/14=>08/14 | 51.010-1, 51.010-2
561 | 620014 | New Training Sequence Codes (TSC) for GERAN | NewToN | 1 | Rel-12 | G1,G2,C1 | 2013-11-22 08:00 | 2014-08-29 17:00 | 50% | GP-131139 | - | Ericsson | Mårten Sundberg | GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002 | GERAN
562 | 620114 | GERAN1 part of New Training Sequence Codes (TSC) for GERAN | - | 2 | Rel-12 | G1 | 2013-11-22 08:00 | 2014-08-29 17:00 | 50% | GP-131139 | - | Ericsson | Mårten Sundberg | - | 45.001, 45.002, 45.008, 45.009, 45.050
563 | 620214 | GERAN2 part of New Training Sequence Codes (TSC) for GERAN | - | 2 | Rel-12 | G2 | 2013-11-22 08:00 | 2014-08-29 17:00 | 50% | GP-131139 | - | Ericsson | Mårten Sundberg | - | 44.018, 44.060
564 | 620314 | CT1 part of New Training Sequence Codes (TSC) for GERAN | - | 2 | Rel-12 | C1 | 2013-11-22 08:00 | 2014-08-29 17:00 | 50% | GP-131139 | - | Ericsson | Mårten Sundberg | Stage 3 | 24.008
565 | 550016 | Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS | HSPA_LTE_measRP_MIMO | 1 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-120368 | - | Vodafone | Luis Anaya | RP#59 moved to Rel-12. Triggered by FS_HSPA_LTE_measRP_MIMO_multi-antenna. Core functionality exists since Rel-6 & Rel-7 (MIMO). Adds a very generic test method to test UEs with 2 or more Rx antennas | UTRA, LTE
566 | 550116 | Perf. Part: Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS | HSPA_LTE_measRP_MIMO-Perf | 2 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-120368 | RP-131507 | Vodafone | luis.anaya@vodafone.com | RP#62 completed. Rx diversity (defined as Rel-6 HSDPA RAN4 enhanced type 1 req.) & MIMO (defined as Rel-7 HSDPA MIMO for HSPA). Rx diversity & MIMO (defined as part of Rel-8 basic LTE WI) | new TR 37.977
567 | 570021 | Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3) | EHNB_enh3 | 1 | Rel-12 | R3,R2 | 2012-09-12 08:00 | 2013-12-06 17:00 | 100% | RP-130741 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Triggered by FS_EHNB_enh (TR 37.803) | UTRA, LTE | HNB
568 | 570121 | Core part: Further enhancements to H(e)NB mobility - Part 3 | EHNB_enh3-Core | 2 | Rel-12 | R3,R2 | 2012-09-12 08:00 | 2013-12-06 17:00 | 100% | RP-130741 | RP-131508 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 completed | 25.304, 25.331, 25.367, 25.467, 25.469, 36.300, 36.331 | HNB
569 | 580037 | LTE UE Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS | 1 | Rel-12 | R4,R5 | 2013-03-15 08:00 | 2015-06-12 17:00 | 16% | RP-130703 | - | Nokia | petri.j.vasenkari@nokia.com | Triggered by Rel-11 TR 37.902 Study on Measurements of radio performances for LTE terminals - TRP and TRS test methodology (FS_LTE_OTA) UID_550022 | UTRA, LTE
570 | 580137 | Core part: LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS-Core | 2 | Rel-12 | R4 | 2013-03-15 08:00 | 2014-09-12 17:00 | 25% | RP-130703 | RP-140785 | Nokia | petri.j.vasenkari@nokia.com | RP#64 completion 06/14=>09/14 | 25.144, New (TS 37.144, TR 37.844)
571 | 630011 | Test part: LTE UE TRP and TRS and UTRA Hand Phantom | LTE_UTRA_TRP_TRS-UEConTest | 2 | Rel-12 | R5 | 2014-03-06 08:00 | 2015-06-12 17:00 | 5% | RP-140090 | RP-140595 | ZTE | TAYLOR Carolyn (carolyn.tayl@zte.com.cn) | - | New TS 37.544
572 | 590019 | Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE | LCS_BDS | 1 | Rel-12 | R2,R3,R4,R5 | 2013-03-04 08:00 | 2015-06-12 17:00 | 81% | RP-130416 | - | CATR | Ying Du (duying1@catr.cn) | BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2 | UTRA, LTE
573 | 590119 | Core part: Support for BeiDou Navigation Satellite System (BDS) for UTRA | LCS_BDS-UTRA-Core | 2 | Rel-12 | R2,R3 | 2013-06-02 08:00 | 2014-03-06 17:00 | 100% | RP-130416 | RP-131500 | ZTE | Huang He (huang.he4@zte.com.cn) | RP#62 completed | 25.305, 25.306, 25.331, 25.453, 25.413, 25.423, 25.433
574 | 590219 | Perf. part: Support for BeiDou Navigation Satellite System (BDS) for UTRA | LCS_BDS-UTRA-Perf | 2 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-06-13 17:00 | 100% | RP-130416 | RP-140714 | ZTE | Ling Soonleh (soonleh.ling@zte.com.cn) | RP#64 completed. TS 25.173v100 for 1-step Approval | 25.172 (FDD), new TS 25.173 (TDD)
575 | 590319 | Core part: Support for BeiDou Navigation Satellite System (BDS) for LTE | LCS_BDS-LTE-Core | 2 | Rel-12 | R2 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130416 | RP-131525 | CATR | Ying Du (duying1@catr.cn) | RP#62 completed | 36.305, 36.355
576 | 590419 | Perf. part: Support for BeiDou Navigation Satellite System (BDS) for LTE | LCS_BDS-LTE-Perf | 2 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-06-13 17:00 | 100% | RP-130416 | RP-140713 | ZTE | Ling Soonleh (soonleh.ling@zte.com.cn) | RP#64 completed | 36.171
577 | 640013 | Test part: BeiDou Navigation Satellite System (BDS) Positioning Support for LTE and UMTS | LCS_BDS-UEConTest | 2 | Rel-12 | R5 | 2014-06-13 08:00 | 2015-06-12 17:00 | 0% | RP-140730 | - | CATT | Chen Xiaiozhong (chenxiaozhong@catt.cn) | - | 34.108, 36.508, 37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5
578 | 620011 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 1 | Rel-12 | G2,G1,G3new | 2013-11-22 08:00 | 2014-11-21 17:00 | 59% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#61 updated WID GP-131122=>GP-140211. GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001 | GERAN
579 | 620111 | GERAN2 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | - | 2 | Rel-12 | G2 | 2013-11-22 08:00 | 2014-08-29 17:00 | 80% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#62 completion 05/14=>08/14 | 44.031, 49.031, 44.071, 48.031
580 | 620211 | GERAN1 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | - | 2 | Rel-12 | G1 | 2013-11-22 08:00 | 2014-08-29 17:00 | 80% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | - | 43.059, 45.005
581 | 630009 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new | LCS_BDS_GERAN-GERAN3new | 2 | Rel-12 | G3new | 2014-02-28 08:00 | 2014-11-21 17:00 | 0% | GP-140244 |  | CATR | Zhou DaiWei, China Academy of Telecommunication Research, zhoudaiwei@catr.cn | - | 51010-1, 51.010-2, 51.010-7
582 | 620311 | Deleted - Test part: Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN-MStest | 2 | Rel-12 | G3new | 2013-11-22 08:00 | 2014-02-28 17:00 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#61 stopped | 51.010-1
583 | 590030 | Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA | 1 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-05 17:00 | 43% | RP-130373 | - | Huawei | ronnie.zhang@huawei.com | Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA) | UTRA, LTE, GERAN
584 | 590130 | Core part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Core | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 70% | RP-130373 | RP-140638 | Huawei | ronnie.zhang@huawei.com | RP#64 completion 06/14=>09/14 | New TS 37.142 (AAS BS Tx & Rx), New TR 37.842
585 | 590230 | Perf. part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Perf | 2 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-12-05 17:00 | 20% | RP-130373 | RP-140638 | Huawei | ronnie.zhang@huawei.com | - | New TS 37.1xy (AAS BS conformance testing)
586 | 600019 | Deleted - New Base Station specification structure | BSspec_struc | 1 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130851 | - | Ericsson | johan.skold@ericsson.com | Triggered by Rel-12 TR 37.810 Study on Base Station specification structure (FS_BSspec_struc) | UTRA, LTE, MSR
587 | 600119 | Deleted - Core part: New Base Station specification structure | BSspec_struc-Core | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130851 | RP-131513 | Ericsson | johan.skold@ericsson.com | RP#62 stopped (at 20% completion) | 25.104, 25.105, 36.104, 37.104, 37.810, New TR 37.811 (New BS specification structure), New TS 37.xya (New RF core specification)
588 | 600219 | Deleted - Perf. part: New Base Station specification structure | BSspec_struc-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2013-12-06 17:00 | 100% | RP-130851 | RP-131514 | Ericsson | johan.skold@ericsson.com | RP#62 stopped (at 0% completion) | 25.113, 25.141, 25.142, 36.113, 36.141, 37.113, 37.141, 37.810, New TS 37.xyz (New RF test specification, New TS 37.xyw (ew EMC specification)
589 | 600021 | L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL | 1 | Rel-12 | R4,R2,R3 | 2013-06-17 08:00 | 2014-06-13 17:00 | 100% | RP-140092 | - | Orange | olfa.benhaddada@orange.com | ECC(12)052 CEPT decision to harmonize 1452-1492 MHz (L-band) for mobile communications Supplemental Downlink (SDL) => standardize L-band and corresponding E-UTRA and UTRA requirements for SDL operation in Region 1 | UTRA, LTE
590 | 600121 | Core part: L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-Core | 2 | Rel-12 | R4,R2,R3 | 2014-02-13 14:20 | 2014-06-13 17:00 | 100% | RP-140092 | RP-140633 | Orange | olfa.benhaddada@orange.com | RP#64 completed | 25.101, 25.104, 25.113, 25.133, 25.307, 25.327, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, 37.104, 37.113
591 | 600221 | Perf. part: L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-Perf | 2 | Rel-12 | R4 | 2013-06-17 08:00 | 2014-06-13 17:00 | 100% | RP-140092 | RP-140633 | Orange | olfa.benhaddada@orange.com | RP#64 completed | 25.133, 25.141, 25.307, 25.327, 36.133, 36.141, 36.307, 37.141
592 | 600027 | LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON | 1 | Rel-12 | R3,S2,C4,G2 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-130831 | - | China Telecom | Jinlian_wu@189.cn | Triggered by Rel-12 TR 37.813 (FS_LTE_HRPD_SON). SA2 should verify the architecture solution in TR 37.813 for inter-RAT load balancing between LTE-HRPD. CT4 should specify the RIM extension to support the feature. | UTRA, LTE | SON
593 | 610103 | Stage 2 for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | - | 2 | Rel-12 | S2 | 2013-09-11 08:00 | 2013-12-11 17:00 | 100% | - | - | Huawei | Huan Li (ivy.lihuan@huawei.com) | SP#62 completed | 23.402
594 | 600127 | Core part: LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON-Core | 2 | Rel-12 | R3 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-130831 | RP-140745 | China Telecom | Jinlian_wu@189.cn | RP#64 completed | 36.300, 36.413
595 | 610003 | CT aspects for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON (Stage 3) | LTE_HRPD_SON-CT | 2 | Rel-12 | C4 | 2013-09-04 08:00 | 2013-09-06 17:00 | 100% | CP-130434 | - | Huawei | Xiaoyan SHI (sean.shixiaoyan@huawei.com | CP#61 WID approved & Completed | 29.274, 29.276, 29.280
596 | 610015 | GERAN aspects for LTE-HRPD inter-RAT SON, RAN Information Management (RIM) - Stage 3 | LTE_HRPD_SON-RIM | 2 | Rel-12 | G2 | 2013-08-26 08:00 | 2013-08-30 17:00 | 100% | GP-130817 | - | Alcatel-Lucent | marguerite.woch@alcatel-lucent.com | GP#59 WID approved & Completed | 48.018
597 | 620042 | Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon | 1 | Rel-12 | R4,R3 | 2013-12-09 08:00 | 2015-03-13 17:00 | 20% | RP-132061 | - | Ericsson | christopher.callender@ericsson.com | - | UTRA, LTE
598 | 620142 | Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Core | 2 | Rel-12 | R4,R3 | 2014-01-06 11:12 | 2014-09-12 17:00 | 70% | RP-132061 | RP-140649 | Ericsson | christopher.callender@ericsson.com | RP#64 completion 06/14=>09/14 | 25.133, 25.331, 36.133
599 | 620242 | Perf. part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2015-03-13 17:00 | 0% | RP-132061 | RP-140649 | Ericsson | christopher.callender@ericsson.com | - | 25.133, 36.133
600 | 620048 | WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2,S2,C1 | 2013-12-06 08:00 | 2014-09-17 17:00 | 70% | RP-140981 | - | Intel | sasha.sirotkin@intel.com | Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw) | UTRA, LTE | WLAN
601 | 620148 | Core part: WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-Core | 2 | Rel-12 | R2 | 2013-12-06 08:00 | 2014-09-12 17:00 | 80% | RP-140981 | RP-14101 | Intel | sasha.sirotkin@intel.com | RP#64 updateed WID RP-132101=>RP-140981 | 25.304, 25.306, 25.331, 36.304, 36.306, 36.331 | WLAN
602 | 630013 | SA2 aspects of WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-SA2 | 2 | Rel-12 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 90% | SP-140169 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#64 completion 06/14=>09/14. Exception in SP-140172 completed | 23.402, 23.401, 23.060, 23.251 | WLAN
603 | 640006 | CT aspects of WLAN/3GPP Radio Interworking (Stage 3) | UTRA_LTE_WLAN_interw-CT | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | CP-140287 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | - | 24.008, 24.301, 24.302, 24.312 | WLAN
604 | 551000 | Rel-12 LTE Carrier Aggregation | LTE_CA_Rel-12 | 1 | Rel-12 | R4 | 2011-09-19 08:00 | 2015-03-13 17:00 | 72% | - | - | - | - | LTE_CA_Rel-12 | LTE | CA
605 | 530025 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7 | LTE_CA_B1_B7 | 2 | Rel-12 | R4 | 2011-09-19 08:00 | 2014-09-12 17:00 | 40% | RP-132042 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band CA 2DL | LTE | CA
606 | 530125 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7 | LTE_CA_B1_B7-Core | 3 | Rel-12 | R4 | 2011-09-19 08:00 | 2014-09-12 17:00 | 80% | RP-132042 | RP-140569 | Ericsson | christian.bergljung@ericsson.com | RP#64 completion 06/14=>09/14 | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
607 | 530225 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7 | LTE_CA_B1_B7-Perf | 3 | Rel-12 | R4 | 2011-09-30 08:00 | 2014-09-12 17:00 | 0% | RP-132042 | RP-140569 | Ericsson | christian.bergljung@ericsson.com | RP#64 completion 06/14=>09/14 | 36.141, 36.307 | CA
608 | 530029 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25 | 2 | Rel-12 | R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-130179 | - | Sprint | George.Cummings@sprint.com | Intra-band NC | LTE | CA
609 | 530129 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25-Core | 3 | Rel-12 | R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-130179 | RP-130563 | Sprint | George.Cummings@sprint.com | RP#60 completed. TR 36.841 for 1-step Approval | 36.101, 36.104, 36.133, new TR 36.833-2-25 | CA
610 | 530229 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25-Perf | 3 | Rel-12 | R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-130179 | RP-130759 | Sprint | George.Cummings@sprint.com | RP#60 completed | 36.141, 36.307 | CA
611 | 550010 | Deleted - LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL | 2 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-03-01 17:00 | 100% | RP-120867 | - | SK Telecom | Seungpyo Hong | Inter-band 2UL | LTE | CA
612 | 550110 | Deleted - Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL-Core | 3 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-03-01 17:00 | 100% | RP-120867 | RP-130098 | SK Telecom | Seungpyo Hong | RP#59 stopped (covered by new WI LTE_CA_2UL-A4) | 36.101, 36.104, 36.133, 36.307, new generic TR 36.851 | CA
613 | 550210 | Deleted - Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL-Perf | 3 | Rel-12 | R4 | 2012-03-12 08:00 | 2013-03-01 17:00 | 100% | RP-120867 | RP-130099 | SK Telecom | Seungpyo Hong | RP#59 stopped (covered by new WI LTE_CA_2UL-A4) | 36.133, 36.141 | CA
614 | 550011 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3 | LTE_CA_NC_B3 | 2 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-131359 | - | SK Telecom | haesung.park@sk.com | Intra-band NC | LTE | CA
615 | 550111 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3 | LTE_CA_NC_B3-Core | 3 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-131359 | RP-131573 | SK Telecom | haesung.park@sk.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-2-03 | CA
616 | 550211 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3 | LTE_CA_NC_B3-Perf | 3 | Rel-12 | R4 | 2012-03-15 08:00 | 2013-12-06 17:00 | 100% | RP-131359 | RP-131574 | SK Telecom | haesung.park@sk.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
617 | 560015 | Deleted - LTE Advanced intra-band contiguous Carrier Aggregation in Band 1 | LTE_CA_C_B1 | 2 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-130298 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Intra-band C | LTE | CA
618 | 560115 | Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1 | LTE_CA_C_B1-Core | 3 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-120826 | RP-130549 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#60 stopped at 10% completion (rationale in RP-130670) | 36.101, 36.104, 36.133, 36.141, 36.307, new TR 36.835 | CA
619 | 560215 | Deleted - Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1 | LTE_CA_C_B1-Perf | 3 | Rel-12 | R4 | 2012-06-22 08:00 | 2013-06-14 17:00 | 100% | RP-120826 | RP-130550 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#60 stopped at 0% completion | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
620 | 560016 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4 | 2 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-131135 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Intra-band NC | LTE | CA
621 | 560116 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4-Core | 3 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-131135 | RP-131039 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed. Updated WID RP-130842=>RP-131135 | 36.101, 36.104, 36.133, new TR 36.833-2-04 | CA
622 | 560216 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4-Perf | 3 | Rel-12 | R4 | 2012-06-22 08:00 | 2013-09-06 17:00 | 100% | RP-131135 | RP-131040 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed. Updated WID RP-130842=>RP-131135 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
623 | 560017 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4 | 2 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130175 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band 1 UL | LTE | CA
624 | 560117 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4-Core | 3 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130175 | RP-131007 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
625 | 560217 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4-Perf | 3 | Rel-12 | R4 | 2012-06-22 08:00 | 2013-09-06 17:00 | 100% | RP-130175 | RP-131376 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
626 | 570012 | LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29 | LTE_CA_B23_B29 | 2 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130170 | - | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | Inter-band 1 UL | LTE | CA
627 | 570112 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29 | LTE_CA_B23_B29-Core | 3 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130170 | RP-130535 | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
628 | 570212 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29 | LTE_CA_B23_B29-Perf | 3 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130170 | RP-130536 | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#60 completed | 36.141, 36.307 | CA
629 | 570013 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26 | LTE_CA_B3_B26 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130658 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band 1 UL | LTE | CA
630 | 570113 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26 | LTE_CA_B3_B26-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130658 | RP-130527 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#60 completed. Updated WID RP-130199=>RP-130658 | 36.101, 36.104, 36.133, 36.307, new generic TR 36.851 | CA
631 | 570213 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26 | LTE_CA_B3_B26-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130658 | RP-130528 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#60 completed. Updated WID RP-130199=>RP-130658 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
632 | 570014 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19 | LTE_CA_B3_B19 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130198 | - | NTT DOCOMO | Kei ANDO | Inter-band 1 UL | LTE | CA
633 | 570114 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19 | LTE_CA_B3_B19-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130198 | RP-130525 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
634 | 570214 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19 | LTE_CA_B3_B19-Perf | 3 | Rel-12 | R4 | 2012-09-13 08:00 | 2013-06-14 17:00 | 100% | RP-130198 | RP-130526 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.141, 36.307 | CA
635 | 570015 | Deleted - LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 | LTE_CA_B38_B39 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121178 | - | China Mobile | Pan Qun (panqun@chinamobile.com) | Inter-band 1 UL | LTE | CA
636 | 570115 | Deleted - Core part: LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 | LTE_CA_B38_B39-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121178 | RP-121624 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#58 stopped at 10% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41) | 36.101, 36.104, 36.307, new generic TR 36.851 | CA
637 | 570215 | Deleted - Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 | LTE_CA_B38_B39-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121178 | RP-121625 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#58 stopped at 0% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41) | 36.133, 36.141 | CA
638 | 570016 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 3 | LTE_CA_C_B3 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-131184 | - | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | Intra-band NC | LTE | CA
639 | 570116 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3 | LTE_CA_C_B3-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-131184 | RP-131029 | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | RP#61 completed. Updated WID RP-130294=>RP-131184 (impacted specs) | 36.101, 36.104, 36.133, new TR 36.833-1-03 | CA
640 | 570216 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3 | LTE_CA_C_B3-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-131184 | RP-131030 | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | RP#61 completed | 36.141, 36.307 | CA
641 | 570018 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8 | LTE_CA_B1_B8 | 2 | Rel-12 | R4 | 2012-02-02 09:36 | 2013-06-14 17:00 | 100% | RP-130181 | - | Softbank Mobile | Kenichi Kihara | Inter-band 1 UL | LTE | CA
642 | 570118 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8 | LTE_CA_B1_B8-Core | 3 | Rel-12 | R4 | 2012-02-02 09:36 | 2013-06-14 17:00 | 100% | RP-130181 | RP-130515 | Softbank Mobile | Kenichi Kihara | RP#60 completed | 36.101, 36.104, new generic TR 36.851 | CA
643 | 570218 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8 | LTE_CA_B1_B8-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130181 | RP-130516 | Softbank Mobile | Kenichi Kihara | RP#60 completed | 36.141, 36.307 | CA
644 | 570026 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28 | LTE_CA_B3_B28 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130189 | - | eAccess | FukumotoShiro@eaccess.net | Inter-band 1 UL | LTE | CA
645 | 570126 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28 | LTE_CA_B3_B28-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130189 | RP-130529 | eAccess | FukumotoShiro@eaccess.net | RP#60 completed | 36.101, 36.104, new generic TR 36.851 | CA
646 | 570226 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28 | LTE_CA_B3_B28-Perf | 3 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130189 | RP-130530 | eAccess | FukumotoShiro@eaccess.net | RP#60 completed | 36.141, 36.307 | CA
647 | 580032 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26 | LTE_CA_B1_B26 | 2 | Rel-12 | R4 | 2012-12-07 08:00 | 2013-09-06 17:00 | 100% | RP-130668 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band 1UL/2DL | LTE | CA
648 | 580132 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26 | LTE_CA_B1_B26-Core | 3 | Rel-12 | R4 | 2012-12-07 08:00 | 2013-09-06 17:00 | 100% | RP-130668 | RP-131005 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
649 | 580232 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26 | LTE_CA_B1_B26-Perf | 3 | Rel-12 | R4 | 2012-12-07 08:00 | 2013-09-06 17:00 | 100% | RP-130668 | RP-131006 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.141, 36.307 | CA
650 | 580033 | LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41 | LTE_CA_B39_B41 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-03-06 17:00 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | Inter-band 2DL | LTE | CA
651 | 580133 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41 | LTE_CA_B39_B41-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-03-06 17:00 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#63 completed. Replaces the Stopped WI - LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 (LTE_CA_B38_B39) UID_570015 | 36.101, 36.104, 36.307, new generic TR 36.851 | CA
652 | 580233 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41 | LTE_CA_B39_B41-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2014-03-06 17:00 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#63 completed | 36.133, 36.141 | CA
653 | 580034 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-09-12 17:00 | 97% | RP-140474 | - | US Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 2DL | LTE | CA
654 | 580134 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-09-12 17:00 | 95% | RP-140474 | RP-140569 | US Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131665=>RP-140474 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.851 | CA
655 | 580234 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2014-03-06 17:00 | 100% | RP-140474 | RP-140428 | US Cellular | sebastian.thalanany@uscellular.com | RP#63 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
656 | 580035 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130813 | - | Ericsson | christian.bergljung@ericsson.com | Intra-band NC | LTE | CA
657 | 580135 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130813 | RP-131575 | Ericsson | christian.bergljung@ericsson.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-2-07 | CA
658 | 580235 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2013-12-06 17:00 | 100% | RP-130813 | RP-131576 | Ericsson | christian.bergljung@ericsson.com | RP#62 completed | 36.141, 36.307 | CA
659 | 580036 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 27 | LTE_CA_C_B27 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-131679 | - | NII Holdings | bill.shvodian@nii.com | Intra-band contig. CA 2DL/1UL | LTE | CA
660 | 580136 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27 | LTE_CA_C_B27-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-131679 | RP-131567 | NII Holdings | bill.shvodian@nii.com | RP#62 completed | 36.101, 36.104, new TR 36.833-1-27 | CA
661 | 580236 | Perf part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27 | LTE_CA_C_B27-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2014-06-13 17:00 | 100% | RP-131679 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed. TR 36.833-1-27v200 for Approval | 36.101, 36.133, 36.141, 36.307, new TR 36.833-1-27 | CA
662 | 590022 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13 | LTE_CA_B2_B13 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130196 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band 1 UL | LTE | CA
663 | 590122 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13 | LTE_CA_B2_B13-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130196 | RP-130523 | Ericsson | christian.bergljung@ericsson.com | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
664 | 590222 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13 | LTE_CA_B2_B13-Perf | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130196 | RP-130524 | Ericsson | christian.bergljung@ericsson.com | RP#60 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
665 | 590024 | LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21 | LTE_CA_B19_B21 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130197 | - | NTT DOCOMO | Kei ANDO | Inter-band 1 UL | LTE | CA
666 | 590124 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21 | LTE_CA_B19_B21-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130197 | RP-130533 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
667 | 590224 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21 | LTE_CA_B19_B21-Perf | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130197 | RP-130534 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.141, 36.307 | CA
668 | 590025 | Deleted - LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26 | LTE_CA_B8_B26 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130201 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band 1 UL | LTE | CA
669 | 590125 | Deleted - Core part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26 | LTE_CA_B8_B26-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130201 | RP-131549 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#62 stopped (at 20%) | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
670 | 590225 | Deleted - Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26 | LTE_CA_B8_B26-Perf | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130201 | RP-131550 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#62 stopped (at 20%) | 36.141, 36.307 | CA
671 | 590029 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 35% | RP-140475 | - | Huawei | Liu Ye (leo.liuye@huawei.com) | Inter-band CA 2UL | LTE | CA
672 | 590129 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 70% | RP-140475 | RP-140569 | Huawei | Liu Ye (leo.liuye@huawei.com) | Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need | 36.101, 36.104, New generic TR 36.860 | CA
673 | 590229 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1-Perf | 3 | Rel-12 | R4 | 2013-03-08 08:00 | 2014-09-12 17:00 | 0% | RP-140475 | RP-140569 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#63 updated WID RP-131713=>RP-140475 (impacted specs). Class A1: Low-high band combination without harmonic relation between bands or intermodulation problem | 36.133 | CA
674 | 590028 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 35% | RP-130327 | - | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | Inter-band CA 2UL | LTE | CA
675 | 590128 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 70% | RP-130327 | RP-140569 | Qualcomm | Gene Fong | Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need | 36.101, 36.104, 36.133, New generic TR 36.860 | CA
676 | 590228 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2-Perf | 3 | Rel-12 | R4 | 2013-03-08 08:00 | 2014-09-12 17:00 | 0% | RP-130327 | RP-140569 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | Class A2: Low-high band combination with harmonic relation between bands | 36.141, 36.307 | CA
677 | 590023 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 27% | RP-140853 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band CA 2UL | LTE | CA
678 | 590123 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 55% | RP-140853 | RP-140569 | Ericsson | christian.bergljung@ericsson.com | RP#64 WID RP-130309=>RP-140853. Current CA (generic&band-specific) for inter-band CA with 1UL CC&2 DL CCs. Work need on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need | 36.101, 36.104, 36.133, New generic TR 36.860 | CA
679 | 590223 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3-Perf | 3 | Rel-12 | R4 | 2013-03-08 08:00 | 2014-09-12 17:00 | 0% | RP-140853 | RP-140569 | Ericsson | christian.bergljung@ericsson.com | Class A3: Low-low or high-high band combination without intermodulation problem (low order IM) | 36.141, 36.307 | CA
680 | 590031 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 33% | RP-140476 | - | Nokia | petri.j.vasenkari@nokia.com | Inter-band CA 2UL | LTE | CA
681 | 590131 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 65% | RP-140476 | RP-140569 | Nokia | petri.j.vasenkari@nokia.com | Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need | 36.101, 36.104, 36.133, New generic TR 36.860 | CA
682 | 590231 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4-Perf | 3 | Rel-12 | R4 | 2013-03-08 08:00 | 2014-09-12 17:00 | 0% | RP-140476 | RP-140569 | Nokia | petri.j.vasenkari@nokia.com | RP#63 updated WID RP-131660=>RP-140476. Class A4: Low-low, low-high or high-high band combination with intermodulation problem (low order IM) | 36.141, 36.307 | CA
683 | 590026 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 35% | RP-131146 | - | Renesas | Antti Immonen | Inter-band CA 2UL | LTE | CA
684 | 590126 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-09-12 17:00 | 70% | RP-131146 | RP-140569 | Renesas | Antti Immonen | Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need | 36.101, 36.104, 36.133, New generic TR 36.860 | CA
685 | 590226 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5-Perf | 3 | Rel-12 | R4 | 2013-03-08 08:00 | 2014-09-12 17:00 | 0% | RP-131146 | RP-140569 | Renesas | Antti Immonen | RP#61 updated WID RP-130289=>RP-131146 (added B19+B21). Class A5: Combinations not classified in A1-A4 | 36.141, 36.307 | CA
686 | 590027 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 39 | LTE_CA_C_B39 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-131171 | - | China Mobile | Li Nan (linan@chinamobile.com) | Intra-band C 2DL/2UL | LTE | CA
687 | 590127 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39 | LTE_CA_C_B39-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-131171 | RP-140428 | China Mobile | Li Nan (linan@chinamobile.com) | RP#63 completed | 36.101, 36.104, 36.133, New TR 36.833-1-39 [instead of 36.845] | CA
688 | 590227 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39 | LTE_CA_C_B39-Perf | 3 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-03-06 17:00 | 100% | RP-131171 | RP-140428 | China Mobile | Li Nan (linan@chinamobile.com) | RP#63 completed | 36.141, 36.307 | CA
689 | 600022 | LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL | LTE_CA_NC_2UL | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 90% | RP-140267 | - | Nokia | petri.j.vasenkari@nokia.com | Intra-band non-contig. CA 2DL | LTE | CA
690 | 600122 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL | LTE_CA_NC_2UL-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 90% | RP-140267 | RP-140569 | Nokia | petri.j.vasenkari@nokia.com | RP#63 updated WID RP-131659=>RP-140267 | 36.101, 36.104, 36.133, 36.306, 36.331, New TR 36.833-4 | CA
691 | 600023 | Deleted - LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL | LTE_CA_NC_B41_2UL | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-03-06 17:00 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | Intra-band NC 2UL | LTE | CA
692 | 600123 | Deleted - Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL | LTE_CA_NC_B41_2UL-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-03-06 17:00 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | RP#63 stopped (5% complete). Reason: Market conditions have eliminated the need for this feature, at least for the foreseeable future | 36.101, 36.104, 36.133, new TR 36.833-3-41 | CA
693 | 600223 | Deleted - Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL | LTE_CA_NC_B41_2UL-Perf | 3 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-03-06 17:00 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | RP#63 stopped (0% complete). | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
694 | 600024 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 45% | RP-131136 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Intra-band non-contig. CA 2DL | LTE | CA
695 | 600124 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 90% | RP-131136 | RP-140569 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 updated WID RP-130602=>RP-131136. Separated from UID_560016 LTE_CA_NC_B4 which remained 1UL-only | 36.101, 36.104, 36.133, new TR 36.833-4-04 | CA
696 | 600224 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Perf | 3 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-09-12 17:00 | 0% | RP-131136 | RP-140569 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 updated WID RP-130602=>RP-131136 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
697 | 600025 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 23 | LTE_CA_C_B23 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131265 | - | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | Intra-band C CA | LTE | CA
698 | 600125 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 23 | LTE_CA_C_B23-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131265 | RP-131565 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-1-23 [instead of 36.864] | CA
699 | 600225 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 23 | LTE_CA_C_B23-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131265 | RP-131566 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.141, 36.307 | CA
700 | 600026 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23 | LTE_CA_NC_B23 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-131700 | - | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | Intra-band non-contig. CA 2DL | LTE | CA
701 | 600126 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23 | LTE_CA_NC_B23-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131700 | RP-131577 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-2-23 | CA
702 | 600226 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23 | LTE_CA_NC_B23-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-131700 | RP-140569 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#64 completed. TR 36.833-2-23v200 for Approval | 36.101, 36.133, 36.141, 36.307, new TR 36.833-2-23 | CA
703 | 600028 | LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25 | LTE_CA_B12_B25 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131159 | - | US Cellular | sebastian.thalanany@uscellular.com | Inter-band 1UL/2DL | LTE | CA
704 | 600128 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25 | LTE_CA_B12_B25-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131159 | RP-131705 | US Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
705 | 600228 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25 | LTE_CA_B12_B25-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2013-12-06 17:00 | 100% | RP-131159 | RP-131706 | US Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.141, 36.307 | CA
706 | 600029 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130669 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band 1UL/2DL | LTE | CA
707 | 600129 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130669 | RP-131003 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.101, new generic TR 36.851 | CA
708 | 600229 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130669 | RP-131004 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.307 | CA
709 | 600030 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130675 | - | AT&T | marc.grant@att.com | Inter-band 2DL | LTE | CA
710 | 600130 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130675 | RP-131009 | AT&T | marc.grant@att.com | RP#61 completed | 36.101, 36.104, 36.307 | CA
711 | 600230 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130675 | RP-131010 | AT&T | marc.grant@att.com | RP#61 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
712 | 600031 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 95% | RP-131696 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | CA
713 | 600131 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 95% | RP-131696 | RP-140569 | AT&T | marc.grant@att.com | RP#64 completion 06/14=>09/14. TR 36.853v100 for Information | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
714 | 600231 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 95% | RP-131696 | RP-140569 | AT&T | marc.grant@att.com | RP#64 completion 06/14=>09/14 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
715 | 600032 | Deleted - LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131130 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | CA
716 | 600132 | Deleted - Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131130 | RP-131590 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131652 discussion | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
717 | 600232 | Deleted - Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2013-12-06 17:00 | 100% | RP-131130 | RP-131591 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131652 discussion | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
718 | 600033 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30 | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 21% | RP-131697 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | CA
719 | 600133 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-06-13 17:00 | 40% | RP-131697 | RP-140569 | AT&T | marc.grant@att.com | RP#62 updated WID RP-131131=>RP-131697 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
720 | 600233 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 5% | RP-131697 | RP-140569 | AT&T | marc.grant@att.com | RP#62 updated WID RP-131131=>RP-131697 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
721 | 600034 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131698 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | CA
722 | 600134 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131698 | RP-140569 | AT&T | marc.grant@att.com | RP#61 updated WID RP-130885=>RP#62 updated WID RP-131132=>RP-131698 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
723 | 600234 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 95% | RP-131698 | RP-140569 | AT&T | marc.grant@att.com | RP#62 updated WID RP-131132=>RP-131698 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
724 | 600035 | Deleted - LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131133 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | CA
725 | 600135 | Deleted - Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131133 | RP-131598 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131653 discussion | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
726 | 600235 | Deleted - Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2013-12-06 17:00 | 100% | RP-131133 | RP-131599 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131653 discussion | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
727 | 600036 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131699 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | CA
728 | 600136 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131699 | RP-140569 | AT&T | marc.grant@att.com | RP#61 updated WID RP-130887=>RP#62 updated WID RP-131134=>RP-131699 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
729 | 600236 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 95% | RP-131699 | RP-140569 | AT&T | marc.grant@att.com | RP#62 updated WID RP-131134=>RP-131699 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
730 | 600037 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131684 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | CA
731 | 600137 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131684 | RP-140569 | Verizon | zheng.zhao@verizonwireless.com | RP#62 updated WID RP-131228=>RP-131684 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
732 | 600237 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 95% | RP-131684 | RP-140569 | Verizon | zheng.zhao@verizonwireless.com | RP#62 updated WID RP-131228=>RP-131684 | 36.101, 36.133, 36.141, 36.307 | CA
733 | 600038 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 95% | RP-131682 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | CA
734 | 600138 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 95% | RP-131682 | RP-140569 | Verizon | zheng.zhao@verizonwireless.com | RP#62 updated WID RP-131227=>RP-131682 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
735 | 600238 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 95% | RP-131682 | RP-140569 | Verizon | zheng.zhao@verizonwireless.com | RP#62 updated WID RP-131227=>RP-131682 | 36.101, 36.133, 36.141, 36.307 | CA
736 | 600039 | LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131683 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | CA
737 | 600139 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131683 | RP-140569 | Verizon | zheng.zhao@verizonwireless.com | RP#62 updated WID RP-131229=>RP-131683 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
738 | 600239 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13-Perf | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 95% | RP-131683 | RP-140569 | Verizon | zheng.zhao@verizonwireless.com | RP#62 updated WID RP-131229=>RP-131683 | 36.101, 36.133, 36.141, 36.307 | CA
739 | 610017 | LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28 | LTE_CA_B7_B28 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131307 | - | Huawei | Liehai Liu (liuliehai@huawei.com) | Inter-band 1UL/2DL | LTE | CA
740 | 610117 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28 | LTE_CA_B7_B28-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131307 | RP-131545 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#62 completed | 36.101, 36.104, 36.307 | CA
741 | 610217 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28 | LTE_CA_B7_B28-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131307 | RP-131546 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#62 completed | 36.141 | CA
742 | 610018 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25 | LTE_CA_B5_B25 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131343 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band 1UL/2DL | LTE | CA
743 | 610118 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25 | LTE_CA_B5_B25-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131343 | RP-131543 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
744 | 610218 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25 | LTE_CA_B5_B25-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131343 | RP-131705 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.141, 36.307 | CA
745 | 610019 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11 | LTE_CA_B1_B11 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131354 | - | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | Inter-band CA 2DL | LTE | CA
746 | 610119 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11 | LTE_CA_B1_B11-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131354 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#64 completed | 36.101, 36.104, new generic TR 36.851 | CA
747 | 610219 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11 | LTE_CA_B1_B11-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131354 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#64 completed | 36.141, 36.307 | CA
748 | 610020 | LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11 | LTE_CA_B8_B11 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 60% | RP-131355 | - | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | Inter-band CA 2DL | LTE | CA
749 | 610120 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11 | LTE_CA_B8_B11-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 60% | RP-131355 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | - | 36.101, 36.104, new generic TR 36.851 | CA
750 | 610220 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11 | LTE_CA_B8_B11-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 60% | RP-131355 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | - | 36.141, 36.307 | CA
751 | 610021 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-02 17:00 | 100% | RP-131365 | - | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | Inter-band 1UL/2DL | LTE | CA
752 | 610121 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-02 17:00 | 100% | RP-131365 | RP-131541 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#62 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
753 | 610221 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-02 17:00 | 100% | RP-131365 | RP-131542 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#62 completed | 36.141, 36.307 | CA
754 | 610022 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 63% | RP-140100 | - | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | Intra-band contig. CA 3DL | LTE | CA
755 | 610122 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 95% | RP-140100 | RP-140569 | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#63 updated WID RP-131695=>RP-140100 | 36.101, 36.104, 36.133, 36.307, New TR 36.833-5-41 | CA
756 | 610222 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 30% | RP-140100 | RP-140569 | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#63 updated WID RP-131695=>RP-140100 | 36.141 | CA
757 | 610023 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2 | LTE_CA_NC_B2 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131366 | - | Ericsson | imadur.rahman@ericsson.com | Intra-band non-contig. CA 2DL | LTE | CA
758 | 610123 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2 | LTE_CA_NC_B2-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131366 | RP-140569 | Ericsson | imadur.rahman@ericsson.com | RP#64 completed. TR 36.833-2-02v100 for 1-step Approval | 36.101, 36.104, 36.133, New TR 36.833-2-02 | CA
759 | 610223 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2 | LTE_CA_NC_B2-Perf | 3 | Rel-12 | R4 | 2013-09-10 08:00 | 2014-06-13 17:00 | 100% | RP-131366 | RP-140569 | Ericsson | imadur.rahman@ericsson.com | RP#64 completed | 36.141, 36.307 | CA
760 | 620018 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3 | LTE_CA_B1_B3 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 30% | RP-132022 | - | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | Inter-band CA 2DL | LTE | CA
761 | 620118 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3 | LTE_CA_B1_B3-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 30% | RP-132022 | RP-140569 | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | - | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
762 | 620218 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3 | LTE_CA_B1_B3-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 30% | RP-132022 | RP-140569 | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | - | 36.141, 36.307 | CA
763 | 620019 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 15% | RP-132028 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 2DL | LTE | CA
764 | 620119 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 30% | RP-132028 | RP-140569 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.101, 36.104, 36.133, 36.307, new generic TR 36.851 | CA
765 | 620219 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | RP-132028 | RP-140569 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.133, 36.141 | CA
766 | 620020 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band 2DL | LTE | CA
767 | 620120 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#63 completed | 36.101, new generic TR 36.851 | CA
768 | 620220 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#63 completed | 36.307 | CA
769 | 620021 | LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27 | LTE_CA_B4_B27 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140142 | - | NII Holdings | bill.shvodian@nii.com | Inter-band CA 2DL | LTE | CA
770 | 620121 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27 | LTE_CA_B4_B27-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140142 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | CA
771 | 620221 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27 | LTE_CA_B4_B27-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140142 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed | 36.141, 36.307 | CA
772 | 620022 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27 | LTE_CA_B3_B27 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 2DL/1UL | LTE | CA
773 | 620122 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27 | LTE_CA_B3_B27-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#63 completed. Updated WID RP-131752=>RP-140119 | 36.101, 36.104, 36.133, 36.307, New generic TR 36.851 | CA
774 | 620222 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27 | LTE_CA_B3_B27-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#63 completed. Updated WID RP-131752=>RP-140119 | 36.101, 36.104, 36.133, 36.141 | CA
775 | 620023 | LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27 | 2 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 10% | RP-140120 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE | CA
776 | 620123 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27-Core | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 10% | RP-140120 | RP-140569 | KT | ilwhan.kim@kt.com | RP#64 completion 06/14=>12/14. Moved to Rel-13 | 36.101, 36.104, 36.133, generic TR 36.851 | CA
777 | 620223 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27-Perf | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 10% | RP-140120 | RP-140569 | KT | ilwhan.kim@kt.com | RP#64 completion 06/14=>12/14 | 36.141, 36.307 | CA
778 | 620072 | LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | Inter-band 2DL | LTE | CA
779 | 620172 | Core part: LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | RP#63 completed | 36.101, 36.104, 36.307 | CA
780 | 620272 | Perf. part: LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | RP#63 completed | 36.141 | CA
781 | 620024 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-131753 | - | KT | Ilwhan Kim (ilwhan.kim@kt.com) | Inter-band CA 3DL | LTE | CA
782 | 620124 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-131753 | RP-140569 | KT | Ilwhan Kim (ilwhan.kim@kt.com) | - | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
783 | 620224 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-131753 | RP-140569 | KT | Ilwhan Kim (ilwhan.kim@kt.com) | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
784 | 620025 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 80% | RP-140209 | - | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | Inter-band CA 3DL | LTE | CA
785 | 620125 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 80% | RP-140209 | RP-140569 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#63 updated WID RP-131634=>RP-140209 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
786 | 620225 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 80% | RP-140209 | RP-140569 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#63 updated WID RP-131634=>RP-140209 | 36.101, 36.133, 36.141, 36.307 | CA
787 | 620026 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140186 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | CA
788 | 620126 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140186 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131724=>RP-140186 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
789 | 620226 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140186 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131724=>RP-140186 | 36.141, 36.307 | CA
790 | 620027 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140189 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | CA
791 | 620127 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140189 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131725=>RP-140189 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
792 | 620227 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140189 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131725=>RP-140189 | 36.141, 36.307 | CA
793 | 620028 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140190 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | CA
794 | 620128 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140190 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131726=>RP-140190 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
795 | 620228 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140190 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131726=>RP-140190 | 36.141, 36.307 | CA
796 | 620029 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131654 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | CA
797 | 620129 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131654 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 | CA
798 | 620229 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131654 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
799 | 620030 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131652 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | CA
800 | 620130 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131652 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
801 | 620230 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131652 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
802 | 620031 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 47% | RP-140244 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | CA
803 | 620131 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-140244 | RP-140569 | Vodafone | luis.anaya@vodafone.com | RP#63 updated WID RP-131824=>RP-140244 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
804 | 620231 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | RP-140244 | RP-140569 | Vodafone | luis.anaya@vodafone.com | RP#63 updated WID RP-131824=>RP-140244 | 36.101, 36.133, 36.141, 36.307 | CA
805 | 620032 | LTE Advanced 3 band Carrier Aggregation 3DL for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27 | 2 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 25% | RP-131754 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 3DL | LTE | CA
806 | 620132 | Core part: LTE Advanced 3 band Carrier Aggregation 3DL for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Core | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 25% | RP-131754 | RP-140569 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#64 completion 06/14=>12/14. Moved to Rel-13 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
807 | 620232 | Perf. part: LTE Advanced 3 band Carrier Aggregation 3DL for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Perf | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 25% | RP-131754 | RP-140569 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#64 completion 06/14=>12/14 | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
808 | 620033 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140191 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | CA
809 | 620133 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140191 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131836=>RP-140191 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
810 | 620233 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 40% | RP-140191 | RP-140569 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#63 updated WID RP-131836=>RP-140191 | 36.141, 36.307 | CA
811 | 620034 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131655 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | CA
812 | 620134 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131655 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
813 | 620234 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131655 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
814 | 620035 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131653 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | CA
815 | 620135 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131653 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | CA
816 | 620235 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 95% | RP-131653 | RP-140569 | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
817 | 620037 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 | LTE_CA_C_B42 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140728 | - | CATT | Yuexia Song (songyuexia@catt.cn) | Intra-band contig. CA 2DL/2UL | LTE | CA
818 | 620137 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 | LTE_CA_C_B42-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140728 | RP-140569 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728 | 36.101, 36.104, 36.133, new TR 36.833-1-42 | CA
819 | 620237 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 | LTE_CA_C_B42-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140728 | RP-140569 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728 | 36.141, 36.307 | CA
820 | 620036 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-131810 | - | Orange | Olfa BEN HADDADA | Intra-band contig. CA 2DL/2UL | LTE | CA
821 | 620136 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-131810 | RP-140569 | Orange | Olfa BEN HADDADA | RP#64 completed | 36.101, 36.307 | CA
822 | 620236 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-131810 | RP-140569 | Orange | Olfa BEN HADDADA | RP#64 completed | 36.307 | CA
823 | 620038 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 | 55% | RP-140101 | - | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | Intra-band non-contig. CA 3DL | LTE | CA
824 | 620138 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 | 80% | RP-140101 | RP-140569 | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#63 updated WID RP-131694=>RP-140101 | 36.101, 36.104, 36.133, 36.307, new TR 36.833-6-xy | CA
825 | 620238 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 | 30% | RP-140101 | RP-140569 | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#63 updated WID RP-131694=>RP-140101 | 36.141 | CA
826 | 620039 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 | LTE_CA_NC_B42 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140671 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Intra-band non-contig. CA 2DL | LTE | CA
827 | 620139 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 | LTE_CA_NC_B42-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140671 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#64 completed. Updated WID RP-140404=>RP-140671. TR 36.833-2-42v100 for 1-step Approval | 36.101, 36.104, 36.133, new TR 36.833-2-42 | CA
828 | 620239 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 | LTE_CA_NC_B42-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140671 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#64 completed | 36.141, 36.307 | CA
829 | 620050 | LTE Advanced 3 Band Carrier Aggregation3DL for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5 | 2 | Rel-12 | R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 40% | RP-132121 | - | SK Telecom | haesung.park@sk.com | Inter-band CA 3DL | LTE | CA
830 | 620150 | Core part: LTE Advanced 3 Band Carrier Aggregation3DL for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5-Core | 3 | Rel-12 | R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 40% | RP-132121 | RP-140569 | SK Telecom | haesung.park@sk.com | - | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
831 | 620250 | Perf. part: LTE Advanced 3 Band Carrier Aggregation3DL for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5-Perf | 3 | Rel-12 | R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 40% | RP-132121 | RP-140569 | SK Telecom | haesung.park@sk.com | - | 36.101, 36.133, 36.141, 36.307 | CA
832 | 620051 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 38% | RP-141017 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | CA
833 | 620151 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 75% | RP-141017 | RP-140569 | Vodafone | luis.anaya@vodafone.com | RP#64 completion 06/14=>09/14 (RP-140569). Updated WID RP-140242=>RP-141017 | 36.101, 36.104, 36.133, new generic TR 36.851 (2 Band CA with 1UL), TR 36.853 (3 Band CA with 1UL) | CA
834 | 620251 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | RP-141017 | RP-140569 | Vodafone | luis.anaya@vodafone.com | RP#64 completion 06/14=>09/14 (RP-140569). Updated WID RP-140242=>RP-141017 | 36.101, 36.133, 36.141, 36.307 | CA
835 | 620052 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 42% | RP-140243 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | CA
836 | 620152 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 85% | RP-140243 | RP-140569 | Vodafone | luis.anaya@vodafone.com | RP#63 updated WID RP-132081=>RP-140243 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL), TR 36.851 (2 Band CA with 1UL) | CA
837 | 620252 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | RP-140243 | RP-140569 | Vodafone | luis.anaya@vodafone.com | RP#63 updated WID RP-132081=>RP-140243 | 36.101, 36.133, 36.141, 36.307 | CA
838 | 620053 | LTE Advanced 3 Band Carrier Aggregation 3DL for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 42% | RP-132080 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | CA
839 | 620153 | Core part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 85% | RP-132080 | RP-140569 | Vodafone | luis.anaya@vodafone.com | - | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL), TR 36.851 (2 Band CA with 1UL) | CA
840 | 620253 | Perf. part: LTE Advanced 3 Band Carrier Aggregation 3DL for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 0% | RP-132080 | RP-140569 | Vodafone | luis.anaya@vodafone.com | - | 36.101, 36.133, 36.141, 36.307 | CA
841 | 630022 | Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700_B29_Bwset | 2 | Rel-12 | R4 | 2014-03-03 08:00 | 2014-03-06 17:00 | 100% | RP-140084 | - | AT&T | marc.grant@att.com | Inter-band 2DL/1UL | LTE | CA
842 | 630122 | Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700_B29_BWset-Core | 3 | Rel-12 | R4 | 2014-03-03 08:00 | 2014-03-06 17:00 | 100% | RP-140084 | - | AT&T | marc.grant@att.com | RP#63 approved WI (no Perf. Part) & completed. Rel-10 and Rel-11 versions of 36.307 affected | 36.101, 36.307 | CA
843 | 630023 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20_BWset | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140447 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 2DL | LTE | CA
844 | 630123 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20_BWset-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140447 | RP-140569 | NSN | iwajlo.angelow@nsn.com | RP#64 completed | 36.101, TR 36.851 | CA
845 | 630024 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20_BWset | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140448 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 2DL | LTE | CA
846 | 630124 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20_BWset-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140448 | RP-140569 | NSN | iwajlo.angelow@nsn.com | RP#64 completed | 36.101, TR 36.851 | CA
847 | 630025 | Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback | LTE_CA_3DL_FB_BW | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140454 | - | Qualcomm | Fong Gene (gfong@qti.qualcomm.com) | Inter-band CA 2DL | LTE | CA
848 | 630125 | Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback | LTE_CA_3DL_FB_BW-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140454 | RP-140569 | Qualcomm | Fong Gene (gfong@qti.qualcomm.com) | RP#64 completed, Additional BW combinations added for 6 Wis: 3 open Rel-12 Wis (B1_B5_B7, B2_B29_B30, B4_B29_B30) and 3 completed Rel-11 Wis (B3_B5, B4_B5, B4_B12); no Perf. Part | 36.101, 36.307 | CA
849 | 630026 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140095 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 3DL | LTE | CA
850 | 630126 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140095 | RP-140569 | NSN | iwajlo.angelow@nsn.com | - | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
851 | 630226 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140095 | RP-140569 | NSN | iwajlo.angelow@nsn.com | - | 36.141, 36.307 | CA
852 | 630027 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140106 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | CA
853 | 630127 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140106 | RP-140569 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | - | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
854 | 630227 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140106 | RP-140569 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | - | 36.141, 36.307 | CA
855 | 630028 | LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140390 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | Inter-band CA 3DL | LTE | CA
856 | 630128 | Core part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140390 | RP-140569 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | - | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | CA
857 | 630228 | Perf. part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 95% | RP-140390 | RP-140569 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | - | 36.141, 36.307 | CA
858 | 630029 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140948 | - | China Mobile | Pan Qun (panqun@chinamobile.com) | Intra-band contig. CA 3DL | LTE | CA
859 | 630129 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140948 | RP-140569 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#64 completed. Updated WID RP-140453=>RP-140948 | 36.101, 36.104, 36.133, New TR 36.833-5-40 | CA
860 | 630229 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140948 | RP-140569 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#64 completed. Updated WID RP-140453=>RP-140948 | 36.141, 36.307 | CA
861 | 630036 | LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42 | LTE_CA_B41_B42 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 21% | RP-140450 | - | Huawei | leo.liuye@huawei.com | Inter-band CA 2DL | LTE | CA
862 | 630136 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42 | LTE_CA_B41_B42-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 60% | RP-140450 | RP-140569 | Huawei | leo.liuye@huawei.com | - | 36.101, 36.104, TR 36.851 | CA
863 | 630236 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42 | LTE_CA_B41_B42-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 0% | RP-140450 | RP-140569 | Huawei | leo.liuye@huawei.com | - | 36.141 | CA
864 | 630045 | Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25_BWset | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 15% | RP-140452 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Intra-band non-contig. CA 2DL | LTE | CA
865 | 630145 | Core part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25_BWset-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 30% | RP-140452 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | - | 36.101, 36.307, TR 36.833-2-25 | CA
866 | 630245 | Perf. part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25_BWset-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 0% | RP-140452 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | - | 36.307 | CA
867 | 640020 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4_BWset | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140599 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | 2DL/1UL | LTE | CA
868 | 640120 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4_Bwset-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140599 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | There was a WI LTE_CA_B2_B4 completed in Rel-12. Add new Bandwidth Combination Set to the channel bandwidth combination table of B2+B4 CA for 1UL/2DL | 36.101, 36.851 | CA
869 | 640021 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_BWset | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140642 | - | AT&T | marc.grant@att.com | 2DL/1UL | LTE | CA
870 | 640121 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_Bwset-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140642 | - | AT&T | marc.grant@att.com | There was a WI LTE_CA_B2_B5 completed in Rel-12. Add a bandwidth combination set 1 to the channel bandwidth combination table of B2+B5 CA for 1UL/2DL as well as 2UL/2DL | 36.101, 36.851 | CA
871 | 640221 | Perf. Part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_Bwset-Perf | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140642 | - | AT&T | marc.grant@att.com | - | 36.307 | CA
872 | 640027 | E-UTRA UE demodulation/CSI performance requirements for multiple Carrier Aggregation configurations | LTE_CA_Mult | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140975 | - | China Mobile | Zhang Xiaoran (zhangxiaoran@chinamobile.com) | LTE | LTE | CA
873 | 640127 | Perf. Part: E-UTRA UE demodulation/CSI performance requirements for multiple Carrier Aggregation configurations | LTE_CA_Mult-Perf | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2015-03-13 17:00 | 0% | RP-140975 | - | China Mobile | Zhang Xiaoran (zhangxiaoran@chinamobile.com) | - | 36.101 | CA
874 | 640028 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19 | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141004 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | 3DL/1UL | LTE | CA
875 | 640128 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141004 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
876 | 640228 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19-Perf | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141004 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | - | 36.141, 36.307 | CA
877 | 640029 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42 | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141007 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | 3DL/1UL | LTE | CA
878 | 640129 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141007 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
879 | 640229 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141007 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | - | 36.141, 36.307 | CA
880 | 640030 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42 | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141005 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | 3DL/1UL | LTE | CA
881 | 640130 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141005 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
882 | 640230 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141005 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | - | 36.141, 36.307 | CA
883 | 640031 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42 | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141006 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | 3DL/1UL | LTE | CA
884 | 640131 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141006 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | CA
885 | 640231 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-141006 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | - | 36.141, 36.307 | CA
886 | 640035 | Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW | 2 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140950 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | contig. 3DL | LTE | CA
887 | 640135 | Core part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW-Core | 3 | Rel-12 | R4 | 2014-06-13 08:00 | 2014-09-12 17:00 | 0% | RP-140950 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | - | 36.101 | CA
888 | 610013 | UE Conformance Test Aspects – Further REL-12 Configurations for LTE Advanced Carrier Aggregation | LTE_CA_Rel12-UEConTest | 1 | Rel-12 | R5 | 2013-09-09 08:00 | 2014-12-05 17:00 | 40% | RP-140621 | RP-140616 | Microsoft | jussi.kuusisto@microsoft.com | RP#64 updated WID RP-140460=>RP-140621. Completion 09/14=>12/14 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | CA
889 | 510033 | Deleted - Carrier based HetNet ICIC for LTE | LTE_CA_HetNet_ICIC | 1 | Rel-12 | R3,R1,R2 | 2011-03-18 08:00 | 2013-06-14 17:00 | 100% | RP-121198 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#60 stopped. RP#58 on hold til June 2013 | LTE
890 | 510133 | Deleted - Core part: Carrier based HetNet ICIC for LTE | LTE_CA_HetNet_ICIC-Core | 2 | Rel-12 | R3,R1,R2 | 2011-03-18 08:00 | 2013-06-14 17:00 | 100% | RP-121198 | RP-130500 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#60 stopped at 40% completion. RP#58 on hold til June 2013 | 36.300, 36.413, 36.420, 36.423
891 | 570017 | LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band | 1 | Rel-12 | R4,R2 | 2012-09-12 08:00 | 2014-12-05 17:00 | 76% | RP-130843 | - | AT&T | marc.grant@att.com | RP#58 RP-121701 work can start based on FCC Order (FCC-12-130) http://hraunfoss.fcc.gov/edocs_public/attachmatch/FCC-12-130A1.pdf | LTE
892 | 570117 | Core part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-Core | 2 | Rel-12 | R4,R2 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130843 | RP-130569 | AT&T | marc.grant@att.com | RP#60 completed. Updated WID RP-121419=>RP-130843 | 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, new TR 36.846
893 | 570217 | Perf. Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-Perf | 2 | Rel-12 | R4 | 2012-09-13 08:00 | 2013-06-14 17:00 | 100% | RP-130843 | RP-130570 | AT&T | marc.grant@att.com | RP#60 completed. Updated WID RP-121419=>RP-130843 | 36.101, 36.133, 36.141
894 | 640002 | Test Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-UEConTest | 2 | Rel-12 | R5 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140643 | - | Ericsson | fredrik.sundstrom@ericsson.com | - | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1
895 | 570019 | Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil | 1 | Rel-12 | R4,R5 | 2012-09-11 08:00 | 2013-12-06 17:00 | 100% | RP-121414 | - | Huawei | Liehai Liu (liuliehai@huawei.com) | - | LTE
896 | 570119 | Core part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-Core | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-121414 | RP-130567 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#60 completed. TR 36.840 v100 for 1-step Approval | 36.101, 36.104, 36.113, 36.124, 36.133, 37.104, 37.113, 36.307, new TR 36.840
897 | 570219 | Perf. part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-Perf | 2 | Rel-12 | R4 | 2012-09-13 08:00 | 2013-09-06 17:00 | 100% | RP-121414 | RP-131070 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#61 completed | 36.133, 36.141, 37.141
898 | 600005 | Test part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-UEConTest | 2 | Rel-12 | R5 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130646 | RP-131457 | Huawei | Xiang Li (tricia.li@huawei.com) | RP#62 completed | 36.508, 36.521-1, 36.521-2, 36.521-3
899 | 570020 | Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh | 1 | Rel-12 | R1,R4 | 2012-09-11 08:00 | 2014-09-12 17:00 | 79% | RP-121416 | - | Alcatel-Lucent | Min Zhang (min.hs.zhang@alcatel-lucent.com) | Stage 3 | LTE
900 | 570120 | Core part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Core | 2 | Rel-12 | R1 | 2012-09-11 08:00 | 2014-06-13 17:00 | 100% | RP-121416 | RP-140652 | Alcatel-Lucent | Min Zhang (min.hs.zhang@alcatel-lucent.com) | - | 36.211, 36.212, 36.213, 36.331
901 | 570220 | Perf. part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Perf | 2 | Rel-12 | R4 | 2012-09-18 08:00 | 2014-09-12 17:00 | 60% | RP-121416 | RP-140652 | Alcatel-Lucent | ren.da@alcatel-lucent.com | RP#62 completion 12/13=>09/14 | 36.101
902 | 570025 | Deleted - New Carrier Type for LTE | LTE_NCT | 1 | Rel-12 | R1,R2,R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-122028 | - | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped. Continue discussion on use cases and requirements for a NCT in LTE beyond Rel-12. Action: Ericsson to provide at RP#62 a summary of work done so far | LTE
903 | 570125 | Deleted - Core part: New Carrier Type for LTE | LTE_NCT-Core | 2 | Rel-12 | R1,R2,R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-122028 | RP-130984 | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped at 20% completion | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.321, 36.331
904 | 570225 | Deleted - Perf. part: New Carrier Type for LTE | LTE_NCT-Perf | 2 | Rel-12 | R4 | 2012-09-17 08:00 | 2013-09-06 17:00 | 100% | RP-122028 | RP-130985 | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped at 0% completion | 36.101, 36.104, 36.133, 36.141
905 | 580027 | Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA | 1 | Rel-12 | R1,R2,R3,R4 | 2012-12-07 08:00 | 2014-12-05 17:00 | 14% | RP-121772 | - | CATT | Zukang Shen (shenzukang@catt.cn) | Stage 3. Triggered by Rel-11 TR 36.828 Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation (FS_LTE_TDD_eIMTA) UID_510039 | LTE | Small cell
906 | 580127 | Core part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Core | 2 | Rel-12 | R1,R2,R3,R4 | 2012-12-07 08:00 | 2014-06-13 17:00 | 100% | RP-121772 | RP-140724 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#62 completion 12/13=>06/14 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423 | Small cell
907 | 580227 | Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Perf | 2 | Rel-12 | R4 | 2012-12-07 08:00 | 2014-12-05 17:00 | 10% | RP-121772 | RP-140724 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#64 completion 09/14=>12/14 | 36.101, 36.104, 36.133, 36.141 | Small cell
908 | 580029 | HetNet Mobility enhancements for LTE | HetNet_eMOB_LTE | 1 | Rel-12 | R2,R4 | 2012-04-13 10:48 | 2014-09-12 17:00 | 97% | RP-122007 | - | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | Stage 3. Triggered by Rel-11 TR 36.839 Study on HetNet mobility enhancements for LTE (FS_HetNet_eMOB_LTE) | LTE
909 | 580129 | Core part: HetNet Mobility enhancements for LTE | HetNet_eMOB_LTE-Core | 2 | Rel-12 | R2,R4 | 2012-04-13 10:48 | 2014-09-12 17:00 | 97% | RP-122007 | RP-140759 | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | RP#64 completion 06/14=>09/14 | 36.133, 36.304, 36.331
910 | 580030 | Further enhancements for HeNB mobility-X2-GW | EHNB_enh2_X2GW | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122006 | - | Alcatel-Lucent | Philippe.Godin@alcatel-lucent.com | Rel-10 H(e)NB Mobility Enhancements adds signalling via horizontal RAN interfaces (Iurh, X2) to support H(e)NB to H(e)NB mobility. Rel-11 TR37.803 triggered WI UID_560014 partly completed in Rel-11; remaining work including solution definition is Rel-12 | LTE | HNB
911 | 580130 | Core part: Further enhancements for HeNB mobility-X2-GW | EHNB_enh2_X2GW-Core | 2 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122006 | RP-140592 | Alcatel-Lucent | Philippe.Godin@alcatel-lucent.com | RP#64 completed | 36.300, 36.413, 36.423 | HNB
912 | 580031 | 8 Rx Antennas for LTE UL | LTE_UL_8Rx | 1 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-121709 | - | China Telecom | Shan Yang (yangshan@ctbri.com.cn) | WI has perf. part only (as change from 4Rx to 8Rx has no Core spec impact) | LTE
913 | 580231 | Perf. part: 8 Rx Antennas for LTE UL | LTE_UL_8Rx-Perf | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-121709 | RP-131523 | China Telecom | Shan Yang (yangshan@ctbri.com.cn) | RP#62 completed | 36.104, 36.141
914 | 600012 | Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE | 1 | Rel-12 | R1,R2,R4 | 2013-06-20 08:00 | 2015-03-13 17:00 | 30% | RP-130848 | - | Vodafone | prakash.bhat@vodafone.com | Triggered by Rel-11 TR 36.888 (FS_LC_MTC_UE) | LTE | MTC, M2M
915 | 600112 | Core part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Core | 2 | Rel-12 | R1,R2,R4 | 2013-10-15 16:28 | 2014-09-12 17:00 | 70% | RP-130848 | RP-140744 | Vodafone | prakash.bhat@vodafone.com | RP#63 completion 06/14=>09/14 | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331 | MTC, M2M
916 | 600212 | Perf. part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2015-03-13 17:00 | 20% | RP-130848 | RP-140744 | Vodafone | prakash.bhat@vodafone.com | - | 36.101, 36.104, 36.133 | MTC, M2M
917 | 600013 | LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD | 1 | Rel-12 | R1,R2,R4 | 2013-04-12 16:44 | 2014-12-05 17:00 | 23% | RP-140465 | - | Nokia | lars.e.lindh@nokia.com | - | LTE | -
918 | 600113 | Core part: LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD-Core | 2 | Rel-12 | R1,R2,R4 | 2013-04-12 16:44 | 2014-06-13 17:00 | 100% | RP-140465 | RP-140982 | Nokia, China Mobile (for the TR) | lars.e.lindh@nokia.com, Xiaodong Shen (shenxiaodong@chinamobile.com) | RP#63 updated WID RP-131399=>RP-140465 | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.331, new TR 36.847
919 | 600213 | Perf. part: LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-12-05 17:00 | 5% | RP-140465 | RP-140982 | Nokia | lars.e.lindh@nokia.com | RP#63 updated WID RP-131399=>RP-140465 | 36.101, 36.104, 36.133
920 | 600014 | LTE Coverage Enhancements | Cov_Enh_LTE | 1 | Rel-12 | R1,R2,R4 | 2013-03-01 15:38 | 2014-12-05 17:00 | 51% | RP-130833 | - | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | Triggered by Rel-11 TR 36.824 (FS_Cov_Enh_LTE) | LTE
921 | 600114 | Core part: LTE Coverage Enhancements | Cov_Enh_LTE-Core | 2 | Rel-12 | R1,R2,R4 | 2013-03-01 15:38 | 2014-06-13 17:00 | 100% | RP-130833 | RP-140683 | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | - | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.321, 36.331
922 | 600214 | Perf. part: LTE Coverage Enhancements | Cov_Enh_LTE-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-12-05 17:00 | 40% | RP-130833 | RP-140683 | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | - | 36.101, 36.104, 36.133, 36.141
923 | 610024 | Further MBMS operations support for E-UTRAN | MBMS_LTE_OS | 1 | Rel-12 | R2,R1,R3,R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 74% | RP-140282 | - | Verizon | yeesin.chan@verizonwireless.com | Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS. | LTE
924 | 610124 | Core part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2014-04-04 15:00 | 2014-09-12 17:00 | 80% | RP-140282 | RP-140672 | Verizon | yeesin.chan@verizonwireless.com | RP#64 completion 06/14=>09/14 | 36.133, 36.214, 36.300, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320
925 | 620073 | Perf. part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 70% | RP-140282 | RP-140672 | Verizon | yeesin.chan@verizonwireless.com | RP#63 updated WID RP-131681=>RP-140282 | 36.133
926 | 620040 | Dual connectivity for LTE | LTE_SC_enh_dualC | 1 | Rel-12 | R2,R1,R3,R4,S2 | 2013-12-09 08:00 | 2014-12-05 17:00 | 36% | RP-132069 | - | NTT DOCOMO | tooru.uchino.fv@nttdocomo.com | Triggered by TR 36.842 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects (UID_580044) | LTE | Small cell
927 | 620140 | Core part: Dual connectivity for LTE | LTE_SC_enh_dualC-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2014-04-29 08:00 | 2014-09-12 17:00 | 50% | RP-132069 | RP-140986 | NTT DOCOMO, NEC | RAN1/2/4 tooru.uchino.fv@nttdocomo.com, RAN3 Chenghock Ng (ngcheng@da.jp.nec.com) | RP#64 completion 06/14=>09/14 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.322, 36.323, 36.331, 36.410, 36.413, 36.420, 36.423 | Small cell
928 | 620240 | Perf. part: Dual Connectivity for LTE | LTE_SC_enh_dualC-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 0% | RP-132069 | RP-140986 | NTT DOCOMO | kunihiko.teshima.hg@nttdocomo.com | - | 36.101, 36.104, 36.133 | Small cell
929 | 631000 | SA2 part of Dual connectivity for LTE | - | 2 | Rel-12 | S2 | 2014-03-19 08:00 | 2014-09-17 17:00 | 99% | - | - | - | - | SP#64 Three CRs agreed in SP-140262 (23.251CR0099, 23.401CR2658&CR2707) | 23.251, 23.401
930 | 620041 | E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1 | 1 | Rel-12 | R1,R2,R4 | 2013-07-19 10:00 | 2014-12-05 17:00 | 36% | RP-132073 | - | Huawei | Xizeng Dai (daixizeng@huawei.com) | Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041) | LTE | Small cell
931 | 620141 | Core part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Core | 2 | Rel-12 | R1,R2,R4 | 2013-07-19 10:00 | 2014-09-12 17:00 | 75% | RP-132073 | RP-141014 | Huawei | Xizeng Dai (daixizeng@huawei.com) | RP#64 completion 06/14=>09/14 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.413, 36.423 | Small cell
932 | 620241 | Perf. part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 5% | RP-132073 | RP-141014 | Huawei | Xizeng Dai (daixizeng@huawei.com) | RP#64 completion 09/14=>12/14 | 36.101, 36.104, 36.133, 36.141 | Small cell
933 | 620047 | Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB | 1 | Rel-12 | R3,R1 | 2014-03-14 10:48 | 2014-09-12 17:00 | 65% | RP-140983 | - | Samsung | Sung Hwan Won (sunghwan.won@samsung.com) | Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation). | LTE
934 | 620147 | Core part: Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB-Core | 2 | Rel-12 | R3,R1 | 2014-03-14 10:48 | 2014-09-12 17:00 | 65% | RP-140983 | RP-140597 | Samsung | Sung Hwan Won (sunghwan.won@samsung.com) | RP#64 updated WID RP-132103=>RP-140983. Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015) | 36.300, 36.423
935 | 630031 | Smart Congestion Mitigation in E-UTRAN | SCM_LTE | 1 | Rel-12 | R2,S1,C1 | 2014-03-05 08:00 | 2014-09-12 17:00 | 24% | RP-140434 | - | LG Electronics | youngdae.lee@lge.com | follow-up of TR 36.848 FS_SCM_LTE | LTE
936 | 630131 | Core part: Smart Congestion Mitigation in E-UTRAN | SCM_LTE-Core | 2 | Rel-12 | R2 | 2014-03-06 08:00 | 2014-09-12 17:00 | 20% | RP-140434 | RP-140645 | LG Electronics | youngdae.lee@lge.com | - | 36.331
937 | 640105 | Stage 1 Prioritization of Multimedia Telephony (MMTel) and Mobile Originating-SMS for Access Class Barring (ACB) | - | 2 | Rel-12 | S1 | 2014-03-05 08:00 | 2014-03-07 17:00 | 100% | CP-140286 | - | - | - | SP#63 SP-140065 CR under TEI12 | 22.011
938 | 640005 | CT aspects of Smart Congestion Mitigation in E-UTRAN (Stage 3) | SCM_LTE-CT | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-09-12 17:00 | 30% | CP-140286 | - | LG Electronics | Kim, Jaehyun (jaehyun7.kim@lge.com) | - | 24.173, 24.301, 24.341, 27.007
939 | 630032 | Positioning Enhancements for RF Pattern Matching in E-UTRA | LCS_LTE_RFPMT | 1 | Rel-12 | R3,R2 | 2014-04-25 08:00 | 2014-06-13 17:00 | 100% | RP-140177 | - | Polaris Wireless | Gordon Scot (sgordon@polariswireless.com) | follow-up of TR 36.809 FS_LCS_LTE_RFPMT | LTE
940 | 630132 | Core part: Positioning Enhancements for RF Pattern Matching in E-UTRA | LCS_LTE_RFPMT-Core | 2 | Rel-12 | R3,R2 | 2014-04-25 08:00 | 2014-06-13 17:00 | 100% | RP-140177 | RP-140591 | Polaris Wireless | Gordon Scot (sgordon@polariswireless.com) | RP#64 completed | 36.305, 36.455
941 | 630046 | Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS | 1 | Rel-12 | R1 | 2014-03-06 08:00 | 2015-06-12 17:00 | 8% | RP-140519 | - | MediaTek | Jeff.Zhuang@mediatek.com | follow-up of TR 36.866 FS_LTE_NAICS | LTE
942 | 630146 | Core part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Core | 2 | Rel-12 | R1,R2,R4 | 2014-07-11 10:40 | 2014-09-12 17:00 | 68% | RP-140519 | RP-140697 | MediaTek | Jeff.Zhuang@mediatek.com | - | 36.211, 36.213, 36.331
943 | 630246 | Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Perf | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-06-12 17:00 | 0% | RP-140519 | RP-140697 | MediaTek | Jeff.Zhuang@mediatek.com | - | 36.101
944 | 630047 | Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX | 1 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 35% | RP-140520 | - | Huawei | Qian Cheng (Q.Cheng@Huawei.com) | no Core part | LTE
945 | 630147 | Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX-Perf | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 35% | RP-140520 | RP-140640 | Huawei | Qian Cheng (Q.Cheng@Huawei.com) | - | 36.101
946 | 580028 | HSPA signalling enhancements for more efficient resource usage for LCR | LCR_TDD_HSPA_sign_enh | 1 | Rel-12 | R1,R2,R3,R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-121984 | - | CATT | Yanping Xing (xingyanping@catt.cn) | Stage 2/3. Triggered by Rel-11 TR 25.874 Study on HSPA feedback and signalling efficiency enhancements for LCR TDD (FS_LCRTDD_HSPAenh) UID_540026 | UTRA
947 | 580128 | Core part: HSPA signalling enhancements for more efficient resource usage for LCR TDD | LCR_TDD_HSPA_sign_enh-Core | 2 | Rel-12 | R1,R2,R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-121984 | RP-131499 | CATT | Yanping Xing (xingyanping@catt.cn) | RP#62 completed | 25.222, 25.224, 25.331, 25.423, 25.433
948 | 580228 | Perf. part: HSPA signalling enhancements for more efficient resource usage for LCR TDD | LCR_TDD_HSPA_sign_enh-Perf | 2 | Rel-12 | R4 | 2012-12-11 08:00 | 2013-09-06 17:00 | 100% | RP-121984 | RP-130968 | CATT | Yanping Xing (xingyanping@catt.cn) | RP#61 completed | 25.102
949 | 600017 | HNB Positioning for UTRA | UTRA_HNB_Pos | 1 | Rel-12 | R3 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-132037 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 completed | UTRA | HNB
950 | 600117 | Core part: HNB Positioning for UTRA | UTRA_HNB_Pos-Core | 2 | Rel-12 | R3 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-132037 | RP-131974 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID) | 25.305, 25.467, new TS 25.470 | HNB
951 | 610025 | Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh | 1 | Rel-12 | R1,R2,R3,R4 | 2013-09-10 08:00 | 2014-12-05 17:00 | 43% | RP-140771 | - | Qualcomm | arjunb@qti.qualcomm.com | Triggered by Rel-12 TR 25.702 Study on Dedicated Channel (DCH) enhancements for UMTS (FS_UTRA_DCHenh) UID_580040. Stage 2/3 | UTRA
952 | 610125 | Core part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Core | 2 | Rel-12 | R1,R2,R3,R4 | 2013-11-18 10:00 | 2014-09-12 17:00 | 80% | RP-140771 | RP-140769 | Qualcomm | arjunb@qti.qualcomm.com | RP#64 revised WID RP-131357=>RP-140771. Completion o6/14=>09/14 | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433
953 | 610225 | Perf. part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Perf | 2 | Rel-12 | R4 | 2013-09-10 08:00 | 2014-12-05 17:00 | 30% | RP-140771 | RP-140769 | Qualcomm | arjunb@qti.qualcomm.com | RP#64 revised WID RP-131357=>RP-140771. Completion o9/14=>12/14 | 25.101, 25.104, 25.133
954 | 610026 | UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob | 1 | Rel-12 | R2,R3,R4 | 2013-07-23 09:12 | 2014-06-13 17:00 | 100% | RP-132039 | - | Huawei | Xudong Yang (yangxudong@huawei.com) | Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3 | UTRA
955 | 610126 | Core part: UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob-Core | 2 | Rel-12 | R2,R3,R4 | 2013-07-23 09:12 | 2014-06-13 17:00 | 100% | RP-132039 | RP-140636 | Huawei | Xudong Yang (yangxudong@huawei.com) | RP#64 completed. TS 25.300v100 for 1-step Approval | 25.101, 25.104, 25.133, 25.141, 25.304, 25.306, 25.331, 25.433, new TS 25.300
956 | 610226 | Perf. part: UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob-Perf | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-132039 | RP-140636 | Huawei | Xudong Yang (yangxudong@huawei.com) | RP#64 completed | 25.101, 25.104, 25.133, 25.141
957 | 620054 | UMTS Heterogeneous Networks enhancements | UTRA_HetNet_enh | 1 | Rel-12 | R1,R2,R3,R4 | 2013-12-06 08:00 | 2014-12-05 17:00 | 37% | RP-140463 | - | Huawei | carmela.cozzo@huawei.com | Triggered by the 2nd part of TR 25.800 (FS_UTRA_HetNet); the 1st part is addressed by UTRA_HetNet_mob UID_610026 | UTRA
958 | 620154 | Core part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Core | 2 | Rel-12 | R1 | 2013-12-06 08:00 | 2014-09-12 17:00 | 85% | RP-140463 | RP-140634 | Huawei | carmela.cozzo@huawei.com | RP#64 completion 06/14=>09/14 | 25.211, 25.212, 25.213, 25.214, 25.304, 25.306, 25.331
959 | 620254 | Perf. part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 0% | RP-140463 | RP-140634 | Huawei | carmela.cozzo@huawei.com | RP#64 completion 09/14=>12/14 | 25.101, 25.104, 25.133, 25.141, 25.433
960 | 620055 | Enhanced Broadcast of System Information | UTRA_SIBenh | 1 | Rel-12 | R2,R1,R3,R4 | 2013-12-06 08:00 | 2014-12-05 17:00 | 28% | RP-140131 | - | Ericsson | martin.van.der.zee@ericsson.com | Triggered by Rel-12 UTRA TR 25.704 Study on Enhanced Broadcast of System Information (FS_UTRA_SIBenh) | UTRA
961 | 620155 | Core part: Enhanced Broadcast of System Information | UTRA_SIBenh-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 70% | RP-140131 | RP-140735 | Ericsson | martin.van.der.zee@ericsson.com | RP#64 completion 06/14=>09/14 | 25.211, 25.212 , 25.213, 25.214, 25.301, 25.302, 25.304, 25.306, 25.321, 25.331, 25.433
962 | 620255 | Perf. part: Enhanced Broadcast of System Information | UTRA_SIBenh-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 0% | RP-140131 | RP-140735 | Ericsson | martin.van.der.zee@ericsson.com | RP#63 updated WID RP-132077=>RP-140131 | 25.101, 25.104, 25.133, 25.141
963 | 620049 | Further Enhanced Uplink (EUL) enhancements | EDCH_enh | 1 | Rel-12 | R2 | 2013-12-09 08:00 | 2014-12-05 17:00 | 36% | RP-140127 | - | Ericsson | mark.curran@ericsson.com | Triggered by Rel-12 UTRA TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh) | UTRA
964 | 620149 | Core part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2014-04-29 08:00 | 2014-09-12 17:00 | 78% | RP-140127 | RP-140732 | Ericsson | mark.curran@ericsson.com | RP#64 completion 06/14=>09/14 | 25.211, 25.212, 25.214, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.425, 25.433, 25.435
965 | 620249 | Perf. part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-05 17:00 | 20% | RP-140127 | RP-140732 | Ericsson | mark.curran@ericsson.com | RP#63 updated WID RP-132078=>RP-140127 | 25.101, 25.104, 25.133, 25.141
966 | 560018 | (Small) Technical Enhancements and Improvements for Rel-12 | TEI12 | 1 | Rel-12 | SP,CP,RP,GP | 2012-12-25 13:00 | 2014-09-17 17:00 | 100% | - | - | - | - | - | -
967 | 610001 | Test - (Small) Technical Enhancements and Improvements for Rel-12 | TEI12_Test | 1 | Rel-12 | R5,G3new | 2014-10-24 13:00 | 2015-12-11 17:00 | 100% | - | - | - | - | - | -
968 | 0 | Release 12 Studies | - | 1 | Rel-12 | SP,CP,GP,RP | 2013-08-05 13:00 | 2014-09-17 17:00 | 80% | - | - | - | - | - | -
969 | 470020 | Study on Alternatives to E.164 for Machine-Type Communications | FS_AMTC | 1 | Rel-12 | S1 | 2010-03-25 08:00 | 2012-03-07 17:00 | 100% | SP-100198 | - | T-Mobile USA | gary.jones@T-Mobile.com | SP#55 completed. Determine an alternative to E.164 for identifying individual devices and route messages between those devices | 22.988 | MTC, M2M
970 | 480032 | Study on enhancements for Machine-Type Communications (MTC) | FS_MTCe | 1 | Rel-12 | S1 | 2010-06-10 08:00 | 2013-03-06 17:00 | 100% | SP-100448 | - | Huawei | laurence.meriau@huawei.com | SP#59 completed. TR 22.888 v100 for Information & Approval. Study addition of new MTC-related use cases and functionality and improvements to existing requirements in TS 22.368 | 22.888 | MTC, M2M
971 | 490035 | Study on Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int | 1 | Rel-12 | S1 | 2010-09-23 08:00 | 2012-03-07 17:00 | 100% | SP-100640 | - | InterDigital | christopher.wallace@interdigital.com | SP#55 completed. Linked to SA3 Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest (UID_480048), SA3 TR 33.924 Extended Identity Management (GBA-IdM) and SA3 TR 33.980 (LibSec) | 22.895
972 | 500035 | Study on Continuity of Data Sessions to Local Networks | FS_CSN | 1 | Rel-12 | S1 | 2010-12-16 08:00 | 2011-12-14 17:00 | 100% | SP-100885 | - | NEC | joerg.swetina@neclab.eu | SP#54 completed. Linked to SA1 Rel-11 Feature UID_490030 SIPTO Service Continuity of IP Data Session (SIPTO_SC) | 22.896
973 | 500036 | Study on non-MTC Mobile Data Applications Impacts | FS_MODAI | 1 | Rel-12 | S1 | 2010-12-16 08:00 | 2011-12-14 17:00 | 100% | SP-100889 | - | Huawei, China Mobile | Amar Deol (adeol@huawei.com), Gang Li | SP#54 completed. Linked to UID_490036 SA2 Rel-11 TR 23.843 Study on Core Network Overload solutions (FS_CNO) | 22.801
974 | 530044 | Study on Proximity-based Services | FS_ProSe | 1 | Rel-12 | S1 | 2011-09-22 08:00 | 2013-03-05 17:00 | 100% | SP-110638 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#59 completed | 22.803 | Public Safety (A-A)
975 | 540027 | Study on User Plane Congestion management | FS_UPCON | 1 | Rel-12 | S1 | 2011-12-14 08:00 | 2012-09-12 17:00 | 100% | SP-110819 | - | KDDI | John Visser (jvisser@rogers.com) | SP#57 completed. Linked to SAPP (Service Awareness and Privacy Policies), FS_UMONC (Study on Usage Monitoring Control Enhancement), QoS_SSL (QoS Control Based on Subscriber Spending Limits) | 22.805
976 | 540028 | Study on RAN Sharing Enhancements | FS_RSE | 1 | Rel-12 | S1 | 2011-12-14 08:00 | 2013-06-19 17:00 | 100% | SP-110820 | - | NEC | joerg.swetina@neclab.eu | SP#60 completed. Extend Rel-6 Network Sharing UID_31018 (basic scenarios of network/RAN sharing) to cover more complex scenarios that arise due to recent needs for more dynamic co-operation among operators | 22.852
977 | 460025 | Deleted - Study on UICC/USIM enhancements | FS_U2e | 1 | Rel-12 | S1 | 2009-12-10 08:00 | 2012-03-07 17:00 | 100% | SP-090903 | - | Giesecke & Devrient | ilario.macchi@gi-de.com | SP#55 work stopped. Triggered by GSMA Smart SIM and 3GNBK projects, and to evolve from traditional USAT to multimedia USIM toolkit support, particularly to Smart Card Web Server | 22.817
978 | 490034 | Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 1 | Rel-12 | S2,S1,S3 | 2010-09-23 08:00 | 2012-12-12 17:00 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | Triggered by TR 22.906 SA1 Study on IMS based Peer-to-Peer Content Distribution Services UID_450047 | 23.844
979 | 490134 | SA1 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | - | 2 | Rel-12 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#53 completed | 23.844
980 | 490234 | SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | - | 2 | Rel-12 | S2 | 2010-09-23 08:00 | 2012-06-20 17:00 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#56 completed. TR 23.844v100 for Information and Approval | 23.844
981 | 570036 | SA3 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | - | 2 | Rel-12 | S3 | 2012-09-12 08:00 | 2012-12-12 17:00 | 100% | SP-120622 | - | China Mobile | Zhu Judy(zhuhongru@chinamobile.com) | SP#58 completed. TR 33.844 v100 for Information and Approval | 33.844
982 | 490036 | Study on Core Network Overload solutions | FS_CNO | 1 | Rel-12 | S2 | 2010-09-23 08:00 | 2013-12-11 17:00 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | SP#62 completed. Linked to CT4 TR 23.857 Study on EPC Nodes Restoration (UID_490014) | 23.843
983 | 490136 | Study on Core Network Overload solutions (Phase 1) | - | 2 | Rel-12 | S2 | 2010-09-23 08:00 | 2012-12-12 17:00 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | Phase 1: complete study of overload control related to MAP /Diameter signalling, other 3GPP Core Network signalling optimization | 23.843
984 | 490236 | Study on Core Network Overload solutions (Phase 2) | - | 2 | Rel-12 | S2 | 2010-09-23 08:00 | 2013-12-11 17:00 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | SP#62 completed | 23.843
985 | 500037 | Study on System Enhancements for Energy Efficiency | FS_SEEE | 1 | Rel-12 | S2 | 2010-12-16 08:00 | 2012-06-20 17:00 | 100% | SP-100888 | - | Huawei | frank.mademann@huawei.com | SP#56 completed | 23.866
986 | 510061 | Study on S2a Mobility based On GTP and WLAN access to EPC | FS_SaMOG | 1 | Rel-12 | S2 | 2011-03-23 08:00 | 2013-09-11 17:00 | 100% | SP-120426 | - | ZTE | Tricci So (tso@zteusa.com) | SP#61 completed. Covers generic non-3GPP access (e.g. WLAN, WIMAX, CDMA/HRPD). Spin-off Feature SaMOG_WLAN. Linked to Rel-8 Support for non-3GPP accesses, Rel-10 SMOG, Rel-11 BBAI | 23.852 | WLAN
987 | 560037 | Study on Optimized Offloading to WLAN in 3GPP-RAT Mobility | FS_WORM | 1 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-09-11 17:00 | 100% | SP-120261 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | SP#61 completed. Linked to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP), UID_410043 MAPIM, UID_450041 IFOM, UID_530046 SaMOG | 23.890 | WLAN
988 | 560038 | Study on Application Based Charging | FS_ABC | 1 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120271 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | SP#59 completed. Linked to Rel-11 Feature UID_500032 Service Awareness and Privacy Policies (SAPP) | 23.800
989 | 410043 | Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 1 | Rel-12 | S2,S1 | 2008-08-08 08:19 | 2012-12-12 17:00 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | Spin-off Features MAPCON, IFOM. SP#58 completed FS_MAPIM part of 23.861 (continued under FS_NBIFOM) | 23.861
990 | 410143 | SA1 part of Study on Multi Access PDN connectivity and IP flow Mobility | - | 2 | Rel-12 | S1 | 2008-08-08 08:19 | 2011-09-21 17:00 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | SP#53 completed | 23.861
991 | 410243 | SA2 part of Study on Multi Access PDN connectivity and IP flow Mobility | - | 2 | Rel-12 | S2 | 2008-09-18 08:00 | 2012-12-12 17:00 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | SP#43 TR 23.861v100 for Information. SP#56 Rel-9 TR 23.861v130 renamed & progressed under new Study FS_NBIFOM. SP#58 completed the FS_MAPIM part of TR 23.861 (TR continued under FS_NBIFOM). | 23.861
992 | 560039 | Deleted - Study on IP Flow Mobility support for S2a and S2b Interfaces | FS_NBIFOM | 1 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120742 | - | ZTE | Tricci So (tso@zteusa.com) | SP#59 stopped (at 40% completion). SP#56 revives dormant Study FS_MAPIM. TR 23.861 title changed from (Multi Access PDN connectivity and IP flow mobility) to (Network based IP flow mobility) | 23.861
993 | 480043 | Study on Extended IMS Media Plane Security features | FS_eMEDIASEC | 1 | Rel-12 | S3 | 2010-06-10 08:00 | 2013-03-06 17:00 | 100% | SP-100256 | - | Vodafone | Aguibou.Barry@vodafone.com | SP#59 completed. Continuation of Rel-9 Feature UID_430036 IMS Media Plane Security (MEDIASEC). Study solutions and extensions to features and functionality described in TR 33.828 and TS 33.328 | 33.829
994 | 500034 | Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int_Sec | 1 | Rel-12 | S3 | 2010-12-16 08:00 | 2014-09-17 17:00 | 55% | SP-100734 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#64 completion 06/14=>09/14 | 33.895
995 | 530047 | Study on Firewall traversal (Stage 2) | FS_Fire | 1 | Rel-12 | S3 | 2011-06-17 08:00 | 2014-09-17 17:00 | 75% | SP-120849 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | SP#64 completion 06/14=>09/14. Linked to Rel-12 Service and Media Reachability for Users over Restrictive Firewalls (SMURFs) UID_530043 | 33.830
996 | 550026 | Study on Security on spoofed call detection and prevention (Stage 2) | FS_SPOOF | 1 | Rel-12 | S3 | 2012-03-07 08:00 | 2014-09-17 17:00 | 90% | SP-120030 | - | China Mobile | lixiangjun@chinamobile.com | SP#64 completion 06/14=>09/14. Linked to Rel-11 SPUCI TR 33.838 | 33.831
997 | 570035 | Study on Security Assurance Methodology for 3GPP Network Elements | FS_SECAM | 1 | Rel-12 | S3 | 2012-09-13 08:00 | 2014-06-18 17:00 | 100% | SP-120654 | - | Orange | loic.habermacher@orange.com | SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible) | 33.805
998 | 610043 | Study on Subscriber Privacy Impact in 3GPP | FS_SPI | 1 | Rel-12 | S3 | 2013-09-12 08:00 | 2014-09-17 17:00 | 75% | SP-130399 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#64 completion 06/14=>09/14. Related to SA1 TR 22.949 Rel-6 Study on Privacy Capability (PrivCap) UID_31030 studied generalized privacy capability (protection of personal data and non-disclosure of identity) | 33.849
999 | 540033 | Study on Improved Support for Dynamic Adaptive Streaming over HTTP in 3GPP | FS_IS_DASH | 1 | Rel-12 | S4 | 2011-12-14 08:00 | 2014-09-17 17:00 | 98% | SP-110887 | - | Qualcomm | c_tstock@qualcomm.com | SP#64 completion 06/14=>09/14. Linked to Feature UID_470034 HTTP-based Streaming and Download Services | 26.938
1000 | 590045 | Study on Enhanced Acoustic Test Specifications | FS_SEATS | 1 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-17 17:00 | 25% | SP-130028 | - | Audience, Intel | Chris Steck (Audience), David Isherwood (Intel) | SP#64 completion 06/14=>09/14. Address existing items designated as FFS in TS 26.131/2. Coordinate with other SDOs (e.g. ITU-T SG 12, ETSI TC STQ) to leverage each other’s work and minimize overlap | 26.931
1001 | 610044 | Study on HTML5 for a new presentation layer in 3GPP services | FS_HTML5 | 1 | Rel-12 | S4 | 2013-09-12 08:00 | 2014-09-17 17:00 | 95% | SP-130357 | - | Samsung | Imed Bouazizi (i.bouazizi@sta.samsung.com) | SP#64 TR 26.907v100 for Information. HTML5 impr. adv. MM technology support; maintains simple readability/impr. compatibility. Define APIs providing access functions (2D drawing, timed media playback, offline mode, web storage, web sockets) via Javascript | 26.907
1002 | 470050 | Study on version handling | FS_OAM_VH | 1 | Rel-12 | S5 | 2010-03-25 08:00 | 2012-12-12 17:00 | 100% | SP-100082 | - | Ericsson | thomas.tovinger@ericsson.com | SP#58 completed | 32.830
1003 | 510046 | Study on management of Heterogeneous Networks | FS_OAM_HetNet | 1 | Rel-12 | S5 | 2011-03-23 08:00 | 2014-06-18 17:00 | 100% | SP-130046 | - | Ericsson | ulf.hubinette@ericsson.com | SP#64 completed | 32.835
1004 | 540032 | Study on OAM aspects of Network Sharing | FS_OAM_SHARE | 1 | Rel-12 | S5 | 2011-12-07 08:00 | 2013-09-11 17:00 | 100% | SP-130044 | - | Alcatel-Lucent, Huawei | Padma.Sudarsan@alcatel-lucent.com, zoulan@huawei.com | SP#61 completed. Linked to Network Sharing UID_31018, SA1 22.951 (Service aspects and requirements for network sharing), SA2 23.251 (Network Sharing; Architecture) | 32.851
1005 | 560032 | Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | FS_SON-NM-CCO | 1 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-09-17 17:00 | 95% | SP-140028 | - | Ericsson | robert.petersen@ericsson.com | SP#64 completion 06/14=>09/14. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060) | 32.836 | SON
1006 | 580052 | Study on Alarm Management | FS_OAM_AM | 1 | Rel-12 | S5 | 2012-12-07 08:00 | 2013-09-11 17:00 | 100% | SP-120774 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#61 completed | 32.859
1007 | 580025 | Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests | FS_NNI_RS | 1 | Rel-12 | C3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | CP-130166 | - | Ericsson | Jan.Holm@ericsson.com | CP#64 completed | 24.802
1008 | 580026 | Study on Diameter Overload Control Mechanisms | FS_DOCME | 1 | Rel-12 | C4 | 2012-01-05 15:53 | 2014-09-12 17:00 | 90% | CP-120917 | - | Orange | lionel.morand@orange.com | CP#64 completion 06/14=>09/14. CP#63 TR 29.809 v100 for Information. Triggered by SA2 Rel-12 TR 23.843 Study on Core Network Overload solutions (FS_CNO) UID_490036. Coordinate with CT3, SA5 | 29.809
1009 | 590010 | Study on Review of dedicated 3GPP UICC features | FS_Red_UCe | 1 | Rel-12 | C6 | 2013-03-04 08:00 | 2014-09-12 17:00 | 50% | CP-130168 | - | BlackBerry | Ian Doig (IDoig@rim.com) | CP#64 completion 06/14=>09/14. Waiting for feedback from external organizations (PTCRB/PVG). | 31.901
1010 | 590011 | Study on XML based access of AF to the PCRF | FS_XML_AF_PCRF | 1 | Rel-12 | C3 | 2013-03-01 08:00 | 2014-06-13 17:00 | 100% | CP-130167 | - | Alcatel-Lucent | horst.brinkman@alcatel-lucent.com | CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications | 29.817
1011 | 610010 | Study on Technical aspects on Roaming End-to-end scenarios with VoLTE IMS and other networks | FS_REVOLTE_IMS | 1 | Rel-12 | C3 | 2013-09-09 08:00 | 2014-09-12 17:00 | 80% | CP-130774 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#64 completion 06/14=>09/14. TR 29.949v100 for Information. Document end-to-end use cases and signalling flows based on the roaming architecture for Voice over IMS with Local Breakout | 29.949
1012 | 620001 | Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME | FS_ISIM_CR | 1 | Rel-12 | C6 | 2013-12-09 08:00 | 2014-09-12 17:00 | 10% | CP-130812 | - | Gemalto | thierry.garnier@gemalto.com | CP#64 completion 06/14=>09/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage | 31.829
1013 | 620002 | Study on Shared Data Update for Multiple Subscribers | FS_SHARED_SubData_UPD | 1 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 70% | CP-130809 | - | Huawei | Susan Shi (susan.shishufeng@huawei.com) | CP#64 completion 06/14=>09/14 | 29.854
1014 | 460001 | Study on GERAN improvements for Machine-Type Communications | FS_NIMTC_GERAN | 1 | Rel-12 | G1,G2 | 2010-05-24 08:00 | 2012-11-23 17:00 | 100% | GP-092418 | - | Ericsson | paul.schliwa-bertling@ericsson.com | GP#56 completed. GP#44 approved WID | 43.868 | MTC, M2M
1015 | 490006 | Study on Solutions for GSM/EDGE BTS Energy Saving | FS_Energy_BTS | 1 | Rel-12 | G1,G2 | 2009-03-10 11:12 | 2014-08-29 17:00 | 90% | GP-101638 | - | NSN, Vodafone | juergen.hofmann@nsn.com, leo.patanapongpibul@vodafone.com | GP#63 completion 05/14=>08/14. GP#55 TR 45.926v100 for Information. GP#47 approved WID | 45.926
1016 | 520001 | Study on Voice services over Adaptive Multi-user channels on One Slot (VAMOS) enhancements | FS_eVAMOS | 1 | Rel-12 | GP,G2,G1 | 2010-10-27 15:16 | 2014-05-30 17:00 | 100% | GP-110991 | - | China Mobile, Huawei | Chao Luo (chluo@huawei.com), dengjuan@chinamobile.com | GP#62 completed. TR 43.801v100 for 1-step Approval. GP#50 approved WID. Triggered by Rel-8 TR 45.914 Study Multi-User-Reusing One Timeslot (MUROS) UID_50590 and Rel-9 VAMOS UID_420002 | 43.801
1017 | 520002 | Study on GERAN enhancements for Mobile Data Applications | FS_GERAN_eMDA | 1 | Rel-12 | G2,G1 | 2011-04-04 08:00 | 2014-08-29 17:00 | 80% | GP-110999 | - | Huawei | ming.fang@huawei.com | GP#62 TR 43.802v100 for Information. GP#50 approved WID (mobile coucou). Triggered by RAN#51 (Mar 2011) WID in RP-110454 (LTE RAN Enhancements for Diverse Data Applications) UID_510031 | 43.802
1018 | 500016 | Study on Inclusion of RF Pattern Matching Technologies as a positioning method in the E-UTRAN | FS_LCS_LTE_RFPMT | 1 | Rel-12 | R4 | 2010-12-10 08:00 | 2013-09-06 17:00 | 100% | RP-120885 | RP-131082 | Polaris Wireless | Scot Gordon (sgordon@polariswireless.com) | RP#61 completed. Linked to Rel-10 WI on Inclusion of RF Pattern Matching Technologies as a positioning method in the UTRAN (LCS_UMTS_RFPMT) UID_460005 | LTE 36.809
1019 | 530052 | Study on Provision of low-cost MTC UEs based on LTE | FS_LC_MTC_LTE | 1 | Rel-12 | R1,R2,R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-121441 | RP-130583 | Vodafone | prakash.bhat@vodafone.com | RP#60 completed | LTE 36.888 | MTC, M2M
1020 | 530054 | Deleted - Study on Mobile Relay for E-UTRA | FS_LTE_mobRelay | 1 | Rel-12 | R3,R1 | 2005-05-19 14:36 | 2014-06-23 17:00 | 100% | RP-131375 | RP-140726 | CATT | Haijing Hu (huhaijing@catt.cn) | RP#64 stopped at 80% completion | LTE 36.836
1021 | 570022 | Study on LTE FDD in the bands 1980-2010 MHz and 2170-2200 MHz | FS_LTE_1980_2170_Korea | 1 | Rel-12 | R4 | 2012-09-11 08:00 | 2014-09-12 17:00 | 80% | RP-140121 | RP-140680 | KT | Dongjun LEE (dj.lee@kt.com) | RP#64 completion 06/14=>09/14. Study only for Region 3 (so far) | LTE 36.861
1022 | 570023 | Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN | FS_LTE_SC_enh_req | 1 | Rel-12 | RP | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121418 | RP-121651 | China Mobile | Hai TANG (tanghai@chinamobile.com) | RP#58 completed. TR 36.932 v100 for Information and Approval | LTE 36.932 | Small cell
1023 | 580041 | Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects | FS_LTE_SC_enh_L1 | 1 | Rel-12 | R1,R2,R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-122032 | RP-131618 | Huawei | Elean Fan (fanxiaoan@huawei.com) | RP#62 completed. RP#61 TR 36.872v100 for 1-step approval. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023 | LTE 36.872 | Small cell
1024 | 580044 | Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects | FS_LTE_SC_enh_hilayer | 1 | Rel-12 | R2,R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-122033 | RP-131619 | NTT DOCOMO | Hideaki Takahashi (h-takahashi@nttdocomo.co.jp) | RP#62 completed. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023 | LTE 36.842 | Small cell
1025 | 580038 | Study on LTE Device-to-Device Proximity Services - Radio Aspects | FS_LTE_D2D_Prox | 1 | Rel-12 | R1,R2,R3,R4 | 2012-12-17 08:00 | 2014-03-06 17:00 | 100% | RP-122009 | RP-131730 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | RP#63 completed. TR 36.843 for 1-step approval (90% complete). Started normative work. Linked to Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) and Feature ProSe | LTE 36.843 | Public Safety (A-A)
1026 | 580042 | Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE | FS_LTE_3D_channel | 1 | Rel-12 | R1 | 2012-12-10 08:00 | 2014-09-12 17:00 | 60% | RP-130811 | RP-140658 | NSN | bishwarup.mondal@nsn.com | RP#64 completion 06/14=>09/14. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network | LTE 36.873
1027 | 580046 | Study on Energy Saving Enhancement for E-UTRAN | FS_Netw_Energy_enh_LTE | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122035 | RP-140604 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | RP#64 completed. Identify potential solutions for energy saving in E-UTRAN non-overlapping scenario. Evaluate possible enhancements in overlapping scenario, so that a subset can be used for further investigation/standardization | LTE 36.887
1028 | 590016 | Study on Expansion of LTE_FDD_1670_US to include 1670-1680MHz Band for LTE in the US | FS_LTE_FDD_1670_US | 1 | Rel-12 | R4 | 2013-03-01 08:00 | 2014-09-12 17:00 | 80% | RP-130202 | RP-140798 | LightSquared | masoud.olfat@lightsquared.com | RP#64 completion 06/14=>09/14 | LTE 36.844
1029 | 590017 | Study on Cell-specific Reference Signals (CRS) Interference Mitigation for homogenous deployments for LTE | FS_LTE_CRSIC | 1 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-131840 | RP-131623 | Ericsson | shaohua.li@ericsson.com | RP#62 completed. Updated WID RP-130393=>RP-131840 | LTE 36.863
1030 | 590018 | Study on Network-Assisted Interference Cancellation and Suppression for LTE | FS_LTE_NAICS | 1 | Rel-12 | R1,R4 | 2013-03-08 08:00 | 2014-03-06 17:00 | 100% | RP-130404 | RP-132108 | MediaTek | jeff.zhuang@mediatek.com | RP#63 completed. TR 36.866 (90% complete) for Approval. Started normative work | LTE 36.866
1031 | 600015 | Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul | FS_COMP_LTE_nibackhaul | 1 | Rel-12 | R1 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130847 | RP-131626 | Samsung | Hyojin Lee (hyojin257.lee@samsung.com) | RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332) | LTE 36.874
1032 | 600020 | Study on Positioning enhancements for E-UTRA | FS_LCSenh_LTE | 1 | Rel-13 | R4,R1 | 2013-04-25 14:36 | 2014-12-05 17:00 | 85% | RP-140667 | RP-140639 | Huawei | Jie Cui (cuijie@huawei.com) | RP#64 updated WID RP-130680=>RP-140667 (still only 3 supporting companies!). Completion 06/14=>12/14. Moved to Rel-13 | LTE 36.855
1033 | 610028 | Study on Group Communication for LTE | FS_LTE_GC | 1 | Rel-12 | R2,R3 | 2013-09-10 08:00 | 2014-03-06 17:00 | 100% | RP-131382 | RP-140182 | Alcatel-Lucent | chandrika.worrall@alcatel-lucent.com | RP#63 completed. Evaluate ability of LTE to meet public safety requirements agreed in SA for GC (GC is a key functionality of Land Mobile Radio/Private Mobile Radio and public safety systems) | LTE 36.868 | Public Safety (A-A)
1034 | 610029 | Study on Smart Congestion Mitigation in E-UTRAN | FS_SCM_LTE | 1 | Rel-12 | R2 | 2013-09-09 08:00 | 2014-03-06 17:00 | 100% | RP-132092 | RP-140102 | LG Electronics | youngdae.lee@lge.com | RP#63 completed | LTE 36.848
1035 | 620044 | Study on RAN aspects of RAN Sharing Enhancements for LTE | FS_RSE-RAN_LTE | 1 | Rel-12 | R3 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | RP-132116 | RP-140746 | NEC | Siva.Vakeesar@emea.nec.com | RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1) | LTE 36.856
1036 | 530056 | Study on RF and EMC requirements for active Antenna Array System (AAS) Base Station | FS_AAS_BS_LTE_UTRA | 1 | Rel-12 | R4,R1 | 2011-09-19 08:00 | 2013-03-01 17:00 | 100% | RP-111349 | RP-130124 | Huawei | Ronnie.zhang@huawei.com | RP#59 completed | UTRA, LTE 37.840
1037 | 550020 | Study on LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | FS_LTE_HRPD_SON | 1 | Rel-12 | R3 | 2012-03-02 08:00 | 2013-06-14 17:00 | 100% | RP-121982 | RP-130585 | China Telecom | Wu Jinlian (wujl@gsta.com) | RP#60 completed | UTRA, LTE 37.813 | SON
1038 | 550021 | Study on Passive InterModulation (PIM) handling for UTRA and LTE Base Stations | FS_BS_PIM | 1 | Rel-12 | R4,G1 | 2012-03-05 08:00 | 2013-09-06 17:00 | 100% | RP-120268 | RP-131076 | Ericsson | johan.skold@ericsson.com | RP#61 completed (Conclusion: no spin-off WI). Linked to Rel-10 WI on Multi-standard radio Base Station RF requirements for non-contiguous spectrum deployments (MSR_NC) UID_480025 | UTRA, LTE 37.808
1039 | 580045 | Study on WLAN/3GPP Radio Interworking | FS_UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-122038 | RP-131611 | Intel | sasha.sirotkin@intel.com | RP#62 completed. Evaluate LTE-WLAN/UTRA-WLAN i/w procedures while improving (non-)seamless mobility. Deployed WLAN often under-utilized; User experience suboptimal when UE connects to overloaded WLAN. | UTRA, LTE 37.834 | WLAN
1040 | 580047 | Study on RAN Enhancements for UMTS/HSPA and LTE Interworking | FS_HSPA_LTE_interworking | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-122036 | RP-131612 | China Unicom | Meng Zhang (zhangmeng68@chinaunicom.cn) | RP#62 completed. TR 37.852v100 for Information & Approval | UTRA, LTE 37.852
1041 | 580048 | Study on Next-Generation SON for UTRA and LTE | FS_UTRA_LTE_NG_SON | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122037 | RP-140747 | NSN | krzysztof.kordybach@nsn.com | RP#64 completed. The study of SON features for small cell functionality covered by the Rel-12 small cell enhancement SIs (e.g. dual connectivity) is not in the scope of this study item | UTRA, LTE 37.822 | SON
1042 | 580049 | Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | FS_UTRA_LTE_1980_2170_REG1 | 1 | Rel-12 | R4 | 2012-12-11 08:00 | 2014-09-12 17:00 | 99% | RP-140505 | RP-140620 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | RP#64 completion 06/14=>09/14. TR 37.846 v100 for 1-step approval. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1 | UTRA, LTE 37.846
1043 | 580050 | Study on Base Station specification structure | FS_BSspec_struc | 1 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-06-14 17:00 | 100% | RP-122039 | RP-130580 | Ericsson | johan.skold@ericsson.com | RP#60 completed (1-step approval). Study new BS spec structure to avoid duplicate work for new RF features (in case of identical features among different RATs); avoid future discussions on how to implement new features in single-RAT/multi-RAT specs | UTRA, LTE, MSR 37.810
1044 | 590032 | Study on RAN aspects of Machine Type and other mobile data applications Communications enhancements | FS_MTCe_RAN | 1 | Rel-12 | R2 | 2013-03-01 08:00 | 2013-09-06 17:00 | 100% | RP-130396 | RP-131081 | ZTE | sergio.parolari@zteitaly.com | RP#61 completed | UTRA, LTE 37.869 | MTC, M2M
1045 | 570024 | Study on UMTS heterogeneous networks | FS_UTRA_HetNet | 1 | Rel-12 | R1,R2,R3 | 2012-06-12 08:00 | 2013-09-06 17:00 | 100% | RP-121436 | RP-131606 | Huawei | carmela.cozzo@huawei.com | RP#62 completed | UTRA 25.800
1046 | 580039 | Study on Scalable UMTS FDD bandwidth | FS_UTRA_SCAL | 1 | Rel-12 | R1,R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130221 | RP-132035 | China Unicom | Han Xiao (hanxiao91@chinaunicom.cn) | RP#62 completed. TR 25.701v200 for Approval | UTRA TR 25.701
1047 | 620046 | Deleted - Study on Scalable UMTS FDD bandwidth by Filtering | FS_UTRA_SCAL_FILT | 1 | Rel-12 | R1 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-132122 | RP-140988 | China Unicom | Han Xiao (hanxiao91@chinaunicom.cn) | RP#64 stopped at 85% completion. Follow-up of Rel-12 Study on scalable UMTS FDD bandwidth (FS_UTRA_SCAL). The result is captured in the same TR 25.701 | UTRA TR 25.701
1048 | 580040 | Study on Dedicated Channel (DCH) enhancements for UMTS | FS_UTRA_DCHenh | 1 | Rel-12 | R1 | 2012-12-10 08:00 | 2013-09-06 17:00 | 100% | RP-130216 | RP-131073 | Qualcomm | Arjun Bharadwaj (arjunb@qti.qualcomm.com) | RP#61 completed | UTRA TR 25.702
1049 | 580043 | Study on Further Enhanced Uplink (EUL) enhancements | FS_EDCH_enh | 1 | Rel-12 | R2,R1,R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130347 | RP-131608 | Ericsson | alessandro.caverni@ericsson.com | RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.) | UTRA TR 25.700
1050 | 600018 | Study on HNB Emergency Warning Area for UTRA | FS_HNB_warn_area | 1 | Rel-12 | R3 | 2013-06-18 08:00 | 2014-03-06 17:00 | 100% | RP-131258 | RP-140129 | Alcatel-Lucent, Ip.access | Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com | RP#63 completed. TR 25.703 v100 for 1-step approval | UTRA TR 25.703 | HNB
1051 | 610027 | Study on Enhanced Broadcast of System Information | FS_UTRA_SIBenh | 1 | Rel-12 | R2,R1 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131386 | RP-131610 | Ericsson | martin.van.der.zee@ericsson.com | RP#62 completed. TR 25.704v100 for Information & Approval. Study need to add capacity to present SI Broadcast mechanism unchanged since R99 | UTRA TR 25.704
1052 | 0 | Release 11 Features | - | 1 | Rel-11 | SP,CP,GP,RP | 2013-06-02 10:00 | 2014-09-17 17:00 | 100% | - | - | - | - | - | -
1053 | 470051 | Advanced IP Interconnection of Services | IPXS | 1 | Rel-11 | S1,S2,C1,C3 | 2010-03-25 08:00 | 2012-09-12 17:00 | 100% | SP-100876 | - | Telefónica | chris.friel@O2.com | CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS) | -
1054 | 470052 | Stage 1 for Advanced IP Interconnection of Services | - | 2 | Rel-11 | S1 | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-100876 | - | Telefónica | chris.friel@O2.com | SP#53 completed | 22.101, 22.228
1055 | 500025 | Stage 2 for Advanced IP Interconnection of Services | - | 2 | Rel-11 | S2 | 2010-12-16 08:00 | 2011-12-14 17:00 | 100% | SP-100876 | - | Ericsson | fredrik.lindholm@ericsson.com | SP#54 completed | 23.228
1056 | 530004 | Stage 3 for Advanced IP Interconnection of Services | - | 2 | Rel-11 | C1,C3 | 2011-09-13 08:00 | 2012-09-12 17:00 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#58 completed | Stage 3
1057 | 530104 | CT1 part of Stage 3 for Advanced IP Interconnection of Services | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-12 17:00 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#58 completed | 24.229
1058 | 530204 | CT3 part of Stage 3 for Advanced IP Interconnection of Services | - | 3 | Rel-11 | C3 | 2011-09-13 08:00 | 2012-09-07 17:00 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#57 completed | 29.165
1059 | 480030 | System Improvements to Machine-Type Communications | SIMTC | 1 | Rel-11 | S1,S2,S5,C1,C3,C4,C6,R2,R3,R5 | 2009-12-10 08:00 | 2014-03-06 17:00 | 100% | SP-120848 | - | KPN | toon.norp@tno.nl | SP#58 completed. Updated WID SP-110877=>SP-120848. Enhancements to Rel-10 Feature UID_410031 (NIMTC) based on Rel-11 Study on enhancements to MTC | - | MTC, M2M
1060 | 480130 | Stage 1 for SIMTC | - | 2 | Rel-11 | S1 | 2010-06-10 08:00 | 2011-09-21 17:00 | 100% | SP-120848 | - | KPN | toon.norp@tno.nl | SP#53 completed. SP#57 added MTC definitions in 21.905 | 22.368, 21.905 (MTC definitions) | MTC, M2M
1061 | 480230 | TR on Stage 2 for SIMTC | - | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#57 completed. TR 23.888v200 for Approval. Was Rel-10 UID_450028 (TR on Stage 2 for NIMTC) | New TR 23.888 | MTC, M2M
1062 | 520021 | BB1: Stage 2 Reachability Aspects of SIMTC | SIMTC-Reach | 2 | Rel-11 | S2 | 2011-06-09 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed. SP#58 updated WID SP-110877=>S3-121111 (SA3 normative work on Security aspects of SIMTC incorporated in SA2 TS 23.682) | 23.221, New 23.368 | MTC, M2M
1063 | 520121 | Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7) | - | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | - | MTC, M2M
1064 | 520221 | On-line device trigger | - | 3 | Rel-11 | S2 | 2011-06-09 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed | New 23.682 | MTC, M2M
1065 | 520321 | MTC Addressing | - | 3 | Rel-11 | S2 | 2011-06-09 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 completed | 23.221, New 23.682 | MTC, M2M
1066 | 520421 | Identifiers – especially removal of MSISDN dependencies in the architecture | - | 3 | Rel-11 | S2 | 2011-06-09 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed | New 23.682 | MTC, M2M
1067 | 520521 | MSISDN-less / PS-Only | - | 3 | Rel-11 | S2 | 2011-06-13 08:00 | 2012-03-07 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#55 completed | 23.060, 23.272, New 23.682 | MTC, M2M
1068 | 540014 | MTC related interfaces and functional entities to support above features (MTCsp, etc.) | - | 3 | Rel-11 | S2 | 2011-12-14 08:00 | 2012-03-07 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#55 completed | New 23.682 | MTC, M2M
1069 | 530006 | BB1: Stage 3 (CS+PS) Reachability Aspects of SIMTC | - | 2 | Rel-11 | C1,C3,C4,C6 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | SP#58 completed | Stage 3 | MTC, M2M
1070 | 530106 | CT1 part of Stage 3 BB1: Reachability Aspects of SIMTC | - | 3 | Rel-11 | C1 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 23.040, 24.008, 24.301, 24.341, 24.368 | MTC, M2M
1071 | 530206 | CT3 part of Stage 3 BB1: Reachability Aspects of SIMTC | - | 3 | Rel-11 | C3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. TS 29.368 v200 for Approval | 29.061, New TS 29.368 | MTC, M2M
1072 | 530306 | CT4 part of Stage 3 BB1: Reachability Aspects of SIMTC | - | 3 | Rel-11 | C4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed | 23.003, 23.008, 29.002, 29.060, 29.230, New TS (29.336, 29.337) | MTC, M2M
1073 | 530406 | CT6 part of Stage 3 BB1: Reachability Aspects of SIMTC | - | 3 | Rel-11 | C6 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | ST Ericsson | Andrzej Winiarski | CP#57 completed | 31.102 | MTC, M2M
1074 | 530005 | Stage 2/3 for CS aspects for SIMTC | SIMTC-CS | 2 | Rel-11 | C4,C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. Updated WID CP-120418=>CP-120617 | Stage 2/3 | MTC, M2M
1075 | 530105 | Deleted - Stage 2 CS aspects for SIMTC | - | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-09-06 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 stopped | 23.012 | MTC, M2M
1076 | 530205 | Stage 3 CS aspects for SIMTC | - | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | Stage 3 | MTC, M2M
1077 | 530305 | CT1 part of Stage 3 CS aspects for SIMTC | - | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 24.008, 24.301 | MTC, M2M
1078 | 530405 | Deleted - CT6 part of Stage 3 CS aspects for SIMTC | - | 4 | Rel-11 | C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 stopped | 31.102 | MTC, M2M
1079 | 560002 | Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 2 | Rel-11 | C1,C4 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed | Stage 2/3 | MTC, M2M
1080 | 560102 | CT1 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | - | 3 | Rel-11 | C1 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 23.040, 24.008, 24.011, 24.301, 29.018, 29.118 | MTC, M2M
1081 | 560202 | CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | - | 3 | Rel-11 | C4 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed. TS 29.338 v200 for Approval | 23.003, 23.008, 23.012, 29.002, 29.272, 29.305, New TS 29.338 | MTC, M2M
1082 | 530009 | RAN overload control for Machine-Type Communications | SIMTC-RAN_OC | 2 | Rel-11 | R2,R3,C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | RP-111373 | - | Huawei | Jeff Gao (gaoyongqiang@huawei.com) | Stage 2,3. TSG#57 completed | UTRA, LTE | MTC, M2M
1083 | 530109 | Core part: RAN overload control for Machine-Type Communications | SIMTC-RAN_OC-Core | 3 | Rel-11 | R2,R3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-111373 | - | Huawei | Jeff Gao (gaoyongqiang@huawei.com) | RP#57 completed | 25.304, 25.331, 25.413, 36.304, 36.331, 36.413 | MTC, M2M
1084 | 530209 | Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN | - | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. Updated WID CP-120418=>CP-120617 | Stage 3 | MTC, M2M
1085 | 530309 | CT1 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN | - | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-06-15 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#56 completed | 23.122, 24.008, 24.301 | MTC, M2M
1086 | 530409 | CT6 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN | - | 4 | Rel-11 | C6 | 2011-09-20 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | ST Ericsson | Andrzej Winiarski | CP#57 completed | 31.102 | MTC, M2M
1087 | 610014 | Test part: System Improvements for Machine-Type Communications | SIMTC-UEConTest | 2 | Rel-11 | R5 | 2013-09-09 08:00 | 2014-03-06 17:00 | 100% | RP-140077 | RP-140075 | Ericsson | calle.hagenfeldt@ericsson.com | RP#63 completed. Updated WID RP-131341=>RP-140077 (added affected TS 36.508). Testing for core part: SIMTC-Reach, SIMTC-CS, SIMTC-PS_Only, SIMTC-RAN_OC | 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | MTC, M2M
1088 | 540019 | BB5: Charging of SIMTC (Stage 2/3) | SIMTC-CH | 2 | Rel-11 | S5 | 2011-12-07 08:00 | 2012-12-12 17:00 | 100% | SP-120848 | - | Ericsson | patrik.teppo@ericsson.com | SP#58 completed | 32.240, 32.251, 32.298, 32.299 | MTC, M2M
1089 | 520022 | Deleted - BB2: Stage 2 Signalling Optimizations of SIMTC | SIMTC-Sig | 2 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped. SP#58 updated WID SP-110877=>SP-120848 | TBD | MTC, M2M
1090 | 520122 | Deleted - Effectively maintain connectivity for a large number of MTC Devices (TS 22.368, 7.1.1) | - | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | MTC, M2M
1091 | 520222 | Deleted - Small Data Transmissions (TS 22.368, 7.2.5) | - | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | MTC, M2M
1092 | 530107 | Deleted - Stage 3 (CS+PS) Signalling Optimizations of SIMTC | - | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | CP#54 work stopped | Stage 3 | MTC, M2M
1093 | 530207 | Deleted - CT1 part of Stage 3 Signalling Optimizations of SIMTC | - | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | - | 23.122, 24.008, 24.301, 24.368 | MTC, M2M
1094 | 530307 | Deleted - CT6 part of Stage 3 Signalling Optimizations of SIMTC | - | 4 | Rel-11 | C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | ST Ericsson | Andrzej Winiarski | - | 31.102 | MTC, M2M
1095 | 520023 | Deleted - BB3: Stage 2 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 2 | Rel-11 | S2 | 2011-06-08 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | MTC, M2M
1096 | 520123 | Deleted - Charging Requirements (TS 22.368, 7.1.5) | - | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | MTC, M2M
1097 | 520223 | Deleted - Lower Power Consumption (TS 22.368, 7.1.1) | - | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | MTC, M2M
1098 | 520323 | Deleted - MTC Monitoring (TS 22.368, 7.2.8) | - | 3 | Rel-11 | S2 | 2011-06-08 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | MTC, M2M
1099 | 530008 | Deleted - Stage 3 (CS+PS) CN-based requirements and Power Considerations of SIMTC | - | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | CP#54 work stopped | Stage 3 | MTC, M2M
1100 | 530108 | Deleted - CT1 part of Stage 3 CN-based requirements and Power Considerations of SIMTC | - | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | - | 23.122, 24.008, 24.301, 24.368 | MTC, M2M
1101 | 530208 | Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC | - | 4 | Rel-11 | C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | ST Ericsson | Andrzej Winiarski | - | 31.101, 31.102 | MTC, M2M
1102 | 490028 | Deleted - TR on Security aspects of Machine-Type Communications | - | 2 | Rel-11 | S3 | 2009-12-10 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | Was Rel-10 UID_460023 (Security for NIMTC). SP#56 stopped (activity transferred to Rel-12 Feature MTCe under UID_560722). | New TR 33.868 | MTC, M2M
1103 | 540119 | Deleted - BB4: Secure Connection and Privacy of SIMTC | SIMTC-Sec | 2 | Rel-11 | S3 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe under UID_560522) | TBD | MTC, M2M
1104 | 520124 | Deleted - Secure Connection MTC Feature (TS 22.368, 7.2.10) | - | 3 | Rel-11 | S3 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe | TBD | MTC, M2M
1105 | 530058 | Deleted - MTC Location Privacy | SIMTC-Priv | 3 | Rel-11 | S3 | 2011-09-19 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe | TBD | MTC, M2M
1106 | 480330 | Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications | - | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#52 stopped | TBD | MTC, M2M
1107 | 480430 | Deleted - Stage 2 on Security part for System Improvements to Machine-Type Communications | - | 2 | Rel-11 | S3 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#52 stopped | TBD | MTC, M2M
1108 | 480031 | Unstructured Supplementary Service Data (USSD) simulation service in IMS | USSI | 1 | Rel-11 | S1,C1,C3 | 2010-06-10 08:00 | 2012-12-07 17:00 | 100% | SP-100408 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | CP#58 completed | -
1109 | 480131 | Stage 1 for USSD simulation service in IMS | - | 2 | Rel-11 | S1 | 2010-06-10 08:00 | 2010-06-10 08:00 | 100% | SP-100408 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | SP#48 completed. Specify a CS domain USSD like service over IMS (see GSM Mobile User Initiated USSD) | 22.173
1110 | 520003 | Stage 3 for USSD simulation service in IMS | - | 2 | Rel-11 | C1,C3 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | SP#58 completed. No stage 2 impact, as reuse existing IMS architecture in TS 23.228 | -
1111 | 520103 | CT1 part of Stage 3 for USSD simulation service in IMS | - | 3 | Rel-11 | C1 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at, TS 24.390 Rapp: lili.yang@huawei.com | CP#58 completed | 24.173, 24.229, new TS 24.390
1112 | 520203 | CT3 part of Stage 3 for USSD simulation service in IMS | - | 3 | Rel-11 | C3 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#57 completed | 29.165
1113 | 490031 | QoS Control Based on Subscriber Spending Limits | QoS_SSL | 1 | Rel-11 | S1,S2,S5,C3 | 2010-09-23 08:00 | 2012-06-20 17:00 | 100% | SP-110519 | - | Vodafone | mona.mustapha@vodafone.com | TSG#56 completed | -
1114 | 490131 | Stage 1 for QoS Control Based on Subscriber Spending Limits | - | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-110519 | - | Vodafone | mona.mustapha@vodafone.com | SP#53 completed. Use cases & service requirements to allow: 1) modification of QoS based on subscriber’s spending limits 2) enforcing of spending limits for roaming subscribers without having dedicated support in the visited network | 22.115
1115 | 510043 | Stage 2 for QoS Control Based on Subscriber Spending Limits | - | 2 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-110519 | - | Huawei | Xu Xia (xiatony@huawei.com) | SP#53 completed | 23.203
1116 | 500029 | Charging for QoS Control Based on Subscriber Spending Limits (Stage 2) | - | 2 | Rel-11 | S5 | 2010-12-16 08:00 | 2012-06-20 17:00 | 100% | SP-110519 | - | Nokia Siemens Networks, Huawei | Gerald.Goermer@nsn.com, shan.mingjun@huawei.com | SP#56 completed | 32.240, 32.296
1117 | 520004 | CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3) | QoS_SSL-CT3 | 2 | Rel-11 | C3 | 2011-06-03 08:00 | 2012-06-15 17:00 | 100% | CP-120203 | - | Huawei | QiaoWeihua@huawei.com | CP#56 completed | 29.212, 29.213, 29.214, 29.215, new TS 29.219
1118 | 490032 | Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 1 | Rel-11 | S1,S2 | 2010-09-23 08:00 | 2012-03-07 17:00 | 100% | SP-110347 | - | Vodafone | mona.mustapha@vodafone.com | SP#55 completed (Stage 2/3 specified under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021. Triggered by S1-102236/GSMA RILTE 10_007r1 (IREG LS_038 to 3GPP on Optimal Media Routing drawbacks) | -
1119 | 490132 | TR on Stage 2 aspects of Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | - | 2 | Rel-11 | S2 | 2010-09-23 08:00 | 2012-03-07 17:00 | 100% | SP-110347 | - | Vodafone | Susana.Sabater@vodafone.com | SP#55 completed | new TR 23.849
1120 | 490232 | Stage 1 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | - | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-110347 | - | Vodafone | mona.mustapha@vodafone.com | SP#53 completed | 22.115, 22.173, 22.228
1121 | 490332 | Deleted - Stage 2 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | - | 2 | Rel-11 | S2 | 2010-09-28 08:00 | 2012-03-07 17:00 | 100% | SP-110347 | - | Vodafone | Susana.Sabater@vodafone.com | SP#55 no normative work in SA2. Stage 2/3 to be done in under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021 | None
1122 | 530021 | Inclusion of Media Resource Broker (Stage 2/3) | MRB | 1 | Rel-11 | C1,C3,IETF | 2011-09-16 08:00 | 2013-06-14 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032 | Stage 2/3
1123 | 530121 | Stage 2 for Inclusion of Media Resource Broker | - | 2 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 23.218
1124 | 530221 | Stage 3 for Inclusion of Media Resource Broker | - | 2 | Rel-11 | C1,C3,IETF | 2011-09-16 08:00 | 2013-06-14 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#60 completed | -
1125 | 530321 | CT1 part of Stage 3 for Inclusion of Media Resource Broker | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 24.229, 29.165
1126 | 531005 | (IETF) Inclusion of Media Resource Broker [RFC 6917 (was draft-ietf-mediactrl-mrb)] | - | 3 | Rel-11 | C1-IETF | 2011-09-16 08:00 | 2013-06-14 17:00 | 100% | CP-120277 | - | Keith Drage | - | CP#60 completed | RFC 6917 (was draft-ietf-mediactrl-mrb)
1127 | 560003 | CT3 part of Stage 3 for Inclusion of Media Resource Broker | - | 3 | Rel-11 | C3 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 29.165
1128 | 500030 | Non Voice Emergency Services | NOVES | 1 | Rel-11 | S1,S2 | 2010-12-16 08:00 | 2012-03-07 17:00 | 100% | SP-100884 | - | Qualcomm | dwilliams@qualcomm.com | SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES) | -
1129 | 500130 | Stage 1 for Non Voice Emergency Services | - | 2 | Rel-11 | S1 | 2010-12-16 08:00 | 2011-09-21 17:00 | 100% | SP-100884 | - | Qualcomm | dwilliams@qualcomm.com | SP#53 completed | 22.101
1130 | 530045 | Stage 2 for Non Voice Emergency Services (Support of IMS Emergency Sessions with Other Media on UTRAN and E-UTRAN) | NOVES-IMSESOM | 2 | Rel-11 | S2 | 2011-09-22 08:00 | 2012-03-07 17:00 | 100% | SP-110644 | - | Alcatel-Lucent | Deb.Barclay@alcatel-lucent.com | SP#55 completed | 23.060, 23.167, 23.203, 23.401
1131 | 510047 | Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE | 1 | Rel-11 | S1,C1 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | SP-110176 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#53 Stage 1 completed. CP#59 completed. Triggered by Rel-11 TR 22.809 Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX (FS_VINE) UID_480033 | -
1132 | 510147 | Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX | - | 2 | Rel-11 | S1 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-110176 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#53 completed | 22.228
1133 | 530010 | Stage 2/3 for Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE-CT1 | 2 | Rel-11 | C1 | 2011-09-20 08:00 | 2013-03-01 17:00 | 100% | CP-110641 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#59 completed | 23.218, 24.229
1134 | 520028 | Anonymous Call Rejection in the CS domain | ACR_CS | 1 | Rel-11 | S1,C4,C3 | 2011-06-07 08:00 | 2011-12-02 17:00 | 100% | SP-110421 | - | Alcatel-Lucent | Betsy.Covell@alcatel-lucent.com | CP#54 completed | -
1135 | 520128 | Stage 1 for Anonymous Call Rejection in the CS domain | - | 2 | Rel-11 | S1 | 2011-06-07 08:00 | 2011-06-08 17:00 | 100% | SP-110421 | - | Alcatel-Lucent | Betsy.Covell@alcatel-lucent.com | SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013) | 22.004, 22.081, 22.082, 22.085, 22.088
1136 | 530011 | Core Network aspects of Anonymous Call Rejection in the CS domain | ACR_CS-CN | 2 | Rel-11 | C4,C3 | 2011-09-14 08:00 | 2011-12-02 17:00 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#54 completed | Stage 2/3
1137 | 530111 | CT4 part of Core Network aspects of Anonymous Call Rejection in the CS domain (Stage 2/3) | - | 3 | Rel-11 | C4 | 2011-09-14 08:00 | 2011-12-02 17:00 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#54 completed | 23.018, 23.081, 23.082, 23.085, 23.088, 23.205, 23.231, 24.088, 29.002, 29.011
1138 | 530211 | CT3 part of Core Network aspects of Anonymous Call Rejection in the CS domain (Stage 3) | - | 3 | Rel-11 | C3 | 2011-09-14 08:00 | 2011-09-16 17:00 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#53 completed | 29.163, 29.292
1139 | 460026 | Support for BroadBand Forum Accesses Interworking | BBAI | 1 | Rel-11 | S2,S1,C1,C3,C4,IETF | 2009-12-10 08:00 | 2012-12-12 17:00 | 100% | SP-120539 | - | Ericsson | peter.bleckert@ericsson.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses) | - | HNB, WLAN
1140 | 460126 | Stage 1 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | - | 2 | Rel-11 | S1 | 2009-12-10 08:00 | 2010-03-25 17:00 | 100% | SP-120539 | - | Ericsson | Olle.Eriksson@ericsson.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#47 completed. Provide service requirements for supporting interworking between 3GPP EPS and the fixed broadband accesses defined by BBF | 22.278 CR#0058 | HNB, WLAN
1141 | 470022 | TR on Stage 2 for BBAI | - | 2 | Rel-11 | S2 | 2010-03-26 08:00 | 2012-06-20 17:00 | 100% | SP-120539 | - | Ericsson | marco.spini@huawei.com | TR 23.839 not Approved in Rel-11; progressed in Rel-12 under P4C-TI (UID_560824) | new TR 23.839 | HNB, WLAN
1142 | 470023 | Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | - | 2 | Rel-11 | S2 | 2010-03-26 08:00 | 2012-06-20 17:00 | 100% | SP-120539 | - | Ericsson | stefan.rommer@ericsson.com | SP#56 completed | 23.203, new 23.139 | HNB, WLAN
1143 | 541001 | (IETF) Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | - | 2 | Rel-11 | S2-IETF | 2011-12-12 08:00 | 2012-12-12 17:00 | 100% | SP-120539 | - | Lionel Morand | Lionel Morand | Solved by IANA-registration. No RFC needed | - | HNB, WLAN
1144 | 530012 | Stage 3 BB I - Core Network impacts: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 2 | Rel-11 | C1,C3,C4 | 2011-09-16 08:00 | 2012-12-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#58 completed | Stage 3 | HNB, WLAN
1145 | 530112 | TR on Stage 3 BB I for BBAI; UE to network protocols | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-06-15 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#56 completed. Identify additional FMC specific procedures in addition to those in 24.302 (on access authentication & authorization and tunnel management; IP mobility mode selection; security aspects) | new TR 24.820 | HNB, WLAN
1146 | 550005 | TR on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface | - | 3 | Rel-11 | C4 | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#56 completed | new TR 29.839 | HNB, WLAN
1147 | 551002 | Deleted - (IETF) on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface | - | 3 | Rel-11 | C4-IETF | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120419 | - | Lionel Morand | - | Draft removed from 3GPP documentation | draft-so-ipsecme-ikev2-cpext | HNB, WLAN
1148 | 530212 | CT1 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#57 completed | 24.229, new TS 24.139 | HNB, WLAN
1149 | 530312 | CT3 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | - | 3 | Rel-11 | C3 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#57 completed | 29.212, 29.213, 29.215 | HNB, WLAN
1150 | 530412 | CT4 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | - | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-12-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#58 completed | 23.008, 29.273, 29.274, new TS 29.139 | HNB, WLAN
1151 | 490026 | Stage 1 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | - | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-120419 | - | Ericsson | Olle.Eriksson@ericsson.com | SP#53 completed | 22.278 | HNB, WLAN
1152 | 470024 | Stage 2 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | - | 2 | Rel-11 | S2 | 2010-09-28 08:00 | 2012-06-20 17:00 | 100% | SP-120419 | - | Ericsson | stefan.rommer@ericsson.com | SP#56 completed | 23.203, 23.401, 23.402, 23.139 | HNB, WLAN
1153 | 530013 | Stage 3 BB II - Core Network impacts: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 2 | Rel-11 | C3,C1,C4 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | Stage 3 | HNB, WLAN
1154 | 530113 | TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-06-15 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#56 completed | 24.820 | HNB, WLAN
1155 | 530213 | CT1 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | new TS 24.320 | HNB, WLAN
1156 | 530313 | CT3 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | - | 3 | Rel-11 | C3 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | 29.212, 29.213, 29.215 | HNB, WLAN
1157 | 530413 | CT4 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | - | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#55 completed | 23.008, 29.273 | HNB, WLAN
1158 | 490027 | Deleted - Stage 1 BB III: BBF convergence and network based mobility | - | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-120539 | - | Huawei | Amar Deol (adeol@huawei.com) | SP#57 stopped. Updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#53 completed | 22.278 | HNB, WLAN
1159 | 470025 | Deleted - Stage 2 BB III: BBF convergence and network based mobility | - | 2 | Rel-11 | S2 | 2010-09-28 08:00 | 2012-03-07 17:00 | 100% | SP-120539 | - | Huawei | marco.spini@huawei.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#55 stopped | 23.203, 23.401, 23.402, 23.139 | HNB, WLAN
1160 | 530014 | Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility | BBAI_BBIII-CT | 2 | Rel-11 | C3,C1,C4 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | Stage 3 | HNB, WLAN
1161 | 530114 | Deleted - TR on Stage 3 BB III for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | new TR 24.820 | HNB, WLAN
1162 | 530214 | Deleted - CT1 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | TBD | HNB, WLAN
1163 | 530314 | Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C3 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | 29.212, 29.213, 29.215 | HNB, WLAN
1164 | 530414 | Deleted - CT4 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | 23.008, 29.273 | HNB, WLAN
1165 | 480035 | Single Radio Voice Call Continuity (SRVCC) aspect of enhancements for Multimedia Priority Service | eMPS_SRVCC | 1 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#54 completed. Analyze and if needed specify mechanisms for the priority handling of SRVCC with regard to LTE/EPC | Stage 2 | Public Safety (I-A)
1166 | 480135 | TR on SRVCC for eMPS | - | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#52 completed | new TR 23.854 | Public Safety (I-A)
1167 | 480235 | Stage 2 on SRVCC for eMPS | - | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#54 completed | 23.216, 23.237 | Public Safety (I-A)
1168 | 500026 | Single Radio Video Call Continuity for 3G-CS | vSRVCC | 1 | Rel-11 | S2,C1,C3,C4 | 2010-10-15 08:00 | 2012-06-15 17:00 | 100% | SP-100704 | - | Samsung | xiaowan.ke@samsung.com | CP#56 completed. Provide Single Radio VIDEO Call Continuity from E-UTRAN to UTRAN-CS based on the agreed architecture alternative in TR 23.886 | -
1169 | 500126 | Stage 2 for Single Radio Video Call Continuity for 3G-CS | - | 2 | Rel-11 | S2 | 2010-10-15 08:00 | 2011-09-21 17:00 | 100% | SP-100704 | - | Samsung | xiaowan.ke@samsung.com | SP#53 completed. Triggered by Feasibility Study on video call handover capability in TR 23.886 UID_470048 Study on Single Radio Video Call Continuity for 3G-CS (FS_vSRVCC) | 23.203, 23.216, 23.237
1170 | 520005 | CN aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 2 | Rel-11 | C1,C3,C4 | 2011-06-03 08:00 | 2012-06-15 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | Stage 3. CP#56 completed | -
1171 | 520105 | CT1 aspects of Single Radio Video Call Continuity for 3G-CS | - | 3 | Rel-11 | C1 | 2011-06-03 08:00 | 2012-06-15 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#56 completed | 24.008, 24.237, 24.301
1172 | 520205 | CT3 aspects of Single Radio Video Call Continuity for 3G-CS | - | 3 | Rel-11 | C3 | 2011-06-03 08:00 | 2011-12-02 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#54 completed | 29.211, 29.212, 29.213, 29.215
1173 | 520305 | CT4 aspects of Single Radio Video Call Continuity for 3G-CS | - | 3 | Rel-11 | C4 | 2011-06-03 08:00 | 2011-12-02 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#54 completed | 29.280
1174 | 480038 | Network-provided Location information for IMS (NETLOC) | NWK-PL2IMS | 1 | Rel-11 | S2,S1,S5,C3,C4,C1 | 2010-06-10 08:00 | 2013-03-01 17:00 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging. | -
1175 | 500027 | Stage 1 for Network-provided Location information for IMS | - | 2 | Rel-11 | S1 | 2010-12-15 08:00 | 2011-09-21 17:00 | 100% | - | - | n/a | n/a | SP#53 completed | 22.115
1176 | 480138 | TR on Stage 2 for Network-provided Location information for IMS | - | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | SP#54 completed | new TR 23.842
1177 | 480238 | Stage 2 for Network-provided Location information for IMS | - | 2 | Rel-11 | S2 | 2010-06-15 08:00 | 2012-03-07 17:00 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | SP#55 completed | 23.060, 23.203, 23.228, 23.401
1178 | 490029 | Charging for Network-provided Location information for IMS | NWK-PL2IMS_CH | 2 | Rel-11 | S5 | 2010-09-23 08:00 | 2012-09-12 17:00 | 100% | SP-110700 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#57 completed | Stage 2 (32.240, 32.260), Stage 3 (32.298, 32.299)
1179 | 550008 | CT aspects of Network-provided Location information for IMS (Stage 3) | NWK-PL2IMS_CT | 2 | Rel-11 | C3,C4,C1 | 2012-03-02 08:00 | 2013-03-01 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | Stage 3 | -
1180 | 550108 | CT3 part of CT aspects of Network-provided Location information for IMS | - | 3 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-09-07 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed | 29.212, 29.214, 29.215
1181 | 550208 | CT4 part of CT aspects of Network-provided Location information for IMS | - | 3 | Rel-11 | C4 | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#56 completed | 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.305, 29.328, 29.329
1182 | 550308 | CT1 part of CT aspects of Network-provided Location information for IMS | - | 3 | Rel-11 | C1 | 2012-03-02 08:00 | 2013-03-01 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#59 completed | 24.229, 24.292
1183 | 500032 | Service Awareness and Privacy Policies | SAPP | 1 | Rel-11 | S2,S1,C3 | 2010-10-12 15:48 | 2011-12-02 17:00 | 100% | SP-100882 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | CP#54 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047 | -
1184 | 500132 | Stage 1 for Service Awareness and Privacy Policies | - | 2 | Rel-11 | S1 | 2010-10-12 15:48 | 2010-12-15 17:00 | 100% | SP-100882 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | For deep packet inspection (i.e. Traffic Detection Functionality) SA1 indicated that no new requirements are needed (see Objective of FS_PP SA1,SA2 Rel-10 Study on Policy solutions and enhancements UID_440047 TR 23.813) | -
1185 | 500232 | Stage 2 for Service Awareness and Privacy Policies | - | 2 | Rel-11 | S2 | 2010-10-15 08:00 | 2011-09-21 17:00 | 100% | SP-100882 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | SP#53 completed | 23.203
1186 | 510003 | CT3 part of Service Awareness and Privacy Policies | SAPP-CT3 | 2 | Rel-11 | C3 | 2011-03-18 08:00 | 2011-12-02 17:00 | 100% | CP-110136 | - | Allot Communications | Alla Goldner (agoldner@allot.com) | CP#54 completed. Stage 3 to support Application Detection and Control Functionality. Update Gx / introduce Sd reference points and procedures. Update S9 reference point in roaming scenarios | 29.212, 29.213, 29.214, 29.215
1187 | 500033 | VPLMN Autonomous CSG Roaming | VCSG | 1 | Rel-11 | S2,C4 | 2010-10-15 08:00 | 2011-12-14 17:00 | 100% | SP-100706 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#56 completed. Linked to Rel-10 UID_450053 Enhanced Home NodeB / eNodeB (EHNB). Implements Rel-9 requirements for CSG support in SA1 TS 22.220 | -
1188 | 500133 | Stage 2 for VPLMN Autonomous CSG Roaming | - | 2 | Rel-11 | S2 | 2010-10-15 08:00 | 2011-12-14 17:00 | 100% | SP-100706 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#54 completed | 23.002, 23.060, 23.401
1189 | 530017 | CT aspects of VPLMN Autonomous CSG Roaming | VCSG-St3 | 2 | Rel-11 | C4 | 2011-12-07 08:00 | 2011-12-07 08:00 | 100% | CP-120196 | - | ZTE | Fei Lu (lu.fei1@zte.com.cn) | CP#57 completed | 23.003, 23.007, 23.008, 23.012, 29.002, 29.230, 29.272
1190 | 510048 | Data Identification in Access Network Discovery and Selection Function (ANDSF) | DIDA | 1 | Rel-11 | S2,C1 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions | Stage 2/3
1191 | 510148 | TR on Stage 2 for Data Identification in ANDSF | - | 2 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#54 completed | New TR 23.855
1192 | 510248 | Stage 2 for Data Identification in ANDSF | - | 2 | Rel-11 | S2 | 2011-03-24 08:00 | 2012-03-07 17:00 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#55 completed | 23.402
1193 | 550003 | CT aspects of Data Identification in Access Network Discovery and Selection Function (ANDSF) Stage 3 | DIDA-CT | 2 | Rel-11 | C1 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120089 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#58 completed | 24.302, 24.312
1194 | 510050 | LOcation-Based Selection of gaTEways foR WLAN | LOBSTER | 1 | Rel-11 | S2,C4 | 2011-03-23 08:00 | 2012-06-15 17:00 | 100% | SP-110752 | - | ZTE | zhu.chunhui@zte.com.cn | CP#56 completed. Related to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP). Enhancements to ePDG and PDN GW selection functions for S2b and S2c based on UE location | - | WLAN
1195 | 510150 | Stage 2 for LOcation-Based Selection of gaTEways foR WLAN | - | 2 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110752 | - | ZTE | zhu.chunhui@zte.com.cn | SP#54 completed | 23.402 | WLAN
1196 | 540010 | CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | Stage 3. CP#56 completed | Stage 3 | WLAN
1197 | 540110 | CT4 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN | - | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | CP#56 completed | 29.273 | WLAN
1198 | 540210 | Deleted - CT1 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN | - | 3 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | CP#56 stopped | 24.302 | WLAN
1199 | 530001 | Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC | 1 | Rel-11 | S2,C1,C3,C4,G2,R2,R3,R5 | 2011-09-12 08:00 | 2014-12-05 17:00 | 93% | SP-110475 | - | Orange | antoine.mouquet@orange-ftgroup.com | Stage 1 in Rel-8 TS 22.278 clause 7.1.4.2. Triggered by Rel-11 TR 23.885 Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (FS_rSRVCC) UID_460030 | -
1200 | 530101 | Stage 2 for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | - | 2 | Rel-11 | S2 | 2011-09-22 08:00 | 2012-06-20 17:00 | 100% | SP-110475 | - | Orange | antoine.mouquet@orange-ftgroup.com | SP#56 completed | 23.216, 23.237
1201 | 530201 | CT aspects for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3) | rSRVCC-CT | 2 | Rel-11 | C1,C3,C4 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | Stage 3
1202 | 530301 | CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 23.009, 24.008, 24.229, 24.237, 24.292, 24.301
1203 | 530401 | CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | - | 3 | Rel-11 | C3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 29.165, 29.292
1204 | 530501 | CT4 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | - | 3 | Rel-11 | C4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 23.003, 23.008, 29.002, 29.230, 29.272, 29.280, 29.303, 29.305, 29.328
1205 | 530601 | GERAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3) | rSRVCC-GERAN | 2 | Rel-11 | G2 | 2011-09-12 08:00 | 2013-06-28 08:48 | 100% | GP-111290 | - | ZTE | li.jing4@zte.com.cn | GP#60 completed. GP#51 approved WID | 44.018, 48.008
1206 | 530701 | UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-RAN_UTRA | 2 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111334 | - | Huawei | liwei.qiu@huawei.com | RP#58 completed | UTRA
1207 | 530801 | Core part: UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-RAN_UTRA-Core | 3 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111334 | RP-121553 | Huawei | liwei.qiu@huawei.com | RP#58 completed | 25.331, 25.401, 25.413
1208 | 640012 | Test part: Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-UEConTest | 2 | Rel-11 | R5 | 2014-06-13 08:00 | 2014-12-05 17:00 | 0% | RP-140960 | - | Ericsson | calle.hagenfeldt@ericsson.com | Testing for core part: rSRVCC-CT and rSRVCC-RAN_UTRA-Core | 36.508, 36.523-1, 36.523-2, 36.523-3
1209 | 530046 | S2a Mobility based On GTP and WLAN access to EPC | SaMOG_WLAN | 1 | Rel-11 | S2,C4,C1,C3,IETF | 2011-09-22 08:00 | 2014-03-05 17:00 | 100% | SP-110642 | - | ZTE | Chunhui Zhu (zhu.chunhui@zte.com.cn) | Triggered by Rel-11 TR 23.852 FS_SaMOG UID_510061, Rel-8 UID_350027 SAE for support for non-3GPP accesses (defines PMIP-S2a) | Stage 2/3 | WLAN
1210 | 530146 | Stage 2 for S2a Mobility based On GTP and WLAN access to EPC | - | 2 | Rel-11 | S2 | 2011-09-22 08:00 | 2012-03-07 17:00 | 100% | SP-110642 | - | ZTE | zhu.chunhui@zte.com.cn | SP#55 completed | 23.002, 23.203, 23.402 | WLAN
1211 | 540011 | CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 2 | Rel-11 | C4,C1,C3,IETF | 2011-12-02 08:00 | 2014-03-05 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | Stage 3 | WLAN
1212 | 540111 | CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | - | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#57 completed | 23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303 | WLAN
1213 | 561010 | (IETF) CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | - | 3 | Rel-11 | C4-IETF | 2012-04-23 08:00 | 2014-03-05 17:00 | 100% | CP-110802 | - | Lionel Morand | - | CP#63 Draft removed from 3GPP documentation | draft-ietf-radext-ieee802ext | WLAN
1214 | 540211 | Deleted - CT1 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | - | 3 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#56 stopped (no CT1 impact) | 24.302 | WLAN
1215 | 540311 | CT3 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | - | 3 | Rel-11 | C3 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#56 completed | 29.212, 29.213, 29.215 | WLAN
1216 | 540029 | Roaming Architecture for Voice over IMS with Local Breakout | RAVEL | 1 | Rel-11 | S2,S5,C1,C3 | 2011-11-28 17:00 | 2012-12-07 17:00 | 100% | SP-110885 | - | Deutsche Telekom | michele.zarri@telekom.com | CP#58 completed. Triggered by Rel-11 TR 23.850 Study on Roaming Architecture for Voice over IMS with Local Breakout (FS_RAVEL). GSMA CPWP LS_in S5-102806 asked 3GPP SA5 to check if CS voice charging principles also apply to voice over IMS | Stage 2/3
1217 | 540129 | Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout | - | 2 | Rel-11 | S2 | 2011-11-28 17:00 | 2011-12-14 17:00 | 100% | SP-110885 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#54 completed | 23.002, 23.228
1218 | 540030 | Charging for Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CH | 2 | Rel-11 | S5 | 2011-12-14 08:00 | 2012-09-12 17:00 | 100% | SP-110886 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | Stage 2/3. SP#57 completed | 32.240, 32.260, 32.298, 32.299
1219 | 550004 | CT aspects of Roaming Architecture for Voice over IMS with Local Breakout (Stage 3) | RAVEL-CT | 2 | Rel-11 | C1,C3 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | Stage 3
1220 | 550104 | CT1 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout | - | 3 | Rel-11 | C1 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | 24.229, 24.292, 24.237
1221 | 550204 | CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout | - | 3 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | 29.165, 29.162, 29.079
1222 | 560027 | IMS Overload Control | IOC | 1 | Rel-11 | S2,C1,C3,IETF | 2012-06-18 08:00 | 2014-12-05 17:00 | 77% | SP-120273 | - | Orange, China Mobile | Antoine MOUQUET, YU Qing | SP#57 Stage 2 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. Linked to UID_410041 Study on IMS Evolution (TR 23.812). Solutions from IETF SOC WG and existing 3GPP procedures to be re-used if possible & backward compatibility ensured | Stage 2/3
1223 | 560127 | Stage 2 for IMS Overload Control | - | 2 | Rel-11 | S2 | 2012-06-18 08:00 | 2012-09-12 17:00 | 100% | SP-120273 | - | Orange, China Mobile | antoine.mouquet@orange-ftgroup.com, YU Qing | SP#57 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. | 23.228
1224 | 570007 | Stage 3 for IMS Overload Control | - | 2 | Rel-11 | C1,C3,IETF | 2012-09-05 08:00 | 2014-12-05 17:00 | 75% | CP-120561 | - | Alcatel-Lucent | Keith Drage | - | -
1225 | 570107 | CT1 part of Stage 3 for IMS Overload Control | - | 3 | Rel-11 | C1 | 2012-09-05 08:00 | 2012-12-07 17:00 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | CP#58 completed | 24.229
1226 | 570207 | CT3 part of Stage 3 for IMS Overload Control | - | 3 | Rel-11 | C3 | 2012-09-05 08:00 | 2012-12-07 17:00 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | CP#58 completed | 29.165
1227 | 571001 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control) | - | 3 | Rel-11 | C1-IETF,C3-IETF | 2013-07-29 08:00 | 2014-12-05 17:00 | 75% | CP-120561 | - | Keith Drage | Keith Drage | in RFC Ed-queue | draft-ietf-soc-overload-control
1228 | 571002 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-rate-control) | - | 3 | Rel-11 | C1-IETF,C3-IETF | 2013-07-29 08:00 | 2014-12-05 17:00 | 50% | CP-120561 | - | Keith Drage | Keith Drage | Not completed internet-draft | draft-ietf-soc-overload-rate-control
1229 | 571003 | (IETF) CT part of Stage 3 for IMS Overload Control (RFC 7200) | - | 3 | Rel-11 | C1-IETF,C3-IETF | 2013-07-29 08:00 | 2014-06-13 17:00 | 100% | CP-120561 | - | Keith Drage | Keith Drage | CP#64 completed | RFC 7200 (was draft-ietf-soc-load-control-event-package)
1230 | 520030 | Rel-11 Security small Enhancements | SEC11 | 1 | Rel-11 | S3 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | - | - | - | - | SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature | -
1231 | 520032 | Lawful Interception in the 3GPP Rel-11 | LI11 | 1 | Rel-11 | S3 | 2011-06-10 08:00 | 2012-06-20 17:00 | 100% | SP-110424 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | Stage 1/2/3. SP#56 completed | 33.106, 33.107, 33.108
1232 | 440055 | ZUC EEA3 and EIA3 (new Encryption & Integrity EPS security Algorithms) | EEA3_EIA3 | 1 | Rel-11 | S3,R5 | 2009-06-04 08:00 | 2012-09-07 17:00 | 100% | SP-090457 | - | CATR | Yuan Qi (yuanqi@catr.cn) | RP#57 completed testing | -
1233 | 440155 | ZUC EEA3 and EIA3 | - | 2 | Rel-11 | S3 | 2009-06-04 08:00 | 2011-12-14 17:00 | 100% | SP-090457 | - | CATR | Yuan Qi (yuanqi@catr.cn) | SP#53 completed new EPS algorithms e.g. for China | 33.401, New (35.221, 35.222, 35.223, 35.924)
1234 | 560009 | Conformance Test Aspects – ZUC (EEA3 and EIA3 Encryption & Integrity EPS security Algorithms) | EEA3_EIA3_UEConTest | 2 | Rel-11 | R5 | 2012-06-18 08:00 | 2012-09-07 17:00 | 100% | RP-120631 | RP-120968 | CATR | Ms Jun Chen (chenjun@catr.cn) | RP#57 completed. Testing for SA3 TSs 33.401, new (35.221, 35.222, 35.223) | 36.523-1, 36.523-2, 36.523-3
1235 | 480039 | Specification of Protection against Unsolicited Communication for IMS (produced TR-only) | SPUCI | 1 | Rel-11 | S3 | 2010-06-10 08:00 | 2012-03-07 17:00 | 100% | SP-100428 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#55 completed (No normative work). TR 33.838v200 for Approval & abandoned new TS 33.237. Continuation of Rel-9 UID_410027/410029. Builds on TR 33.937 Study of Mechanisms for PUCI | New TR 33.838, abandoned New TS 33.237
1236 | 510053 | H(e)NB security features for UE mobility scenarios (Stage 2) | HNB_mob_Sec | 1 | Rel-11 | S3 | 2011-03-23 08:00 | 2012-03-07 17:00 | 100% | SP-110025 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#55 completed. Add HeNB Security extensions to Extended H(e)NB Features (EHNBF) UID_450053 | 33.320 | HNB
1237 | 540012 | Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials | GBA-ext | 1 | Rel-11 | S3,C4,C1 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | SP-110884 | - | Nokia | Silke.Holtmanns@nokia.com | Stage 2/3. CP#57 completed | -
1238 | 540112 | Stage 2 for GBA extensions for re-use of SIP Digest credentials | - | 2 | Rel-11 | S3 | 2011-12-14 08:00 | 2012-03-07 17:00 | 100% | SP-110884 | - | Nokia | Silke.Holtmanns@nokia.com | SP#55 completed | 33.220
1239 | 540212 | Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 2 | Rel-11 | C4,C1 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | Stage 3
1240 | 540312 | CT4 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials | - | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 29.109
1241 | 540412 | CT1 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials | - | 3 | Rel-11 | C1 | 2011-12-05 08:00 | 2012-09-07 17:00 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 24.109
1242 | 520033 | Extensions of Acoustic Test Specifications in TS 26.131 and TS 26.132 | Ext_ATS | 1 | Rel-11 | S4 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-110309 | - | Orange, Qualcomm | stephane.ragot@orange-ftgroup.com, Andre Schevciw (aschevci@qualcomm.com) | SP#57 completed | 26.131, 26.132
1243 | 530048 | Enhancements to Multimedia: PSS, MMS, and MBMS Enhancements and Performance Improvements | EMM | 1 | Rel-11 | S4 | 2011-09-07 08:00 | 2013-03-06 17:00 | 100% | SP-120025 | - | Qualcomm | Nikolai Leung (nleung@qualcomm.com) | Stage 3. SP#59 completed | 26.140, 26.234, 26.247, New TR 26.951=>26.851
1244 | 530148 | Enhancement to FEC for MBMS | EMM-EFEC | 2 | Rel-11 | S4 | 2011-09-21 08:00 | 2013-03-06 17:00 | 100% | SP-120182 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#59 completed | 26.346, new TR 26.947
1245 | 530248 | Download Delivery Enhancements for MBMS | EMM-DDE | 2 | Rel-11 | S4 | 2011-09-21 08:00 | 2012-12-12 17:00 | 100% | SP-120025 | - | Qualcomm | Nikolai Leung (nleung@qualcomm.com) | SP#58 completed | 26.346, new TR 26.951=>26.851
1246 | 530348 | IMS-based PSS and MBMS Streaming Synchronization Enhancements | EMM-IPME | 2 | Rel-11 | S4 | 2011-09-07 08:00 | 2012-09-12 17:00 | 100% | SP-120025 | - | InterDigital Communications | hang.liu@interdigital.com | SP#58 completed | 26.237, new TR 26.951=>26.851
1247 | 560041 | Mobile 3D Video Coding | M3DV | 1 | Rel-11 | S4 | 2012-06-07 08:00 | 2012-09-12 17:00 | 100% | SP-120229 | - | Orange | gilles.teniou@orange.com | SP#57 completed. Triggered by UID_520036 Rel-11 Study on Mobile 3D Video Coding (FS_M3DVC) TR 26.905. | 26.140, 26.234, 26.244, 26.245, 26.247, 26.346, 26.430, 26.905
1248 | 510051 | Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM11 | 1 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-06 17:00 | 100% | - | - | - | - | OAM11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI | -
1249 | 510151 | Rel-11 Network Infrastructure Management | OAM11-NIM | 2 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-06 17:00 | 100% | - | - | - | - | - | -
1250 | 510056 | IRP framework enhancements to support Management of Converged Networks | OAM-FMC-IRP | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-06 17:00 | 100% | SP-120652 | - | Nokia Siemens Networks, Ericsson | thomas.tovinger@ericsson.com, olaf.pollakowski@nsn.com | SP#59 completed. Triggered by SA5 Studies TR 32.833, 32.828, 32.831 | 32.101/103/150, new (28.620/621/622/623/624/625/626/627/628/629/631/632/633/651/652/653/654/655/656/657/658/659/661/662/663/671/672/673/674/675/676/701/702/703/704/705/706/707/708/709/731/732/733/734/735/736/751/752/753, 32.107/156/157/853/854
1251 | 510251 | Rel-11 Performance Management | OAM11-PM | 2 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-12-12 17:00 | 100% | - | - | - | - | - | -
1252 | 510057 | IMS Performance Management enhancements | OAM-ePM-IMS | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-03-07 17:00 | 100% | SP-110134 | - | ZTE | guo.wenjie1@zte.com.cn | SP#55 completed | 32.409
1253 | 510058 | Enhanced Management of UE based network performance measurements | OAM-ePM-UE | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-12-12 17:00 | 100% | SP-110135 | - | Huawei, Ericsson, Nokia Siemens Networks | Zou Lan (zlan@huawei.com), ulf.hubinette@ericsson.com, gyula.bodog@nsn.com | SP#58 completed | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446
1254 | 520034 | CN performance measurements enhancement | OAM-ePM-CN | 3 | Rel-11 | S5 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-110275 | - | China Mobile | Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com), Li Jian (lijian@chinamobile.com) | SP#57 completed | 32.406, 32.407, 32.426
1255 | 530049 | Management of Carrier Aggregation for LTE | OAM-CA | 3 | Rel-11 | S5 | 2011-09-21 08:00 | 2012-12-12 17:00 | 100% | SP-120776 | - | Nokia Siemens Networks, Ericsson | yizhi.yao@nsn.com, per.elmdahl@ericsson.com | SP#58 completed. Updated WID SP-110636=>SP-120776. Stage 2 in Rel-10 RAN Feature UID_460007 Carrier Aggregation for LTE (LTE_CA) | 32.425 | CA
1256 | 510351 | Rel-11 Self-Organizing Networks (SON) - OAM aspects | OAM11-SON | 2 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-06 17:00 | 100% | - | - | - | - | - | - | SON
1257 | 510059 | UTRAN Self-Organizing Networks (SON) management | OAM-SON-UTRAN | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-09-12 17:00 | 100% | SP-120552 | - | Huawei | kai.zhangkai@huawei.com | SP#57 completed. Updated WID SP-110518=>SP-120552 | UTRA 32.405, 32.500, 32.511, 32.521, 32.522, 32.526, 32.642, 32.646 | SON
1258 | 530051 | LTE Self-Organizing Networks (SON) coordination management | OAM-SON-LTE_COORD | 3 | Rel-11 | S5 | 2011-09-21 08:00 | 2013-03-06 17:00 | 100% | SP-110637 | - | Huawei, Nokia Siemens Networks | kai.zhangkai@huawei.com, clemens.suerbaum@nsn.com | SP#59 completed | LTE 32.425, 32.500, 32.521, 32.522, 32.526, 32.762, 32.766 | SON
1259 | 540031 | Inter-RAT Energy Saving Management | OAM-IRAT-ESM | 3 | Rel-11 | S5 | 2011-12-07 08:00 | 2012-12-12 17:00 | 100% | SP-110701 | - | Nokia Siemens Networks, Huawei | clemens.suerbaum@nsn.com, xiahaitao@huawei.com | SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs | 32.405, 32.551, 32.522, 32.526, 32.642, 32.646, 32.762, 32.766 | SON
1260 | 510052 | Rel-11 Charging Management small Enhancements | CH11 | 1 | Rel-11 | S5 | 2010-03-25 08:00 | 2012-12-12 17:00 | 100% | - | - | - | - | CH11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI | TR 30.821
1261 | 470045 | Add solutions for Rc - reference point within the Online Charging System (OCS) | CH-Rc | 2 | Rel-11 | S5 | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-110129 | - | Huawei | shan.mingjun@huawei.com | SP#53 completed. Stage 3 (Stage 1 in 22.115). Triggered by Rel-10 TR 32.825 SA5 Study on Rc Reference Point Functionalities and Message Flows (UID_410044) | 32.296, 32.299
1262 | 510060 | Charging for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Data Bases | PEST-CH | 2 | Rel-11 | S5 | 2011-03-21 08:00 | 2011-09-21 17:00 | 100% | SP-110126 | - | Ericsson | patrik.teppo@@ericsson.com | SP#53 completed. Stage 3 | 32.251, 32.298, 32.299
1263 | 550019 | Unification of Charging session from SIP AS and SRVCC functions in IMS | UCHIMS_AS-SRVCC | 2 | Rel-11 | S5 | 2012-03-07 08:00 | 2012-12-12 17:00 | 100% | SP-120042 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Stage 2/3. SP#58 completed | 32.260, 32.275, 32.298, 32.299
1264 | 510029 | Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 1 | Rel-11 | S5,S1,C1 | 2010-10-27 08:00 | 2012-06-15 17:00 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | Stage 2/3. CP#56 completed. Stage 1 in SA1 22.115 | -
1265 | 510129 | Stage 1 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | - | 2 | Rel-11 | S1 | 2010-10-27 08:00 | 2011-09-21 17:00 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#53 completed under IPXS | 22.115
1266 | 510229 | Stage 2/3 SA5 part of Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | - | 2 | Rel-11 | S5 | 2010-10-27 13:48 | 2011-12-07 17:00 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#54 completed | 32.240, 32.260, 32.298, 32.299
1267 | 520006 | Stage 3 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | - | 2 | Rel-11 | C1 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | CP-110440 | - | Deutsche Telekom | martin.huelsemann@telekom.de] | CP#56 completed | 24.229
1268 | 480011 | User Data Convergence - Data Model | UDC_DM | 1 | Rel-11 | C4,S1 | 2010-03-25 08:00 | 2012-09-07 17:00 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed. SP#48 Stage 1 completed as Rel-10 | -
1269 | 480036 | Stage 1 for UDC Data Model | - | 2 | Rel-11 | S1 | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | - | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | SP#53 completed under Rel-10 UDC | 22.101
1270 | 480111 | TR on User Data Convergence (UDC) Data Model | - | 2 | Rel-11 | C4 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed | new TR 29.935
1271 | 480211 | User Data Convergence (UDC) Data Model | - | 2 | Rel-11 | C4 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed | 29.335
1272 | 510004 | Definition of the UICC Application for Hosting Party Module | HPM_UICC | 1 | Rel-11 | C6 | 2011-03-18 08:00 | 2012-06-15 17:00 | 100% | CP-110289 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#56 completed | 31.102, New TS 31.104
1273 | 520007 | Usability improvement of Inter-IMS Network to Network Interface (II-NNI) specification for inter-connection by means of Option Item list | NNI_OI | 1 | Rel-11 | C3 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | CP-110533 | - | NTT | arai.kenjiro@lab.ntt.co.jp | CP#56 completed. Stage 3 (No architectural change, specify the list of selectable items related to control plane signalling directly for the same architecture) | 29.165
1274 | 520008 | enhanced Nodes Restoration for EPC (Stage 2/3) | eNR_EPC | 1 | Rel-11 | C4,C1,C3,IETF | 2011-06-03 08:00 | 2013-12-06 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration UID_490014 | -
1275 | 520108 | CT4 part of enhanced Nodes Restoration for EPC | - | 2 | Rel-11 | C4 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed | 23.007, 23.008, 23.018, 29.274, 29.275
1276 | 581001 | (IETF) CT4 part of enhanced Nodes Restoration for EPC (RFC 7077) | - | 2 | Rel-11 | C4-IETF | 2012-12-07 08:00 | 2013-12-06 17:00 | 100% | CP-120449 | - | Lionel Morand | Lionel Morand | CP#62 completed | RFC 7077 (was draft-ietf-netext-update-notifications)
1277 | 540013 | CT1 part of enhanced Nodes Restoration for EPC | - | 2 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-03-02 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#55 completed | 29.118
1278 | 570009 | CT3 part of enhanced Nodes Restoration for EPC | - | 2 | Rel-11 | C3 | 2012-09-10 08:00 | 2012-12-07 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed | 29.212
1279 | 520009 | Reference Location Information (Stage 3) | RLI | 1 | Rel-11 | C4,C1 | 2011-06-03 08:00 | 2011-09-16 17:00 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11) | -
1280 | 520109 | CT4 part of Reference Location Information (Stage 3) | - | 2 | Rel-11 | C4 | 2011-06-03 08:00 | 2011-06-03 08:00 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#52 completed | 23.008, 29.228, 29.328, 29.329
1281 | 520209 | CT1 part of Reference Location Information (Stage 3) | - | 2 | Rel-11 | C1 | 2011-06-03 08:00 | 2011-09-16 17:00 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#53 completed | 24.229
1282 | 520010 | IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 1 | Rel-11 | C1,C3,IETF | 2011-06-07 08:00 | 2014-12-05 17:00 | 87% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | -
1283 | 520110 | CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 | - | 2 | Rel-11 | C1 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | 23.218, 24.229, 24.930
1284 | 591001 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (drage-sipping-rfc3455bis) | - | 2 | Rel-11 | C1-IETF | 2013-03-01 08:00 | 2014-12-05 17:00 | 75% | CP-110437 | - | Roland Jesske | Roland Jesske | in RFC Ed-queue | draft-drage-sipping-rfc3455bis
1285 | 611002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135) | - | 2 | Rel-11 | C1-IETF | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-110437 | - | Roland Jesske | Roland Jesske | CP#64 completed | RFC 7135 (was draft-polk-local-emergency-rph-namespace)
1286 | 520210 | CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 | - | 2 | Rel-11 | C3 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | 29.163, 29.165
1287 | 581002 | (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (avasarala-dispatch-comm-div-notification) | - | 2 | Rel-11 | C3-IETF | 2012-12-07 08:00 | 2014-12-05 17:00 | 75% | CP-110437 | - | Andrew Allen | Andrew Allen | Not completed internet-draft | draft-avasarala-dispatch-comm-div-notification
1288 | 530003 | Service Identification for RRC Improvements in GERAN (Stage 2/3) | SIRIG | 1 | Rel-11 | S2,C4,C3,G2 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | TSG#57, GP#55 completed. CT defined a generic solution (not only for GERAN) | GERAN
1289 | 560008 | Stage 2 for Service Identification for RRC Improvements in GERAN | - | 2 | Rel-11 | S2 | 2012-06-18 08:00 | 2012-09-07 17:00 | 100% | - | - | - | - | SP#57 completed | 23.060, 23.251
1290 | 540018 | CN aspects of Service Identification for RRC Improvements in GERAN | - | 2 | Rel-11 | C4,C3 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#57 completed | -
1291 | 540118 | CT4 part of CN aspects of Service Identification for RRC Improvements in GERAN | - | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#57 completed | 29.281
1292 | 550009 | Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN | - | 3 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#56 stopped (SA2 decided NO CT3 impact) | 29.212
1293 | 530103 | GERAN2 part of Service Identification for RRC Improvements in GERAN | - | 2 | Rel-11 | G2 | 2011-09-19 08:00 | 2012-08-31 17:00 | 100% | GP-111876 | - | China Mobile, Huawei | Juan Deng, Yang Zhao | GP#55 completed. GP#51 approved WID | 48.018
1294 | 530019 | SAE Protocol Development - Phase 2 | SAES2 | 1 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed. Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005 | -
1295 | 530119 | SAE Protocol Development (Stage 3) - Phase 2 | - | 2 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118
1296 | 530219 | CS Fallback in EPS - Phase 2 | SAES2-CSFB | 2 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118
1297 | 530020 | GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3) | RT_VGCS_Red | 1 | Rel-11 | C1 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069) | Stage 2/3
1298 | 530120 | CT1 part of GCSMSC and GCR Redundancy for VGCS/VBS | - | 2 | Rel-11 | C1 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 43.068, 43.069
1299 | 530220 | Deleted - CT4 part of GCSMSC and GCR Redundancy for VGCS/VBS | - | 2 | Rel-11 | C4 | 2011-09-19 08:00 | 2012-06-15 17:00 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#56 stopped (no CT4 impact) | 29.002
1300 | 540015 | Support of RFC 6140 in IMS | GINI | 1 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110760 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#57 completed. Stage 3. Support procedures and protocol extensions in RFC6140 "Registration for Multiple Phone Numbers in SIP" to IMS for complex UEs. Ensure co-existence with NGCN IP-PBX registration procedures already defined in IMS. | 24.229
1301 | 540017 | Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 1 | Rel-11 | C4,C3 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed. Stage 3. Stage 1 for MPS in 22.153. Details of any MGW actions for priority needs to be further studied within the scope of this WI. | Stage 3 | Public Safety (I-A)
1302 | 540117 | CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | - | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed | 23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | Public Safety (I-A)
1303 | 540217 | CT3 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | - | 2 | Rel-11 | C3 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed | 29.162, 29.163, 29.292 | Public Safety (I-A)
1304 | 550007 | Inter-IMS Network to Network Interface (II-NNI) enhancements: SIP timers applicability (Stage 3) | NNI_timers | 1 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-09-07 17:00 | 100% | CP-120082 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | CP#57 completed | 29.165
1305 | 560005 | AT commands for Universal Resource Identifier (URI) support | ATURI | 1 | Rel-11 | C1 | 2012-06-15 08:00 | 2013-03-01 17:00 | 100% | CP-120275 | - | Intel | frank.kowalewski@intel.com | CP#59 completed. Define new AT cmd for URI addresses for IMS services (eg VoLTE). 27.007(AT cmd to control MT functions and GSM/UMTS/LTE network services from TE), 27.005(AT commands for SMS). Currently address types for AT cmd based on dialling# | 27.005, 27.007
1306 | 560006 | PS Additional Number (Stage 3) | PSAN | 1 | Rel-11 | C4 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120253 | - | Deutsche Telekom | Yvette.koza@t-mobile.at | CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact) | 23.003, 23.008, 29.002, 29.272, 29.230
1307 | 560007 | Generic IMS User Group Over Sh | GenUG_Sh | 1 | Rel-11 | C4 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120254 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 29.364
1308 | 570010 | IMS Operator Determined Call Barring | IODB | 1 | Rel-11 | C1,C4 | 2012-09-07 08:00 | 2013-06-14 17:00 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | LS_in C4-121615 GSMA IREG RILTE concluded that TS 22.041 clause 5.4 Stage 1 requirements are not covered by stage 3 specifications | -
1309 | 570110 | CT1 part of IMS Operator Determined Call Barring | - | 2 | Rel-11 | C1 | 2012-09-10 08:00 | 2013-06-14 17:00 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | CP#60 completed. Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CT decision. | New TS 24.315
1310 | 570210 | CT4 part of IMS Operator Determined Call Barring | - | 2 | Rel-11 | C4 | 2012-09-07 08:00 | 2013-03-12 17:00 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | CP#58 completed | 23.008 , 23.015 , 29.328 , 29.329 , 29.364
1311 | 570011 | Enhanced T.38 FAX support (Stage 3) | MMTel_T.38_FAX | 1 | Rel-11 | C3,C1,C4 | 2012-09-06 08:00 | 2012-12-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed. Linked to Rel-8 Feature: IMS Multimedia Telephony Service (IMS-MMTel) UID_7038. SA1 added FAX stage 1 requirement only in Rel-10 under TEI10 to TS 22.173 (CR#0064) | -
1312 | 570111 | CT3 part of Enhanced T.38 FAX support | - | 2 | Rel-11 | C3 | 2012-09-07 08:00 | 2012-12-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed | 29.163
1313 | 570211 | CT1 part of Enhanced T.38 FAX support | - | 2 | Rel-11 | C1 | 2012-09-07 08:00 | 2012-12-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed | 24.229
1314 | 570311 | CT4 part of Enhanced T.38 FAX support | - | 2 | Rel-11 | C4 | 2012-09-06 08:00 | 2012-09-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#57 completed | 29.332
1315 | 540016 | Deleted - Enhancement of the Protocols for SMS over SGs (Stage 3) | PROTOC_SMS_SGs | 1 | Rel-11 | C4,C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped. Reason: Protocols for SMS over SGs is replaced by the SIMTC SMS in MME solution (as solution not only for MTC user but for general subscribers) | Stage 3
1316 | 540116 | Deleted - TR Study on enhancement of protocols for SMS service over SGs | - | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped (abandonned new TR 29.818) | new TR 29.818
1317 | 540216 | Deleted - CT4 part of Enhancement of the Protocols for SMS over SGs | - | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped (abandonned new TS 29.218 Diameter based protocols for SMS service over SGs) | 29.305, new TS 29.218
1318 | 540316 | Deleted - CT1 part of Enhancement of the Protocols for SMS over SGs | - | 2 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped | 23.040, 24.011, 43.068
1319 | 510001 | Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 1 | Rel-11 | G2,S2,C1 | 2011-03-04 08:00 | 2013-05-17 17:00 | 100% | GP-121090 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UEs in GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001 | GERAN
1320 | 510101 | GERAN part of Full Support of Multi-Operator Core Network by GERAN | - | 2 | Rel-11 | G2 | 2011-03-04 08:00 | 2013-05-17 17:00 | 100% | GP-121090 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#58 completed. GP#49 approved WID | 44.018, 44.060, 45.002, 45.008, 48.008, 48.018
1321 | 510201 | Stage 2 for Full Support of Multi-Operator Core Network by GERAN | - | 2 | Rel-11 | S2 | 2011-06-08 08:00 | 2012-03-07 17:00 | 100% | SP-110390 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#55 completed | 23.251, 23.272
1322 | 510301 | CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | - | 2 | Rel-11 | C1,C4 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-120563 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#58 completed | -
1323 | 510401 | CT1 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | - | 3 | Rel-11 | C1 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-120563 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#58 completed | 24.008
1324 | 560004 | CT4 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | - | 3 | Rel-11 | C4 | 2012-06-13 08:00 | 2012-09-07 17:00 | 100% | CP-120563 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | CP#57 completed | 23.003
1325 | 560042 | Stage 2 for Gateway Core Network Sharing for GERAN | Full_MOCN-GERAN-GWCN | 2 | Rel-11 | S2 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120268 | - | Vodafone | chris.pudney@vodafone.com | SP#59 completed. (23.251CR0062R2 as TEI11. TS 23.251 specifies both MOCN and GWCN for E-UTRAN and UTRAN, but GWCN is not yet supported on GERAN. Extend Full_MOCN-GERAN to also cover GWCN GERAN | 23.251
1326 | 540003 | Medium range/local area requirements for multicarrier BTS | MRLA | 1 | Rel-11 | G1 | 2011-11-25 08:00 | 2012-11-23 17:00 | 100% | GP-111780 | - | Ericsson | Eric Nordström | GP#56 completed. GP#52 approved WID | GERAN
1327 | 540103 | Core part: Medium range/local area requirements for multicarrier BTS | MRLA-Core | 2 | Rel-11 | G1 | 2011-11-25 08:00 | 2012-11-23 17:00 | 100% | GP-111899 | - | Ericsson | Eric Nordström | Stage 3. GP#56 completed. GP#52 approved WID | 45.005
1328 | 540203 | Perf. part: Medium range/local area requirements for multicarrier BTS | MRLA-Perf | 2 | Rel-11 | G1 | 2011-11-28 08:00 | 2012-11-23 17:00 | 100% | GP-111782 | - | Ericsson | Eric Nordström | Test spec. GP#56 completed. GP#52 approved WID | 51.021
1329 | 550023 | Domain Specific Access Control in GERAN | GDSAC | 1 | Rel-11 | G2 | 2012-03-05 08:00 | 2012-08-31 17:00 | 100% | GP-120452 | - | Vodafone | chris.pudney@vodafone.com | GP#55 completed. GP#53 approved WID. Work is dependent upon Full_MOCN-GERAN (UID_510001) | GERAN 44.018
1330 | 500020 | Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB | 1 | Rel-11 | R4,R2,R3,R5 | 2010-12-10 08:00 | 2013-03-01 17:00 | 100% | RP-111396 | - | Sprint | John.J.Humbert@Sprint.com | Stage 3 Triggered by R4 Rel-10 LTE TR 37.806 Study on Extending 850 MHz (UID_440016) | UTRA, LTE
1331 | 500120 | Core part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-Core | 2 | Rel-11 | R4,R2,R3 | 2010-12-10 08:00 | 2012-03-02 17:00 | 100% | RP-111396 | RP-120075 | Sprint | John.J.Humbert@Sprint.com | RP#55 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141
1332 | 500220 | Perf. part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-Perf | 2 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-03-02 17:00 | 100% | RP-111396 | RP-120076 | Sprint | John.J.Humbert@Sprint.com | RP#55 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141
1333 | 510016 | Test part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-UEConTest | 2 | Rel-11 | R5 | 2011-03-18 08:00 | 2013-03-01 17:00 | 100% | RP-110377 | RP-130043 | Sprint | John.J.Humbert@Sprint.com | RP#59 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1334 | 530030 | Further Self Optimizing Networks (SON) enhancements | SONenh2_LTE_UTRA | 1 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120314 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | Stage 1/2/3. RP#58 Core completed | UTRA, LTE | SON
1335 | 530130 | Core part: Further Self Optimizing Networks (SON) enhancements | SONenh2_LTE_UTRA-Core | 2 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120314 | RP-121557 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#58 completed | 25.331, 25.401, 25.410, 25.413, 25.423, 25.433, 36.300, 36.331, 36.413, 36.423 | SON
1336 | 530033 | Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE | 1 | Rel-11 | R2,R1,R3,R4,R5 | 2011-09-19 08:00 | 2013-12-06 17:00 | 100% | RP-121204 | - | MediaTek | Johan Johansson | Stage 2/3. RP#58 Core completed | UTRA, LTE
1337 | 530133 | Core part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121204 | RP-121556 | MediaTek | Johan Johansson | RP#58 completed | 25.133, 25.123, 25.304, 25.331, 25.413, 25.423, 36.133, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320, 36.300
1338 | 590001 | Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130172 | RP-131447 | NTT DoCoMo | masahiro.tamaoki.eu@nttdocomo.com | RP#62 completed | 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3
1339 | 530036 | Network Energy Saving for E-UTRAN | Netw_Energy_LTE | 1 | Rel-11 | R3,GP | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120620 | - | China Mobile | yangning@chinamobile.com | Stage 2,3. RP#56 updated WID RP-111376=>RP-120620 | LTE, GERAN
1340 | 530136 | Core part: Network Energy Saving for E-UTRAN | Netw_Energy_LTE-Core | 2 | Rel-11 | R3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120620 | RP-121016 | China Mobile | yangning@chinamobile.com | RP#57 completed. Inter-RAT aspect can affect UTRA and GERAN as well | 25.413, 36.300, 36.413, 36.423
1341 | 570001 | GERAN part: Network Energy Saving for E-UTRAN | - | 2 | Rel-11 | GP | 2012-08-27 08:00 | 2012-08-31 17:00 | 100% | GP-121178 | - | Alcatel-Lucent | marguerite.woch@alcatel-lucent.com | GP#55 approved WID and completed. Stage 3. Changes in RIM protocol and in SON Transfer RIM application to provide support for Energy Savings Indication feature | 48.018 [Serving GPRS Support Node (SGSN); BSS GPRS protocol (BSSGP)]
1342 | 530037 | E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR | 1 | Rel-11 | R4,G1 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111383 | - | Ericsson | johan.skold@ericsson.com | Stage 3. RP#58 completed. GP#56 completed. GERAN BS RF requirements specs need aligned with RAN4 ongoing Rel-11 Feature UID_530037 E-UTRA medium range and MSR medium range/local area BS class requirements (medBS_class_LTE_MSR) | UTRA, LTE, GERAN
1343 | 530137 | Core part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-Core | 2 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111383 | RP-121558 | Ericsson | johan.skold@ericsson.com | RP#58 completed. TR 37.809 v200 for Approval | 25.104, 36.104, 37.104, new TR 37.809
1344 | 530237 | Perf. part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-Perf | 2 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-111383 | RP-121559 | Ericsson | johan.skold@ericsson.com | RP#58 completed | 25.141, 36.141, 37.141
1345 | 540002 | GERAN part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-GERAN | 2 | Rel-11 | G1 | 2011-11-28 08:00 | 2012-11-23 17:00 | 100% | GP-111779 | - | Ericsson | Eric Nordström | GP#56 completed. GP#52 approved WID | 45.005, 51.021
1346 | 550015 | RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF | 1 | Rel-11 | R4,G1 | 2012-02-06 16:12 | 2014-03-06 17:00 | 100% | RP-120857 | - | Huawei | Liu Ye (leo.liuye@huawei.com) | - | UTRA, LTE, GERAN
1347 | 550115 | Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF-Core | 2 | Rel-11 | R4,G1 | 2012-02-06 16:12 | 2012-12-07 17:00 | 100% | RP-120857 | RP-121985 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#58 completed | 25.104, 25.105, 36.104, 37.104, new TR 37.812
1348 | 550215 | Perf. part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF-Perf | 2 | Rel-11 | R4,G1 | 2012-03-08 08:00 | 2014-03-06 17:00 | 100% | RP-120857 | RP-140064 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#63 completed | 25.141, 25.142, 36.141, 37.141
1349 | 560013 | Further enhancements to H(e)NB mobility - Part 1 | EHNB_enh1 | 1 | Rel-11 | R3,R2 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | RP-121427 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Stage 2/3. RP#58 completed. Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2). Compare also Rel-10 WI HNB_HENB_mob_enh RP-110183 | UTRA, LTE | HNB
1350 | 560113 | Core part: Further enhancements to H(e)NB mobility - Part 1 | EHNB_enh1-Core | 2 | Rel-11 | R3,R2 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | RP-121427 | RP-121563 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#58 completed | 25.413, 25.467, 25.469, 36.300, 36.413, 36.423 | HNB
1351 | 560014 | Further enhancements to H(e)NB mobility - Part 2 | EHNB_enh2 | 1 | Rel-11 | R3,R2 | 2012-06-19 08:00 | 2012-12-07 17:00 | 100% | RP-121712 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Stage 2/3. RP#58 completed Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2) | UTRA, LTE | HNB
1352 | 560114 | Core part: Further enhancements to H(e)NB mobility - Part 2 | EHNB_enh2-Core | 2 | Rel-11 | R3,R2 | 2012-06-19 08:00 | 2012-12-07 17:00 | 100% | RP-121712 | RP-121564 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#58 completed Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Updated WID RP-121147=>RP-121712 | 25.413, 25.467, 25.469, 25.471 | HNB
1353 | 430011 | Network-Based Positioning Support for LTE | LCS_LTE-NBPS | 1 | Rel-11 | R2,R1,R3,R4 | 2009-03-05 08:00 | 2014-06-13 17:00 | 100% | RP-131259 | - | TruePosition | terri.brooks@trueposition.com | - | LTE
1354 | 430111 | Core part: Network-Based Positioning Support for LTE | LCS_LTE-NBPS-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2009-03-05 08:00 | 2013-06-12 17:00 | 100% | RP-131259 | RP-130483 | TruePosition | terri.brooks@trueposition.com | RP#60 completed | 36.214, 36.300, 36.305, 36.401, 36.413, 36.455, new TS (36.111, 36.456, 36.457, 36.458, 36.459)
1355 | 430211 | Perf. part: Network-Based Positioning Support for LTE | LCS_LTE-NBPS-Perf | 2 | Rel-11 | R4 | 2009-03-24 08:00 | 2014-06-13 17:00 | 100% | RP-131259 | RP-140626 | TruePosition | terri.brooks@trueposition.com | RP#64 completed. TS 36.112v100 for 1-step Approval | 36.111, new TS 36.112
1356 | 480026 | Service continuity improvements for MBMS for LTE | MBMS_LTE_SC | 1 | Rel-11 | R2,R3,R5 | 2010-06-04 08:00 | 2014-03-06 17:00 | 100% | RP-120258 | - | Huawei | David.Lecompte@huawei.com | - | LTE
1357 | 480126 | Core part: Service continuity improvements for MBMS for LTE | MBMS_LTE_SC-Core | 2 | Rel-11 | R2,R3 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | RP-120258 | RP-121001 | Huawei | David.Lecompte@huawei.com | RP#57 completed | 25.446, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445
1358 | 590002 | Test part: Service continuity improvements for MBMS for LTE | MBMS_LTE_SC-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-130296 | RP-140074 | Ericsson | leif.mattisson@ericsson.com | RP#63 completed | 36.508, 36.523-1, 36.523-2, 36.523-3
1359 | 510021 | Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2011-03-22 08:00 | 2014-09-12 17:00 | 99% | RP-120860 | - | China Mobile | ShenXiaodong@chinamobile.com | RP#58 Core completed | LTE
1360 | 510121 | Core part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120860 | RP-121986 | China Mobile | ShenXiaodong@chinamobile.com | RP#58 completed | 36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.321, 36.331, 36.413, 36.423
1361 | 510221 | Perf. part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-Perf | 2 | Rel-11 | R4 | 2011-03-23 08:00 | 2013-12-06 17:00 | 100% | RP-120860 | RP-131463 | China Mobile | ShenXiaodong@chinamobile.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141
1362 | 600001 | Test part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-UEConTest | 2 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-09-12 17:00 | 95% | RP-130649 | RP-140594 | ZTE | Carolyn Taylor (carolyn.tayl@zte.com.cn) | RP#64 completion 06/14=>09/14 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1363 | 510028 | New Band LTE Downlink FDD 716-728 MHz (Band 29, Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29) | LTE_DL_FDD700 | 1 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-110435 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | CA
1364 | 510128 | Core part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700-Core | 2 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-110710 | RP-121604 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.141, 36.307
1365 | 510228 | Perf. part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700-Perf | 2 | Rel-11 | R4 | 2011-03-29 08:00 | 2012-12-07 17:00 | 100% | RP-110435 | RP-121605 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307
1366 | 510031 | LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA | 1 | Rel-11 | R2,R5 | 2011-03-18 08:00 | 2013-09-06 17:00 | 100% | RP-120256 | - | BlackBerry | Gordon Young (gyoung@rim.com) | Stage 2/3 | LTE
1367 | 510131 | Core part: LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA-Core | 2 | Rel-11 | R2 | 2011-03-18 08:00 | 2012-12-07 17:00 | 100% | RP-120256 | RP-121571 | BlackBerry | Gordon Young (gyoung@rim.com) | RP#58 completed | 36.300, 36.321, 36.331, new TR 36.822
1368 | 590003 | Test part: LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-09-06 17:00 | 100% | RP-130338 | RP-130946 | BlackBerry | Eniko Sokondár (esokondar@rim.com) | RP#61 completed | 36.523-1, 36.523-2, 36.523-3
1369 | 510032 | LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB | 1 | Rel-11 | R1,R2,R4,R5 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | RP-120602 | - | NII Holdings | bill.shvodian@nii.com | Stage 3 | LTE
1370 | 510132 | Core part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-Core | 2 | Rel-11 | R1,R2,R4 | 2011-06-15 08:00 | 2012-09-07 17:00 | 100% | RP-120602 | RP-120570 | NII Holdings | bill.shvodian@nii.com | RP#56 completed | 25.101, 25.104, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.307, 37.104, 37.113
1371 | 510232 | Perf. part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-Perf | 2 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-06-15 17:00 | 100% | RP-120602 | RP-120571 | NII Holdings | bill.shvodian@nii.com | RP#56 completed | 25.123, 25.133, 25.141, 36.133, 36.141, 37.141
1372 | 560010 | Test part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-UEConTest | 2 | Rel-11 | R5 | 2012-06-18 08:00 | 2013-03-01 17:00 | 100% | RP-120603 | RP-130045 | NII Holdings | bill.shvodian@nii.com | RP#59 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1
1373 | 520017 | LTE for 700 MHz Digital Dividend | LTE_APAC700 | 1 | Rel-11 | R4,R2,R3,R5 | 2011-06-07 08:00 | 2013-06-14 17:00 | 100% | RP-110875 | - | Ericsson | olav.queseth@ericsson.com | RP#56 Core & Perf completed. Stage 3 . Asian Pacific American Caucus (APAC) Asia-Pacific Telecommunity (APT) Wireless Forum | LTE
1374 | 520117 | Core part: LTE for 700 MHz Digital Dividend | LTE_APAC700-Core | 2 | Rel-11 | R4,R2,R3 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | RP-110875 | RP-120572 | Ericsson | olav.queseth@ericsson.com | RP#56 completed. TR 36.820 v100 for Information and Approval | 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.113, new TR 36.820
1375 | 520217 | Perf. part: LTE for 700 MHz Digital Dividend | LTE_APAC700-Perf | 2 | Rel-11 | R4 | 2011-06-09 08:00 | 2012-06-15 17:00 | 100% | RP-110875 | RP-120573 | Ericsson | olav.queseth@ericsson.com | RP#56 completed | 36.133, 36.141, 37.141
1376 | 560011 | Test part: LTE for 700 MHz Digital Dividend | LTE_APAC700-UEConTest | 2 | Rel-11 | R5 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-120600 | RP-130467 | Ericsson | fredrik.sundstrom@ericsson.com | RP#60 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1
1377 | 520019 | Relays for LTE (part 2) | LTE_Relay2 | 1 | Rel-11 | R4 | 2009-12-04 08:00 | 2013-06-14 17:00 | 100% | RP-110914 | - | Ericsson | christian.hoymann@ericsson.com | Continuation of Rel-10 (open RAN4 Core & Perf parts) | LTE
1378 | 520119 | Core part: Relays for LTE (part 2) | LTE_Relay2-Core | 2 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110914 | RP-121008 | Ericsson | christian.hoymann@ericsson.com | RP#57 completed. TS 36.116, TR 36.826 v100 for Information & Approval. RP#52 Core part not completed in Rel-10 | 36.133, new RAN4 (36.116, 36.826)
1379 | 520219 | Perf. part: Relays for LTE (part 2) | LTE_Relay2-Perf | 2 | Rel-11 | R4 | 2009-12-04 08:00 | 2013-06-14 17:00 | 100% | RP-110914 | RP-130487 | Ericsson | christian.hoymann@ericsson.com | RP#60 completed. New TS 36.117 v100 for 1-step Approval. RP#52 transferred completely from Rel-10 UID_460213 | 36.133, new TS 36.117 (E-UTRA Relay conformance testing)
1380 | 530031 | Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE | 1 | Rel-11 | R2,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111355 | - | China Mobile | Zhenping HU | Stage 2/3. RP#58 completed | LTE
1381 | 530131 | Core part: Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE-Core | 2 | Rel-11 | R2,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111355 | RP-121573 | China Mobile | Zhenping HU | RP#58 completed | 36.133, 36.300, 36.306, 36.321, 36.331
1382 | 530231 | Perf. part: Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE-Perf | 2 | Rel-11 | R4 | 2011-09-20 08:00 | 2012-12-07 17:00 | 100% | RP-111356 | RP-121574 | China Mobile | Zhenping HU | RP#58 completed | 36.133
1383 | 530032 | Coordinated Multi-Point Operation for LTE | COMP_LTE | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2011-09-19 08:00 | 2014-09-12 17:00 | 95% | RP-111365 | - | Huawei, Samsung | Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com | Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE) | LTE
1384 | 530132 | Core part: Coordinated Multi-Point Operation for LTE – Uplink | COMP_LTE_UL-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111365 | RP-121575 | Huawei | david.mazzarese@huawei.com | RP#58 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423
1385 | 530232 | Perf. part: Coordinated Multi-Point Operation for LTE – Uplink | COMP_LTE_UL-Perf | 2 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-111365 | RP-121576 | Huawei | Xinwei Zhi (zhixinwei@huawei.com) | RP#58 completed | 36.101, 36.104, 36.133, 36.141
1386 | 530332 | Core part: Coordinated Multi-Point Operation for LTE – Downlink | COMP_LTE_DL-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111365 | RP-121577 | Samsung | Juho Lee (juho95.lee@samsung.com) | RP#58 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423
1387 | 530432 | Perf. part: Coordinated Multi-Point Operation for LTE – Downlink | COMP_LTE_DL-Perf | 2 | Rel-11 | R4 | 2011-09-23 08:00 | 2013-12-06 17:00 | 100% | RP-111365 | RP-131465 | Samsung | xutao.zhou@samsung.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141, 36.307
1388 | 590004 | Test part: Coordinated Multi-Point Operation for LTE | COMP_LTE-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-09-12 17:00 | 75% | RP-130376 | RP-140614 | Samsung | Stoyan.Baev@partner.samsung.com | RP#63 completion 03/14=>09/14 | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3
1389 | 540025 | Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl | 1 | Rel-11 | R1,R2,R4,R5 | 2011-12-09 08:00 | 2014-09-12 17:00 | 97% | RP-120871 | - | Alcatel-Lucent | sigen.ye@alcatel-lucent.com | Stage 3. RP#58 Core completed. Triggered by UID_510037 Rel-11 TR 36.871 Study on further Downlink MIMO enhancements for LTE-Advanced (FS_LTE_eDL_MIMO_enh) | LTE
1390 | 540125 | Core part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-Core | 2 | Rel-11 | R1,R2,R4 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-120871 | RP-121579 | Alcatel-Lucent | sigen.ye@alcatel-lucent.com | RP#58 completed | 36.101, 36.211, 36.212, 36.213, 36.331
1391 | 540225 | Perf. part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-Perf | 2 | Rel-11 | R4 | 2011-12-16 08:00 | 2014-06-13 17:00 | 100% | RP-120871 | RP-140651 | Alcatel-Lucent | teck.hu@alcatel-lucent.com | RP#64 completed | 36.101, 36.104, 36.133, 36.141
1392 | 590005 | Test part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-09-12 17:00 | 90% | RP-130304 | RP-140641 | Huawei | Xu Kai (xk.xukai@huawei.com) | RP#64 completion 06/14=>09/14 | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3
1393 | 550012 | Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE | 1 | Rel-11 | R4,R5 | 2012-03-05 08:00 | 2013-09-06 17:00 | 100% | RP-120362 | - | Motorola Solutions | xiaowei.jin@motorolasolutions.com | Stage 3. RP#58 completed | LTE | Public Safety (A-A)
1394 | 550112 | Core part: Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE-Core | 2 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-120362 | RP-121581 | Motorola Solutions | xiaowei.jin@motorolasolutions.com | RP#58 completed. TR 36.837 v100 for Information and Approval | 36.101, new TR 36.837 | Public Safety (A-A)
1395 | 590006 | Test part: Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-09-06 17:00 | 100% | RP-130169 | RP-130949 | Motorola Solutions | xiaowei.jin@motorolasolutions.com | RP#61 completed | 36.521-1, 36.521-2 | Public Safety (A-A)
1396 | 550013 | Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej | 1 | Rel-11 | R4,R5 | 2012-03-05 08:00 | 2014-09-12 17:00 | 91% | RP-120382 | - | Renesas Mobile | Timo Roman | RP#58 completed. Triggered by FS_enh_perf_UE_LTE. Adds Perf. requirements for demodulation of the already specified PDSCH with the transmission modes defined in Rel-8 to Rel-10 | LTE
1397 | 550113 | Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej-Perf | 2 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-120382 | RP-121582 | Renesas Mobile | Timo Roman | RP#58 completed | 36.101
1398 | 600002 | Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej-UEConTest | 2 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-09-12 17:00 | 85% | RP-140491 | RP-140612 | Broadcom | jarkko.hellsten@broadcom.com | RP#64 completion 06/14=>09/14. TR 36.904 for 1-step Approval. Testing for 36.101 | 36.508, 36.521-1, 36.521-2, New TR 36.904
1399 | 550014 | Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe | 1 | Rel-11 | R4,R2,R3,R5 | 2012-03-05 08:00 | 2013-06-14 17:00 | 100% | RP-120384 | - | China Mobile | Xiaodong Shen | Stage 3. Exists already for 1UL a WI LTE_CA_B3_B5 | LTE
1400 | 550114 | Core part: Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe-Core | 2 | Rel-11 | R4,R2,R3 | 2012-03-05 08:00 | 2012-09-07 17:00 | 100% | RP-120384 | RP-121019 | China Mobile | Xiaodong Shen | RP#57 completed | 36.211, 36.213, 36.331, 36.423
1401 | 590007 | Test part: Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130305 | RP-130475 | Huawei | Li Xiang (tricia.li@huawei.com) | RP#60 completed | 36.508, 36.523-1, 36.523-2, 36.523-3
1402 | 580158 | Rel-11 LTE Carrier Aggregation | LTE_CA_Rel-11 | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2010-12-10 08:00 | 2014-12-05 17:00 | 99% | - | - | - | - | LTE_CA_Rel-11 | LTE | CA
1403 | 510030 | LTE Carrier Aggregation Enhancements | LTE_CA_enh | 2 | Rel-11 | R1,R2,R3,R4,R5 | 2011-03-22 08:00 | 2014-12-05 17:00 | 93% | RP-121999 | - | Nokia | lars.e.lindh@nokia.com | Stage 3 | LTE | CA
1404 | 510130 | Core part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-Core | 3 | Rel-11 | R1,R2,R4,R3 | 2011-03-22 08:00 | 2013-03-01 17:00 | 100% | RP-121999 | RP-130059 | Nokia | lars.e.lindh@nokia.com | RP#59 completed. New TR 36.823 v100 for Information and Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, new TR 36.823 | CA
1405 | 510230 | Perf. part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-Perf | 3 | Rel-11 | R4 | 2011-03-29 08:00 | 2014-12-05 17:00 | 96% | RP-121999 | RP-140783 | Nokia | lars.e.lindh@nokia.com | RP#64 completion 06/14=>12/14 | 36.101, 36.104, 36.133, 36.141 | CA
1406 | 600003 | Test part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-UEConTest | 3 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-09-12 17:00 | 75% | RP-140619 | RP-140615 | Microsoft | jussi.kuusisto@microsoft.com | RP#64 revised WID RP-130702=>RP-140619. Completion 06/14=>09/14 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | CA
1407 | 570006 | UE Conformance Test Aspects – LTE Advanced Carrier Aggregation of Intra-band contiguous and Inter-band configurations | LTE_CA_intraC_inter_UEConTest | 2 | Rel-11 | R5 | 2012-09-11 08:00 | 2013-12-06 17:00 | 100% | RP-121814 | RP-131446 | Nokia | jussi.kuusisto@nokia.com | RP#62 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1 | CA
1408 | 580258 | Rel-11 inter-band Carrier Aggregation | - | 2 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | CA
1409 | 480023 | LTE Advanced Carrier Aggregation of Band 3 and Band 7 | LTE_CA_B3_B7 | 3 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120830 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed. In Europe Band 3,7,20 are interesting for LTE and LTE-Advanced deployment. Different CA combinations for these bands are of high priority for Region 1 | LTE | CA
1410 | 480123 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 7 | LTE_CA_B3_B7-Core | 4 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-09-07 17:00 | 100% | RP-120830 | RP-121022 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | CA
1411 | 480223 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 7 | LTE_CA_B3_B7-Perf | 4 | Rel-11 | R4 | 2010-12-17 08:00 | 2012-12-07 17:00 | 100% | RP-120830 | RP-121023 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed | 36.133, 36.141 | CA
1412 | 500017 | LTE Advanced Carrier Aggregation of Band 4 and Band 17 | LTE_CA_B4_B17 | 3 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-121458 | - | AT&T | marc.grant@att.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | CA
1413 | 500117 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 17 | LTE_CA_B4_B17-Core | 4 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-09-07 17:00 | 100% | RP-121458 | RP-121024 | AT&T | marc.grant@att.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | CA
1414 | 500217 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17 | LTE_CA_B4_B17-Perf | 4 | Rel-11 | R4 | 2010-12-17 08:00 | 2012-12-07 17:00 | 100% | RP-121458 | RP-121595 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | CA
1415 | 500018 | LTE Advanced Carrier Aggregation of Band 4 and Band 13 | LTE_CA_B4_B13 | 3 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120905 | - | Ericsson | christian.bergljung@ericsson.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | CA
1416 | 500118 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 13 | LTE_CA_B4_B13-Core | 4 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-09-07 17:00 | 100% | RP-120905 | RP-121026 | Ericsson | christian.bergljung@ericsson.com | RP#57 completed | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | CA
1417 | 500218 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 13 | LTE_CA_B4_B13-Perf | 4 | Rel-11 | R4 | 2010-12-21 08:00 | 2012-12-07 17:00 | 100% | RP-120905 | RP-121594 | Ericsson | christian.bergljung@ericsson.com | RP#58 completed | 36.101, 36.133, 36.141 | CA
1418 | 510022 | LTE Advanced Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12 | 3 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120877 | - | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | Stage 3. RP#58 completed | LTE | CA
1419 | 510122 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12-Core | 4 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120877 | RP-121592 | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | CA
1420 | 510222 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12-Perf | 4 | Rel-11 | R4 | 2011-03-29 08:00 | 2012-12-07 17:00 | 100% | RP-120877 | RP-121593 | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | RP#58 completed | 36.133, 36.141 | CA
1421 | 510023 | LTE Advanced Carrier Aggregation of Band 5 and Band 12 | LTE_CA_B5_B12 | 3 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120221 | - | US Cellular | sebastian.thalanany@uscellular.com | Stage 3. RP#58 completed | LTE | CA
1422 | 510123 | Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 12 | LTE_CA_B5_B12-Core | 4 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120221 | RP-121596 | US Cellular | sebastian.thalanany@uscellular.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | CA
1423 | 510223 | Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 12 | LTE_CA_B5_B12-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-120221 | RP-121597 | US Cellular | sebastian.thalanany@uscellular.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | CA
1424 | 510024 | LTE Advanced Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20 | 3 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-09-07 17:00 | 100% | RP-120889 | - | Huawei | Steven Chen | Stage 3. RP#57 completed | LTE | CA
1425 | 510124 | Core part: LTE Advanced Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20-Core | 4 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-09-07 17:00 | 100% | RP-120889 | RP-121032 | Huawei | Steven Chen | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | CA
1426 | 510224 | Perf. part: LTE Advanced Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-09-07 17:00 | 100% | RP-120889 | RP-121033 | Huawei | Steven Chen | RP#57 completed | 36.133, 36.141 | CA
1427 | 510025 | LTE Advanced Carrier Aggregation of Band 2 and Band 17 | LTE_CA_B2_B17 | 3 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110432 | - | AT&T | marc.grant@att.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | CA
1428 | 510125 | Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17 | LTE_CA_B2_B17-Core | 4 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-09-07 17:00 | 100% | RP-110432 | RP-121034 | AT&T | marc.grant@att.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | CA
1429 | 510225 | Perf. part: LTE Advanced Carrier Aggregation of Band 2 and Band 17 | LTE_CA_B2_B17-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-110432 | RP-121585 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | CA
1430 | 510026 | LTE Advanced Carrier Aggregation of Band 4 and Band 5 | LTE_CA_B4_B5 | 3 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110433 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | CA
1431 | 510126 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 5 | LTE_CA_B4_B5-Core | 4 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110433 | RP-121757 | AT&T | marc.grant@att.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | CA
1432 | 510226 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5 | LTE_CA_B4_B5-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-110433 | RP-121589 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | CA
1433 | 510027 | LTE Advanced Carrier Aggregation of Band 5 and Band 17 | LTE_CA_B5_B17 | 3 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110434 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | CA
1434 | 510127 | Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 17 | LTE_CA_B5_B17-Core | 4 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110434 | RP-121598 | AT&T | marc.grant@att.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | CA
1435 | 510227 | Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 17 | LTE_CA_B5_B17-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-110434 | RP-121599 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
1436 | 530023 | LTE Advanced Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120887 | - | Vodafone | tim.frost@vodafone.com | Stage 3. RP#57 completed | LTE | CA
1437 | 530123 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120887 | RP-121046 | Vodafone | tim.frost@vodafone.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | CA
1438 | 530223 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20-Perf | 4 | Rel-11 | R4 | 2011-09-20 08:00 | 2012-09-07 17:00 | 100% | RP-120887 | RP-121047 | Vodafone | tim.frost@vodafone.com | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
1439 | 530024 | LTE Advanced Carrier Aggregation of Band 8 and Band 20 | LTE_CA_B8_B20 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120888 | - | Vodafone | Luis.Anaya@vodafone.com | Stage 3. RP#58 completed | LTE | CA
1440 | 530124 | Core part: LTE Advanced Carrier Aggregation of Band 8 and Band 20 | LTE_CA_B8_B20-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120888 | RP-121600 | Vodafone | Luis.Anaya@vodafone.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | CA
1441 | 530224 | Perf. part: LTE Advanced Carrier Aggregation of Band 8 and Band 20 | LTE_CA_B8_B20-Perf | 4 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-120888 | RP-121601 | Vodafone | Luis.Anaya@vodafone.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141 | CA
1442 | 530026 | LTE Advanced Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120899 | - | SK Telecom | Haesung Park | Stage 3. RP#57 completed | LTE | CA
1443 | 530126 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120899 | RP-121042 | SK Telecom | Haesung Park | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | CA
1444 | 530226 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5-Perf | 4 | Rel-11 | R4 | 2011-09-21 08:00 | 2012-09-07 17:00 | 100% | RP-120899 | RP-121043 | SK Telecom | Haesung Park | RP#57 completed | 36.133, 36.141 | CA
1445 | 530027 | LTE Advanced Carrier Aggregation of Band 4 and Band 7 | LTE_CA_B4_B7 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121152 | - | Rogers Wireless | takwing.wan@rci.rogers.com | Stage 3. RP#58 completed | LTE | CA
1446 | 530127 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 7 | LTE_CA_B4_B7-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121152 | RP-121590 | Rogers Wireless | takwing.wan@rci.rogers.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new generic TR 36.850 | CA
1447 | 530227 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 7 | LTE_CA_B4_B7-Perf | 4 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-121152 | RP-121591 | Rogers Wireless | takwing.wan@rci.rogers.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
1448 | 540020 | LTE Advanced Carrier Aggregation of Band 11 and Band 18 | LTE_CA_B11_B18 | 3 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-120898 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Stage 3. RP#58 completed | LTE | CA
1449 | 540120 | Core part: LTE Advanced Carrier Aggregation of Band 11 and Band 18 | LTE_CA_B11_B18-Core | 4 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-120898 | RP-121602 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | CA
1450 | 540220 | Perf. part: LTE Advanced Carrier Aggregation of Band 11 and Band 18 | LTE_CA_B11_B18-Perf | 4 | Rel-11 | R4 | 2011-12-15 08:00 | 2012-12-07 17:00 | 100% | RP-120898 | RP-121603 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#58 completed | 36.133 | CA
1451 | 540021 | LTE Advanced Carrier Aggregation of Band 1 and Band 18 | LTE_CA_B1_B18 | 3 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-120892 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Stage 3. RP#57 completed | LTE | CA
1452 | 540121 | Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 18 | LTE_CA_B1_B18-Core | 4 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-120892 | RP-121052 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | CA
1453 | 540221 | Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 18 | LTE_CA_B1_B18-Perf | 4 | Rel-11 | R4 | 2011-12-13 08:00 | 2012-09-07 17:00 | 100% | RP-120892 | RP-121053 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#57 completed | 36.133, 36.141 | CA
1454 | 540022 | LTE Advanced Carrier Aggregation of Band 1 and Band 19 | LTE_CA_B1_B19 | 3 | Rel-11 | R4,R2 | 2011-12-12 08:00 | 2012-09-07 17:00 | 100% | RP-120866 | - | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | Stage 3. RP#56 completed. Updated WID RP-111765=>RP-120866 | LTE | CA
1455 | 540122 | Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19 | LTE_CA_B1_B19-Core | 4 | Rel-11 | R4,R2 | 2012-03-05 08:00 | 2012-09-07 17:00 | 100% | RP-120866 | RP-120552 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | CA
1456 | 540222 | Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 19 | LTE_CA_B1_B19-Perf | 4 | Rel-11 | R4 | 2011-12-12 08:00 | 2012-06-15 17:00 | 100% | RP-120866 | RP-120553 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#56 completed | 36.133, 36.141 | CA
1457 | 540023 | LTE Advanced Carrier Aggregation of Band 1 and Band 21 | LTE_CA_B1_B21 | 3 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-121173 | - | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | Stage 3. RP#57 completed. Updated WID RP-111764=>RP-121173 | LTE | CA
1458 | 540123 | Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 21 | LTE_CA_B1_B21-Core | 4 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-121173 | RP-121054 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | CA
1459 | 540223 | Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21 | LTE_CA_B1_B21-Perf | 4 | Rel-11 | R4 | 2011-12-13 08:00 | 2012-12-07 17:00 | 100% | RP-121173 | RP-121055 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#57 completed | 36.133, 36.141 | CA
1460 | 550018 | LTE Advanced Carrier Aggregation of Band 3 and Band 8 | LTE_CA_B3_B8 | 3 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-121162 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Stage 3. RP#58 completed | LTE | CA
1461 | 550118 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 8 | LTE_CA_B3_B8-Core | 4 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-121162 | RP-121586 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | CA
1462 | 550218 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8 | LTE_CA_B3_B8-Perf | 4 | Rel-11 | R4 | 2012-03-06 08:00 | 2012-12-07 17:00 | 100% | RP-121162 | RP-121587 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#58 completed | 36.133, 36.141 | CA
1463 | 580358 | Rel-11 intra-band Carrier Aggregation | - | 2 | Rel-11 | RP | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | CA
1464 | 520015 | LTE Advanced Carrier Aggregation in Band 38 | LTE_CA_B38 | 3 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110862 | - | Huawei | ronnie.zhang@huawei.com | Stage 3. RP#57 completed. WI only covers intra-band contiguous and not non-contiguous aspects | LTE | CA
1465 | 520115 | Core part: LTE Advanced Carrier Aggregation in Band 38 | LTE_CA_B38-Core | 4 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110862 | RP-121060 | Huawei | ronnie.zhang@huawei.com | RP#57 completed. TR 36.830 v100 for Information & Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new TR 36.833-1-38 [instead of 36.830] | CA
1466 | 520215 | Perf. part: LTE Advanced Carrier Aggregation in Band 38 | LTE_CA_B38-Perf | 4 | Rel-11 | R4 | 2011-06-08 08:00 | 2012-09-07 17:00 | 100% | RP-110862 | RP-121061 | Huawei | ronnie.zhang@huawei.com | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141 | CA
1467 | 520016 | LTE Advanced Carrier Aggregation in Band 41 | LTE_CA_B41 | 3 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-03-02 17:00 | 100% | RP-120249 | - | Clearwire | michael.hart@clearwire.com | RP#55 completed. WI only covers intra-band contiguous and not non-contiguous aspects. | LTE | CA
1468 | 520116 | Core part: LTE Advanced Carrier Aggregation in Band 41 | LTE_CA_B41-Core | 4 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-03-02 17:00 | 100% | RP-120249 | RP-120126 | Clearwire | michael.hart@clearwire.com | RP#55 completed. Updated WID RP-110673=>RP-120249. TR 36.827 v100 for Information + Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new TR 36.833-1-41 [instead of 36.827] | CA
1469 | 520216 | Perf. part: LTE Advanced Carrier Aggregation in Band 41 | LTE_CA_B41-Perf | 4 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-03-02 17:00 | 100% | RP-120249 | RP-120127 | Clearwire | michael.hart@clearwire.com | RP#55 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | CA
1470 | 530028 | LTE Advanced Carrier Aggregation in Band 7 | LTE_CA_B7 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-121193 | - | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | Stage 3. RP#57 completed. Updated WID RP-111356=>RP-121193. WI only covers intra-band contiguous and not non-contiguous aspects | LTE | CA
1471 | 530128 | Core part: LTE Advanced Carrier Aggregation in Band 7 | LTE_CA_B7-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-121193 | RP-121062 | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | RP#57 completed. TR 36.831 v100 for Information & Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new TR 36.833-1-07 [instead of 36.831] | CA
1472 | 530228 | Perf. part: LTE Advanced Carrier Aggregation in Band 7 | LTE_CA_B7-Perf | 4 | Rel-11 | R4 | 2011-09-20 08:00 | 2012-09-07 17:00 | 100% | RP-121193 | RP-121063 | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141 | CA
1473 | 450016 | UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest | 1 | Rel-11 | R4,R5 | 2009-09-18 08:00 | 2014-12-05 17:00 | 97% | RP-111381 | - | CATR | Guo Lin (guolin@emcite.com) | RP#54 Core completed | UTRA
1474 | 450116 | Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-Core | 2 | Rel-11 | R4 | 2009-09-18 08:00 | 2011-12-09 17:00 | 100% | RP-111381 | RP-111456 | CATR | Guo Lin (guolin@emcite.com) | RP#54 completed | 25.144, 25.914, 34.114
1475 | 520011 | Test part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-UEConTest | 2 | Rel-11 | R5 | 2011-06-07 08:00 | 2014-12-05 17:00 | 95% | RP-110629 | RP-140593 | ZTE | carolyn.tayl@zte.com.cn | RP#64 completion 06/14=>12/14 | 34.114
1476 | 500019 | Eight carrier HSDPA | 8C_HSDPA | 1 | Rel-11 | R1,R2,R3,R4 | 2010-09-15 17:00 | 2012-12-07 17:00 | 100% | RP-101419 | - | Ericsson | johan.hultell@ericsson.com | Stage 3. RP#57 completed | UTRA
1477 | 500119 | Core part: Eight carrier HSDPA | 8C_HSDPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2010-09-15 17:00 | 2012-06-15 17:00 | 100% | RP-101419 | RP-120971 | Ericsson | johan.hultell@ericsson.com | RP#57 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306
1478 | 500219 | Perf. part: Eight carrier HSDPA | 8C_HSDPA-Perf | 2 | Rel-11 | R4 | 2010-12-15 08:00 | 2012-12-07 17:00 | 100% | RP-101419 | RP-120972 | Ericsson | johan.hultell@ericsson.com | RP#57 completed | 25.101, 25.104, 25.133, 25.141
1479 | 500021 | UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc | 1 | Rel-11 | R4,R5 | 2010-12-10 08:00 | 2012-03-02 17:00 | 100% | RP-111244 | - | China Mobile | Li Nan (linan@chinamobile.com) | RP#53 Perf completed. Stage 3 | UTRA
1480 | 500121 | Perf. part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc-Perf | 2 | Rel-11 | R4 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-111244 | RP-110996 | China Mobile | Li Nan (linan@chinamobile.com) | RP#53 completed. TR 25.873v100 for Approval | 25.102, new TR 25.873
1481 | 530038 | Test part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc-UEConTest | 2 | Rel-11 | R5 | 2011-09-19 08:00 | 2012-03-02 17:00 | 100% | RP-111181 | RP-120052 | China Mobile | Ma Shuai (mashuai@chinamobile.com) | RP#55 completed | 34.108, 34.122
1482 | 500022 | Uplink Transmit Diversity for HSPA | HSPA_UL_TxDiv | 1 | Rel-11 | R1,R4,R2,R3,R5 | 2010-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-120367 | - | Huawei | zongjie.wang@huawei.com | Stage 2/3 | UTRA
1483 | 500122 | Core part: Uplink Transmit Diversity for HSPA - Closed Loop | HSPA_UL_TxDiv-CL-Core | 2 | Rel-11 | R1,R4,R2,R3 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120367 | RP-121542 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433
1484 | 500222 | Perf. part: Uplink Transmit Diversity for HSPA - Closed Loop | HSPA_UL_TxDiv-CL-Perf | 2 | Rel-11 | R4 | 2010-12-14 08:00 | 2013-09-06 17:00 | 100% | RP-120367 | RP-130477 | Huawei | zongjie.wang@huawei.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141
1485 | 500322 | Core part: Uplink Transmit Diversity for HSPA - Open Loop | HSPA_UL_TxDiv-OL-Core | 2 | Rel-11 | R4,R1,R2,R3 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120367 | RP-121544 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.133, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433
1486 | 500422 | Perf. part: Uplink Transmit Diversity for HSPA - Open Loop | HSPA_UL_TxDiv-OL-Perf | 2 | Rel-11 | R4 | 2010-12-14 08:00 | 2012-12-07 17:00 | 100% | RP-120367 | RP-121545 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.133
1487 | 590008 | Test part: Uplink Transmit Diversity for HSPA | HSPA_UL_TxDiv-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-06-13 17:00 | 100% | RP-130351 | RP-140767 | Qualcomm | Shubhang Vora (svora@qti.qualcomm.com) | RP#64 completed | 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
1488 | 510018 | Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config | 1 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-06-15 17:00 | 100% | RP-110308 | - | Telus Communications | jorge.delrio@telus.com | RP#56 Perf completed | UTRA
1489 | 510118 | Core part: Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config-Core | 2 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2011-12-09 17:00 | 100% | RP-110308 | RP-111463 | Telus Communications | jorge.delrio@telus.com | RP#54 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327
1490 | 510218 | Perf. part: Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config-Perf | 2 | Rel-11 | R4 | 2011-03-24 08:00 | 2012-06-15 17:00 | 100% | RP-110308 | RP-120475 | Telus Communications | jorge.delrio@telus.com | RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327
1491 | 510019 | Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA | 1 | Rel-11 | R4,R2,R3 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | RP-110416 | - | Ericsson | muhammad.kazmi@ericsson.com | - | UTRA
1492 | 510119 | Core part: Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA-Core | 2 | Rel-11 | R4,R2,R3 | 2011-06-15 08:00 | 2012-09-07 17:00 | 100% | RP-110416 | RP-120842 | Ericsson | muhammad.kazmi@ericsson.com | RP#56 completed | 25.101, 25.104, 25.133, 25.331, 25.423, 25.433
1493 | 510219 | Perf. part: Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA-Perf | 2 | Rel-11 | R4 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | RP-110416 | RP-130049 | Ericsson | muhammad.kazmi@ericsson.com | RP#59 completed | 25.101, 25.104, 25.133, 25.141
1494 | 510020 | Further Enhancements to CELL_FACH | Cell_FACH_enh | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2011-03-18 08:00 | 2014-09-12 17:00 | 88% | RP-111321 | - | Qualcomm | Ravi Agarwal | - | UTRA
1495 | 510120 | Core part: Further Enhancements to CELL_FACH | Cell_FACH_enh-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2011-03-18 08:00 | 2012-12-07 17:00 | 100% | RP-111321 | RP-121547 | Qualcomm | Ravi Agarwal | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.433
1496 | 510220 | Perf. part: Further Enhancements to CELL_FACH | Cell_FACH_enh-Perf | 2 | Rel-11 | R4 | 2011-03-24 08:00 | 2013-12-06 17:00 | 100% | RP-111321 | RP-131459 | Qualcomm | Heechoon Lee (heechoon@qti.qualcomm.com) | RP#62 completed | 25.101, 25.104, 25.133, 25.141
1497 | 600004 | Test part: Further Enhancements to CELL_FACH | Cell_FACH_enh-UEConTest | 2 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-09-12 17:00 | 45% | RP-130644 | RP-140601 | Ericsson | leif.mattisson@ericsson.com | RP#63 completion 03/14=>09/14 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3
1498 | 530034 | HSDPA Multiflow Data Transmission | HSDPA_MFTX | 1 | Rel-11 | R2,R1,R3,R4,R5 | 2011-09-19 08:00 | 2014-12-05 17:00 | 85% | RP-111375 | - | Nokia Siemens Networks | Alexander Sayenko | Stage 2,3 | UTRA
1499 | 530134 | Core part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111375 | RP-121551 | Nokia Siemens Networks | Alexander Sayenko | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.214, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433
1500 | 530234 | Perf. part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-Perf | 2 | Rel-11 | R4 | 2011-09-20 08:00 | 2013-09-06 17:00 | 100% | RP-111375 | RP-130959 | Nokia Siemens Networks | kamil.bechta@nsn.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141
1501 | 620016 | Test part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-UEConTest | 2 | Rel-11 | R5 | 2013-12-06 08:00 | 2014-12-05 17:00 | 35% | RP-131692 | RP-140768 | Qualcomm | Shubhang Vora (svora@qti.qualcomm.com) | - | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
1502 | 530035 | Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA | 1 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2013-12-06 17:00 | 100% | RP-111393 | - | Ericsson | johan.hultell@ericsson.com | Stage 3. RP#58 Core completed | UTRA
1503 | 530135 | Core part: Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111393 | RP-121549 | Ericsson | johan.hultell@ericsson.com | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306
1504 | 530235 | Perf. part: Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA-Perf | 2 | Rel-11 | R4 | 2011-09-21 08:00 | 2013-12-06 17:00 | 100% | RP-111393 | RP-131460 | Ericsson | johan.hultell@ericsson.com | RP#62 completed | 25.101, 25.104, 25.133, 25.141
1505 | 540009 | MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA | 1 | Rel-11 | R1,R2,R3,R4 | 2011-12-09 08:00 | 2013-09-06 17:00 | 99% | RP-121794 | - | Nokia Siemens Networks | Karri Ranta-aho | Specified UE and BS performance requirements for uplink MIMO together with QPSK and 16QAM modulations for E-DCH/HSUPA. 64QAM is for future releases | UTRA
1506 | 540109 | Core part: MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-121794 | RP-121554 | Nokia Siemens Networks | Karri Ranta-aho | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 25.423, 25.433, 26.306
1507 | 540209 | Perf. part: MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA-Perf | 2 | Rel-11 | R4 | 2011-12-13 08:00 | 2013-09-06 17:00 | 100% | RP-121794 | RP-130960 | Nokia Siemens Networks | kamil.bechta@nsn.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141
1508 | 540024 | HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC | 1 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-111746 | - | Ericsson | muhammad.kazmi@ericsson.com | Stage 3. RP#57 completed | UTRA
1509 | 540124 | Core part: HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC-Core | 2 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-111746 | RP-120987 | Ericsson | muhammad.kazmi@ericsson.com | RP#57 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327
1510 | 540224 | Perf. part: HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC-Perf | 2 | Rel-11 | R4 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-111746 | RP-120988 | Ericsson | muhammad.kazmi@ericsson.com | RP#57 completed | 25.101, 25.104, 25.141
1511 | 620015 | Split TTCN Test Models for IMS testing in TS 34.229-3 | IMS-CCR_Test2 | 1 | Rel-11 | R5 | 2013-12-09 08:00 | 2014-09-12 17:00 | 90% | RP-140440 | RP-140613 | Spirent | richard.catmur@spirent.com | RP#64 completion 06/14=>09/14. Split out of old TS 34.229-3 a new TS 34.229-4 | 34.229-3, New TS 34.229-4
1512 | 480004 | (Small) Technical Enhancements and Improvements for Rel-11 | TEI11 | 1 | Rel-11 | SP,CP,RP,GP | 2010-06-18 08:00 | 2012-09-20 17:00 | 100% | - | - | - | - | SP#50 EU-Alert is introduced under Public Warning System in parallel with the already existing ETWS and CMAS. SA1 22.268 CR#9r1 adds EU-ALERT specific requirements & CT1 23.041 CRs# | -
1513 | 560001 | Test - (Small) Technical Enhancements and Improvements for Rel-11 | TEI11_Test | 1 | Rel-11 | R5,G3new | 2012-06-15 08:00 | 2013-12-11 17:00 | 100% | - | - | - | - | - | -
1514 | 571004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-11 (RFC 7077) | TEI11_IETF | 1 | Rel-11 | C4-IETF | 2012-09-07 08:00 | 2013-12-06 17:00 | 100% | - | - | Lionel Morand | Lionel Morand | CP#62 completed | RFC 7077 (was draft-ietf-netext-update-notifications)
1515 | 0 | Release 11 Studies | - | 1 | Rel-11 | SP,CP,GP,RP | 2009-12-10 08:00 | 2012-09-14 17:00 | 100% | - | - | - | - | - | -
1516 | 450047 | Study on IMS based Peer-to-Peer Content Distribution Services | FS_IMS_P2P | 1 | Rel-11 | S1,S2 | 2009-05-12 08:00 | 2010-06-10 17:00 | 100% | SP-090491 | - | China Mobile | Li Gang (ligangyf@chinamobile.com) | SP#48 completed | 22.906
1517 | 460024 | Study on Non Voice Emergency Services | FS_NOVES | 1 | Rel-11 | S1 | 2009-12-10 08:00 | 2011-09-21 17:00 | 100% | SP-090897 | - | Qualcomm | dwilliams@qualcomm.com | SP#53 completed. Spin-off Feature UID_500030 Non Voice Emergency Services (NOVES) | 22.871
1518 | 480033 | Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX | FS_VINE | 1 | Rel-11 | S1,S2 | 2010-09-23 08:00 | 2011-03-23 17:00 | 100% | SP-100411 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#51 completed. Support Interworking between 3GPP networks and Enterprise environments to provide enterprise voice services via 3GPP mobile devices | 22.809
1519 | 490033 | Study on IMS Network-Independent Public User Identities | FS_INIPUI | 1 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-06-08 17:00 | 100% | SP-100652 | - | Vodafone | mona.mustapha@vodafone.com | SP#52 completed | 22.894
1520 | 410041 | Study on IMS Evolution | FS_eIMS | 1 | Rel-11 | S2 | 2008-09-18 08:00 | 2011-12-14 17:00 | 100% | SP-100360 | - | China Mobile | Li Gang (ligangyf@chinamobile.com), Yu Qing (yuqing@chinamobile.com) | SP#54 completed | 23.812
1521 | 440047 | Study on Policy solutions and enhancements | FS_PP | 1 | Rel-11 | S2,S1 | 2000-01-03 08:00 | 2002-01-03 17:00 | 100% | SP-090895 | - | AT&T | farooq.bari@att.com | SP#52 completed | 23.813
1522 | 440048 | Study on IPv6 Migration | FS_IP6M | 1 | Rel-11 | S2 | 2009-06-04 08:00 | 2011-06-08 17:00 | 100% | SP-090362 | - | China Mobile | Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com) | SP#52 completed | 23.975
1523 | 460030 | Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | FS_rSRVCC | 1 | Rel-11 | S2 | 2009-12-10 08:00 | 2011-12-14 17:00 | 100% | SP-090806 | - | Orange | delphin.barankanira@orange-ftgroup.com | SP#54 completed. Study on "reverse direction" from UTRAN/GERAN to E-UTRAN/HSPA (Rel-8 SRVCC was in the other direction E-UTRAN/HSPA to GERAN/UTRAN) | 23.885
1524 | 510044 | Study on Roaming Architecture for Voice over IMS with Local Breakout | FS_RAVEL | 1 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110087 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#54 completed. Linked to Rel-11 OSCAR (Optimized Service Charging and Allocation of Resources in IMS whilst Roaming) UID_490032. Related to LBO/home routing decision | 23.850
1525 | 380084 | Study on UTRAN key management enhancements | FS_UKM | 1 | Rel-11 | S3 | 2007-12-20 08:00 | 2012-03-07 17:00 | 100% | SP-090283 | - | Ericsson | karl.norrman@ericsson.com | SP#55 completed | 33.859
1526 | 480048 | Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest | FS_SSO_APS | 1 | Rel-11 | S3 | 2010-06-10 08:00 | 2012-06-20 17:00 | 100% | SP-100639 | - | Nokia | Silke.Holtmanns@nokia.com | SP#56 completed. SP#55 TR 33.914v200 approved (converted 33.804). Study reuse of non-UICC credentials (in particular SIP Digest) to provide security for access to applications. Provide reference material for IMS based non-UICC based SSO to applications | 33.914 converted to 33.804
1527 | 520036 | Study on Mobile 3D Video Coding | FS_M3DVC | 1 | Rel-11 | S4 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-110310 | - | Orange | gilles.teniou@orange-ftgroup.com | SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS | 26.905
1528 | 480047 | Study on Management of Converged Networks | FS_ManCon | 1 | Rel-11 | S5 | 2010-06-10 08:00 | 2012-09-12 17:00 | 100% | SP-100377 | - | Nokia Siemens Networks | Jörg Schmidt (J.Schmidt@nsn.com) | SP#57 completed. TR 32.833v200 for Approval | 32.833
1529 | 490039 | Study on User Data Convergence (UDC) information model handling and provisioning: Example Use Cases | FS_UDC_AppUseCase | 1 | Rel-11 | S5 | 2010-09-23 08:00 | 2011-12-14 17:00 | 100% | SP-110127 | - | Alcatel-Lucent | Nick Mazzarella (njmazzarella@alcatel-lucent.com) | SP#54 completed | 32.901
1530 | 510045 | Study on OAM aspects of inter-RAT Energy Saving | FS_OAM_ES_iRAT | 1 | Rel-11 | S5 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110138 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#54 completed. Triggered by Rel-10 UID_430044 TR 32.826 Study on Energy Savings Management (FS_OAM_ESM) and UID_470037 OAM aspects of Energy Saving in Radio Networks (OAM-ES) | 32.834 | SON
1531 | 480015 | Study on impacts on UE-Core Network signalling from Energy Saving | FS_UE-CN_ES | 1 | Rel-11 | C1 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-100330 | - | NEC | gottfried.punz@nw.neclab.eu | CP#52 completed. Linked to SA5 UID_430044 (FS_OAM-ESM) & UID_470037 (OAM-ES), RAN3 UID_470015 (FS_Energy_LTE), RAN1 UID_460016 (FS_Energy_UMTS) | 24.826
1532 | 490014 | Study on EPC Nodes Restoration | FS_EPC_NR | 1 | Rel-11 | C4 | 2010-09-17 08:00 | 2012-12-07 17:00 | 100% | CP-100700 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed. Continue work in Rel-11 especially to cover handling of Idle mode Signalling Reduction (ISR). Linked to SA2 UID_490036 Study on Core Network Overload solutions | 23.857
1533 | 480003 | Study on Signal Precoding enhancements for EGPRS2 DL | FS_SPEED | 1 | Rel-11 | G1,G2 | 2010-09-03 08:00 | 2012-03-02 17:00 | 100% | GP-111281 | - | Ericsson | marten.sundberg@ericsson.com | GP#53 completed (03/12). GP#46 approved WID. | GERAN 45.860
1534 | 470014 | Study on Coordinated Multi-Point operation for LTE | FS_CoMP_LTE | 1 | Rel-11 | R1,R2,R3 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101425 | RP-111343 | Samsung | bruno.clerckx@samsung.com | RP#53 completed | LTE 36.819
1535 | 480028 | Study on Signalling and procedure for interference avoidance for in-device coexistence | FS_SPIA_IDC | 1 | Rel-11 | R2,R4 | 2010-06-04 08:00 | 2011-09-16 17:00 | 100% | RP-100671 | RP-111057 | China Mobile | Zhenping Hu (huzhenping@chinamobile.com) | RP#53 completed. Studied coexistence scenario of LTE and Industrial, Scientific and Medical (ISM) Radio within the same device working in adjacent frequencies | LTE 36.816
1536 | 510034 | Study on HetNet mobility enhancements for LTE | FS_HetNet_eMOB_LTE | 1 | Rel-11 | R2,R1,R3,R4 | 2011-03-18 08:00 | 2012-09-07 17:00 | 100% | RP-110709 | RP-121085 | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | RP#57 completed. TR 36.839 v100 for Information & Approval | LTE 36.839
1537 | 510037 | Study on further Downlink MIMO enhancements for LTE-Advanced | FS_LTE_eDL_MIMO_enh | 1 | Rel-11 | R1 | 2011-03-18 08:00 | 2011-12-09 17:00 | 100% | RP-111366 | RP-111550 | Alcatel-Lucent | federico.boccardi@alcatel-lucent.com | RP#54 completed | LTE 36.871
1538 | 510039 | Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | FS_LTE_TDD_eIMTA | 1 | Rel-11 | R1,R4 | 2011-03-22 08:00 | 2012-06-15 17:00 | 100% | RP-110450 | RP-120587 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#56 completed. TR 36.828 for Information and Approval | LTE 36.828 | Small cell
1539 | 530053 | Study on LTE Coverage Enhancements | FS_Cov_Enh_LTE | 1 | Rel-11 | R1,R2 | 2011-09-19 08:00 | 2012-06-15 17:00 | 100% | RP-120225 | RP-120589 | China Telecom | Peng Chen (chenpeng@ctbri.com.cn) | RP#56 completed. TR 36.824 v200 for Approval | LTE 36.824
1540 | 530055 | Study on Enhanced performance requirement for LTE UE | FS_enh_perf_UE_LTE | 1 | Rel-11 | R4,R1 | 2011-09-19 08:00 | 2012-03-02 17:00 | 100% | RP-111378 | RP-120167 | NTT DoCoMo | Yuta Sagae | RP#55 completed. TR 36.829 v100 for Information + Approval | LTE 36.829
1541 | 550022 | Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology | FS_LTE_OTA | 1 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-09-07 17:00 | 100% | RP-120412 | RP-121083 | CATR | Xudong An (anxudong@emcite.com) | RP#57 completed | LTE 25.914, New TR 37.902
1542 | 430020 | Study on Measurement of Radiated Performance for MIMO and multi-antenna reception for HSPA and LTE terminals | FS_HSPA_LTE_measRP_MIMO_multi-antenna | 1 | Rel-11 | R4 | 2009-03-06 08:00 | 2012-03-02 17:00 | 100% | RP-111754 | RP-120154 | Vodafone | Tim.frost@vodafone.com | RP#55 completed. TR 37.976 v200 for Approval | UTRA, LTE 37.976
1543 | 440016 | Study on Extending 850 MHz | FS_e850 | 1 | Rel-11 | R4 | 2009-05-30 08:00 | 2012-09-07 17:00 | 100% | RP-090666 | RP-121080 | Ericsson | christian.bergljung@ericsson.com | RP#57 completed. TR 37.806 v200 for Approval | UTRA, LTE 37.806
1544 | 450015 | Study on RAN improvements for Machine-Type Communications | FS_NIMTC_RAN | 1 | Rel-11 | R2,R1,R3,R4 | 2009-09-18 08:00 | 2011-09-16 17:00 | 100% | RP-100330 | RP-111052 | Huawei | Jeff Gao (gaoyq@huawei.com) | RP#53 completed. TR 37.868v100 for Approval (No WID change: RAN overload only). Triggered by TR 22.868 Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) UID_7027 and Rel-10 NIMTC UID_410030 | UTRA, LTE 37.868 | MTC, M2M
1545 | 500002 | Study on UE Application Layer Data Throughput Performance | FS_UE_App_Data_Perf | 1 | Rel-11 | R5,R4 | 2010-09-16 08:00 | 2011-09-16 17:00 | 100% | RP-101422 | RP-111543 | Spirent | ron.borsato@spirent.com | RP#54 completed | UTRA, LTE 37.901
1546 | 510036 | Study on further enhancements for HNB and HeNB | FS_EHNB_enh | 1 | Rel-11 | R3,R2 | 2011-03-18 08:00 | 2012-06-15 17:00 | 100% | RP-120373 | RP-120579 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#56 completed. TR 37.803 v200 for Approval | UTRA, LTE 37.803 | HNB
1547 | 510038 | Study on Interference analysis between 800~900 MHz bands | FS_B800_B900_Interf_LTE | 1 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-06-15 17:00 | 100% | RP-111752 | RP-120586 | LG Uplus | Koo Yeon Sang (yskoo@lguplus.co.kr) | RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 | UTRA, LTE impacts TR 37.804
1548 | 520018 | Study on UMTS/LTE in 900 MHz band (Japan, Korea) | FS_UTRA_LTE_900MHz | 1 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | RP-120617 | RP-120580 | NTT DoCoMo | Masahiro Fujii (fujiima@nttdocomo.co.jp) | RP#56 completed. Updated WID RP-111751=>RP-120617. TR 37.804 v100 for Information and Approval. Linked to Study on Interference analysis between 800~900 MHz bands UID_510038 | UTRA, LTE 37.804
1549 | 500014 | Study on Uplink MIMO | FS_UTRA_UL_MIMO | 1 | Rel-11 | R1 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101432 | RP-111048 | Qualcomm | Sharad Sambhwani | RP#53 completed (1-step Approval) | UTRA 25.871
1550 | 500015 | Study on HSDPA Multipoint Transmission | FS_HSDPA_MP_TX | 1 | Rel-11 | R1,R2,R3 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101439 | RP-111049 | Nokia Siemens Networks | karri.ranta-aho@nsn.com | RP#53 completed | UTRA 25.872
1551 | 530057 | Study on UE Over The Air (OTA) test method with Head and Hand Phantoms | FS_OTA_phantoms_UTRA | 1 | Rel-11 | R4,R5 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120208 | RP-121078 | Nokia | petri.j.vasenkari@nokia.com | RP#57 completed | UTRA 25.914
1552 | 540026 | Study on HSPA feedback and signalling efficiency enhancements for LCR TDD | FS_LCRTDD_HSPAenh | 1 | Rel-11 | R1 | 2011-12-07 08:00 | 2012-09-07 17:00 | 100% | RP-111766 | RP-121079 | TD Tech | limei.wei@td-tech.com | RP#57 completed. TR 25.874 v100 for Information & Approval | UTRA 25.874
1553 | 510035 | Deleted - Study on Enhanced Uplink Transmission for LTE | FS_eUL_TX_LTE | 1 | Rel-11 | R1 | 2011-03-22 08:00 | 2012-06-15 17:00 | 100% | RP-120259 | RP-120585 | Huawei | Yongxing Zhou | RP#56 stopped. RP-120856 discussion: most content moved to Rel-11 Coordinated Multi-Point Operation for LTE – Uplink (COMP_LTE_UL) and RAN1 has no time to look at it | LTE 36.8xy
1554 | 0 | Release 10 Features | - | 1 | Rel-10 | CP,GP,RP,SP | 2008-12-11 08:00 | 2011-09-21 17:00 | 100% | - | - | - | - | - | -
1555 | 390073 | Enhancements for Multimedia Priority Service | eMPS | 1 | Rel-10 | S1,S2,C4,C3,C1 | 2006-03-13 08:00 | 2011-03-18 17:00 | 100% | SP-080051 | - | Telcordia | jgarraha@telcordia.com | CP#51 completed. SP#49 moved Stage 1 from Rel-9 & Completed Stage 2. SP#40 Stage 1 completed. Continuation of Rel-8 Feature PRIOR (UID_340044) | - | Public Safety (I-A)
1556 | 390074 | Stage 1 on enhancements for Multimedia Priority Service | ePRIOR | 2 | Rel-10 | S1 | 2006-03-13 08:00 | 2008-06-05 17:00 | 100% | SP-080051 | - | Telcordia | jgarraha@telcordia.com | ePRIOR started Mar 2006 as a Rel-8 Feature. It was delayed to Rel-9 (completed at SP#40), then moved to Rel-10 at SP#49 and demoted to Building Block level. | 22.153, 22.278 | Public Safety (I-A)
1557 | 460029 | Stage 2 on enhancements for Multimedia Priority Service | - | 2 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 completed. Updated WID SP-100166=>SP-100647 | - | Public Safety (I-A)
1558 | 460329 | Stage 2 on eMPS for CSFB | - | 3 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 completed | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | Public Safety (I-A)
1559 | 460429 | Stage 2 on eMPS for EPS Bearer Service | - | 3 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 completed | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | Public Safety (I-A)
1560 | 460529 | Stage 2 on eMPS for IMS Aspects | - | 3 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 completed | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | Public Safety (I-A)
1561 | 460229 | Deleted - TR 23.854 on Stage 2 on enhancements for Multimedia Priority Service | - | 2 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-12-16 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 TR 23.854 v100 for Information. SP#50 moved to Rel-11 SRVCC aspect of enhancements for Multimedia Priority Service UID_480135 (place holder for solution alternatives and agreed functions to be reflected in affected existing TS) | new TR 23.854 | Public Safety (I-A)
1562 | 490008 | Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 2 | Rel-10 | C4,C3,C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | Stage 3 | Public Safety (I-A)
1563 | 490108 | CT4 part on Stage 3 on enhancements for Multimedia Priority Service | - | 3 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 23.008, 29.002, 29.228, 29.229, 29.272, 29.274, 29.277, 29.328, 29.329 | Public Safety (I-A)
1564 | 490208 | CT3 part on Stage 3 on enhancements for Multimedia Priority Service | - | 3 | Rel-10 | C3 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 29.212, 29.213, 29.214 | Public Safety (I-A)
1565 | 490308 | CT1 part on Stage 3 on enhancements for Multimedia Priority Service | - | 3 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 24.008, 24.229, 24.301 | Public Safety (I-A)
1566 | 410030 | Network Improvements for Machine-Type Communications | NIMTC | 1 | Rel-10 | S1,S2,S5,C1,C4,C6,G2,R2,R3,R5,G3new | 2008-09-18 08:00 | 2013-11-22 17:00 | 100% | SP-100863 | - | KPN | toon.norp@tno.nl | Triggered by Rel-8 UID_7027 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) TR 22.868 | - | MTC, M2M
1567 | 410031 | Stage 1 for Network Improvements for Machine-Type Communications | - | 2 | Rel-10 | S1 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-100863 | - | KPN | toon.norp@tno.nl | SP#47 completed | 22.011, New 22.368 | MTC, M2M
1568 | 450028 | Deleted - TR on Stage 2 for Network Improvements for Machine-Type Communications | - | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-12-16 17:00 | 100% | SP-100863 | - | Samsung | erik.guttman@partner.samsung.com | SP#50 updated WID SP-090832=>SP-100863 (TR 23.888 not submitted for approval to conclude Rel-10 NIMTC as it will continue to serve as basis for Rel-11 SIMTC work item) | New TR 23.888 | MTC, M2M
1569 | 490037 | Stage 2 for Network Improvements for Machine-Type Communications | - | 2 | Rel-10 | S2 | 2010-08-30 08:00 | 2010-09-23 17:00 | 100% | SP-100863 | - | Samsung | erik.guttman@partner.samsung.com | SP#49 completed | 23.060, 23.236, 23.401 | MTC, M2M
1570 | 460023 | Deleted - Security for Network Improvements for Machine-Type Communications | - | 2 | Rel-10 | S3 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100863 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#49 stopped (activity transferred to Rel-11 Feature SIMTC under UID_490028 "TR on Security aspects of Machine-Type Communications". | New TR 33.868 | MTC, M2M
1571 | 510040 | Charging for Network Improvements for Machine-Type Communication | NIMTC-CH | 2 | Rel-10 | S5 | 2011-03-21 08:00 | 2011-03-23 17:00 | 100% | SP-110136 | - | Ericsson | patrik.teppo@@ericsson.com | SP#51 completed | 32.251, 32.298, 32.299 | MTC, M2M
1572 | 480005 | CN part of Stage 3 for Network Improvements for Machine-Type Communications | - | 2 | Rel-10 | C1,C4,C6 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | Stage 3 | MTC, M2M
1573 | 480105 | CT1 part of Stage 3 for Network Improvements for Machine-Type Communications | - | 3 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | 23.122, 24.008, 24.301, New 24.368 | MTC, M2M
1574 | 480205 | Deleted - CT3 part of Stage 3 for Network Improvements for Machine-Type Communications | - | 3 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 stopped (SA2 decided to move impact from CT3 to CT4). Updated WID CP-110147=>CP-110442 (no CT3 impact) | 29.212, 29.213, 29.215 | MTC, M2M
1575 | 480305 | CT4 part of Stage 3 for Network Improvements for Machine-Type Communications | - | 3 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | 23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.275, 29.282 | MTC, M2M
1576 | 510005 | CT6 part of Stage 3 for Network Improvements for Machine-Type Communications | - | 3 | Rel-10 | C6 | 2011-03-18 08:00 | 2011-06-03 17:00 | 100% | - | - | Sagem-Orga | heiko.kruse@sagem-orga.com | CP#52 completed | 31.102 | MTC, M2M
1577 | 490003 | GERAN part of Network Improvements for Machine-Type Communications (Stage 3) | - | 2 | Rel-10 | G2 | 2010-09-03 08:00 | 2011-09-02 17:00 | 100% | GP-101647 | - | Vodafone, Ericsson | leo.patanapongpibul@vodafone.com, john.diachina@ericsson.com | GP#51 completed. GP#47 approved WID | 44.018, 44.060 | MTC, M2M
1578 | 570003 | MS Conformance Test Aspects for GERAN - Network Improvements for Machine-Type Communications | NIMTC_GERAN-MSTest | 2 | Rel-10 | G3new | 2012-08-27 08:00 | 2013-11-22 17:00 | 100% | GP-121141 | - | ST-Ericsson | hakan.e.grunditz@stericsson.com | GP#60 completed. GP#55 approved WID. Testing for CT1 part of Stage 3 for NIMTC UID_480105, GERAN part of NIMTC (Stage 3) UID_490003 | 51.010-1, 51.010-2 | MTC, M2M
1579 | 490024 | RAN mechanisms to avoid CN overload due to Machine-Type Communications | NIMTC-RAN_overload | 2 | Rel-10 | R2,R3 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | RP-101026 | RP-110063 | Huawei | Jeff Gao (gaoyq@huawei.com) | RP#51 completed | UTRA, LTE 25.331, 25.413, 36.331, 36.413 | MTC, M2M
1580 | 570004 | UE Conformance Test Aspects - Network Improvements for Machine-Type Communications | NIMTC-UEConTest | 2 | Rel-10 | R5 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-121124 | RP-130465 | Ericsson | calle.hagenfeldt@ericsson.com | RP#60 completed. Testing for CT1 part of Stage 3 UID_480105, RAN mechanisms to avoid CN overload due to MTC UID_490024 | 34.123-1, 34.123-2, 34.123-3, 36.523-1, 36.523-2, 36.523-3 | MTC, M2M
1581 | 430035 | Multi Access PDN Connectivity | MAPCON | 1 | Rel-10 | S2,C4,C1,C3 | 2009-03-13 08:00 | 2011-03-18 17:00 | 100% | SP-090659 | - | Telecom Italia | ivano.guardini@telecomitalia.it | CP#51 completed. SP#49 Stage 2 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control) | -
1582 | 430135 | Stage 2 for Multi Access PDN Connectivity | - | 2 | Rel-10 | S2 | 2009-03-13 08:00 | 2010-09-23 17:00 | 100% | SP-090659 | - | Telecom Italia | ivano.guardini@telecomitalia.it | SP#49 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control) | 23.237, 23.401, 23.402
1583 | 500004 | CT aspects of Multi Access PDN Connectivity | MAPCON-St3 | 2 | Rel-10 | C4,C1,C3 | 2010-11-15 08:00 | 2011-03-18 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | -
1584 | 500104 | CT4 aspects of Multi Access PDN Connectivity | - | 3 | Rel-10 | C4 | 2010-11-15 08:00 | 2010-12-10 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#50 completed | 29.273, 29.272, 29.002, 23.008
1585 | 500204 | CT1 aspects of Multi Access PDN Connectivity | - | 3 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | 24.302, 24.312
1586 | 500304 | CT3 aspects of Multi Access PDN Connectivity | - | 3 | Rel-10 | C3 | 2010-11-15 08:00 | 2011-03-18 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | 29.215
1587 | 440052 | IMS Service Continuity – Inter Device Transfer enhancements | IMS_SC_eIDT | 1 | Rel-10 | S1,S2,C1,IETF | 2009-06-04 08:00 | 2012-12-07 17:00 | 100% | SP-090452 | - | Huawei | Amar Deol (adeol@huawei.com) | CP#51 completed. SP#47 Stage 1 completed. Rel-9 set Inter-Device Transfer requirements UID_410033 (IMS_SCC-IDT). Adds IDT scenarios and requirements | -
1588 | 440152 | Stage 1 - IMS Service Continuity – Inter Device Transfer enhancements | - | 2 | Rel-10 | S1 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090452 | - | Huawei | Amar Deol (adeol@huawei.com) | SP#47 completed | 22.228
1589 | 450029 | Stage 2 - IMS Inter-UE Transfer enhancements | - | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-100167 | - | Huawei | Lee Valerius (lvalerius@huawei.com) | SP#49 completed | 23.237, 23.292, new 23.831
1590 | 470001 | Stage 3 - IMS Inter-UE Transfer enhancements | - | 2 | Rel-10 | C1 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | CP-110285 | - | Huawei | georg.mayer@huawei.com | CP#51 completed. WID updated CP-100334=>CP-110285 | 24.216, 24.229, 24.237, new (24.837, 24.337)
1591 | 521001 | (IETF) Stage 3 - IMS Inter-UE Transfer enhancements | - | 2 | Rel-10 | C1-IETF | 2010-03-19 08:00 | 2012-12-07 17:00 | 100% | CP-110285 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature)
1592 | 450030 | IP-Short-Message-Gateway enhancements for CPM-SMS Interworking | CPM-SMS | 1 | Rel-10 | S1,S2,C3 | 2009-09-24 08:00 | 2010-09-17 17:00 | 100% | SP-090615 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | CP#49 completed. SP#47 Stage 1 completed. IP-SM-GW enhancements for interworking with OMA CPM | -
1593 | 450031 | Stage 1 for CPM-SMS | - | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-090615 | - | China Mobile | Qing Huang | SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C) | 22.340
1594 | 450032 | Stage 2 for CPM-SMS | - | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-090615 | - | Orange | antoine.mouquet@orange-ftgroup.com | SP#47 completed | 23.204, new TR 23.824
1595 | 460017 | Stage 3 for IP-Short-Message-Gateway enhancements for CPM-SMS Interworking | - | 2 | Rel-10 | C3 | 2009-12-04 08:00 | 2010-09-17 17:00 | 100% | CP-090859 | - | Ericsson | Jan Holm | CP#49 completed. Linked to Rel-8 UID_340031 Service-Level Interworking for Messaging Services (MESSIW) 23.204 | 29.311
1596 | 450033 | Completion of Communications on Not Logged-in | CCNL | 1 | Rel-10 | S1,C1,C3 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-090493 | - | Deutsche Telekom | Kurt Bischinger | CP#51 completed. SP#45 Stage 1 completed | -
1597 | 450034 | Stage 1 for Completion of Communications on Not Logged-in | - | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2009-09-24 17:00 | 100% | SP-090493 | - | Deutsche Telekom | Kurt Bischinger | SP#45 completed | 22.173 CR#0056r1
1598 | 470002 | CT1 part of Stage 3 for Completion of Communications on Not Logged-in | - | 2 | Rel-10 | C1 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | CP-100335 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#51 completed | 24.173, 24.642
1599 | 480006 | CT3 part of Stage 3 for Completion of Communications on Not Logged-in | - | 2 | Rel-10 | C3 | 2010-06-04 08:00 | 2010-09-17 17:00 | 100% | CP-100335 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#49 completed | 29.165
1600 | 450035 | Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 1 | Rel-10 | S2,S1,S3,S5,C4,C1 | 2009-09-24 08:00 | 2011-03-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | TSG#51 completed. Updated WID SP-100696=>SP-110131. SP#49 Stage 2 & Security completed. UID_400035 Enhanced Home NodeB/eNodeB (EHNB) formerly covered Local IP Access to Internet and Local access to Home Network from the Home NodeB/eNodeB | - | HNB
1601 | 450037 | Stage 1 for Local IP Access and Selected Internet IP Traffic Offload | - | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | Amar Deol (adeolf@huawei.com), Gang Li (ligangyf@chinamobile.com) | SP#47 completed | 22.101, 22.220 | HNB
1602 | 450036 | TR on Local IP Access and Selected Internet IP Traffic Offload | - | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#51 completed. TR 23.829 for Approval | New TR 23.829 | HNB
1603 | 450039 | Security for Local IP Access and Selected Internet IP Traffic Offload | - | 2 | Rel-10 | S3 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-110131 | - | Huawei, Qualcomm | Marcus Wong (mwong@huawei.com), Brian Rosenberg (bmr@qualcomm.com) | SP#49 completed | 33.102, 33.107, 33.108, 33.320, 33.401 | HNB
1604 | 450040 | OAM&P for Local IP Access and Selected Internet IP Traffic Offload | - | 2 | Rel-10 | S5 | 2009-09-24 08:00 | 2011-03-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | Zou Lan (zlan@huawei.com), Chen Gang (chengang@chinamobile.com) | SP#51 completed. Updated WID SP-100696=>SP-110131 | 32.581, 32.582, 32.584, 32.591, 32.592, 32.642, 32.646, 32.772, 32.782 | HNB
1605 | 460039 | Charging for Local IP Access and Selected Internet IP Traffic Offload | - | 2 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | shan.mingjun@huawei.com, Ai Chen (chenai@chinamobile.com) | SP#51 completed. Updated WID SP-100696=>SP-110131 | 32.251 | HNB
1606 | 450238 | Stage 2/3 for Local IP Access | LIPA | 2 | Rel-10 | S2,C4,C1 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | - | - | HNB
1607 | 450338 | Stage 2 for Local IP Access | - | 3 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#49 completed (has impacts to RAN) | 23.060, 23.401 | HNB
1608 | 480008 | Stage 3 for Local IP Access | - | 3 | Rel-10 | C4,C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | - | HNB
1609 | 480108 | CT4 part of Stage 3 for Local IP Access | - | 4 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | 23.008, 23.015, 29.002, 29.060, 29.272, 29.274, 29.281, 29.303 | HNB
1610 | 480208 | CT1 part of Stage 3 for Local IP Access | - | 4 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | 24.008, 24.301 | HNB
1611 | 450038 | Stage 2/3 for SIPTO for macro networks | SIPTO | 2 | Rel-10 | S2,C4,C1 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | - | - | HNB
1612 | 450138 | Stage 2 for SIPTO for macro networks | - | 3 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#49 completed (SIPTO GW selection for wild card APN and for GERAN. Serving-GW selection for SIPTO. Corrections and Clarifications of the SIPTO procedure) | 23.060, 23.401 | HNB
1613 | 480007 | Stage 3 for SIPTO for macro networks | - | 3 | Rel-10 | C4,C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#51 completed. Updated WID CP-100419=>CP-110091 | - | HNB
1614 | 480107 | CT4 part of Stage 3 for SIPTO for macro networks | - | 4 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#51 completed. Updated WID CP-100419=>CP-110091 | 23.003, 23.008, 29.002, 29.272, 29.303 | HNB
1615 | 480207 | CT1 part of Stage 3 for SIPTO for macro networks | - | 4 | Rel-10 | C1 | 2010-06-04 08:00 | 2010-12-10 17:00 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#50 completed | 24.008, 24.301 | HNB
1616 | 450041 | IP Flow Mobility and seamless WLAN offload | IFOM | 1 | Rel-10 | S2,S1,S5,C1,C3 | 2009-09-24 08:00 | 2011-03-23 17:00 | 100% | SP-100089 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#51 completed. Triggered by Rel-10 TR 23.861 (UID_410043 Study on Multi Access PDN connectivity and IP flow mobility - MAPIM) | - | WLAN
1617 | 450042 | Stage 1 for IP Flow Mobility and seamless WLAN offload | - | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2009-12-10 17:00 | 100% | SP-100089 | - | Qualcomm | David Williams (dwilliam@qualcomm.com) | SP#46 completed | 22.278 | WLAN
1618 | 450043 | Stage 2 for IP Flow Mobility and seamless WLAN offload | - | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-100089 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#49 completed | 23.203, 23.402, new 23.261 | WLAN
1619 | 470021 | Charging for IP Flow Mobility and seamless WLAN offload | - | 2 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100089 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#51 completed | 32.240, 32.251, 32.252, 32.298, 32.299 | WLAN
1620 | 480009 | Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 2 | Rel-10 | C1,C3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | Stage 3 | WLAN
1621 | 480109 | CT1 part of Stage 3 for IP Flow Mobility and seamless WLAN offload | - | 3 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | 24.008, 24.301, 24.302, 24.303, 24.312, 24.327 | WLAN
1622 | 480209 | CT3 part of Stage 3 for IP Flow Mobility and seamless WLAN offload | - | 3 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | 29.212, 29.213, 29.214, 29.215 | WLAN
1623 | 450044 | Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 1 | Rel-10 | S2,S4,C4,C3,C1,IETF | 2009-07-15 13:48 | 2012-09-07 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#52 completed. Triggered by Rel-9 UID_440013 Vocoder rate adaptation for LTE | UTRA, LTE
1624 | 450045 | TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 2 | Rel-10 | S2,S4 | 2010-01-07 08:00 | 2010-09-23 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#48 completed | new 23.860
1625 | 450145 | SA4 review of TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 2 | Rel-10 | S4 | 2009-09-24 08:00 | 2010-12-15 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#50 completed | new 23.860
1626 | 450046 | Stage 2 for Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#49 completed | 23.060, 23.203, 23.228, 23.401
1627 | 490038 | SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 2 | Rel-10 | S4 | 2010-09-23 08:00 | 2011-03-23 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#51 completed | 26.114
1628 | 490007 | CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 2 | Rel-10 | C4,C3,C1 | 2009-07-15 13:48 | 2012-09-07 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | Stage 2/3
1629 | 490107 | CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 3 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 23.334, 29.334, 29.238, 23.333, 29.333, 29.232, 29.332
1630 | 531006 | (IETF) CT3, CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 3 | Rel-10 | C3-IETF,C4-IETF | 2009-07-15 13:48 | 2012-09-07 17:00 | 100% | CP-100702 | - | Lionel Morand | - | CP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)
1631 | 490207 | CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 3 | Rel-10 | C3 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 29.162, 29.163, 29.213, 29.235, 29.292
1632 | 490307 | CT1 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | - | 3 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 24.229
1633 | 450053 | Extended H(e)NB features | EHNBF | 1 | Rel-10 | S1,S2,S3 | 2008-12-11 08:00 | 2010-09-23 17:00 | 100% | SP-100407 | - | NEC | joerg.swetina@neclab.eu | SP#49 completed. Adds extensions to Rel-9 functionality in UID_400035 Enhanced Home NodeB / eNodeB (EHNB) | UTRA, LTE | HNB
1634 | 450153 | Stage 1 of Extended H(e)NB features | - | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-100407 | - | NEC | joerg.swetina@neclab.eu | SP#47 completed | 22.220 | HNB
1635 | 420034 | IMS aspects of Architecture for Home NodeB | EHNB-IMS | 2 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080799 | - | Alcatel-Lucent | Nicolas Drevon | SP#47 completed. Chosen solution has no normative impacts | New 23.832 | HNB
1636 | 480034 | Extended H(e)NB Security features (Stage 2) | EHNBF-Sec | 2 | Rel-10 | S3 | 2010-06-10 08:00 | 2010-09-23 17:00 | 100% | SP-100257 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#49 completed | 33.320 | HNB
1637 | 460028 | Optimal Media Routing | OMR | 1 | Rel-10 | S2,S5,C3,C1 | 2010-03-25 17:00 | 2011-06-08 17:00 | 100% | SP-090803 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | CP#52 completed. SP#47 Stage 2 completed. Triggered by TR 23.894 (UID_370050 Study on System enhancements for the use of IMS services in local breakout) | -
1638 | 460128 | Stage 2 for Optimal Media Routing | - | 2 | Rel-10 | S2 | 2010-03-25 17:00 | 2010-03-25 17:00 | 100% | SP-090803 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#47 completed | 23.228
1639 | 480010 | Stage 3 for Optimal Media Routing | - | 2 | Rel-10 | C3,C1,C4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 completion 03/11=>06/11. WID updated CP-100327=>CP-110134 | -
1640 | 480110 | CT3 part of Stage 3 for Optimal Media Routeing | - | 3 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#52 completed | 29.162, 29.163, 29.165, 29.235, new TS 29.079
1641 | 480210 | CT1 part of Stage 3 for Optimal Media Routeing | - | 3 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 completed. WID updated CP-100327=>CP-110134 | 24.229
1642 | 480310 | Deleted - CT4 part of Stage 3 for Optimal Media Routeing | - | 3 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134 | -
1643 | 500013 | Charging for Optimal Media Routing | - | 2 | Rel-10 | S5 | 2010-12-16 08:00 | 2011-06-08 17:00 | 100% | SP-100772 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#52 completed. Stage 3: Linked to CT3 TS 29.079 OMR within the IMS; Stage 3 (UID_480110) | 32.260, 32.298, 32.299
1644 | 470026 | IMS Emergency Session Enhancements | IESE | 1 | Rel-10 | S1,S2,C1 | 2010-03-25 08:00 | 2011-06-03 17:00 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | michele.zarri@t-mobile.co.uk | CP#52 completed. SP#49 completed. Source of external requirements: ETSI TISPAN TS 181.019 (Business Communication Requirements) | - | Public Safety (I-A)
1645 | 470027 | Stage 1 for IMS Emergency Session Enhancements | - | 2 | Rel-10 | S1 | 2010-03-25 08:00 | 2010-03-25 17:00 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | Kurt Bischinger | SP#47 completed | 22.101 CR#0343 | Public Safety (I-A)
1646 | 470028 | Stage 2 for IMS Emergency Session Enhancements | - | 2 | Rel-10 | S2 | 2010-03-25 08:00 | 2010-09-23 17:00 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | michele.zarri@t-mobile.co.uk | SP#49 completed | 23.167 | Public Safety (I-A)
1647 | 500005 | Stage 3 for IMS Emergency Session Enhancements | - | 2 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-06-03 17:00 | 100% | CP-100880 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#52 completed | 24.229 | Public Safety (I-A)
1648 | 480037 | S2b Mobility based on GTP | SMOG | 1 | Rel-10 | S2,C4,C3,C1 | 2010-06-10 08:00 | 2011-03-18 17:00 | 100% | SP-100357 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed. SP#49 Stage 2 completed. Related to Rel-10 UID_470049 Study on S2b mobility based on GTP (TR23.834), UID_350027 SAE for support for non-3GPP accesses. Stage1 in Rel-8 UID_320022 Reqs for evolution of 3GPP system architecture (AIPN-SAE) | - | WLAN
1649 | 480137 | Stage 2 for S2b Mobility based on GTP | - | 2 | Rel-10 | S2 | 2010-06-10 08:00 | 2010-09-23 17:00 | 100% | SP-100357 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | SP#49 completed | 23.002, 23.203, 23.402 | WLAN
1650 | 490009 | Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 2 | Rel-10 | C4,C3,C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 Stage 3 completed | - | WLAN
1651 | 490109 | CT4 part of Stage 3 for S2b Mobility based on GTP | - | 3 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed | 23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303 | WLAN
1652 | 490209 | CT3 part of Stage 3 for S2b Mobility based on GTP | - | 3 | Rel-10 | C3 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed | 29.212, 29.213, 29.215 | WLAN
1653 | 490309 | CT1 part of Stage 3 for S2b Mobility based on GTP | - | 3 | Rel-10 | C1 | 2010-09-17 08:00 | 2010-12-10 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#50 completed | 24.302 | WLAN
1654 | 500006 | Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST | 1 | Rel-10 | S2,C3 | 2010-10-12 15:48 | 2011-03-18 17:00 | 100% | SP-110196 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#51 completed. SP#50 Stage 2 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047. Provides Video Call seamless service continuity for 3G/LTE terminal user | -
1655 | 500106 | Stage 2 for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | - | 2 | Rel-10 | S2 | 2010-10-12 15:48 | 2010-12-15 17:00 | 100% | SP-110196 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#51 updated WID SP-100702=>SP-110196. SP#49 work completed as SA2 CRs approved under TEI10 (SP-10557) | 23.002, 23.203
1656 | 500206 | CT3 aspects of Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST-CT3 | 2 | Rel-10 | C3 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100860 | - | ZTE | zhou.xiaoyun@zte.com.cn | CP#51 completed | 29.212, 29.213, 29.214, 29.215
1657 | 470029 | Lawful Interception in the 3GPP Rel-10 | LI10 | 1 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106 (LI requirements), 33.107 (LI architecture and functions), 33.108 (Handover interface for LI)
1658 | 470129 | LI for CAT (Customer Alerting Tones) | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108
1659 | 470229 | LI for CRS (Customized Ringing Signal) | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108
1660 | 470329 | LI for EPS enhancements | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108
1661 | 470429 | LI for VCC (Voice Call Continuity) | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108
1662 | 470529 | LI for MEDIASEC (IMS Media security) | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108
1663 | 470629 | LI for H(e)NB also with Local IP Access and Selected IP Traffic Offload (LIPA, SIPTO) | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108
1664 | 470729 | LI for MBMS enhancements | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108
1665 | 470829 | LI for LCLS (Local Call Local Switch) | - | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108
1666 | 470033 | Optimization of IMS based PSS and MBMS User Service | OPT_IMS_PSS_MBMS_US | 1 | Rel-10 | S4 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100031 | - | Ericsson | markus.kampmann@ericsson.com | SP#51 completed. Work to enhance UID_430046 Rel-9 IMS_PSS_MBMS_US_EXT | 26.237
1667 | 470034 | HTTP-based Streaming and Download Services | HTTP_SDS | 1 | Rel-10 | S4,IETF | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-100032 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#52 completed. Work to enhance UID_430038 Rel-9 PSS and MBMS extensions | -
1668 | 470134 | HTTP-based Streaming and Download Services in 3GPP | - | 2 | Rel-10 | S4 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100032 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#52 completed | 26.234, 26.244, 26.346, new TS 26.247
1669 | 521002 | (IETF) HTTP-based Streaming and Download Services in 3GPP | - | 2 | Rel-10 | S4-IETF | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-100032 | - | - | - | SP#53/IETF#81: Draft not included in 3GPP documentation | draft-gellens-mime-bucket-bis
1670 | 480040 | PSS and MBMS enhancements | MBS_Enh | 1 | Rel-10 | S4 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100305 | - | Ericsson | Markus.Kampmann@ericsson.com | SP#51 completed. Linked to Rel-9 Feature UID_430038 PSS and MBMS extensions (PMA-MBS_Ext). | 26.234, 26.346
1671 | 480041 | Enhancements and Addition of Audio Tests to 26.131 and 26.132 | EAAT | 1 | Rel-10 | S4 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-100306 | - | Vodafone | ramin.afchar@vodafone.com | SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec | 26.131, 26.132
1672 | 510055 | Video Coding Enhancements in MTSI | VCEM | 1 | Rel-10 | S4 | 2011-03-21 08:00 | 2011-03-23 17:00 | 100% | SP-110050 | - | Ericsson | frederic.gabin@ericsson.com | SP#51 completed. Linked to Rel-7 UID_7040 Multimedia Telephony Service for IMS - Media handling and interaction in MTSI (MTSI-MHI) | 26.114
1673 | 460031 | Rel-10 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM10 | 1 | Rel-10 | S5,C4 | 2009-12-10 08:00 | 2011-09-21 17:00 | 100% | - | - | - | - | OAM10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI | TR 30.820 | -
1674 | 460032 | Rel-10 Network Infrastructure Management | OAM10-NIM | 2 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-09-21 17:00 | 100% | - | - | - | - | umbrella BB | - | -
1675 | 460033 | Common RAT Network Resource Model (NRM) | RAT_NRM_common | 3 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-06-08 17:00 | 100% | SP-100293 | - | Ericsson | robert.petersen@ericsson.com | SP#52 completed. Share equipment btw several RATs (RET,TMA,repeaters) to reduce costs. With existing modelling is difficult to see that several cells are affected when an antenna tilt is changed etc | 32.616, 32.642, 32.646, 32.652, 32.656, 32.762, 32.766 new (32.791, 32.792, 32.796) | -
1676 | 470035 | IRP Solution Set specification organisation improvements | OAM-IRP-SS | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100774 | - | Nokia Siemens Networks, Huawei | Jörg Schmidt (J.Schmidt@nsn.com), Lan Zou (zlan@huawei.com) | SP#51 completed | 32.153, new (32.111-6,32.126,32.176,32.306,32.316,32.326,32.336,32.346,32.356,32.366,32.376,32.386,32.396,32.416,32.446,32.506/26/36,32.606,32.616,32.626,32.636,32.646,32.656,32.666,32.676,32.696,32.716,32.726,32.736,32.746,32.756,32.766,32.776,32.786)
1677 | 470036 | Deleted - Service Oriented Architecture (SOA) for IRP continuation from Rel-9 | OAM-SOA-IRP | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100076 | - | Nokia Siemens Networks, Ericsson | Jörg Schmidt (J.Schmidt@NSN.com), edwin.tse@ericsson.com | SP#51 work stopped (Reason: lack of progress). Continuation of Rel-9 UID_440065 SOA for IRP (covering SOA Architecture & SOA-supporting Solution Set) to address SOA conforming Registration & Discovery capabilities | 32.101, 32.150
1678 | 480042 | IRP Overview, Profiles & Usage Guide | OAM-NIM-IRP_OPU | 3 | Rel-10 | S5 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-110277 | - | Nokia Siemens Networks | Jörg Schmidt (J.Schmidt@NSN.com) | SP#52 completed. Updated WID SP-100777=>SP-110277 | new TS 32.103
1679 | 510041 | Alarm Correlation and Root Cause Analysis | OAM-AC-RCA | 3 | Rel-10 | S5 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-110137 | - | Ericsson | brendan.hassett@ericsson.com | SP#53 completed. Triggered by Rel-10 TR 32.832 Study on Alarm Correlation and Alarm Root Cause Analysis UID_480045 & TR 32.829 Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program Fault Management UID_460038 | 32.111-1, 32.111-2, 32.111-6
1680 | 510042 | Inventory Management Network Resource Model enhancements | OAM-IM-NMR | 3 | Rel-10 | S5 | 2011-03-23 08:00 | 2011-06-08 17:00 | 100% | SP-110141 | - | Nokia Siemens Networks | olaf.pollakowski@nsn.com | SP#52 completed. Inventory NRM specified in Rel-6 is mainly hardware related. Rel-10 TR 32.828 recommends extending the scope of inventory NRM. Additionally, NGMN Top OPE Recs, v1.0 sets inventory enhancements as one of top 10 priority items | 32.690, 32.691, 32.692, 32.696
1681 | 460034 | Rel-10 Self-Organizing Networks (SON) - OAM aspects | OAM10-SON | 2 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-06-08 17:00 | 100% | - | - | - | - | umbrella BB | - | SON
1682 | 460035 | SON Self-optimization management continuation | LTE-SON-OAM_SO | 3 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-06-08 17:00 | 100% | SP-110130 | - | Huawei | Lan Zou (zlan@huawei.com) | SP#52 completed. Cont'd Rel-9 SON self-optimization management UID_390007 | 32.425, 32.521, 32.522, 32.526, 32.762, 32.766 | SON
1683 | 460036 | SON Self-healing management | LTE-SON-OAM_SH | 3 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-110150 | - | ZTE | zhu.weihong@zte.com.cn | SP#51 completed. WID updated SP-100776=>SP-110150. Work moved to Rel-10 after split of the Rel-9 UID_390007 SON self-optimization (removed Self-Healing handling) | 32.522, 32.526, 32.762, 32.766, new TS 32.541 | SON
1684 | 470037 | OAM aspects of Energy Saving in Radio Networks | OAM-ES | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-110128 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#51 completed. WID updated SP-100226=>SP-110128. Triggered by Rel-10 TR 32.826 Study on Telecommunication Management; Energy Savings Management (FS_OAM_ESM) UID_430044 | 32.425, 32.522, 32.526, 32.626, 32.762, 32.766, new TS 32.551 | SON
1685 | 470038 | Rel-10 Subscription Management (SuM) evolution | OAM10-SuM | 2 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100086 | - | Ericsson | leo.yang@ericsson.com | SP#51 completed | 32.172, 32.175, 32.176
1686 | 470039 | Rel-10 Performance Management | - | 2 | Rel-10 | S5,C4 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | - | - | - | - | umbrella BB | -
1687 | 470040 | Key Performance Indicators (KPIs) for IMS | OAM-PM-KPI_IMS | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100083 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#51 completed | new 32.454
1688 | 470041 | Key Performance Indicators (KPIs) for EPC | OAM-PM-KPI_EPC | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100084 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#51 completed | new 32.455
1689 | 470042 | Management of UE based network performance measurements | OAM-PM-UE | 3 | Rel-10 | S5,C4 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100612 | - | Huawei, Nokia Siemens Networks, Ericsson | Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com | SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE) | -
1690 | 470142 | SA5 aspects of Management of UE based network performance measurements | - | 4 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100612 | - | Huawei, Nokia Siemens Networks, Ericsson | Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com | SP#52 completed | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446
1691 | 510006 | CN aspects of Management of UE based network performance measurements | - | 4 | Rel-10 | C4 | 2011-02-21 08:00 | 2011-03-18 17:00 | 100% | - | - | Nokia Siemens Networks | ulrich.wiehe@nsn.com | CP#51 completed under the SA5 WI code | 23.008 (CR#0330), 29.002 (CR#1007), 29.230 (CR#0207), 29.272 (CR#0329)
1692 | 470043 | 3G HNB and LTE HeNB Subsystem performance measurements | OAM-PM-HeNS | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100081 | - | China Mobile | Chen Gang (chengang@chinamobile.com) | SP#51 completed | 32.582, 32.592, new (32.452, 32.453) | HNB
1693 | 470044 | Rel-10 Charging Management small Enhancements | CH10 | 1 | Rel-10 | S5 | 2009-06-04 08:00 | 2011-03-23 17:00 | 100% | - | - | - | - | CH10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI | TR 30.820 | WLAN
1694 | 440063 | IWLAN mobility charging | eIWLAN_Mob | 2 | Rel-10 | S5 | 2009-06-04 08:00 | 2011-03-23 17:00 | 100% | SP-100090 | - | Orange | Jean-Luc Garcia (jl.garcia@orange-ftgroup.com) | SP#51 completed. RAT differentiation for charging. Completes Rel-8 Feature IWLAN_Mob UID_370049 Mobility between 3GPP-WLAN Interworking and 3GPP Systems. Cooperation with CT1,CT3 on affected protocols | 32.240, 32.252, 32.298, 32.299 | WLAN
1695 | 470046 | Advice of Charge (AoC) service support enhancements | eAoC | 1 | Rel-10 | S5,C1 | 2010-03-25 08:00 | 2011-06-03 17:00 | 100% | SP-100080 | - | Deutsche Telekom | matthias.seibel@telekom.de | CP#52 completed. SP#51 completed SA5. Continuation of Rel-8 BB UID_80042: Advice of Charge (AoC) support in IMS Charging (IMSTSS). Stage 2/3 work | -
1696 | 470047 | SA5 part - AoC enhancements | - | 2 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100080 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#51 completed. SA1 Stage 1 in 22.115 | 32.275, 32.280, 32.298, 32.299
1697 | 490010 | CT1 part - AoC enhancements (Stage 3) | - | 2 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100645 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#52 completed. SA1 Stage 1 in 22.115, 22.173, 22.024. Add mobile-specific CAI format and volume charging elements. Extensions to existing AoC XML | 24.647
1698 | 470003 | IMS Stage 3 IETF Protocol Alignment - phase 4 | IMSProtoc4 | 1 | Rel-10 | C1 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | CP-100099 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#51 completed. Ensure protocol alignment between 3GPP Stage 3 IMS work and IETF. Review capabilities provided in SIP by IETF and document whether these capabilities are supported in the IM CN Subsystem or not | 23.218, 24.229, 24.930
1699 | 480012 | Enhanced User Data Convergence (UDC) Model | eUDC | 1 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100295 | - | China Mobile | Lan Sizhong (lansizhong@chinamobile.com) | CP#51 completed. Specify CRUD (Create/Read/Update/Delete) operations based on SOAP protocol, which may be used by the applications having no high real-time requirement to the data access operations | 29.335
1700 | 480014 | Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications | II-NNI2 | 1 | Rel-10 | C3 | 2010-06-04 08:00 | 2013-03-01 17:00 | 100% | CP-100326 | - | Orange | beata.dobrowolska@orange-ftgroup.com | Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI) | -
1701 | 480114 | Further improvements of II-NNI Stage 3 | - | 2 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100326 | - | Orange | beata.dobrowolska@orange-ftgroup.com | CP#51 completed | 29.165
1702 | 561001 | (IETF) Further improvements of II-NNI Stage 3 (RFC 6794) | - | 2 | Rel-10 | C3-IETF | 2012-04-20 08:00 | 2013-03-01 17:00 | 100% | CP-100326 | - | Lionel Morand | Lionel Morand | CP#59 completed AUTH 48 RFC-to-be-6794 | RFC 6794 (was draft-ietf-sip-session-policy-framework)
1703 | 561002 | (IETF) Further improvements of II-NNI Stage 3 (RFC 6809) | - | 2 | Rel-10 | C3-IETF | 2012-04-20 08:00 | 2012-12-07 17:00 | 100% | CP-100326 | - | christer.holmberg@ericsson.com | Christer Holmberg | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature)
1704 | 480013 | AT Commands for IMS-configuration | AT_IMS | 1 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100376 | - | Ericsson | atle.monrad@ericsson.com | CP#51 completed. Specify 1) IMS-related AT-commands to configure MT and 2) IMS-related unsolicited response codes from MT to present to end-user | 27.007
1705 | 490011 | AT Commands for USIM Application Toolkit (USAT) | AT_UICC | 1 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100646 | - | ST-Ericsson | magnus.mk.karlsson@stericsson.com | CP#51 completed | 27.007
1706 | 490012 | Communication Control for IMS by USIM (Stage 3) | CC_IMS_USIM | 1 | Rel-10 | C6 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100647 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed. Stage 1 in TS 22.038 USAT service description. Linked to CT6's UID_1273 Rel-5 BB Provisioning of IP-based multimedia services (24.229, 31.103) and UID_390021 Rel-8 BB CT6 aspects of SAE (31.102, 31.111) | 31.102, 31.103, 31.111
1707 | 500003 | Dynamic view of SIP message for Inter-IMS Network to Network Interface (II-NNI) (Stage 3) | NNI_DV | 1 | Rel-10 | C3 | 2010-12-10 08:00 | 2011-06-03 17:00 | 100% | CP-100795 | - | NTT | arai.kenjiro@lab.ntt.co.jp | CP#52 completed. Linked to CT3 Rel-10 Feature UID_480014 Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications (II-NNI2) | 29.165
1708 | 500007 | Introduction of Smart Card Web Server launch functionality | SCWS_L | 1 | Rel-10 | C6 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100883 | - | Telecom Italia | davide.pratone@telecomitalia.it | CP#51 completed. Define a solution which allows enabling to launch Smart Card Web Server services in an easy and simple manner | 31.102
1709 | 500008 | USAT using AT Commands | USAT_AT | 1 | Rel-10 | C6 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100884 | - | Giesecke & Devrient | enric.fort@gi-de.com | CP#51 completed. Stage 3 based on SA1 22.038CR#37r1 (Make USAT proactive capability reqs applicable to ME as a whole without regard to any particular configuration; e.g. a modem connected to an external display) | Stage 3 31.102, 31.111
1710 | 500010 | Single Radio Voice Call Continuity (SRVCC) enhancements (Stage 3) | eSRVCC | 1 | Rel-10 | C1,C4,IETF | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | Triggered by SA2 TR 23.856 Study on Single Radio Voice Call Continuity enhancements (FS_eSRVCC) UID_440049 | -
1711 | 500110 | CT1 part of Stage 3 for SRVCC enhancements | - | 2 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | CP#51 completed | 24.229, 24.237
1712 | 500210 | CT4 part of Stage 3 for SRVCC enhancements | - | 2 | Rel-10 | C4 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | CP#51 completed | 23.003, 23.008, 29.002, 29.230, 29.272, 29.305, 29.328, 29.329
1713 | 521003 | (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809) | - | 2 | Rel-10 | C1-IETF | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | CP-100881 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature)
1714 | 500011 | Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3) | aSRVCC | 1 | Rel-10 | C1,R5 | 2010-12-10 08:00 | 2013-03-01 17:00 | 100% | CP-110145 | - | ZTE | li.shitao@zte.com.cn | Builds on Rel-8 UID_390057 (IMS-Cont) TS 23.216 Stage 2. Provide Stage 3 for SRVCC PS-CS transfer of a call in alerting phase. Stage 2 TEI10 in TS 23.237 (6.3.2.1.4c/d, 6.3.2.1.7a/b) | -
1715 | 500111 | CT aspects of Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3) | - | 2 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-06-03 17:00 | 100% | CP-110145 | - | ZTE | li.shitao@zte.com.cn | CP#52 completed | 24.008, 24.237
1716 | 570005 | Conformance test aspects SRVCC in alerting phase | aSRVCC-UEConTest | 2 | Rel-10 | R5 | 2012-09-11 08:00 | 2013-03-01 17:00 | 100% | RP-121700 | RP-130042 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#59 completed | 36.523-1, 36.523-2, 36.523-3, 34.229-1, 34.229-2, 34.229-3
1717 | 500012 | PCRF failure and restoration | PCRF_FR | 1 | Rel-10 | C4,C3 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed. Triggered by CT3 TR 29.816 Study on Policy and Charging Rules Function (PCRF) failure and restoration (FS_PCRF-FR) UID_450013 | Stage 2/3 work
1718 | 500112 | CT4 part of PCRF failure and restoration | - | 2 | Rel-10 | C4 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed | Stage 2 23.007, Stage 3 29.230
1719 | 500212 | CT3 part of PCRF failure and restoration | - | 2 | Rel-10 | C3 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed | Stage 3 29.212, 29.213, 29.214, 29.215
1720 | 510002 | Formalization of WLAN Files | FoWF | 1 | Rel-10 | C1 | 2011-02-23 08:00 | 2011-03-18 17:00 | 100% | CP-110288 | - | Deutsche Telekom | dieter.jacobsohn@telekom.de | CP#51 completed. TS 24.235 for Info+Approval. Define the ME files as specified in 24.234 in OMA Device Management structure | Stage 3: 24.234, New 24.235 | WLAN
1721 | 510007 | CS and IMS Interworking for CAT service - Early Session model | CIIC_ES | 1 | Rel-10 | C3 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110283 | - | ZTE | li.shitao@zte.com.cn | CP#52 completed. Stage 1 in Rel-8 TS 22.182 Customized Alerting Tones (CAT) service. Stage 3 TS 24.182 defines 3 impl models: Gateway, Forking, Early Session. Specify missing CAT service interworking procedures btw CS & IMS networks | Stage 3 29.163, 29.235, 29.292
1722 | 510008 | EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated | EPC_NR | 1 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | CP-110092 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014 | Stage 2/3: 23.007, 29.274
1723 | 510108 | EPC Node Restoration with Idle mode Signalling Reduction (ISR) activated | EPC_NR_ISR | 1 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110287 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#52 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014 | Stage 2/3: 23.007, 29.274
1724 | 510009 | Mobile Terminating Roaming Forwarding with pre-paging | MTRF | 1 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110093 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed. Provides Stage 2/3 alternative solution to Mobile Terminating Roaming Retry to solve roaming events during paging, in particular to support CSFB. Hence, no new Stage 1 requirements exist | Stage 2/3: 23.012, 23.018, 23.116, 29.002
1725 | 510010 | UICC access to IMS Specification | IMS-UICC-S | 1 | Rel-10 | C6,C1 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#52 completed. Triggered by Rel-10 TR 31.828 Study on UICC access to IMS (FS_IMS-UICC) UID_480017. Specify mechanism in UICC and ME to make use of IMS functionality implemented in ME for case a) an ISIM is present b) no ISIM is present in UICC | -
1726 | 510110 | CT6 part of UICC access to IMS Specification | - | 2 | Rel-10 | C6 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed | 31.102, 31.103, 31.111
1727 | 510210 | CT1 part of UICC access to IMS Specification | - | 2 | Rel-10 | C1 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#52 completed | 24.229
1728 | 550006 | Deleted - Testing for Terminal support of Rel-10 USIM, ISIM and USAT features | USIM_R10_Test | 1 | Rel-10 | C6 | 2012-03-05 08:00 | 2013-12-03 17:00 | 100% | CP-120396 | - | Gemalto | Denis.Praca@gemalto.com | CP#62 stopped (at 70% completion 06/13). Testing for New features in Rel-10 specifications for USIM, ISIM applications and USIM Application Toolkit (USAT) in TS 31.102, 31.103, 31.111 | 31.121, 31.124, New TS 31.ABC (Conformance Testing of specific features)
1729 | 440021 | CN aspects of Local Call Local Switch | LCLS-CN | 1 | Rel-10 | C4 | 2009-05-29 08:00 | 2011-03-18 17:00 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | GERAN Stage 2/3
1730 | 440022 | TR on CN aspects of Local Call Local Switch | - | 2 | Rel-10 | C4 | 2009-05-29 08:00 | 2010-09-16 17:00 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#49 completed | new TR 23.889
1731 | 490013 | Stage 2/3 for CN aspects of Local Call Local Switch | - | 2 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | 23.003, 23.009, 23.205, 23.231, 29.002, 29.205, 29.232, new TS 23.284
1732 | 440023 | Deleted - CT3 aspects of Local Call Local Switch | - | 2 | Rel-10 | C3 | 2009-05-29 08:00 | 2010-09-16 17:00 | 100% | CP-090812 | - | Vodafone | David.Hutton@vodafone.com | CP#49 stopped. Result of study TR 23.889: no CT3 specification impact | -
1733 | 440024 | Deleted - CT1 aspects of Local Call Local Switch | - | 2 | Rel-10 | C1 | 2009-05-29 08:00 | 2010-09-16 17:00 | 100% | CP-090812 | - | Vodafone | David.Hutton@vodafone.com | CP#49 stopped. Result of study TR 23.889: no CT1 specification impact | -
1734 | 430001 | Local Call Local Switch | LCLS | 1 | Rel-10 | GP,G2 | 2007-05-07 09:36 | 2011-05-20 17:00 | 100% | GP-101989 | - | Huawei | wang_zhixi@huawei.com | GP#50 completed. GP#41 WID approved | GERAN Stage 3: 48.008, 48.103
1735 | 480002 | Tightened Link Level Performance Requirements for Single Antenna MS | TIGHTER | 1 | Rel-10 | G1,G2,C1,G3new | 2010-09-03 08:00 | 2013-03-01 17:00 | 100% | GP-101083 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#46 approved WID | GERAN
1736 | 480102 | CT1 part for TIGHTER | - | 2 | Rel-10 | C1 | 2010-09-03 08:00 | 2011-06-03 17:00 | 100% | GP-101083 | - | Renesas Mobile | marko.niemi@renesasmobile.com | CP#52 completed | 24.008
1737 | 480202 | TIGHTER Performance Requirements | - | 2 | Rel-10 | G1,G2 | 2010-09-03 08:00 | 2011-05-20 17:00 | 100% | GP-101084 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#50 completed | 45.005, 45.015
1738 | 480302 | TIGHTER Testing | - | 2 | Rel-10 | G3new | 2010-09-08 08:00 | 2013-03-01 17:00 | 100% | GP-101085 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#57 completed | 51.010
1739 | 490001 | Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 1 | Rel-10 | G2,S2,C1 | 2010-05-21 08:00 | 2011-03-04 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#47 approved WID. 900 MHz spectrum re-farming to other RATs lead operators to reduce GSM capacity and therefore share their GSM networks. Hence the need for the most suitable (GE)RAN sharing method | GERAN
1740 | 490101 | Stage 2 for Support of Multi-Operator Core Network by GERAN | - | 2 | Rel-10 | S2 | 2010-05-21 08:00 | 2010-12-16 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | SP#50 completed | 23.251
1741 | 490201 | CT1 part of Stage 3 for Support of Multi-Operator Core Network by GERAN | - | 2 | Rel-10 | C1 | 2010-05-21 08:00 | 2010-12-10 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | CP#50 completed | 24.008 CR#1644
1742 | 490301 | GERAN2 part of Stage 3 for Support of Multi-Operator Core Network by GERAN | - | 2 | Rel-10 | G2 | 2010-08-30 08:00 | 2011-03-04 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#49 completed | 48.008 CR#0325, 48.018 CR#0303
1743 | 490002 | Enhancements of Iur-g interface | eIurg | 1 | Rel-10 | G2,R3 | 2010-09-03 08:00 | 2011-06-03 17:00 | 100% | GP-101758 | - | China Mobile, ZTE | Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn) | GP#47 approved WID | GERAN,UTRA
1744 | 490102 | GERAN part for Enhancements of Iur-g interface (Stage 2/3) | eIurg-GERAN | 2 | Rel-10 | G2 | 2010-09-03 08:00 | 2011-03-04 17:00 | 100% | GP-101758 | - | China Mobile, ZTE | Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn) | GP#49 completed. GP#48 updated WID GP-101659=>GP-101758 (restricting the scope to GERAN BSC and TD-SCDMA RNC only). GP#47 approved WID | 43.130, 48.008
1745 | 490021 | Core part: Enhancements of Iur-g interface (Stage 2/3) | eIurg-RAN | 2 | Rel-10 | R3 | 2010-09-03 08:00 | 2011-06-03 17:00 | 100% | RP-101232 | RP-110526 | ZTE | Liu Junqiang (liu.junqiang@zte.com.cn) | RP#52 completed | UTRA Stage 2 (25.401, 25.420), Stage 3 (25.423)
1746 | 380077 | 1.28 Mcps TDD Repeater | RANimp-Repeaters1.28TDD | 1 | Rel-10 | R4 | 2007-12-04 08:00 | 2010-03-19 17:00 | 100% | RP-071003 | RP-100039 | RITT | qinyan@chinattl.com | RP#47 completed | UTRA 25.113, New 25.116, 25.153 (testing)
1747 | 450019 | 1.28 Mcps TDD Multi-carrier HSUPA | TDD_MC_HSUPA | 1 | Rel-10 | R1,R2,R3,R4 | 2009-09-18 08:00 | 2010-12-10 17:00 | 100% | RP-090990 | RP-101079 | CATR | Aihui Song (songaihui@mail.ritt.com.cn) | RP#50 completed | UTRA 25.102, 25.105, 25.123, 25.221, 25.222, 25.223, 25.224, 25.225, 25.306, 25.319, 25.321, 25.331, 25.423, 25.427, 25.433
1748 | 460014 | 1.28 Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF | 1 | Rel-10 | R4 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-100607 | - | TD Tech | Li Rong (lirong@td-tech.com) | RP#50 completed. Triggered by FS_RAN-HNBLCRTDD UID_410016 Study on 1.28 Mcps TDD Home NodeB (TR 25.866) | UTRA | HNB
1749 | 460114 | Core part: 1.28Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF-Core | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2010-06-04 17:00 | 100% | RP-100607 | RP-100446 | TD Tech | Li Rong (lirong@td-tech.com) | RP#48 completed | 25.105 | HNB
1750 | 460214 | Perf. part: 1.28Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-100607 | RP-101081 | TD Tech | Li Rong (lirong@td-tech.com) | RP#50 completed. TR 25.968 v100 for Approval | 25.142, new TR 25.968 | HNB
1751 | 470012 | Multi-User Multiple-Input and Multiple-Output (MU-MIMO) for 1.28Mcps TDD | MUMIMO_LCR_TDD | 1 | Rel-10 | R1,R2,R3,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100347 | - | CATT | Yanping Xing (xingyanping@datangmobile.cn) | RP#52 completed | UTRA
1752 | 470112 | Core part: MU-MIMO for 1.28Mcps TDD | MUMIMO_LCR_TDD-Core | 2 | Rel-10 | R1,R2,R3 | 2010-03-19 08:00 | 2010-12-10 17:00 | 100% | RP-100347 | RP-101085 | CATT | Yanping Xing (xingyanping@datangmobile.cn) | RP#50 completed | 25.221, 25.222, 25.224, 25.306, 25.308, 25.319, 25.331, 25.423, 25.425, 25.433, 25.435
1753 | 470212 | Perf. part: MU-MIMO for 1.28Mcps TDD | MUMIMO_LCR_TDD-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100347 | RP-110520 | CATT | Sanjun Feng (fengsanjun@datangmobile.cn) | RP#52 completed | 25.102, 25.105, 25.142
1754 | 450027 | AGNSS Minimum Performance for UTRAN | AGNSSPerf_UTRAN | 1 | Rel-10 | R4,R5 | 2009-09-18 08:00 | 2011-09-16 17:00 | 100% | RP-100363 | - | Thales | Michel.monnerat@thalesaleniaspace.com | RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures) | UTRA
1755 | 450127 | AGNSS Minimum Performance Specification Development | - | 2 | Rel-10 | R4 | 2009-09-18 08:00 | 2010-12-10 17:00 | 100% | RP-100363 | RP-101078 | Thales | Michel.monnerat@thalesaleniaspace.com | RP#50 completed | new 25.172
1756 | 480018 | AGNSS test case development for UMTS | - | 2 | Rel-10 | R5 | 2010-06-04 08:00 | 2011-09-16 17:00 | 100% | RP-101405 | RP-110979 | Thales | Michel.monnerat@thalesaleniaspace.com | RP#53 completed | 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.37.571-5, new 34.172
1757 | 460005 | Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN | LCS_UMTS_RFPMT | 1 | Rel-10 | R2,R3 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-091427 | RP-110048 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907) | UTRA
1758 | 460105 | Core part: Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN | LCS_UMTS_RFPMT-Core | 2 | Rel-10 | R2,R3 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-091427 | RP-110048 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#51 completed | 25.305, 25.453
1759 | 460015 | Four carrier HSDPA | 4C_HSDPA | 1 | Rel-10 | R1,R2,R3,R4,R5 | 2009-12-04 08:00 | 2013-09-06 17:00 | 100% | RP-100991 | - | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#53 completed | UTRA
1760 | 460115 | Core part: Four carrier HSDPA | 4C_HSDPA-Core | 2 | Rel-10 | R1,R2,R3,R4 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-100991 | RP-110046 | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#51 completed. RP#52 TR 25.864 v200 for Approval | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306, new TR 25.864
1761 | 460215 | Perf. part: Four carrier HSDPA | 4C_HSDPA-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-09-16 17:00 | 100% | RP-100991 | RP-110986 | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#53 completed | 25.101, 25.104, 25.133, 25.141
1762 | 540006 | Test part: Four carrier HSDPA | 4C_HSDPA-UEConTest | 2 | Rel-10 | R5 | 2011-12-02 08:00 | 2013-09-06 17:00 | 100% | RP-111565 | RP-130940 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#61 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
1763 | 470013 | Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD | 1 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100168 | - | TD Tech | dafei.wang@td-tech.com | Stage 3. RP#52 completed | UTRA
1764 | 470113 | Core part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD-Core | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2010-06-04 17:00 | 100% | RP-100168 | RP-100454 | TD Tech | dafei.wang@td-tech.com | RP#48 completed | 25.102
1765 | 470213 | Perf. part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100168 | RP-110521 | TD Tech | dafei.wang@td-tech.com | RP#52 completed | 25.102
1766 | 480020 | Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN | 1 | Rel-10 | R3,R2,R5 | 2010-06-04 08:00 | 2012-12-07 17:00 | 100% | RP-100688 | - | ZTE | Zhai.hengxing@zte.com.cn | RP#52 Core completed. Automatic Neighbour Relation (ANR) function for UTRAN relieves operators from the burden of manually managing the Neighbour cell Relations (NRs) | UTRA
1767 | 480120 | Core part: Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN-Core | 2 | Rel-10 | R3,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100688 | RP-110522 | ZTE | Zhai.hengxing@zte.com.cn | RP#52 completed | 25.331, 25.413, 25.423, new TS 25.484 (Stage 2)
1768 | 530039 | Test part: Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN-UEConTest | 2 | Rel-10 | R5 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120599 | RP-121529 | Ericsson | leif.mattisson@ericsson.com | RP#58 completed | 34.108, 34.123-1, 34.123-2, 34.123-3
1769 | 480021 | Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA | 1 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100657 | - | AT&T | Vince Spatafora (vs5785@att.com) | RP#52 completed. Rel-9 Dual-Band Dual-Cell HSDPA (UID_430015 Support for different bands for Dual-Cell HSDPA) has one combination per region in principle. This work adds additional combinations: Band I and XI (Region 3) and Band II and V (Region 2) | UTRA
1770 | 480121 | Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA-Core | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100657 | RP-110523 | AT&T | Vince Spatafora (vs5785@att.com) | RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327
1771 | 480221 | Deleted - Perf. part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA-Perf | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2010-09-17 17:00 | 100% | RP-100657 | RP-100759 | AT&T | Vince Spatafora (vs5785@att.com) | RP#49 stopped (Reason: no need for Performance work) | 25.101, 25.104, 25.141, 25.317
1772 | 480022 | MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA | 1 | Rel-10 | R4,R5 | 2010-06-04 08:00 | 2012-03-02 17:00 | 100% | RP-100993 | - | Qualcomm | Heechoon Lee | RP#52 completed. RP#49 updated WID RP-100687=>RP-100993 (changed Title: MIMO Testing in HSDPA => MIMO operation with non-MIMO coexistence in HSDPA) | UTRA
1773 | 490023 | Core part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-Core | 2 | Rel-10 | R4 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | RP-100993 | RP-110524 | Qualcomm | Heechoon Lee | RP#52 completed | 25.104
1774 | 480122 | Perf. part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-Perf | 2 | Rel-10 | R4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100993 | RP-110525 | Qualcomm | Heechoon Lee | RP#52 completed | 25.101, 25.141
1775 | 510017 | Test part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-UEConTest | 2 | Rel-10 | R5 | 2011-03-18 08:00 | 2012-03-02 17:00 | 100% | RP-110244 | RP-120042 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#55 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
1776 | 490022 | Interfrequency detected set measurements for UMTS | Interf_dset_meas_UMTS | 1 | Rel-10 | R2,R4 | 2010-09-17 08:00 | 2010-12-10 17:00 | 100% | RP-101015 | RP-101093 | Nokia | Chris.callender@nokia.com | RP#50 completed | UTRA 25.133, 25.331
1777 | 460007 | Carrier Aggregation for LTE | LTE_CA | 1 | Rel-10 | R1,R2,R3,R4,R5 | 2009-12-04 08:00 | 2012-12-07 17:00 | 100% | RP-100661 | - | Nokia | Asbjorn.grovlen@nokia.com | - | LTE | CA
1778 | 460107 | Core part: Carrier Aggregation for LTE | LTE_CA-Core | 2 | Rel-10 | R1,R2,R3,R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-100661 | RP-110535 | Nokia | lars.e.lindh@nokia.com | RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, 37.104, new RAN4 TR (36.807, 36.808) | CA
1779 | 460207 | Perf. part: Carrier Aggregation for LTE | LTE_CA-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-12-09 17:00 | 100% | RP-100661 | RP-111452 | Nokia | lars.e.lindh@nokia.com | RP#54 completed | 36.101, 36.104, 36.133, 36.141, 37.141 | CA
1780 | 530040 | Test part: Carrier Aggregation for LTE | LTE_CA-UEConTest | 2 | Rel-10 | R5 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121246 | RP-121528 | Nokia | jussi.kuusisto@nokia.com | RP#58 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | CA
1781 | 460008 | Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO | 1 | Rel-10 | R1,R2,R4,R5 | 2009-12-04 08:00 | 2013-06-14 17:00 | 100% | RP-100196 | - | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | - | LTE
1782 | 460108 | Core part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-Core | 2 | Rel-10 | R1,R2,R4 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-100196 | RP-110067 | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 TR 36.807
1783 | 460208 | Perf. part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2012-03-02 17:00 | 100% | RP-091429 | RP-120053 | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | RP#55 completed | 36.101, 36.104, 36.133, 36.141
1784 | 560012 | Test part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-UEConTest | 2 | Rel-10 | R5 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-120612 | RP-130464 | ZTE | Carolyn Taylor (carolyn.tayl@zte.com.cn) | RP#60 completed. Testing for 36.101, 36.133 | 36.508, 36.521-1, 36.521-2
1785 | 460009 | Uplink Multiple Antenna Transmission for LTE | LTE_UL_MIMO | 1 | Rel-10 | R1,R2,R4,R5 | 2000-01-03 08:00 | 2013-03-01 17:00 | 100% | RP-100959 | - | Huawei | Mattias.wennstrom@huawei.com | - | LTE
1786 | 460109 | Core part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-Core | 2 | Rel-10 | R1,R2,R4 | 2000-01-03 08:00 | 2001-06-29 17:00 | 100% | RP-100959 | RP-110537 | Huawei | Mattias.wennstrom@huawei.com | RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 (TR 36.807, 36.817)
1787 | 460209 | Perf. part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-09-16 17:00 | 100% | RP-100959 | RP-110992 | Huawei | Mattias.wennstrom@huawei.com | RP#53 completed | 36.101, 36.104, 36.133, 36.141, 36.817
1788 | 540007 | Test part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-UEConTest | 2 | Rel-10 | R5 | 2011-12-02 08:00 | 2013-03-01 17:00 | 100% | RP-111614 | RP-130038 | Huawei | Zhang Xin (suzanna.zhang@huawei.com) | RP#59 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1789 | 460013 | Relays for LTE | LTE_Relay | 1 | Rel-10 | R1,R2,R4,S2,S3,C4,C6 | 2009-12-04 08:00 | 2011-06-08 17:00 | 100% | RP-110911 | - | Ericsson | christian.hoymann@ericsson.com | RP#52 completed (open RAN4 Core & Perf parts moved to new Rel-11) | LTE
1790 | 460113 | Core part: Relays for LTE | LTE_Relay-Core | 2 | Rel-10 | R1,R2,R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-110911 | RP-110540 | Ericsson | christian.hoymann@ericsson.com | RP#52 completed. Updated WID RP-101417=>RP-101911 (contains only Core part completed in Rel-10). Open RAN4 Core & Perf parts moved to new Rel-11 | 36.201, 36.211, 36.212, 36.213, 36.300, 36.321, 36.323, 36.331, New RAN1 TS 36.216
1791 | 460213 | Deleted - Perf. part: Relays for LTE | LTE_Relay-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-101417 | RP-110541 | Ericsson | christian.hoymann@ericsson.com | RP#52 stopped at 30% (no CRs so far) . Transferred completely to Rel-11 together with remaining core part | 36.133, New TS 36.117 (E-UTRA Relay conformance testing)
1792 | 520020 | Stage 2 for Relays for LTE | - | 2 | Rel-10 | S2 | 2011-06-06 08:00 | 2011-06-08 17:00 | 100% | - | - | Vodafone | chris.pudney@vodafone.com | SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview | 23.401
1793 | 500038 | LTE Relay Nodes Security | LTE_Relay-Sec | 2 | Rel-10 | S3,C6 | 2010-12-16 08:00 | 2011-03-22 17:00 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | - | -
1794 | 500238 | TR on LTE Relay Nodes Security | - | 3 | Rel-10 | S3 | 2010-12-16 08:00 | 2011-03-22 17:00 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | SP#51 completed | 33.816
1795 | 500138 | Security for LTE Relay Nodes (Stage 2) | - | 3 | Rel-10 | S3 | 2010-12-16 08:00 | 2011-03-22 17:00 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | SP#51 completed (impacting Stage 3 in CT and RAN) | 33.401 (CR#0437,0438), CT1 24.301, CT4 (29.272, 29.274), CT6 31.102, RAN2 (36.331, 36.323), RAN3 36.413
1796 | 510011 | CT6 aspects of LTE Relay Node Security | - | 3 | Rel-10 | C6 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | - | - | n/a | n/a | CP#51 completed | 31.101, 31.102
1797 | 510012 | Core Network Impacts for Relay Nodes | LTE_Relay-CN | 2 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | CP-110094 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | 23.003, 23.008, 29.303, 29.230, 29.272
1798 | 470007 | Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE | 1 | Rel-10 | R1,R2,R3,R4,R5 | 2010-03-19 08:00 | 2014-06-13 17:00 | 100% | RP-100383 | - | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#56 completed | LTE
1799 | 470107 | Core part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE-Core | 2 | Rel-10 | R1,R2,R3,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100383 | RP-110543 | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#52 completed | 36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423
1800 | 470207 | Perf. part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2012-06-15 17:00 | 100% | RP-100383 | RP-120461 | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#56 completed | 36.101, 36.133
1801 | 550001 | Test part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE-UEConTest | 2 | Rel-10 | R5 | 2012-03-05 08:00 | 2014-06-13 17:00 | 100% | RP-120217 | RP-140766 | Qualcomm | Anjali Mishra (ajha@qualcomm.com) | RP#64 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1802 | 470008 | LTE TDD in 2600MHz for US | LTE_TDD_2600_US | 1 | Rel-10 | R4,R2,R3,R5 | 2010-03-19 08:00 | 2010-12-10 17:00 | 100% | RP-101003 | - | Clearwire | michael.hart@clearwire.com | RP#50 Testing completed. RP#49 Core+Perf completed | LTE
1803 | 470108 | Core part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-Core | 2 | Rel-10 | R4,R2,R3 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-101003 | RP-100782 | Clearwire | michael.hart@clearwire.com | RP#49 completed | 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141, new TR 36.812
1804 | 470208 | Perf. part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-101003 | RP-100783 | Clearwire | michael.hart@clearwire.com | RP#49 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new TR 36.812
1805 | 480019 | UE conformance test part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-UEConTest | 2 | Rel-10 | R5 | 2010-06-04 08:00 | 2010-12-10 17:00 | 100% | RP-100615 | RP-101071 | Clearwire | michael.hart@clearwire.com | RP#50 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1806 | 470009 | Adding 2 GHz band LTE FDD (Band 23) for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America | S_Band_LTE_ATC_MSS | 1 | Rel-10 | R2,R4,R5 | 2010-03-19 08:00 | 2011-12-09 17:00 | 100% | RP-110775 | - | DBSD | Mariam.Sorond@ico.com | RP#52 completed. Updated WID RP-101401=>RP-110775 (changed in Title "LTE" to "LTE FDD (Band 23)" | LTE
1807 | 470109 | Core part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-Core | 2 | Rel-10 | R4,R2 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-110775 | RP-110545 | DBSD | Mariam.Sorond@ico.com | RP#52 completed | 25.101, 25.104, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new TR 36.811
1808 | 470209 | Perf. part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-110775 | RP-110546 | DBSD | Mariam.Sorond@ico.com | RP#52 completed | 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.811
1809 | 520012 | Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-UEConTest | 2 | Rel-10 | R5 | 2011-06-07 08:00 | 2011-12-09 17:00 | 100% | RP-110623 | RP-111444 | DBSD | Mariam.Sorond@ico.com | RP#54 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1810 | 470010 | Adding L-Band (Band 24) LTE for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America | L_Band_LTE_ATC_MSS | 1 | Rel-10 | R4,R2,R5 | 2009-12-11 08:00 | 2011-09-16 17:00 | 100% | RP-101284 | - | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#53 completed | LTE
1811 | 470110 | Core part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-Core | 2 | Rel-10 | R4,R2 | 2009-12-11 08:00 | 2010-12-10 17:00 | 100% | RP-101284 | RP-101117 | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#51 completed | 25.101, 25.104, 25.141, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new RAN4 TR 36.813
1812 | 470210 | Perf. part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-101284 | RP-110548 | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#52 completed | 34.121-1, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.521-1, 36.813
1813 | 510015 | Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-UEConTest | 2 | Rel-10 | R5 | 2011-03-18 08:00 | 2011-09-16 17:00 | 100% | RP-110777 | RP-110980 | LightSquared | masoud.olfat@lightsquared.com | RP#53 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2
1814 | 470011 | LTE Self Optimizing Networks (SON) enhancements | SONenh_LTE | 1 | Rel-10 | R3,R2,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-101004 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#52 completed | LTE | SON
1815 | 470111 | Core part: LTE Self Optimizing Networks (SON) enhancements | SONenh_LTE-Core | 2 | Rel-10 | R3,R2,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-101004 | RP-110547 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#52 completed (Stage 1,2,3) | 36.300, 36.331, 36.413, 36.423 | SON
1816 | 480027 | Further enhancements to MBMS for LTE | MBMS_LTE_enh | 1 | Rel-10 | R2,R3,R5 | 2010-06-04 08:00 | 2012-03-02 17:00 | 100% | RP-101244 | - | Huawei | Ms Zhao Junhui (zhaojh@huawei.com) | RP#51 completed. SA2 decided not to support MBR>GBR in Rel-10 MBMS. For SA2, MBR=GBR in Rel-10 MBMS. Hence RAN removed “enabling statistical multiplexing gains for variable bit rate services” in Objectives | LTE
1817 | 480127 | Core part: Further enhancements to MBMS for LTE | MBMS_LTE_enh-Core | 2 | Rel-10 | R2,R3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | RP-101244 | RP-110083 | Huawei | Ms Zhao Junhui (zhaojh@huawei.com) | RP#51 completed | 25.446, 36.300, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445
1818 | 540008 | Test part: Further enhancements to MBMS for LTE | MBMS_LTE_enh-UEConTest | 2 | Rel-10 | R5 | 2011-12-02 08:00 | 2012-03-02 17:00 | 100% | RP-111615 | RP-120049 | Huawei | Zhang Xin (suzanna.zhang@huawei.com) | RP#55 completed | 36.508, 36.523-1, 36.523-2, 36.523-3
1819 | 380173 | UMTS/LTE 3500 MHz | RInImp8-UMTSLTE3500 | 1 | Rel-10 | R4,R2,R3,R5 | 2007-11-30 08:00 | 2013-06-14 17:00 | 100% | RP-091380 | - | Ericsson | johan.skold@ericsson.com | - | UTRA, LTE
1820 | 380073 | Core part: UMTS/LTE 3500 MHz | - | 2 | Rel-10 | R4,R2,R3 | 2007-11-30 08:00 | 2011-09-16 17:00 | 100% | RP-091380 | RP-110987 | Ericsson | johan.skold@ericsson.com | RP#53 completed. TR 37.801v200 for Approval | 25.101, 25.104, 25.113, 25.133, 25.141, 25.307, 25.307, 25.331, 25.461, 25.463, 34.124, 36.101, 36.104, 36.113, 36.141, 36.331, new 37.801
1821 | 420013 | Conformance Test Aspects – LTE 3500 | LTE-UEConTest_LTE3500 | 2 | Rel-10 | R5 | 2008-12-05 08:00 | 2013-06-14 17:00 | 100% | RP-080859 | RP-130461 | Ericsson | fredrik.sundstrom@ericsson.com | RP#60 completed | 36.508, 36.521-1, 36.521-2, 36.521-3
1822 | 420014 | Conformance Test Aspects – UMTS 3500 | RInImp-UEConTest_UMTS3500 | 2 | Rel-10 | R5 | 2008-12-05 08:00 | 2012-06-15 17:00 | 100% | RP-110386 | RP-120450 | Ericsson | fredrik.sundstrom@ericsson.com | RP#56 completed | 34.108, 34.121-1, 34.121-2
1823 | 460003 | Minimization of Drive Tests for E-UTRAN and UTRAN | MDT_UMTSLTE | 1 | Rel-10 | R2,R4,R3,R5 | 2009-12-04 08:00 | 2013-03-01 17:00 | 100% | RP-100360 | - | Nokia Siemens Networks | malgorzata.tomala@nsn.com | Triggered by UID_430021 TR 36.805 (Study on Minimization of drive-tests in NGN) | UTRA, LTE
1824 | 460103 | Core part: Minimization of Drive Tests for E-UTRAN and UTRAN | MDT_UMTSLTE-Core | 2 | Rel-10 | R2,R4,R3 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-100360 | RP-110528 | Nokia Siemens Networks | malgorzata.tomala@nsn.com | RP#52 completed | 25.133, 25.215, 25.304, 25.331, 25.423, 36.133, 36.214, 36.300, 36.304, 36.331, 36.413, 36.423, new 37.320 (Stage 2)
1825 | 530041 | Test part: Minimization of Drive Tests for E-UTRAN | MDT_UMTSLTE-UEConTest | 2 | Rel-10 | R5 | 2011-09-19 08:00 | 2013-03-01 17:00 | 100% | RP-120598 | RP-130036 | Ericsson | leif.mattisson@ericsson.com | RP#59 completed. Testing for LTE only | LTE 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3
1826 | 470005 | HNB and HeNB Mobility Enhancements | HNB_HENB_mob_enh | 1 | Rel-10 | R3,R2,R5 | 2010-03-19 08:00 | 2012-12-07 17:00 | 100% | RP-110183 | - | Alcatel-Lucent | Martin,Warner@alcatel-lucent.com | - | UTRA, LTE | HNB
1827 | 470105 | Core part: HNB and HeNB Mobility Enhancements | HNB_HENB_mob_enh-Core | 2 | Rel-10 | R3,R2 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | RP-110183 | RP-110058 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#51 completed | 25.413, 25.467, 25.469, 36.300, 36.413, 36.423, new 25.471 | HNB
1828 | 550002 | Test part: HeNB Mobility Enhancements | HNB_HENB_mob_enh-UEConTest_LTE | 2 | Rel-10 | R5 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-120218 | RP-121533 | Qualcomm | Anjali Mishra (ajha@qualcom.com) | RP#58 completed | 34.108, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | HNB
1829 | 480024 | Expanded 1900 MHz Band for UTRA and LTE | E1900 | 1 | Rel-10 | R4,R2,R5 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | RP-100676 | - | Sprint | nick.j.baustert@sprint.com | Expand UTRA and E-UTRA band 2 to include frequencies between 1910 – 1915 MHz and 1990-1995 MHz (US FCC allocation) | UTRA, LTE
1830 | 480124 | Core part: Expanded 1900 MHz Band for UTRA and LTE | E1900-Core | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100676 | RP-110529 | Sprint | nick.j.baustert@sprint.com | RP#52 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new TR 36.818
1831 | 480224 | Perf. part: Expanded 1900 MHz Band for UTRA and LTE | E1900-Perf | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100676 | RP-110530 | Sprint | nick.j.baustert@sprint.com | RP#52 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new TR 36.818
1832 | 520013 | Test part: Expanded 1900 MHz Band for UTRA and LTE | E1900-UEConTest | 2 | Rel-10 | R5 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110712 | RP-120957 | Sprint | nick.j.baustert@sprint.com | RP#57 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
1833 | 480025 | Multi-Standard Radio Base Station RF requirements for non-contiguous spectrum deployments | MSR_NC | 1 | Rel-10 | R4,G1 | 2010-06-04 08:00 | 2011-11-25 17:00 | 100% | RP-101402 | - | Ericsson | johan.skold@ericsson.com | - | UTRA, LTE, GERAN
1834 | 480125 | Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-Core | 2 | Rel-10 | R4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-101402 | RP-110531 | Ericsson | johan.skold@ericsson.com | RP#52 completed | 25.104, 36.104, 37.104, new TR 37.802
1835 | 480225 | Perf. part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-Perf | 2 | Rel-10 | R4 | 2010-06-04 08:00 | 2011-09-16 17:00 | 100% | RP-101402 | RP-110988 | Ericsson | johan.skold@ericsson.com | RP#53 completed | 25.141, 36.141, 37.141, 37.802
1836 | 490004 | GERAN part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 2 | Rel-10 | G1 | 2010-09-03 08:00 | 2011-11-25 17:00 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | - | -
1837 | 490104 | GERAN Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | - | 3 | Rel-10 | G1 | 2010-09-03 08:00 | 2011-09-02 17:00 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#51 completed. GP#47 approved WID | 45.005
1838 | 540001 | GERAN BS Test part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | - | 3 | Rel-10 | G1 | 2011-09-02 08:00 | 2011-11-25 17:00 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#52 completed | 51.021
1839 | 440044 | (Small) Technical Enhancements and Improvements for Rel-10 | TEI10 | 1 | Rel-10 | SP,CP,RP,GP | 2009-06-04 08:00 | 2011-03-23 17:00 | 100% | - | - | - | - | - | -
1840 | 521004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius) | TEI10_IETF | 1 | Rel-10 | C1-IETF | 2009-06-04 08:00 | 2014-12-05 17:00 | 75% | - | - | Andrew Allen | Andrew Allen | Not completed internet-draft, waiting for draft-montemurro to complete | draft-atarius-dispatch-meid-urn
1841 | 531001 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (RFC6275) | TEI10_IETF1 | 1 | Rel-10 | C1-IETF | 2009-06-04 08:00 | 2011-07-29 17:00 | 100% | - | - | - | - | SP#53/IETF#81: RFC 6275 completed | RFC 6275 (was draft-ietf-mext-rfc3775bis)
1842 | 540004 | Test - (Small) Technical Enhancements and Improvements for Rel-10 | TEI10_Test | 1 | Rel-10 | R5,G3new | 2011-12-01 08:00 | 2012-12-07 17:00 | 100% | - | - | n/a | - | - | -
1843 | 350014 | Deleted - Registration in Densely-populated area (RED) | RED | 1 | Rel-10 | S1 | 2007-03-12 08:00 | 2009-09-24 17:00 | 100% | SP-070133 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned | -
1844 | 370030 | Deleted - Stage 1 for RED | - | 2 | Rel-10 | S1 | 2007-03-12 08:00 | 2007-03-15 17:00 | 100% | SP-070133 | - | NTT DoCoMo | takakurat@s1.nttdocomo.co.jp | SP#35 completed. SP#46 work stopped/abandoned | 22.101 CR#0207
1845 | 370031 | Deleted - Stage 2 for RED | - | 2 | Rel-10 | S2 | 2007-09-25 08:00 | 2009-09-24 17:00 | 100% | SP-070694 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#45 Stage 2 work stopped | draft TR 23.880 withdrawn, 23.002, 23.060, 23.221, 23.236
1846 | 380062 | Deleted - Network Selection for non-3GPP Access | N3GtoNSP | 1 | Rel-10 | S1,C6 | 2007-12-07 08:00 | 2009-09-24 17:00 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | -
1847 | 380162 | Deleted - Stage 1 for N3GtoNSP | - | 2 | Rel-10 | S1 | 2007-12-07 08:00 | 2009-09-24 17:00 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | 22.011
1848 | 380262 | Deleted - CT6 issues for N3GtoNSP | - | 2 | Rel-10 | C6 | 2007-12-07 08:00 | 2009-09-24 17:00 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | 36.300
1849 | 420025 | Deleted - GTP-based S8 chaining | GTPchaining | 1 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080798 | - | Huawei | Haining Wang (wanghaining@huawei.com) | SP#47 work stopped (depending on ongoing related CT4 work). Stage 1 in UID_320022 Rel-8 Requirements for evolution of the 3GPP system architecture (AIPN-SAE): 22.278, 22.011, 22.246 | -
1850 | 420026 | Deleted - Stage 2 for GTPchaining | - | 2 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080798 | - | Huawei | Haining Wang (wanghaining@huawei.com) | SP#47 work stopped | 23.402
1851 | 430017 | Deleted - UTRAN 2 ms TTI uplink range improvement | RANimp-2mTTI_ULimp | 1 | Rel-10 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-090333 | RP-100040 | Nokia Siemens Networks | Karri Ranta-aho (karri.ranta-aho@nsn.com) | RP#47 work stopped/abandoned (no CR approved). Cell sets the TTI (Transmission Time Interval) to 2 ms | 25.133, 25.212, 25.214, 25.321, 25.331
1852 | 440043 | Deleted - Enhanced Home NodeB / eNodeB continuation of Rel-9 | eEHNB | 1 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | - | - | Alcatel-Lucent | Nicolas Drevon | SP#47 deleted (SA2 work moved under SA1 UID_450053). SP#44 Umbrella Feature created to host WIs moved out of Rel-9 (SA2 UID_420034 on IMS aspects of Architecture for Home NodeB) | - | HNB
1853 | 460010 | Deleted - Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF | 1 | Rel-10 | R4,R5 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-091432 | - | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped (lack of contributions). Add new power classes in E-UTRAN UL to allow CPE type applications to be operated at higher max output power | LTE
1854 | 460110 | Deleted - Core part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF-Core | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-091432 | RP-110539 | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped at 55% (lack of contributions) | 36.101
1855 | 460210 | Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF-UEConTest | 2 | Rel-10 | R5 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-091432 | RP-110504 | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped (lack of contributions) | 36.521-1
1856 | 460012 | Deleted - Latency reductions for LTE | LTE_LATRED | 1 | Rel-10 | R2,R1 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-091449 | - | Ericsson | henrik.enbuske@ericsson.com | RP#50 work stopped (RP-101266) | LTE
1857 | 460112 | Deleted - Core part: Latency reductions for LTE | LTE_LATRED-Core | 2 | Rel-10 | R2,R1 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-091449 | RP-101112 | Ericsson | henrik.enbuske@ericsson.com | RP#50 work stopped (RP-101266) | 36.213, 36.300, 36.306, 36.321, 36.331
1858 | 470006 | Deleted - Enhanced Interference Management for Home NodeBs | HNB_IM | 1 | Rel-10 | R3 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-100392 | RP-100754 | Qualcomm | Andrei Radulescu (aradules@qualcomm.com) | RP#49 stopped (no further standardization needed). Ensure that Enhanced Interference Management methods identified in Rel-9 for HNBs do not fail in deployments with a large penetration of CSG-aware UEs | UTRA | HNB
1859 | 470106 | Deleted - Core part: Enhanced Interference Management for Home NodeBs | HNB_IM-Core | 2 | Rel-10 | R3 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-100392 | RP-100754 | Qualcomm | Andrei Radulescu (aradules@qualcomm.com) | RP#49 stopped (no further standardization needed) | 25.413, 25.467, 25.469 | HNB
1860 | 0 | Release 10 Studies | - | 1 | Rel-10 | CP,GP,RP,SP | 2009-03-12 08:00 | 2011-03-23 17:00 | 100% | - | - | - | - | - | -
1861 | 370045 | Study on enhanced voice service requirements for the Evolved Packet System (EPS) | FS_EV_EPS | 1 | Rel-10 | S1,S4 | 2007-09-03 08:00 | 2010-03-25 17:00 | 100% | SP-070698 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed. TR 22.813-100 for Approval. Spin-off Feature UID_470030 Codec for Enhanced Voice Services | 22.813
1862 | 370047 | Use cases definition and service and system requirements | FS_EV_EPS-S1 | 2 | Rel-10 | S1 | 2007-09-03 08:00 | 2008-12-11 17:00 | 100% | SP-070698 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed. TR 22.813-100 for Approval | 22.813
1863 | 370048 | Codec specific part of FS_EV_EPS | FS_EV_EPS-S4 | 2 | Rel-10 | S4 | 2007-09-03 08:00 | 2010-03-25 17:00 | 100% | SP-070698 | - | Ericsson | stefan.bruhn@ericson.com | SP#47 completed. TR 22.813-100 for Approval | 22.813
1864 | 380083 | Study on advanced requirements for IP interconnect | FS_IPXS | 1 | Rel-10 | S1 | 2007-12-04 08:00 | 2009-12-10 17:00 | 100% | SP-070878 | - | Telefónica O2 | chris.friel@O2.com | SP#46 completed. Linked to Rel-8 Feature UID_380060 IP Interconnection of Services (IPinterc). Spin-off Feature Rel-11 UID_470051 Advanced IP Interconnection of Services | 22.893
1865 | 410039 | Study on Personal Broadcast Service | FS_PBS | 1 | Rel-10 | S1 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-080504 | - | ETRI | Jaihyung Cho | SP#47 completed | 22.947
1866 | 410040 | Study on LCS support in SAE for non-3GPP accesses | FS_LCS_n3GPP | 1 | Rel-10 | S1 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-080648 | - | SK Telecom | jinhan.song@sktelecom.com | SP#47 completed | 22.814
1867 | 430030 | Study on Haptic Services | FS_Haptics | 1 | Rel-10 | S1 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090664 | - | SK Telecom | jinhan.song@sktelecom.com | SP#47 completed. Covers Mobile/Fixed/Cordless/etc terminals. Haptic (human-machine tactile communication) extend service offering & richness of user experience beyond current visual & auditory senses | 22.987
1868 | 370050 | Study on System enhancements for the use of IMS services in Local BreakOut and Optimal Routing of Media | FS_IMS_LBO_ORM | 1 | Rel-10 | S2 | 2007-10-01 08:00 | 2009-12-10 17:00 | 100% | SP-080556 | - | Telecom Italia, BT | mario.madella@telecomitalia.it, victor.kueh@bt.com | SP#46 completed. Spin-off Feature UID_460028 Optimal Media Routeing (OMR). Linked to Study on Multimedia Session Continuity UID_350051, Study on Centralized IMS Service Control UID_330012, IMS inter-operator service interconnection interface UID_360011 | 23.894
1869 | 390055 | Study on Intra Domain Connection of RAN Nodes to Multiple CN Nodes | FS_IDC | 1 | Rel-10 | S2 | 2008-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-080094 | - | China Mobile | LIU HONG (liuhongyfw@chinamobile.com) | SP#47 completed. Concluded no further normative work expected. Linked to 23.236 | 23.924 (was 23.823)
1870 | 440049 | Study on Single Radio Voice Call Continuity enhancements | FS_eSRVCC | 1 | Rel-10 | S2 | 2009-06-04 08:00 | 2010-09-23 17:00 | 100% | SP-090363 | - | China Mobile | Hou zhiqiang (houzhiqiang@chinamobile.com), Jiang Yi (jiangyi@chinamobile.com) | SP#49 completed (Conclusion: select the SIP anchoring based solution for normative work CR (TEI10) introducing and completing stage-2). Analyzed performance of Rel-8 SRVCC solution from E-UTRAN/HSPA to UTRAN/GERAN | 23.856
1871 | 470048 | Study on Single Radio Video Call Continuity for 3G-CS | FS_vSRVCC | 1 | Rel-10 | S2 | 2010-03-25 08:00 | 2010-09-23 17:00 | 100% | SP-100168 | - | Samsung | Haris Zisimopoulos (haris.z@samsung.com) | SP#49 completed. TR 23.886v100 for Approval. Related to Rel-8 UID_350030 Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC). Study how to provide Video Call seamless service continuity for 3G/LTE terminal user | 23.886
1872 | 470049 | Study on S2b Mobility based on GTP | FS_SMOG | 1 | Rel-10 | S2 | 2010-03-25 08:00 | 2010-06-10 17:00 | 100% | SP-100169 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | SP#48 completed. Triggered by Rel-8 UID_350027 SAE for support for non-3GPP accesses. Nature of relationship: S2b one of the interfaces defined for non-3GPP accesses support in EPS. Stage 1 in Rel-8 UID_320022 (AIPN-SAE) 22.278,22.101 | 23.834
1873 | 430040 | Study on Surround Sound codec extension for PSS and MBMS | FS_SS_PSS_MBMS | 1 | Rel-10 | S4 | 2009-03-12 08:00 | 2011-03-23 17:00 | 100% | SP-090019 | - | Fraunhofer Gesellschaft | jan.plogsties@iis.franhofer.de | SP#51 completed. Extend Rel-8 UID_34043 (Extending PSS and MBMS User Services for optimized Mobile TV) | 26.950
1874 | 480044 | Study on Improved Video Coding Support | FS_IVCS | 1 | Rel-10 | S4 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100304 | - | Nokia, ETRI | imed.bouazizi@nokia.com, jaihyung@etri.re.kr | SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039) | 26.904
1875 | 410044 | Study on Rc Reference Point Functionalities and Message Flows | FS_OAM_Rc | 1 | Rel-10 | S5 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-080464 | - | Huawei | shan.mingjun@huawei.com | SP#47 completed | 32.825
1876 | 430044 | Study on Telecommunication Management; Energy Savings Management | FS_OAM_ESM | 1 | Rel-10 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090048 | - | Orange, Vodafone | Jean-Michel Cornilly (Orange) | SP#47 completed. Study result might impact Feature UID_420011 Self Organising Networks (SON) | 32.826
1877 | 440069 | Study on Integration of Device Management Information with Itf-N | FS_IDMI_Itf-N | 1 | Rel-10 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-100088 | - | Motorola | Yizhi Yao (yzyao@motorola.com) | SP#47 completed | 32.827
1878 | 460037 | Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model | FS_3GNRM_TMFSID | 1 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-090759 | - | Nokia Siemens Networks | olaf.pollakowski@nsn.com | SP#51 completed | 32.828
1879 | 460038 | Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program (TIP) Fault Management | FS_3G_TMF_FM | 1 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-090760 | - | Nokia Siemens Networks, Alcatel-Lucent | olaf.pollakowski@nsn.com, Padma.Sudarsan@alcatel-lucent.com | SP#51 completed | 32.829
1880 | 480045 | Study on Alarm Correlation and Alarm Root Cause Analysis | FS_AC_ARCA | 1 | Rel-10 | S5 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100775 | - | Ericsson | edwin.tse@ericsson.com | SP#51 completed | 32.832
1881 | 480046 | Study on Alignment of 3GPP PM IRP and TMF Interface Program (TIP) PM | FS_3G_TMF_PM | 1 | Rel-10 | S5 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100291 | - | Alcatel-Lucent | Padma.Sudarsan@alcatel-lucent.com | SP#51 completed | 32.831
1882 | 450013 | Study on Policy and Charging Rules Function (PCRF) failure and restoration | FS_PCRF-FR | 1 | Rel-10 | C3 | 2009-08-18 13:48 | 2010-09-17 17:00 | 100% | CP-090861 | - | NEC | gottfried.punz@nw.neclab.eu | CP#49 completed | 29.816
1883 | 480016 | Study on User Data Convergence (UDC) evolution | FS_UDCe | 1 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100296 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#51 completed. Study UDC evolution from Features in Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model | 23.845
1884 | 480017 | Study on UICC access to IMS | FS_IMS-UICC | 1 | Rel-10 | C6 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100424 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed | 31.828
1885 | 450014 | Study on Uplink Tx Diversity for HSPA | FS_UL-TxDiv-HSPA | 1 | Rel-10 | R4 | 2009-08-18 13:48 | 2010-06-04 17:00 | 100% | RP-090987 | RP-100499 | Qualcomm | Heechoon Lee (heechoon@qualcomm.com) | RP#48 completed | UTRA 25.863
1886 | 460016 | Study on Solutions for Energy Saving within UTRA Node B | FS_Energy_UMTS | 1 | Rel-10 | R1,R3 | 2009-12-04 08:00 | 2010-09-17 17:00 | 100% | RP-091439 | RP-100796 | Vodafone | Prakash.bhat@vodafone.com | RP#49 completed. Based on ETSI EE TS 102 706. | UTRA 25.927
1887 | 470015 | Study on Potential solutions for energy saving for E-UTRAN | FS_Energy_LTE | 1 | Rel-10 | R3,R2 | 2010-02-02 10:00 | 2011-06-03 17:00 | 100% | RP-100674 | RP-110597 | China Mobile | Yang Ning (yangning@chinamobile.com) | RP#52 completed | LTE 36.927
1888 | 470016 | Study on Improvements of distributed antenna for 1.28Mcps TDD | FS_distr_ant_LCR_TDD | 1 | Rel-10 | R1,R2,R3 | 2010-03-05 11:36 | 2010-12-10 17:00 | 100% | RP-100178 | RP-101287 | ZTE | huang.he4@zte.com.cn | RP#50 completed. TR 25.865 v101 for Approval | UTRA 25.865
1889 | 400037 | Deleted - Study on Unauthenticated PS Emergency Calls | FS_UAPSEC | 1 | Rel-10 | S1 | 2008-06-05 08:00 | 2010-03-25 17:00 | 100% | SP-080320 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#47 work stopped/abandoned | 22.984
1890 | 410042 | Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services | FS_eIMS_IBCF | 1 | Rel-10 | S2 | 2008-09-18 08:00 | 2010-12-15 17:00 | 100% | SP-090809 | - | Starent Networks | Rajat Ghai (rghai@starentnetworks.com) | SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS) | 23.848
1891 | 440050 | Deleted - Study on EPC Charging enhancement | FS_EPCcharg | 1 | Rel-10 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090318 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#47 work stopped. Issue covered by Rel-10 UID_460039 Charging for LIPA_SIPTO and UID_4700xy Charging for IFOM | -
1892 | 450012 | Deleted - Study on Interworking Proxy between GTP based and PMIP based interfaces | FS_GTP-MIP-IW | 1 | Rel-10 | C4 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | CP-090517 | - | NTT DoCoMo | takaaki.matsuura.sp@s1.nttdocomo.com | CP#48 work stopped/abandoned | 29.875
1893 | 0 | Release 9 Features | - | 1 | Rel-9 | CP,GP,RP,SP | 2000-01-01 08:00 | 2000-01-01 08:00 | 100% | - | - | - | - | - | -
1894 | 400035 | Enhanced Home NodeB / eNodeB | EHNB | 1 | Rel-9 | S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP | 2008-06-05 08:00 | 2011-12-09 17:00 | 100% | SP-090214 | - | T-Mobile | michael.kurz@t-mobile.at | RP#54 Testing completed | UTRA, LTE | HNB
1895 | 400047 | Stage 1 for EHNB | - | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080791 | - | T-Mobile | michael.kurz@t-mobile.at | CP#49 the SA1-reqs are moving. CT1 will align when the work in SA1 is clear. (was SP#44 completed.) | 22.220, 22.011 | HNB
1896 | 410026 | Architecture aspects of EHNB | - | 2 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-09-24 17:00 | 100% | SP-080636 | - | T-Mobile | sebastian.speicher@telekom.de | SP#45 completed | 23.401, 23.402, 23.060, New 23.830 | HNB
1897 | 420035 | Security aspects of Enhanced Home NodeB / eNodeB | EHNB-Sec | 2 | Rel-9 | S3 | 2008-12-11 08:00 | 2009-12-10 17:00 | 100% | SP-080879 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#46 completed | New 33.320 | HNB
1898 | 450003 | CT1 aspects - Support of Home NB and Home eNB enhancements | EHNB-CT1 | 2 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-12-10 17:00 | 100% | CP-090741 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#50 completed (Roaming aspects for manual CSG selection, Support of temporary users and CSG membership changes, Support of user controlled and operator controlled lists) | 23.122, 24.008, 24.285, 24.301 | HNB
1899 | 450004 | CT6 aspects - Support of Home NB and Home eNB enhancements | EHNB-CT6 | 2 | Rel-9 | C6 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090741 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#47 completed. Storing of CSG related data items on the USIM | 31.102 | HNB
1900 | 420036 | 3G HNB Gateway and LTE HeNB Gateway OAM&P | HNB-OAM_GW | 2 | Rel-9 | S5 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-100087 | - | China Mobile | GangChen (chengang@chinamobile.com) | SP#47 completed | 32.632, 32.633, 32.635, New (32.771, 32.772, 32.773, 32.775, 32.781, 32.782, 32.783, 32.785) | HNB
1901 | 430012 | 3G HNB and LTE HeNB OAM&P Type 1 Interface | HNB_eHNB-OAM_Type1 | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090208 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#47 completed | 32.581, 32.582, 32.583, 32.584, New (32.591, 32.592, 32.593, 32.594) | HNB
1902 | 440066 | 3G HNB and LTE HeNB OAM&P Type 2 Interface | HNB_eHNB-OAM_Type2 | 2 | Rel-9 | S5 | 2009-05-15 08:00 | 2010-03-25 17:00 | 100% | SP-090315 | - | Ericsson | edwin.tse@ericsson.com | SP#47 completed | New (32.571, 32.572) | HNB
1903 | 420008 | LTE FDD Home eNodeB RF Requirements | HeNB-RF_FDD | 2 | Rel-9 | R4 | 2008-12-05 08:00 | 2010-03-19 17:00 | 100% | RP-091300 | RP-100035 | Motorola | Ying Cai (yingcai@motorola.com) | RP#47 completed | 36.104, 36.141, New TR 36.921 | HNB
1904 | 430005 | LTE TDD Home eNodeB RF Requirements | HeNB-RF_TDD | 2 | Rel-9 | R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091386 | RP-100036 | China Mobile | Nan Li (linan@chinamobile.com) | RP#47 completed | 36.104, 36.141, 36.300, 36.331, 36.413, New TR 36.922 | HNB
1905 | 430025 | Home NB and Home eNB enhancements - RAN3 aspects | EHNB-RAN3 | 2 | Rel-9 | R3 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090349 | RP-091050 | Alcatel-Lucent | Martin Warner (mw15@alcatel-lucent.com) | RP#46 completed (based on high priority items specified in RP-090995) | 25.413, 25.467, 25.467, 25.468, 25.469, 25.469, 36.401, 36.413, New 25.444 | HNB
1906 | 430026 | Home NB and Home eNB enhancements - RAN2 aspects | EHNB-RAN2 | 2 | Rel-9 | R2 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091392 | RP-100037 | Huawei | Yang Xudong (yangxudong@huawei.com) | RP#47 completed | 25.304, 25.331, 25.367, 36.300, 36.304, 36.331 | HNB
1907 | 490020 | Conformance Test Aspects – Home NB enhancements for FDD | EHNB-UTRA_FDD_UEConTest | 2 | Rel-9 | R5 | 2010-09-17 08:00 | 2011-12-09 17:00 | 100% | RP-111315 | RP-111679 | Huawei | trica_li@huawei.com | UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367) | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | HNB
1908 | 500023 | Conformance Test Aspects – Home eNB enhancements | EHNB-LTE_UEConTest | 2 | Rel-9 | R5 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101191 | RP-110972 | Qualcomm | Mrs Lena Chaponniere (lchaponn@qualcomm.com) | RP#53 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | HNB
1909 | 440001 | Home NB and Home eNB enhancements - GERAN aspects | EHNB-GERAN | 2 | Rel-9 | GP | 2009-05-18 08:00 | 2010-09-03 17:00 | 100% | GP-090975 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#47 completed. GP#42 WID approved | 43.055, 43.129, 44.018, 44.060, 45.008, 48.008, 48.018 | HNB
1910 | 370026 | Value-Added Services for Short Message Service | VAS4SMS | 1 | Rel-9 | S1,C4,C1 | 2007-09-10 08:00 | 2009-12-04 17:00 | 100% | SP-070572 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | -
1911 | 370126 | Stage 1 for VAS4SMS | - | 2 | Rel-9 | S1 | 2007-09-10 08:00 | 2008-03-12 17:00 | 100% | SP-070572 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | SP#39 completed. SP#43 Feature moved to Rel-9 | new 22.142
1912 | 410011 | CT4 aspects of VAS4SMS Interface and Signalling Flow | - | 2 | Rel-9 | C4 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090813 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | new 23.142
1913 | 410014 | CT1 aspects of VAS4SMS Interface and Signalling Flow | - | 2 | Rel-9 | C1 | 2008-09-09 14:36 | 2009-12-04 17:00 | 100% | CP-090813 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | 23.040
1914 | 370027 | Definition of End-User Identity | EUI | 1 | Rel-9 | S1 | 2007-09-03 08:00 | 2008-12-11 17:00 | 100% | SP-090380 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905) | -
1915 | 410024 | Stage 1 for Definition of End-User Identity | - | 2 | Rel-9 | S1 | 2007-09-03 08:00 | 2008-12-11 17:00 | 100% | SP-090380 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905) | 21.905
1916 | 380067 | Customized Ringing Signal | CRS | 1 | Rel-9 | S1,C1 | 2007-12-06 08:00 | 2009-12-03 17:00 | 100% | SP-080502 | - | SK Telecom, China Mobile | Donghee Shim (SK Telecom), Jianping Zheng (China Mobile) | CP#48 completed | -
1917 | 410025 | Stage 1 for Customized Ringing Signal | - | 2 | Rel-9 | S1 | 2007-12-06 08:00 | 2008-12-11 17:00 | 100% | SP-080502 | - | SK Telecom, China Mobile | Donghee Shim (SK Telecom), Jianping Zheng (China Mobile) | SP#42 completed. | 22.173, new 22.183
1918 | 440041 | Stage 3 for IMS Customized Ringing Signal (CRS) Service | - | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2009-12-03 17:00 | 100% | CP-090444 | - | China Mobile | wangzhao | CP#48 completed | 24.173, new 24.183
1919 | 380057 | Public Warning System | PWS | 1 | Rel-9 | S1,C1,C4,R2,R3,R5 | 2007-12-06 08:00 | 2012-12-07 17:00 | 100% | SP-070876 | - | T-Mobile | Mark.Younge@t-mobile.com | TSG#46 completed. Larger scope than Rel-8 Feature UID_370051 (ETWS). Triggered by TR 22.968 Study UID_320025 (FS_PWS) | LTE | Public Safety (I-A)
1920 | 380058 | Stage 1 for Public Warning System | - | 2 | Rel-9 | S1 | 2007-12-06 08:00 | 2008-12-11 17:00 | 100% | SP-070876 | - | T-Mobile | Mark.Younge@t-mobile.com | SP#42 completed | 22.268 | Public Safety (I-A)
1921 | 440029 | Stage 3 for Public Warning System | PWS-St3 | 2 | Rel-9 | C1,C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | RP#46 completed | - | Public Safety (I-A)
1922 | 440030 | CT1 aspects of Stage 3 for Public Warning System | - | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#46 completed | 23.041 | Public Safety (I-A)
1923 | 440031 | CT4 aspects of Stage 3 for Public Warning System | - | 3 | Rel-9 | C4 | 2009-05-30 08:00 | 2009-12-04 17:00 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#46 completed | 29.168 | Public Safety (I-A)
1924 | 440005 | Public Warning System (PWS) – RAN aspects | PWS-RAN | 2 | Rel-9 | R2,R3 | 2009-05-30 08:00 | 2009-12-04 17:00 | 100% | RP-090649 | RP-091052 | AT&T | don.zelmer@att.com | RP#46 completed | LTE 36.300, 36.302, 36.331, 36.413 | Public Safety (I-A)
1925 | 540005 | Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE | PWS-RAN_UEConTest | 2 | Rel-9 | R5 | 2011-12-02 08:00 | 2012-12-07 17:00 | 100% | RP-111564 | RP-121525 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#58 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | Public Safety (I-A)
1926 | 400031 | Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 1 | Rel-9 | S1,C1 | 2008-06-05 08:00 | 2010-06-04 17:00 | 100% | SP-080430 | - | Vodafone | armin.toepfer@vodafone.com | CP#48 completed | -
1927 | 400043 | Stage 1 for Support of Personal Area Networks and Enhancements to Personal Network Management | - | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-06-05 08:00 | 100% | SP-080430 | - | Vodafone | armin.toepfer@vodafone.com | SP#40 completed | 22.259
1928 | 430002 | Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management | - | 2 | Rel-9 | C1 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | CP-090435 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#46 completed | 23.259
1929 | 430102 | Stage 3 for Support of Personal Area Networks and Enhancements to Personal Network Management | - | 2 | Rel-9 | C1 | 2009-03-09 08:00 | 2010-06-04 17:00 | 100% | CP-090435 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#48 completed | 24.259
1930 | 400032 | Multi-Media Telephony Service enhancements | eMMTel | 1 | Rel-9 | S1,S5,C1 | 2008-06-05 08:00 | 2010-03-25 17:00 | 100% | SP-080503 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed | -
1931 | 400044 | Stage 1 for eMMTel | - | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-12-11 17:00 | 100% | SP-080503 | - | France Telecom | philippe.lottin@orange.com | SP#42 completed | 22.173
1932 | 430031 | Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services) | eMMTel-SS-CH | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090196 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#47 completed | 32.275, 32.298, 32.299
1933 | 430032 | Support of Real-time Transfer of Tariff Information (RTTI) in IMS charging | IMSTSS-RTTI-CH | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090306 | - | Orange | Jean-Luc Garcia (jl.garcia@orange-ftgroup.com) | SP#47 completed. Linked to SA5 Rel-8 UID_380042 AoC support in IMS Charging (IMSTSS) | 32.240, 32.280, 32.298, 32.299
1934 | 440032 | Stage 3 - Enhancements for Completion of Communications Supplementary service | eMMTel-CC | 2 | Rel-9 | C1 | 2009-05-30 08:00 | 2009-12-04 17:00 | 100% | CP-090490 | - | France Telecom | Youssef.chadli@orange-ftgroup.com | CP#46 completed | 24.642
1935 | 400034 | User Data Convergence (UDC) | UDC | 1 | Rel-9 | S1,S5,C4 | 2008-06-05 08:00 | 2010-06-10 17:00 | 100% | SP-080448 | - | Nokia Siemens Networks | juergen.merkel@nsn.com | SP#48 completed. Triggered by Rel-8 SA5 Study of Common Profile Storage Framework of User Data for network services and management (UID_320006) TR 32.808 | -
1936 | 400046 | Stage 1 for User Data Convergence (UDC) | - | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-12-11 17:00 | 100% | SP-080448 | - | Nokia Siemens Networks | juergen.merkel@nsn.com | SP#42 completed | 22.101, new 22.985
1937 | 430103 | Stage 2/3 for User Data Convergence (UDC) Technical Realization | UDC-CN | 2 | Rel-9 | C4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | CP-090017 | - | Ericsson | emiliano.merino@ericsson.com | - | -
1938 | 430003 | User Data Convergence (UDC) Technical Realization (Stage 2) | - | 3 | Rel-9 | C4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | CP-090017 | - | Ericsson | emiliano.merino@ericsson.com | CP#47 completed | new 23.335
1939 | 450002 | User Data Convergence (UDC) Protocol Description | - | 3 | Rel-9 | C4 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090516 | - | China Mobile, Ericsson | Lan Si Zhong (lansizhong@chinamobile.com), emiliano.merino@ericsson.com | CP#47 completed | new 29.335
1940 | 440060 | User Data Convergence (UDC) Modelling and Management | UDC-MMAN | 2 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090309 | - | T-Mobile, China Mobile, Ericsson | istvan.aba@t-mobile.at, lansizhong@chinamobile.com, miguel.a.garcia@ericsson.com | SP#48 completed | -
1941 | 440062 | UDC – Framework for Model Handling and Management | UDC-MMAN-MFRM | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090311 | - | T-Mobile | istvan.aba@t-mobile.at | SP#48 completed | 32.172, new 32.181
1942 | 440061 | UDC – Common Baseline Information Model | UDC-MMAN-CBIM | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090310 | - | China Mobile, Ericsson | Lan Si Zhong, Miguel Garcia | SP#47 completed | 32.172, new 32.182
1943 | 410032 | IMS Services Centralization and Continuity | IMS_SCC | 1 | Rel-9 | S1,S2,C1 | 2008-09-18 08:00 | 2010-03-19 17:00 | 100% | SP-080633 | - | NEC | joerg.swetina@neclab.eu | CP#47 completed | -
1944 | 410033 | Stage 1 - Inter-Device Transfer – Requirements | IMS_SCC-IDT | 2 | Rel-9 | S1 | 2008-09-18 08:00 | 2008-12-11 17:00 | 100% | SP-080507 | - | NEC | joerg.swetina@neclab.eu | SP#42 completed | 22.101, 22.228
1945 | 410134 | Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions | IMS_SCC-SPI | 2 | Rel-9 | S2,C1 | 2008-09-18 08:00 | 2010-03-19 17:00 | 100% | SP-080561 | - | Huawei | HengLiang Zhang (hl_zhang@huawei.com) | - | -
1946 | 410034 | Stage 2 for IMS Service Continuity Enhancements: Service, Policy and Interactions | - | 3 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-06-04 17:00 | 100% | SP-080561 | - | Huawei | HengLiang Zhang (hl_zhang@huawei.com) | SP#57 Removal of the MSC server assisted mid-call feature from Rel-9 by 23.237CR#0433 (CT1 proposed moving this feature to Rel-10). SP#44 completed. TR 23.838 for Approval | 23.237, 23.292, 23.216, new 23.838
1947 | 440034 | Stage 3 for IMS Service Continuity Enhancements: Service, Policy, Interactions and Inter UE Transfer | - | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090440 | - | Qualcomm | Roozbeh Atarius (ratarius@qualcomm.com) | CP#47 completed | 24.216, 24.229, 24.237
1948 | 410135 | Stage 2/3 for IMS Centralized Services | IMS_SCC-ICS | 2 | Rel-9 | S2,C1 | 2008-09-18 08:00 | 2010-03-19 17:00 | 100% | SP-080634 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | -
1949 | 410035 | Stage 2 for IMS Centralized Services | - | 3 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-06-04 17:00 | 100% | SP-080634 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#44 completed. TR 23.883 for Information + Approval | 23.292, new 23.883
1950 | 440033 | Stage 3 for Enhancements to IMS Centralized Services | - | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090883 | - | Nokia Siemens Networks | Peter.Leis@nsn.com | CP#47 completed | 24.292, 24.604, 24.607, 24.608, 24.611, 24.623
1951 | 430004 | Stage 3 - IMS Centralized Services support via I1 interface | IMS_SCC-ICS_I1 | 2 | Rel-9 | C1 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | CP-090640 | - | Huawei | Lili Yang(kadyyang@huawei.com) | CP#47 completed | 24.237, 24.292, new 24.294
1952 | 420020 | Service Specific Access Control in EPS | SSAC | 1 | Rel-9 | S1,C1,R5 | 2008-12-11 08:00 | 2012-06-15 17:00 | 100% | SP-080882 | - | NTT DoCoMo | Frederic Thepot (thepot@docomolab-euro.com) | CP#47 completed. Triggered by TR 22.986 Study on Service Specific Access Control in EPS. As EPS is a PS-Domain only system, Domain Specific Access Control (DSAC) doesn't apply, hence SSAC allows restriction of voice and non-voice calls separately | -
1953 | 420021 | Stage 1 for Service Specific Access Control in EPS | - | 2 | Rel-9 | S1 | 2008-12-11 08:00 | 2008-12-11 17:00 | 100% | SP-080882 | - | NTT DoCoMo | Frederic Thepot (thepot@docomolab-euro.com) | SP#42 completed. If UE supports E-UTRA and IMS, SSAC is a mandatory Rel-9 function (during congestion in emergency case earthquake/tsunami improves mobile communications). | 22.011 CR0136
1954 | 440040 | Stage 3 for Service Specific Access Control in EPS | - | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090885 | - | NTT DoCoMo | Hideyuki Yamashita (yamashitahi@s1.nttdocomo.co.jp) | CP#47 completed | 24.173, 27.007
1955 | 520014 | Conformance Test Aspects - Service Specific Access Control | SSAC_UEConTest | 2 | Rel-9 | R5 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | RP-110765 | RP-120447 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#56 completed. Testing for Stage 3 for Service Specific Access Control in EPS (24.173, 27.007) UID_440040 | 34.229-1, 34.229-2, 34.229-3
1956 | a | Support for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 1 | Rel-9 | S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF | 2000-01-03 08:00 | 2014-06-13 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | RP#56 completed testing. CP#47 completed. SP#48 completed | GERAN, LTE | Public Safety (I-A)
1957 | 410036 | Stage 1 for IMS Emergency Calls over GPRS and EPS | - | 2 | Rel-9 | S1 | 2008-01-14 08:00 | 2008-12-11 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#42 completed | 22.101 | Public Safety (I-A)
1958 | 410037 | Stage 2 for IMS Emergency Calls over GPRS and EPS | - | 2 | Rel-9 | S2 | 2008-01-14 08:00 | 2009-06-04 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#44 completed | 23.869, 23.060, 23.167, 23.203, 23.221, 23.228, 23.271, 23.401, 23.402 | Public Safety (I-A)
1959 | 420022 | Security aspects for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS-Sec | 2 | Rel-9 | S3 | 2008-12-12 08:00 | 2010-06-10 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#48 completed | 33.401, 33.402 | Public Safety (I-A)
1960 | 440035 | Stage 3 for IMS Emergency Calls over GPRS and EPS | - | 2 | Rel-9 | C1,C3,C4,R5 | 2009-05-29 08:00 | 2012-06-15 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | RP#56 completed testing. CP#47 completed | GERAN, LTE | Public Safety (I-A)
1961 | 440036 | CT1 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | - | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#47 completed | 23.122, 24.008, 24.229, 24.301, 24.302 | Public Safety (I-A)
1962 | 480029 | Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS_UEConTest | 3 | Rel-9 | R5 | 2010-06-04 08:00 | 2012-06-15 17:00 | 100% | RP-100567 | RP-120445 | Samsung | stoyan.baev@partner.samsung.com | RP#56 completed | 34.108, 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2, 34.229-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | Public Safety (I-A)
1963 | 440037 | CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | - | 3 | Rel-9 | C3 | 2009-05-29 08:00 | 2009-09-18 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#45 completed | 29.212, 29.213, 29.214, 29.215 | Public Safety (I-A)
1964 | 440038 | CT4 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | - | 3 | Rel-9 | C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#46 completed | 23.003, 23.008, 29.060, 29.272, 29.273, 29.274, 29.275, 29.276 | Public Safety (I-A)
1965 | 420041 | Support for IMS Emergency Calls over LTE | IMS_EMER_LTE | 2 | Rel-9 | R2,R3 | 2000-01-03 08:00 | 2000-10-16 17:00 | 100% | RP-081140 | RP-090698 | Alcatel-Lucent | Sudeep Palat (spalat@alcatel-lucent.com) | RP#45 completed | 36.331, 36.413 | Public Safety (I-A)
1966 | 470017 | Conformance Test Aspects – Support for IMS Emergency Calls over LTE | IMS_EMER_LTE_UEConTest | 2 | Rel-9 | R5 | 2010-03-25 08:00 | 2010-12-10 17:00 | 100% | RP-100118 | RP-101068 | Ericsson | leif.mattisson@ericsson.com | RP#50 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | Public Safety (I-A)
1967 | 410038 | Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 2 | Rel-9 | S2,C1,C4,C3,IETF | 2008-09-18 08:00 | 2014-06-13 17:00 | 100% | SP-090099 | - | China Mobile | Yu Qing (Yuqing@chinamobile.com) | CP#56 added IETF dependency | - | Public Safety (I-A)
1968 | 410138 | SRVCC support for IMS Emergency Calls | - | 3 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-12-10 17:00 | 100% | SP-090099 | - | China Mobile | Yu Qing (Yuqing@chinamobile.com) | SP#46 completed | 23.870, 23.216, 23.237 | Public Safety (I-A)
1969 | 460018 | CT aspects of SRVCC support for IMS Emergency Calls | - | 3 | Rel-9 | C1,C4,C3,IETF | 2009-05-29 08:00 | 2014-06-13 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | - | Public Safety (I-A)
1970 | 440027 | CT1 aspects of SRVCC support for IMS Emergency Calls | - | 4 | Rel-9 | C1 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 24.229, 24.237 | Public Safety (I-A)
1971 | 440028 | CT4 aspects of SRVCC support for IMS Emergency Calls | - | 4 | Rel-9 | C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 29.205, 29.280 | Public Safety (I-A)
1972 | 460019 | CT3 aspects of SRVCC support for IMS Emergency Calls | - | 4 | Rel-9 | C3 | 2009-12-04 08:00 | 2009-12-04 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 29.163 | Public Safety (I-A)
1973 | 561003 | (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254) | - | 4 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-06-13 17:00 | 100% | CP-090882 | - | Andrew Allen | Andrew Allen | CP#64 completed | RFC 7254 (was draft-montemurro-gsma-imei-urn) | Public Safety (I-A)
1974 | 430006 | LCS for LTE and EPS | LCS_LTE_EPS | 1 | Rel-9 | S2,C1,C4,R2,R1,R3,R4,R5 | 2008-06-05 08:00 | 2012-03-02 17:00 | 100% | - | - | - | - | - | LTE | Public Safety (I-A)
1975 | 400038 | LCS Control Plane Solution for EPS | LCS_EPS-CPS | 2 | Rel-9 | S2,C4,C1 | 2008-06-05 08:00 | 2010-03-19 17:00 | 100% | SP-080445 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | Triggered by abandoned Study UID_380068 (FS_LCS_EPS). Linked to Feature UID_380064 Support for IMS Emergency Calls over GPRS and EPS | - | Public Safety (I-A)
1976 | 400048 | Stage 2 for LCS Control Plane Solution for EPS | - | 3 | Rel-9 | S2 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080445 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | SP#44 completed | 23.891, 23.271, 23.401, 23.402 | Public Safety (I-A)
1977 | 440020 | CT4 aspects of Control Plane LCS in the EPC | - | 3 | Rel-9 | C4 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090811 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | CP#47 completed (IANA registrations outstanding). Stage 3 SLs and SLg interfaces & transport of positioning messages between E-SMLC and MME in the scope of UID_420006 (Positioning Support for LTE) | 24.080, 29.002, 29.272, 29.230, new 24.171, 29.171, 29.172, 29.173 | Public Safety (I-A)
1978 | 440120 | CT1 aspects of Control Plane LCS in the EPC | - | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090811 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | CP#47 completed | 24.301 | Public Safety (I-A)
1979 | 420006 | Positioning Support for LTE | LCS_LTE | 2 | Rel-9 | R2,R1,R3,R4 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | RP-091389 | RP-100442 | Qualcomm | Nathan Tenny (ntenny@qualcomm.com) | RP#48 completed. UID_400038 (LCS Control Plane Solution for EPS) depends on this WI | 34.213, 36.133, 36.211, 36.214, 36.300, 36.305, 36.331, 36.355, 36.410, 36.413, 36.455, new 36.171 | Public Safety (I-A)
1980 | 470018 | Conformance Test Aspects – Positioning Support for LTE | LCS_LTE_UEConTest | 2 | Rel-9 | R5 | 2010-03-19 08:00 | 2012-03-02 17:00 | 100% | RP-111209 | RP-120034 | Qualcomm | Shubhang Vora (svoral@qualcomm.com) | RP#55 completed. RP#56 TS 37.571-4 v200 for Approval | 36.508, 36.509, new (37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5) | Public Safety (I-A)
1981 | 400039 | MBMS support in EPS | MBMS_EPS | 1 | Rel-9 | S2,S3,S5,C3,C4,R2,R3,R4,R5 | 2008-06-05 08:00 | 2011-12-09 17:00 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | RP#47 completed. SP#46, CP#46 completed | LTE
1982 | 400040 | Stage 2 for MBMS support in EPS | - | 2 | Rel-9 | S2 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | SP#44 completed | 23.246
1983 | 420023 | Security for MBMS support in EPS | - | 2 | Rel-9 | S3 | 2008-12-11 08:00 | 2009-12-10 17:00 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | SP#46 completed | 33.246
1984 | 430033 | MBMS Charging in EPS | - | 2 | Rel-9 | S5 | 2009-03-06 08:00 | 2009-12-10 17:00 | 100% | SP-090052 | - | ZTE | guo.wenjie1@zte.com.cn | SP#46 completed | 32.273, 32.251, 32.298, 32.299
1985 | 440025 | CT4 aspects of MBMS support in EPS (Stage 3) | - | 2 | Rel-9 | C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090325 | - | China Mobile, ZTE | wangjingyf@chinamobile.com, lu.fei1@zte.com.cn | CP#46 completed | 29.274, 29.281, 23.007, 23.008
1986 | 440026 | CT3 aspects of MBMS support in EPS (Stage 3) | - | 2 | Rel-9 | C3 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090330 | - | ZTE, China Mobile | zhou.xiaoyun@zte.com.cn, wangjingyf@chinamobile.com | CP#46 completed | 29.061
1987 | 430007 | MBMS support in LTE | MBMS_LTE | 2 | Rel-9 | R2,R3,R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091457 | RP-100033 | Huawei | arnaud.meylan@huawei.com | RP#47 completed | 25.446, 36.101, 36.104, 36.141, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.444, 36.445
1988 | 500024 | Conformance Test Aspects – MBMS support in LTE | MBMS_LTE-UEConTest | 2 | Rel-9 | R5 | 2010-12-10 08:00 | 2011-12-09 17:00 | 100% | RP-101245 | RP-111437 | Huawei | Zhang Xin (zhangxin0208@huawei.com) | RP#54 completed | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3
1989 | 420024 | Access Network Discovery and Selection Function enhancements | eANDSF | 1 | Rel-9 | S2,C1 | 2008-12-11 08:00 | 2010-03-19 17:00 | 100% | SP-080887 | - | Motorola | Apostolis Salkintzis (salki@motorola.com) | CP#47 completed. No new Rel-9 use cases defined. Implement service requirements not covered in Rel-8 | 22.278, SA3 33.402 CR#0055
1990 | 420040 | Stage 2 for Access Network Discovery and Selection Function enhancements | - | 2 | Rel-9 | S2 | 2008-12-11 08:00 | 2009-06-04 17:00 | 100% | SP-080887 | - | Motorola | Apostolis Salkintzis (salki@motorola.com) | SP#44 completed | 23.402, 23.002
1991 | 450006 | CT1 aspects of Access Network Discovery and Selection Function enhancements | - | 2 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090742 | - | Panasonic | benjamin.limck@sg.panasonic.com | CP#47 completed | 24.302, 24.312
1992 | 430034 | Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 1 | Rel-9 | S2,C4,C1 | 2009-03-13 08:00 | 2010-03-19 17:00 | 100% | SP-090098 | - | Samsung | erik.guttman@partner.samsung.com | CP#47 completed. Continues Rel-8 SAES Stage 2 UID_320005. Stage 1 in 22.278 (EPS Service requirements) | -
1993 | 430134 | Stage 2 for Multiple PDN Connection to the Same APN for PMIP-based Interfaces | - | 2 | Rel-9 | S2 | 2009-03-13 08:00 | 2009-06-04 17:00 | 100% | SP-090098 | - | Samsung | erik.guttman@partner.samsung.com | SP#44 completed | 23.060, 23.203, 23.401, 23.402
1994 | 450007 | CT4 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces | - | 2 | Rel-9 | C4 | 2009-09-18 08:00 | 2009-12-04 17:00 | 100% | CP-090515 | - | Samsung | Surjyakanta Mohapatra (surjya.kanta@samsung.com) | CP#46 completed | 29.275, 23.008, 29.282
1995 | 450008 | CT1 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces | - | 2 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090515 | - | Samsung | Surjyakanta Mohapatra (surjya.kanta@samsung.com) | CP#47 completed | 24.302
1996 | 450049 | System aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 1 | Rel-9 | S2,S4,C1,C3,R2,IETF | 2007-05-07 10:34 | 2012-09-12 17:00 | 100% | SP-090653 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | Triggered by RAN2 UID_440013 Vocoder rate adaptation for LTE | LTE
1997 | 450050 | SA2 system aspects of vocoder rate adaptation for LTE | - | 2 | Rel-9 | S2 | 2009-06-04 08:00 | 2009-09-24 17:00 | 100% | SP-090653 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#45 completed (CR adding support for Explicit Congestion Notification) | 23.401 CR#1103r3
1998 | 450051 | SA4 system aspects of vocoder rate adaptation for LTE | - | 2 | Rel-9 | S4 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090653 | - | Qualcomm | Nikolai Leung | SP#46 completed | 26.114
1999 | 440013 | Vocoder rate adaptation for LTE | - | 2 | Rel-9 | R2 | 2009-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-090978 | RP-090704 | Alcatel-Lucent | Sudeep Palat (spalat@alcatel-lucent.com) | RP#45 completed | 36.300 CR#0114
2000 | 521005 | (IETF) SA4 system aspects of vocoder rate adaptation for LTE | - | 2 | Rel-9 | S4-IETF | 2009-06-04 08:00 | 2012-09-12 17:00 | 100% | SP-090653 | - | Lionel Morand | - | SP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)
2001 | 521006 | (IETF) CT aspects of vocoder rate adaptation for LTE | - | 2 | Rel-9 | C1-IETF,C3-IETF,C4-IETF | 2007-05-07 10:34 | 2012-09-07 17:00 | 100% | SP-090653 | - | Lionel Morand | - | CP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)
2002 | 33025 | Access Security Enhancements | ACCSEC2 | 1 | Rel-9 | S3 | 2007-07-02 08:00 | 2009-06-04 17:00 | 100% | SP-040865 | - | Ericsson | Bengt.Sahlin@ericsson.com | SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security) | 33.102, 43.020
2003 | 410027 | Protection against Unsolicited Communication for IMS (PUCI) | PUCI | 1 | Rel-9 | S3,S1 | 2008-09-18 08:00 | 2009-12-10 17:00 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#46 TR 33.937 completed but no specification work done in Rel-9. Related work in OMA Categorization Based Content Screening | -
2004 | 410028 | Stage 1 for PUCI | - | 2 | Rel-9 | S1 | 2008-09-18 08:00 | 2008-12-11 17:00 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#42 completed | 22.228
2005 | 410029 | SA3 work on PUCI | - | 2 | Rel-9 | S3 | 2008-09-18 08:00 | 2009-12-10 17:00 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#46 completed. No normative work done in Rel-9 | New 33.937
2006 | 430036 | IMS Media Plane Security | MEDIASEC | 1 | Rel-9 | S3,C1,C4,C3,IETF | 2009-03-13 08:00 | 2012-09-14 17:00 | 100% | SP-090128 | - | Vodafone | Peter.Howard@vodafone.com | - | -
2007 | 430136 | SA3 aspects of IMS Media Plane Security | - | 2 | Rel-9 | S3 | 2009-03-13 08:00 | 2010-03-25 17:00 | 100% | SP-090128 | - | Vodafone | Peter.Howard@vodafone.com | SP#47 completed | New 33.828, 33.328
2008 | 521007 | (IETF) SA3, CT1, CT3 aspects of IMS Media Plane Security | - | 2 | Rel-9 | S3-IETF,C1-IETF,C3-IETF | 2009-03-18 08:00 | 2012-09-14 17:00 | 100% | SP-090128 | - | Peter Dawes | - | CP#57 completed, ietf-draft discontinued, documented within 3GPP | draft-dawes-dispatch-mediasec-parameter
2009 | 460020 | CN aspects of IMS Media Plane Security | MEDIASEC_CORE | 2 | Rel-9 | C1,C4,C3 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#48 completed | -
2010 | 450010 | CT1 aspects of IMS Media Plane Security | - | 3 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#47 completed | 23.218, 24.229
2011 | 450021 | CT4 aspects of IMS Media Plane Security | - | 3 | Rel-9 | C4 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#47 completed | 29.238, 23.334, 29.334
2012 | 460021 | CT3 aspects of IMS Media Plane Security | - | 3 | Rel-9 | C3 | 2009-12-04 08:00 | 2010-06-04 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#48 completed | 29.162
2013 | 440053 | GBAPush enhancements (Generic push layer) | eGBAPush | 1 | Rel-9 | S3 | 2008-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090282 | - | Ericsson | Rolf Blom | SP#43 umbrella to host 33.224, moved from Rel-8 to Rel-9. SP#47 completed | New 33.224
2014 | 420039 | SA3 part of eGBAPush (Generic push layer) | - | 2 | Rel-9 | S3 | 2008-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090282 | - | Ericsson | Rolf Blom | SP#47 completed | New 33.224
2015 | 440054 | Extended Identity Management | GBA-IdM | 1 | Rel-9 | S3 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090284 | - | Nokia | Silke.Holtmanns@nokia.com | SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous) | New 33.924, CT4 29.109 (added service code)
2016 | 440056 | Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 1 | Rel-9 | S3,IETF | 2009-06-04 08:00 | 2012-12-07 17:00 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | Continuation of Rel-8 UID_390044 SAE security architecture. Covers gaps in backhaul security in SAE (also applicable to UTRAN and GERAN backhaul) | -
2017 | 440156 | SA3 part of Network Domain Security (NDS) enhancements to support backhaul security | - | 2 | Rel-9 | S3 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | SP#47 completed | 33.102, 33.210, 33.310, 33.401, 33.402
2018 | 521008 | (IETF) SA3 part of Network Domain Security (NDS) enhancements to support backhaul security | - | 2 | Rel-9 | S3-IETF | 2009-06-04 08:00 | 2012-12-07 17:00 | 100% | SP-090286 | - | Bengt Sahlin | - | CP#58 completed | RFC 6712 (was draft-ietf-pkix-cmp-transport-protocols)
2019 | 440256 | Deleted - CT4 part of Network Domain Security (NDS) enhancements to support backhaul security | - | 2 | Rel-9 | C4 | 2009-06-04 08:00 | 2009-12-04 17:00 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | CP#46 completed. No impact on CT4 specs | -
2020 | 440057 | 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 1 | Rel-9 | S3,C1,C4,G2,G3new | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | Allow 128 as an alternative to 64 bit keys (Stage 2/3 + Test spec) | -
2021 | 440157 | SA3 part of 128 bit encryption for GSM and GPRS | - | 2 | Rel-9 | S3 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | SP#46 completed | 33.102,43.020, New 55.226
2022 | 440357 | CT1 part of 128 bit encryption for GSM and GPRS | - | 2 | Rel-9 | C1 | 2009-06-04 08:00 | 2009-09-18 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | CP#45 completed | 24.008,44.064
2023 | 440457 | CT4 part of 128 bit encryption for GSM and GPRS | - | 2 | Rel-9 | C4 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060 | -
2024 | 440557 | GERAN2 part of 128 bit encryption for GSM and GPRS | - | 2 | Rel-9 | G2 | 2009-06-04 08:00 | 2009-09-04 17:00 | 100% | GP-091212 | - | Ericsson | Karl Norrman | GP#43 WID approved + completed | 44.018,48.008,48.018,48.058
2025 | 440657 | GERAN3new (testing) part of 128 bit encryption for GSM and GPRS | - | 2 | Rel-9 | G3new | 2009-06-04 08:00 | 2009-11-20 17:00 | 100% | GP-091212 | - | Ericsson | Karl Norrman | GP#44 completed. GP#43 WID approved | 51.010
2026 | 440257 | Deleted - SA2 part of 128 bit encryption for GSM and GPRS | - | 2 | Rel-9 | S2 | 2009-06-04 08:00 | 2009-09-24 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | SP#45 work stopped/abandoned | 23.060
2027 | 420027 | Timed Graphics | TG | 1 | Rel-9 | S4 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080683 | - | Ericsson | clinton.priddle@ericsson.com | SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142) | 26.114, 26.140, 26.234, 26.244, 26.245, 26.346, New 26.430
2028 | 430037 | Managing MTSI Media Adaptation | M3A | 1 | Rel-9 | S4 | 2009-03-12 08:00 | 2009-12-10 17:00 | 100% | SP-090021 | - | Samsung | kyunghun.jung@samsung.com | SP#46 completed. Work extending Rel-8 UID_34041 MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size. Update speech/video adaptation algorithms used by network to control MTSI client terminal in congestion or poor transmission conditions. | 26.114
2029 | 440046 | PSS and MBMS Aspects | PMA | 1 | Rel-9 | S4 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090261 | - | Ericsson, Nokia | Clinton.Priddle@ericsson.com, imed.bouazizi@nokia.com | Umbrella WI | -
2030 | 430038 | PSS and MBMS extensions | PMA-MBS_Ext | 2 | Rel-9 | S4 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090262 | - | Ericsson | Clinton.Priddle@ericsson.com | SP#47 completed. Extends Rel-8 UID_34043 (PSS_MBMS_OMTV) & ensures compatibility with UID_34046 (IMS_PSS_MBMS_US) | 26.234, 26.346
2031 | 430039 | Improved Video Support for PSS and MBMS | PMA-IVS | 2 | Rel-9 | S4 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090263 | - | Nokia | imed.bouazizi@nokia.com | SP#47 completed | 26.234, 26.244, 26.346, new 26.903
2032 | 430046 | IMS based PSS and MBMS User Service extensions | IMS_PSS_MBMS_US_EXT | 1 | Rel-9 | S4 | 2009-03-12 08:00 | 2009-12-10 17:00 | 100% | SP-090225 | - | Ericsson | Markus Kampmann | SP#46 completed. Work extending Rel-8 UID_34046 (IMS_PSS_MBMS_US), SA2 UID_410034 IMSSCC-SPI (IMS Service Continuity Enhancements: Service, Policy and Interactions) | 26.237
2033 | 440051 | Syndicated Feed Reception within 3GPP environments | SFR | 1 | Rel-9 | S4 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090260 | - | Ericsson | Thorsten.Lohmar@ericsson.com | SP#46 completed. TS 26.150v100 for Approval. RSS optimized for mobile use. Reuse/reference OMA's enabler DCD. | New 26.150
2034 | 450048 | Distortion Measurement Test Methods and Requirements | DTMR | 1 | Rel-9 | S4 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-090575 | - | Motorola | Stephen Kendall (wcsk01@motorola.com) | SP#47 completed | 26.131, 26.132
2035 | 420029 | Rel-9 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM9 | 1 | Rel-9 | S5 | 2008-02-22 08:00 | 2010-06-10 17:00 | 100% | - | - | - | - | OAM9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI | TR 30.819
2036 | 420030 | Rel-9 Network Infrastructure Management | OAM9-NIM | 2 | Rel-9 | S5 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | - | - | - | - | SP#42 umbrella BB created to host OAM WIs | -
2037 | 420031 | Software Management for Network Elements | OAM9-NE_SWM | 3 | Rel-9 | S5 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080756 | - | Huawei, Nokia Siemens Networks | Bidipta Das (bidipta@huawei.com), Clemens Suerbaum (clemens.suerbaum@nsn.com) | SP#47 completed | 32.531, 32.532, 32.533, new 32.537
2038 | 440064 | Service Oriented Architecture (SOA) for IRP | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090313 | - | Ericsson, Nokia Siemens Networks | edwin.tse@ericsson.com, Jörg Schmidt (joerg@cox.net) | SP#47 completed (covering SOA Architecture & SOA-supporting Solution Set). Triggered by UID_400029 Study on Service Oriented Architecture (SOA) for IRP (TR 32.824) | 32.101, 32.102, 32.150
2039 | 440065 | IRP SOAP Solution Sets continuation from Rel-8 | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090314 | - | Ericsson | John Power | SP#47 completed. Continuation of Rel-8 UID_400030 IRP SOAP Solution Sets | New (32.127/ 327/ 337/ 357/ 387/ 397/ 447/ 397/ 447/ 507/ 537), 32.121,32.122,32.123,32,32.321,32.322,32.323,32.325,32.331,32.332,32.333,32.335,32.351,32.352,32.353,32.381,32.382,32.383,32.385,32.391,32.392,32.393,32.395,32.441,32.442,32.443
2040 | 420032 | Rel-9 Performance Management | OAM9-PM | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-06-10 17:00 | 100% | - | - | - | - | SP#42 umbrella BB created to host OAM WIs | -
2041 | 440059 | Enhancement of UTRAN Performance Measurements | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090308 | - | China Mobile | liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao | SP#46 completed | 32.405
2042 | 430041 | Enhancement of E-UTRAN Performance Measurements | - | 3 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-06-10 17:00 | 100% | SP-090053 | - | Motorola, Huawei | Yizhi Yao (yzyao@motorola.com),Lan Zou (zlan@huawei.com) | SP#48 completed | 32.425
2043 | 430042 | Enhancement of EPC Performance Measurements | - | 3 | Rel-9 | S5 | 2009-03-12 08:00 | 2009-12-10 17:00 | 100% | SP-090049 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#46 completed | 32.426
2044 | 430043 | Rel-9 Self-Organizing Networks (SON) - OAM aspects | OAM9-SON | 2 | Rel-9 | S5 | 2008-02-22 08:00 | 2010-06-10 17:00 | 100% | - | - | - | - | SP#43 umbrella BB created to host OAM WIs | - | SON
2045 | 390007 | SON self-optimization management (moved from Rel-8 LTE_SON-OAM) | - | 3 | Rel-9 | S5 | 2008-02-22 08:00 | 2010-06-10 17:00 | 100% | SP-100091 | - | Huawei | Lan Zou (zlan@huawei.com) | SP#48 completed | 32.425, new (32.521, 32.522, 32.523, 32.525) | SON
2046 | 440067 | Automatic Radio Network Configuration Data Preparation | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090869 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#48 completed | 32.501, 32.502, 32.503, 32.505, new 32.507 | SON
2047 | 440058 | Rel-9 Subscription Management (SuM) evolution | OAM9-SuM | 2 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090307 | - | Ericsson | frode.nergard@ericsson.com | SP#48 completed | 32.140, 32.141, 32.152, 32.172, 32.175
2048 | 420033 | Deleted - Rel-9 Trace | OAM9-Trace | 2 | Rel-9 | S5 | 2009-03-13 08:00 | 2009-12-10 17:00 | 100% | - | - | - | - | SP#46 stopped (no work in Rel-9) | -
2049 | 440068 | Rel-9 Charging Management small Enhancements | CH9 | 1 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | - | - | - | - | CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI | TR 30.819
2050 | 400008 | CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 1 | Rel-9 | C3,C4 | 2008-05-30 08:00 | 2010-03-19 17:00 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#47 completed. Rel-8 UID_380061 (Ipinterc) covers Stage 1 in SA1 22.101, 22.228 | -
2051 | 400109 | CT3 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications | - | 2 | Rel-9 | C3 | 2008-05-30 08:00 | 2010-03-19 17:00 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#47 completed | 29.235
2052 | 400010 | CT4 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications | - | 2 | Rel-9 | C4 | 2008-05-30 08:00 | 2009-12-04 17:00 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#46 completed | 23.231, 29.232, new 29.238
2053 | 410008 | IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 1 | Rel-9 | C4,C3 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | -
2054 | 410108 | CT4 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | - | 2 | Rel-9 | C4 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | new 29.238
2055 | 410208 | CT3 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | - | 2 | Rel-9 | C3 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | 29.162, 29.235
2056 | 410009 | IMS Application Level Gateway Control Function (ALGCF) – IMS Access Media Gateway (IMA-MGW); Iq Interface; Stage 2 and Stage 3 | IMS_AGCF | 1 | Rel-9 | C4 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090020 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | New 23.334, 29.334
2057 | 420016 | Enhancements of IMS Customized Alerting Tone (CAT) Service | eCAT | 1 | Rel-9 | C1 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | CP-080796 | - | China Mobile | Jiang Yi | CP#48 completed. Stage 1 in 22.182 | -
2058 | 420017 | Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service | eCAT-SS | 2 | Rel-9 | C1 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | CP-080796 | - | China Mobile | Jiang Yi | CP#48 completed | 24.182
2059 | 440017 | Completion of IMS Restoration Procedures | eIMS_RP | 1 | Rel-9 | C3,C4,C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed. Continuation of Rel-8 Feature UID_400012 IMS Restoration Procedures | -
2060 | 440018 | CT4 aspects of Completion of IMS Restoration Procedures | - | 2 | Rel-9 | C4 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 23.380, 23.820
2061 | 440019 | CT1 aspects of Completion of IMS Restoration Procedures | - | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 24.229
2062 | 460022 | CT3 aspects of Completion of IMS Restoration Procedures | - | 2 | Rel-9 | C3 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 29.061, 29.212, 29.213, 29.214, 29.215
2063 | 440039 | IMS Stage 3 IETF Protocol Alignment - phase 3 | IMSProtoc3 | 1 | Rel-9 | C1,IETF | 2009-05-29 08:00 | 2014-12-05 17:00 | 94% | CP-090491 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | -
2064 | 440139 | CT1 aspects of IMS Stage 3 - IETF Protocol Alignment - phase 3 | - | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090491 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | 23.218, 24.229, 24.930
2065 | 521009 | (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (draft-kaplan) | - | 2 | Rel-9 | C1-IETF | 2009-05-29 08:00 | 2014-12-05 17:00 | 90% | CP-090491 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Will be documented in an informational RFC (draft-kaplan-insipid-session-id), work continue in draft-jones-insipid-session-id, but this is not referenced in our specifications yet | draft-kaplan-dispatch-session-id
2066 | 531007 | (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7044) | - | 2 | Rel-9 | C1-IETF | 2011-09-13 08:00 | 2014-03-07 17:00 | 100% | CP-090491 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#63 completed | RFC 7044 (was draft-ietf-sipcore-rfc4244bis)
2067 | 440070 | Operational description of the Inter-IMS Network to Network Interface (II-NNI) | II-NNI | 1 | Rel-9 | C3,IETF | 2009-05-29 08:00 | 2014-12-05 17:00 | 83% | CP-090331 | - | Orange | sebastien.daudet@orange-ftgroup.com | - | -
2068 | 440170 | Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3 | 2009-05-29 08:00 | 2010-06-04 17:00 | 100% | CP-090331 | - | Orange | - | CP#48 completed | 29.165
2069 | 561004 | (IETF) Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-05 17:00 | 90% | CP-090331 | - | christer.holmberg@ericsson.com | Christer Holmberg | Will be documented in an informational RFC (draft-kaplan-insipid-session-id), work continue in draft-jones-insipid-session-id, but this is not referenced in our specifications yet | draft-kaplan-dispatch-session-id
2070 | 561005 | (IETF) Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-05 17:00 | 75% | CP-090331 | - | Keith Drage | Keith Drage | in RFC Ed-queue | draft-vanelburg-dispatch-private-network-ind
2071 | 561006 | (IETF) Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-05 17:00 | 75% | CP-090331 | - | Roland Jesske | Roland Jesske | Submitted to IESG for publicatio | draft-ietf-salud-alert-info-urns
2072 | 561007 | (IETF) Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-05 17:00 | 90% | CP-090331 | - | Roland Jesske | Roland Jesske | Submitted to IESG for publication | draft-ietf-cuss-sip-uui
2073 | 561008 | (IETF) Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-05 17:00 | 75% | CP-090331 | - | Keith Drage | Keith Drage | Submitted to IESG for publication | draft-ietf-cuss-sip-uui-isdn
2074 | 561009 | (IETF) Operational description of the Inter-IMS Network to Network Interface | - | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-05 17:00 | 75% | CP-090331 | - | Peter Dawes | peter.dawes@vodafone.com | Removed from Rel-8 to Rel-11. Not completed internet-draft | Rel-12 remains draft-dawes-sipping-debug
2075 | 591002 | Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface (avasarala-dispatch-comm-div-notification) | - | 2 | Rel-9 | C3-IETF | 2013-03-01 08:00 | 2014-06-13 17:00 | 100% | CP-090331 | - | Andrew Allen | Andrew Allen | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification
2076 | 450005 | Definition of Ml interface for Control Plane LCS (Stage 3) | EMC2 | 1 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090746 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed [Stage 3 for Rel-7 Emergency Calls (EMC1)]. Related to Rel-9 UID_400038 LCS Control Plane Solution for EPS. Stage 2 in Rel-9 UID_400038 (23.271), UID_410037 (23.167) | 24.229 | Public Safety (I-A)
2077 | 450009 | PCC enhancements | PCC-Enh | 1 | Rel-9 | C3 | 2009-09-18 08:00 | 2009-12-04 17:00 | 100% | CP-090744 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#46 completed | 29.212, 29.213, 29.215
2078 | 460004 | 3GPP IMS Conferencing Management Object (MO) | IMS_ConfMO | 1 | Rel-9 | C1 | 2009-12-03 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2) | New 24.166
2079 | 470004 | In Case of Emergency (ICE) Graphics | ICE_Graphics | 1 | Rel-9 | C6 | 2010-03-17 08:00 | 2010-03-19 17:00 | 100% | CP-100178 | - | Sagem-Orga | heiko.kruse@sagem-orga.com | CP#47 approved WID and completed. Added capability to store ICE graphical information (picture). Linked to CT6 Rel-8 ICE Feature UID_380059 In Case of Emergency numbers storage and easy access on UICC | 31.102 CR#0433
2080 | 410023 | Rel-9 Improvements of the Radio Interface | RInImp9 | 1 | Rel-9 | RP,GP | 2008-09-12 08:00 | 2010-03-19 17:00 | 100% | - | - | - | - | RP#41 umbrella Feature created to host Rel-9 WIs | GERAN, UTRA, LTE
2081 | 410017 | LCR TDD UE OTA Performance Requirements | RInImp9-RFLCROTA | 2 | Rel-9 | R4 | 2008-09-12 08:00 | 2009-05-29 17:00 | 100% | RP-080744 | RP-090389 | RITT | Wu Xiang (wuxiang@chinattl.com) | RP#44 completed technical work (RAN4 internal TR abandoned) | UTRA (no TR 25.8xy produced)
2082 | 410019 | RF requirements for Multicarrier and Multi-RAT BS | RInImp9-RFmulti | 2 | Rel-9 | R4,G1 | 2008-11-21 08:00 | 2010-03-19 17:00 | 100% | RP-091381 | - | Ericsson | Johan.skold@ericsson.com | RP#47 completed. RF requirements specification applicable to Multi-Standard Radio (MSR) Base Station with multiple carriers and/or multiple 3GPP Radio Access Technologies (RAT) | GERAN, UTRA, LTE
2083 | 420009 | RAN4 part of RF requirements for Multicarrier and Multi RAT BS | RInImp9-Rfmulti | 3 | Rel-9 | R4 | 2008-12-05 08:00 | 2010-03-19 17:00 | 100% | RP-091381 | RP-100027 | Ericsson | johan.skold@ericsson.com | RP#48 completed | UTRA, LTE 25.104, 25.105, 36.104, new 37.104, 37.113, 37.141, 37.900
2084 | 420001 | GERAN part of RF requirements for Multicarrier and Multi RAT BS | RInImp9-RFmulti-GERAN | 3 | Rel-9 | G1 | 2008-11-21 08:00 | 2009-11-20 17:00 | 100% | GP-081945 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#44 Core spec completed. GP#40 WID approved | GERAN 45.005, 51.021
2085 | 420010 | Extended UMTS/LTE 800 MHz | RInImp9-UMTSLTE800 | 2 | Rel-9 | R4,R2,R3 | 2008-12-05 08:00 | 2009-09-18 17:00 | 100% | RP-080884 | RP-090687 | NTT DoCoMo | Shingo Suwa (suwas@nttdocomo.co.jp) | RP#45 completed | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466, new 36.800
2086 | 430009 | UMTS/LTE 800 MHz for Europe | RInImp9-UMTSLTE800EU | 2 | Rel-9 | R4,R2,R3 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-090156 | RP-100028 | Ericsson | olav.queseth@ericsson.com | RP#47 completed | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, new 36.810, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466
2087 | 430010 | Performance requirement for LCR TDD with UE speeds up to 350 km/h | RInImp9-LCRTDD350 | 2 | Rel-9 | R4 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090258 | RP-091035 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#46 completed | UTRA 25.102, 25.105, 25.142
2088 | 440004 | Extended UMTS/LTE 1500 MHz | UMTSLTE1500 | 2 | Rel-9 | R4,R2,R3 | 2009-05-30 08:00 | 2010-03-19 17:00 | 100% | RP-090470 | RP-100029 | NTT DoCoMo | Shingo Suwa (suwas@nttdocomo.co.jp) | RP#47 completed. For potential deployment in Japan | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.331, new (36.821, 36.307)
2089 | 440006 | Rel-9 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-9 | R5 | 2009-05-19 08:00 | 2010-09-17 17:00 | 100% | - | - | - | - | - | UTRA, LTE
2090 | 440007 | Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe | RInImp-UEConTest-UMTSLTE800EU | 2 | Rel-9 | R5 | 2009-05-19 08:00 | 2010-09-17 17:00 | 100% | RP-090485 | RP-100736 | Ericsson | fredrik.sundstrom@ericsson.com | RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe | UTRA, LTE 34.108, 34.121-1, 34.121-2, 36.508, 36.521-1, 36.521-2, 36.521-3
2091 | 450017 | Conformance Test Aspects – Extended UMTS/LTE 1500 MHz | UMTSLTE1500_UEConTest | 2 | Rel-9 | R5 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | RP-091366 | RP-100487 | NTT DoCoMo | Nguyen Dung Dao (dao@nttdocomo.co.jp) | RP#48 completed | UTRA, LTE 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3
2092 | 440012 | TDD UE Over The Air (Antenna) conformance testing methodology | UEAnt_TDDTest | 2 | Rel-9 | R5 | 2009-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-090621 | RP-090727 | CATR | Qu Yan (quyan@emcite.com) | RP#45 completed. Finalized TDD UE test methodology based on R4 TR 25.914 (UE and MS antenna performance evaluation method) and TS 25.144 Over the Air (Antenna) minimum performance requirements for the speech mode (terminal close to head) | UTRA 34.114
2093 | 470019 | Conformance Test Aspects – Performance requirement for LCR TDD with UE speeds up to 350 km/h | RInImp9-LCRTDD350_UEConTest | 2 | Rel-9 | R5 | 2010-03-19 08:00 | 2010-06-04 17:00 | 100% | RP-100167 | RP-100496 | CATT | Xiaozhong Chen (chexiaozhong@datangmobile.cn) | RP#48 completed. Testing for UID_430010 Performance requirement for LCR TDD with UE speeds up to 350 km/h | UTRA 34.122
2094 | 450018 | Conformance Test Aspects – SMS over IMS in E-UTRAN | SMSoverIMS_UEConTest | 1 | Rel-9 | R5 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | RP-090959 | RP-100072 | Alcatel-Lucent | Nidal Khrais (khrais@alcatel-lucent.com) | RP#47 completed | LTE 34.229-1, 34.229-2, 34.229-3
2095 | 430013 | Rel-9 RAN improvements | - | 1 | Rel-9 | RP | 2000-01-03 08:00 | 2010-03-19 17:00 | 100% | - | - | - | - | RP#47 completed | UTRA
2096 | 430014 | Dual-Cell HSUPA | RANimp-DC_HSUPA | 2 | Rel-9 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-090014 | RP-100030 | Nokia Siemens Networks | Karri Ranta-aho (karri.ranta-aho@nsn.com) | RP#47 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.319, 25.306, 25.321, 25.331, 25.423, 25.433
2097 | 430015 | Support for different bands for Dual-Cell HSDPA | RANimp-MultiBand_DC_HSDPA | 2 | Rel-9 | R4,R2,R3 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090973 | RP-091038 | Nokia Siemens Networks | Tuomo Säynäjäkangas (tuomo.saynajakangas@nsn.com) | RP#46 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.133, 25.306, 25.308, 25.331, 25.423, 25.433, new 25.317 replaced by new TS 25.327
2098 | 430016 | Combination of DC-HSDPA with MIMO | RANimp-DC_MIMO | 2 | Rel-9 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090332 | RP-091039 | Ericsson | johan.bergman@ericsson.com | RP#46 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 26.306, 25.423, 25.433
2099 | 430018 | Transmit Antenna Array (TxAA) extension for non-MIMO UEs | RANimp-TxAA_nonMIMO | 2 | Rel-9 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090013 | RP-091040 | Nokia | Arto Lehti (arto.lehti@nokia.com) | RP#46 completed | 25.101, 25.104, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.306, 25.321, 25.331, 25.423, 25.433
2100 | 440014 | Cell Portion for 1.28 Mcps TDD | CP_LCRTDD | 2 | Rel-9 | R3,R1,R4 | 2000-01-03 08:00 | 2000-07-07 17:00 | 100% | RP-090659 | RP-091041 | CATT | Ying Zhang (zhangying2@datangmobile.cn) | RP#46 completed | 25.102, 25.105, 25.123, 25.225, 25.423, 25.433
2101 | 490025 | Rel-9 RAN improvements - UE Conformance Testing | - | 1 | Rel-9 | R5 | 2010-09-17 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | - | -
2102 | 490019 | Conformance Test Aspects – Combination of DC-HSDPA with MIMO | RANimp-DC_MIMO_UEConTest | 2 | Rel-9 | R5 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | RP-101001 | RP-110510 | Ericsson | leif.mattisson@ericsson.com | UTRA. RP#52 completed. Testing for Rel-9 UID_430016 Combination of DC-HSDPA with MIMO | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2103 | 510014 | Conformance Test Aspects – Dual-Cell HSUPA | RANimp-DC_HSUPA_UEConTest | 2 | Rel-9 | R5 | 2011-03-18 08:00 | 2012-12-07 17:00 | 100% | RP-110116 | RP-121524 | Ericsson | leif.mattisson@ericsson.com | RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2104 | 510013 | Conformance Test Aspects – Support for different bands for Dual-Cell HSDPA | RANimp-MultiBand_DC_HSDPA_UEConTest | 2 | Rel-9 | R5 | 2011-03-18 08:00 | 2012-03-02 17:00 | 100% | RP-110115 | RP-120036 | Ericsson | leif.mattisson@ericsson.com | RP#55 completed. Testing for Rel-9 UID_430015 Support for different bands for Dual-Cell HSDPA | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2105 | 420007 | LTE improvements | LTEimp | 1 | Rel-9 | R1,R2,R4,R5 | 2009-03-06 08:00 | 2011-06-03 17:00 | 100% | - | - | - | - | - | LTE
2106 | 430019 | LTE Pico NodeB RF Requirements | LTEimp-Pico_eNB-RF | 2 | Rel-9 | R4 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-091155 | RP-091045 | Huawei | Liyan Yin (yinliyan@huawei.com) | RP#46 completed | 36.104, 36.141, new 36.931
2107 | 430029 | Enhanced Dual-Layer transmission for LTE | LTEimp-eDL | 2 | Rel-9 | R1,R2,R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091385 | RP-100034 | China Mobile | Xu Xiaodong (xuxiaodong@chinamobile.com) | RP#47 completed | 36.101, 36.211, 36.212, 36.213, 36.331
2108 | 490018 | UE Conformance Test Aspects – Enhanced Dual-layer transmission for LTE TDD | LTEimp-eDL_UEConTest | 2 | Rel-9 | R5 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | RP-100868 | RP-110509 | China Mobile | Shanpeng Xiao (xiaoshanpeng@chinamobile.com) | RP#52 completed. Testing for UID_430029 (Enhanced Dual-Layer transmission for LTE) | 36.508, 36.521-1, 36.521-2
2109 | 420011 | Rel-9 Self-Organizing Networks (SON) | SON | 1 | Rel-9 | R3,R2 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-090162 | RP-100038 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#47 completed | LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902 | SON
2110 | 38002 | AGNSS Performances and Testing Procedures | AGNSSPTP | 1 | Rel-9 | G1,G3new | 2008-05-16 08:00 | 2011-05-20 17:00 | 100% | GP-092342 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#46 still ongoing MS testing. Linked to Rel-10 RAN4 UID_450027 (AGNSS Minimum Performance for UTRAN) | -
2111 | 38003 | AGNSS Minimum Performances | AGNSSPTP-Perfreq | 2 | Rel-9 | G1 | 2008-05-16 08:00 | 2010-03-05 17:00 | 100% | GP-081786 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#45 completed (open performance requirements alignment GPS/Galileo) | 45.005
2112 | 38004 | AGNSS Testing Procedures | AGNSSPTP-MStest | 2 | Rel-9 | G3new | 2008-05-16 08:00 | 2011-05-20 17:00 | 100% | GP-092343 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#50 completed | 51.010-1, new 51.010-7
2113 | 420002 | Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 1 | Rel-9 | GP,G1,G2,G3new | 2008-11-21 08:00 | 2012-03-02 17:00 | 100% | GP-081949 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | Triggered by UID_50590 (MUROS) Study on Multi-User Reusing-One-Slot | -
2114 | 420003 | Stage 2 for Voice services over Adaptive Multi-user channels on One Slot | - | 2 | Rel-9 | GP,G1,G2 | 2008-11-21 08:00 | 2010-05-21 17:00 | 100% | GP-081964 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#46 completed. GP#40 WID approved | 45.001
2115 | 420004 | Stage 3 for Voice services over Adaptive Multi-user channels on One Slot | - | 2 | Rel-9 | GP,G1,G2 | 2008-11-24 08:00 | 2011-03-04 17:00 | 100% | GP-081965 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#49 completed. GP#40 WID approved | 24.008, 44.018, 45.002, 45.003, 45.004, 45.008, 48.008, 48.058
2116 | 420005 | VAMOS Radio Performance Requirements | - | 2 | Rel-9 | GP,G1,G2 | 2008-11-24 08:00 | 2011-05-20 17:00 | 100% | GP-081966 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#50 completed. GP#40 WID approved | 45.005
2117 | 490005 | VAMOS - MS conformance testing | VAMOS_MStest | 2 | Rel-9 | G3new | 2010-09-03 08:00 | 2012-03-02 17:00 | 100% | GP-101604 | - | BlackBerry | Raveendra Seetharam (rseetharam@rim.com) | GP#53 completed. GP#47 WID approved | 51.010-1, 51.010-2
2118 | 500001 | VAMOS - BTS conformance testing | VAMOS_BTStest | 2 | Rel-9 | G1 | 2010-11-26 08:00 | 2011-09-02 17:00 | 100% | GP-102005 | - | Nokia Siemens Networks | eddie.riddington@nsn.com | GP#51 completed. GP#48 WID approved | 51.021
2119 | 440002 | Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC) | CEBRO | 1 | Rel-9 | GP,C1 | 2009-05-15 08:00 | 2010-03-19 17:00 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | CP#47 completed. GP#45 completed. GP#42 WID approved | -
2120 | 440102 | GERAN part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre | - | 2 | Rel-9 | GP | 2009-05-15 08:00 | 2010-03-05 17:00 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | GP#45 completed. GP#42 WID approved | new 48.049
2121 | 440202 | CT1 part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre | - | 2 | Rel-9 | C1 | 2009-05-15 08:00 | 2010-03-19 17:00 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | CP#47 completed | 23.041
2122 | 440003 | Hybrid Location | HILT | 1 | Rel-9 | GP | 2009-05-18 08:00 | 2009-11-20 17:00 | 100% | GP-091075 | - | TruePosition | Matt Ward (mward@trueposition.com) | GP#44 completed. GP#42 WID approved (Hybrid Integrated Location Technology=HILT) | 43.059, 48.071
2123 | 420099 | (Small) Technical Enhancements and Improvements for Rel-9 | TEI9 | 1 | Rel-9 | SP,CP,RP,GP | 2008-09-15 08:00 | 2009-12-10 17:00 | 100% | - | - | - | - | SP#46 completed | -
2124 | 460002 | Test - (Small) Technical Enhancements and Improvements for Rel-9 | TEI9_Test | 1 | Rel-9 | R5,G3new | 2009-11-20 08:00 | 2010-12-24 17:00 | 100% | - | - | - | - | GP#44 created | -
2125 | 330017 | Deleted - Services Alignment and Migration | ServAl | 1 | Rel-9 | S1 | 2006-12-06 08:00 | 2008-09-18 17:00 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#41 closed (no tangible result of this work; no CR against TR 22.983). Triggered by Study UID_370086 (FSServAl) | -
2126 | 410001 | Deleted - Stage 1 for ServAl | - | 2 | Rel-9 | S1 | 2006-12-06 08:00 | 2008-09-18 17:00 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#41 closed (no tangible result of this work; no CR against TR 22.983) | 22.983
2127 | 380071 | Deleted - Harmonization of Gq'/Rx for Common IMS | IMS_Comm_GqRx_Harm | 1 | Rel-9 | S2 | 2008-01-14 08:00 | 2009-03-12 17:00 | 100% | SP-070822 | - | Alcatel-Lucent | geoffrey.cristallo@alcatel-lucent.be | SP#43 stopped. LS_out to TISPAN informs about stopping this activity | 23.822, 23.203
2128 | 380081 | Deleted - Support of WiMAX - LTE Mobility | WiMAX_LTE_Mobility | 1 | Rel-9 | R2 | 2008-06-06 08:00 | 2009-12-25 17:00 | 100% | RP-070511 | - | Samsung | - | RP#39: No agreed WID | 36.306, 36.331, 36.413, 36.300, 36.214, 36.133, 36.304
2129 | 380082 | Deleted - Support of WiMAX - UMTS Mobility | WiMAX_UMTS_Mobility | 1 | Rel-9 | R2 | 2008-06-06 08:00 | 2009-12-25 17:00 | 100% | RP-070511 | - | Intel | - | RP#39: No agreed WID | 25.306, 25.331, 25.413
2130 | 380086 | Deleted - Definition of 3GPP UICC services over the new high-speed interface | UICCHS | 1 | Rel-9 | C6 | 2010-03-19 17:00 | 2010-03-19 17:00 | 100% | CP-070837 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#47 work stopped/abandoned | 31.xyz
2131 | 390040 | Deleted - SAES Enhancements (non RAN aspects) | SAES_Ph2 | 1 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-12-08 17:00 | 100% | - | - | Nokia Siemens Networks | - | SP#39 created to host Rel-9 Wis. BUT no agreed WID | -
2132 | 350028 | Deleted - Functions and procedures for SAE to support LTE MBMS | - | 2 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-12-08 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. WID returned to SA2 for re-consideration & remove MBMS for EPS from Rel 8 | -
2133 | 390041 | Deleted - CS over EPS | - | 2 | Rel-9 | S2 | 2008-03-12 08:00 | 2008-12-08 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | -
2134 | 390042 | Deleted - SAE for generic support for non-3GPP accesses | - | 2 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-06-09 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | -
2135 | 390043 | Deleted - Single Radio Aspects of SAE for Optimized Handover with WiMAX | - | 3 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-06-09 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | -
2136 | 440071 | Deleted - Lawful Interception in the 3GPP Rel-9 | LI9 | 1 | Rel-9 | S3 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090831 | - | PIDS, Nortel | Koen Jaspers, Ronald Ryan | SP#47 stopped. WI + new topics moved to Rel-10 | 33.106, 33.107, 33.108
2137 | 0 | Release 9 Studies | - | 1 | Rel-9 | CP,RP,SP | 2008-06-05 08:00 | 2010-03-19 17:00 | 100% | - | - | - | - | - | -
2138 | 400036 | Study on Service Specific Access Control in EPS | FS_SSAC | 1 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-12-11 17:00 | 100% | SP-080319 | - | NTT DoCoMo | Shin-ichi Isobe (isobes@nttdocomo.co.jp) | SP#42 completed. Spin-off Feature UID_420020 (SSAC) | 22.986
2139 | 350052 | Study on CS Domain Services over EPS access | FS_CSoPS | 1 | Rel-9 | S2 | 2007-04-25 08:00 | 2009-03-12 17:00 | 100% | SP-080800 | - | T-Mobile | Karl-Heinz.Nenner@T-Mobile.net | SP#43 completed. Linked to Combinational Services UID_31064, Services Alignment and Migration (ServAl) UID_330017 and 3GPP System Architecture Evolution (SAES) UID_3208 | 23.879
2140 | 370043 | Study on Extended Support of IMS Emergency Calls | FS_IMS-eCall | 1 | Rel-9 | S2 | 2007-09-24 08:00 | 2008-12-11 17:00 | 100% | SP-070547 | - | Qualcomm | Stephen Edge | SP#42 completed | 23.868 | Public Safety (I-A)
2141 | 320031 | Study on Service Continuity for Emergency Voice Calls | FS_VCCEm | 1 | Rel-9 | S2 | 2006-06-08 08:00 | 2009-03-12 17:00 | 100% | SP-080555 | - | Nortel | Ricky Kaura (rkaura@nortel.com) | SP#43 completed | 23.826 | Public Safety (I-A)
2142 | 370053 | Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M Equipment | FS_UM2M | 1 | Rel-9 | S3,C6 | 2004-04-06 15:48 | 2009-12-10 17:00 | 100% | SP-070702 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#46 completed. Triggered by the SA1 Rel-8 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) UID_7027 in TR 22.868. | 33.812 | MTC, M2M
2143 | 360006 | Study on System Maintenance over Itf-N | FS_OAM-Maint-Itf-N | 1 | Rel-9 | S5 | 2007-06-07 08:00 | 2009-09-24 17:00 | 100% | SP-070306 | - | ZTE | Shuqiang Huang (huangsq@zte.com.cn) | SP#45 completed | 32.822
2144 | 360007 | Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB | FS_OAM-SON-HNB | 1 | Rel-9 | S5 | 2007-06-07 08:00 | 2009-06-04 17:00 | 100% | SP-080461 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#44 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036) | 32.821 | HNB, SON
2145 | 390017 | Study on Self-healing of Self-Organizing Networks (SON) | FS_OAM-SON-SH | 1 | Rel-9 | S5 | 2008-02-22 08:00 | 2009-09-24 17:00 | 100% | SP-080076 | - | ZTE | zhu.weihong@zte.com.cn | SP#45 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036) | 32.823 | SON
2146 | 400029 | Study on Service Oriented Architecture (SOA) for IRP | FS_OAM_SOA_IRP | 1 | Rel-9 | S5 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080281 | - | Ericsson | edwin.tse@ericsson.com | SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP | 32.824
2147 | 380079 | Study on Evaluation of the inclusion of Path Loss Based Technology in the UTRAN | FS_RAN-Pathloss | 1 | Rel-9 | R4 | 2007-12-17 08:00 | 2009-12-04 17:00 | 100% | RP-071050 | RP-091080 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#46 completed | 25.907
2148 | 390031 | Study on LTE-Advanced | FS_RAN_LTEA | 1 | Rel-9 | R1,R2,R3,R4 | 2007-03-23 15:24 | 2010-03-19 17:00 | 100% | RP-091360 | RP-100080 | NTT DoCoMo | Tetsushi Abe | RP#47 completed | 36.913 , New 36.814, 36.912, R2 36.806 (Relay architectures for E-UTRA), R4 36.815 (LTE-Advanced feasibility studies in RAN4) | CA
2149 | 410016 | Study on 1.28 Mcps TDD Home NodeB | FS_RAN-HNBLCRTDD | 1 | Rel-9 | R4 | 2008-02-20 13:00 | 2009-12-04 17:00 | 100% | RP-080767 | RP-091081 | TD Tech | Li Rong (lirong@td-tech.com) | RP#46 completed | 25.866 | HNB
2150 | 420012 | Study on E-UTRAN Mobility Evaluation and Enhancement | FS_EUTRAN_mob | 1 | Rel-9 | R1 | 2008-12-05 08:00 | 2009-05-29 17:00 | 100% | RP-081137 | RP-090426 | Qualcomm | Rajat Prakash (rprakash@qualcomm.com) | RP#44 closed (RP-090452 R1 LS to RAN on Conclusions for LTE Mobility Study Item - no further Rel-9 action / no TR needed) | none
2151 | 430021 | Study on Minimization of drive-tests in Next Generation Networks | FS_NGN_min_drive-tests | 1 | Rel-9 | R2 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090341 | RP-091084 | Qualcomm | Masato Kitazoe (mkitazoe@qualcomm.com) | RP#46 completed | 36.805
2152 | 430027 | Study on Enhanced Interference Management for HNBs | FS_eInterfMgmt_HNB | 1 | Rel-9 | R4 | 2009-03-06 08:00 | 2009-05-29 17:00 | 100% | RP-090361 | RP-090429 | Qualcomm | Farhad Meshkati (fmeshkat@qualcomm.com) | RP#44 completed. Linked to UID_420008 LTE FDD Home eNodeB RF Requirements. Spin-off RAN3 UID_440015 Study on Enhanced Interference Management Mechanisms for HNBs | 25.967 | HNB
2153 | 440015 | Study on Enhanced Interference Management Mechanisms for HNBs | FS_eInterfMgmtMchsm_HNB | 1 | Rel-9 | R3 | 2009-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-090667 | RP-090733 | Qualcomm | Farhad Meshkati (fmeshkat@qualcomm.com) | RP#45 completed. Triggered by RAN4 UID_430027 Study on Enhanced Interference Management for HNBs | 25.967 | HNB
2154 | 320026 | Deleted - Study on Protection against SMS and MMS spam | FS_CPSMal | 1 | Rel-9 | S3 | 2006-06-08 08:00 | 2009-09-24 17:00 | 100% | SP-060446 | - | Orange | eric.gauthier@orange.ch | SP#45 work stopped/abandoned | 33.9xx
2155 | 0 | Release 8 Features | - | 1 | Rel-8 | CP,GP,RP,SP | 2006-09-19 14:36 | 2010-03-19 17:00 | 100% | - | - | - | - | - | -
2156 | 320005 | 3GPP System Architecture Evolution Specification - Evolved Packet System (non RAN aspects) | SAES | 1 | Rel-8 | S1,S2,S3,S5,C1,C3,C4,C6,IETF | 2006-04-12 08:00 | 2012-06-15 17:00 | 100% | SP-080132 | - | T-Mobile | michael.kurz@t-mobile.at | Role model for SAE/LTE system wide project management by SA2 in SP-060166 | -
2157 | 320022 | Requirements for evolution of the 3GPP system architecture | AIPN-SAE | 2 | Rel-8 | S1 | 2006-06-08 08:00 | 2007-12-12 17:00 | 100% | SP-080132 | - | T-Mobile | michael.kurz@t-mobile.at | SP#38 completed | 22.011, 22.246, New 22.278
2158 | 370005 | High level and common (for all accesses) functions | EPS-ComF | 2 | Rel-8 | S2,S3,C1,C3,C4 | 2007-01-02 08:00 | 2009-05-29 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#44 completed | -
2159 | 350024 | Stage 2 for High level functions | SAES-SA-HLF | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-02 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | New 23.402
2160 | 390044 | Stage 2 Security Architecture | - | 3 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | marc.blommaert.ext@nsn.com | SP#42 completed | 33.210, 33.310, New 33.401
2161 | 340051 | Stage 3 (CT1) for SAE impact on services, network functions and capabilities | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.229, 27.007, New 24.305
2162 | 340054 | Stage 3 SAE impact on existing capabilities | - | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080772 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#42 completed | 29.061
2163 | 340062 | Stage 3 (CT4) of SAE impact on existing capabilities | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | New (29.274, 29.275)
2164 | 340049 | Stage 2/3 for Network selection procedures | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 23.122, New 24.302
2165 | 340023 | Stage 3 EPC interworking with external PDNs (SGi) | SAES-St3-intwk | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2009-05-29 17:00 | 100% | CP-080772 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#44 completed | 29.061
2166 | 340022 | Stage 3 PCC within SAE | SAES-St3-PCC | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2009-05-29 17:00 | 100% | CP-080576 | - | Ericsson | j.javier.pastor@ericsson.com | CP#44 completed | 29.212, 29.213, 29.214, New 29.215
2167 | 340028 | Stage 3 for SAE / LTE identities | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 23.003
2168 | 370017 | Unified guidelines for Diameter usage within 3GPP | SAES-DIAM | 3 | Rel-8 | C3 | 2007-09-21 08:00 | 2008-12-05 17:00 | 100% | CP-080055 | - | Huawei | Javier Gonzalez Gallego | CP#42 completed | New 29.909
2169 | 350025 | SAE for LTE access | SAES-LTE | 2 | Rel-8 | S2,C1,C3,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed | -
2170 | 340060 | CT4 Stage 3 for protocol between EPCs | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275
2171 | 350042 | SAES-SA-FP_LTE with GTP variant | SAES-SA-FP_LTE-GTP | 3 | Rel-8 | S2,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#43 completed | -
2172 | 370006 | Stage 2 for SAES-SA-FP_LTE with GTP variant | SAES-SA-FP_LTE-GTP-St2 | 4 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | 23.401, 23.060, 23.002, 23.246, 23.203, 23.107, 23.234, 23.271
2173 | 340055 | CT4 Stage 3 for GTP v2 protocol | - | 4 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274
2174 | 350043 | SAES-SA-FP_LTE with PMIP variant | SAES-SA-FP_LTE-IETF | 3 | Rel-8 | S2,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#43 completed | -
2175 | 370007 | Stage 2 for SAES-SA-FP_LTE with PMIP variant | SAES-SA-FP_LTE-IETF-St2 | 4 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | -
2176 | 370018 | CT4 Stage 3 for PMIP protocol within EPC | - | 4 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.275, 29.282
2177 | 410004 | Mobile IPv4 (MIPv4) based Mobility protocols | - | 4 | Rel-8 | C4 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-090247 | - | Motorola | Lewis Milton | CP#42 completed | 29.279
2178 | 340020 | Stage 3 for UE Non-Access-Stratum (NAS) mobility procedures in idle and active mode | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.007, 24.301
2179 | 340050 | Stage 3 for Session management, bearer control and QoS aspects | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.007, 24.301
2180 | 340053 | Stage 3 for security aspects of LTE Access | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301
2181 | 340025 | Stage 3 for QoS mechanisms | - | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080576 | - | Ericsson | j.javier.pastor@ericsson.com | CP#42 completed | 29.213
2182 | 340026 | Stage 3 for EPC - HSS interface | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.272
2183 | 350026 | SAE for Interoperation between LTE and legacy cellular PS accesses | SAES-SA-FP_3GPP | 2 | Rel-8 | S2,C1,C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed | -
2184 | 370008 | Stage 2 for Interoperation between LTE and 2G/3G | EPSto2_3G | 3 | Rel-8 | S2 | 2007-02-05 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#41 completed | 23.401, 23.402
2185 | 380031 | Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301
2186 | 340018 | Stage 2 GPRS enhancements for LTE access | SAES-GPRS_LTE | 3 | Rel-8 | S2 | 2007-09-04 17:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.401
2187 | 390008 | Stage 2 GPRS for EPC (23.060, etc.) | - | 3 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#41 completed | 23.060
2188 | 340056 | Stage 3 for EPC - GPRS | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275, 29.281
2189 | 380032 | Stage 3 for EPC to UTRAN | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275, 29.281
2190 | 380033 | Stage 3 for EPC to 3GPP2 | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.277, 29.276
2191 | 370009 | Stage 2 for Interoperation between LTE and CDMA2000 | EPStoC2k | 3 | Rel-8 | S2 | 2007-06-18 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Motorola, Vodafone | Irfan.Ali@motorola.com, chris.pudney@vodafone.com | SP#41 completed (except: Handover of multiple PDNs=>Rel-9) | 23.401, 23.402
2192 | 360023 | Stage 3 for Inter-system mobility between E-UTRAN and CDMA2000 | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.301, 24.302
2193 | 340061 | Stage 3 for MME - SGSN signalling free protocol | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.272, 29.274
2194 | 350027 | SAE for support for non-3GPP accesses | SAES-SA-FP_n3GPP | 2 | Rel-8 | S2,S3,C1,C4,IETF | 2007-01-02 08:00 | 2012-06-15 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed. SP#39 retained in Rel-8 (in addition to the essential functionality defined in SP-070699). Replaces UID_340037 | -
2195 | 350044 | Stage 2 for Host-based Mobility aspects | SAES-SA-FP_n3GPP-HBMob | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | 23.402
2196 | 350045 | Stage 2 for Network-based Mobility aspects | SAES-SA-FP_n3GPP-NBMob | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#41 completed | 23.402
2197 | 360022 | Stage 3 for Mobility management based on DSMIPv6 | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.303
2198 | 521011 | (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt) | - | 3 | Rel-8 | C1-IETF | 2007-02-05 08:00 | 2012-06-15 17:00 | 100% | CP-080493 | - | Mark Jones | - | CP#56 completed | RFC 6610 (was draft-ietf-mip6-hiopt)
2199 | 521012 | (IETF) Stage 3 for Mobility management based on DSMIPv6 (RFC6275) | - | 3 | Rel-8 | C1-IETF | 2007-02-05 08:00 | 2011-07-29 17:00 | 100% | CP-080493 | - | - | - | SP#53/IETF#81 completed | RFC 6275 (was draft-ietf-mext-rfc3775bis)
2200 | 390009 | Stage 3 for Mobility management based on MIP v4 | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.304
2201 | 380030 | Stage 3 for Inter-system mobility between E-UTRAN and non 3GPP accesses | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301
2202 | 360019 | Stage 2 for Optimized Dual-Radio Handover with WiMAX | SAES-SA-FP_n3GPP-OptWIMAX | 3 | Rel-8 | S2 | 2007-06-25 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | 23.402
2203 | 390045 | Stage 2 Security aspects for non-3GPP Access | - | 3 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | marc.blommaert.ext@nsn.com | SP#42 completed | 33.402, 33.210, 33.310
2204 | 370010 | Stage 3 security aspects for DSMIPv6 Access | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.303
2205 | 390172 | Stage 3 security aspects for MIPv4 Access | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.304
2206 | 360021 | Stage 3 for Access to the EPC via non-3GPP access networks | - | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.302, 24.312
2207 | 370011 | Stage 3 for interfaces within EPC | - | 3 | Rel-8 | C4 | 2007-09-19 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.281
2208 | 340057 | Stage 3 for Interfaces EPC - non-3GPP IP access | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.273, 29.275
2209 | 521013 | (IETF) Stage 3 for Interfaces EPC - non-3GPP IP access | - | 3 | Rel-8 | C4-IETF | 2007-02-05 08:00 | 2012-06-15 17:00 | 100% | CP-090247 | - | Lionel Morand | - | CP#56 completed | RFC 6611 (was draft-ietf-mip6-bootstrapping-integrated)
2210 | 340058 | Stage 3 for AAA/HSS related | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#42 completed | 29.273
2211 | 340059 | Stage 3 for EPC - AAA interface | - | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#42 completed | 29.273
2212 | 360018 | Deleted (already covered) SAES-SA-FP_n3GPP Optimized Handover with CDMA | SAES-SA-FP_n3GPP-OptCDMA | 3 | Rel-8 | S2 | 2007-06-25 08:00 | 2007-06-25 08:00 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | -
2213 | 350030 | Single Radio Voice Call Continuity for 3GPP (SRVCC) | SAES-SRVCC | 2 | Rel-8 | S2,C1,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-070949 | - | Nokia Siemens Networks | curt.c.wong@nokia.com | CP#43 completed. SP#38 WID approved (extract from SAE WID SP-070817). | -
2214 | 350130 | Stage 2 for 2G/3G SRVCC | - | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-09-18 17:00 | 100% | SP-070949 | - | Nokia Siemens Networks | curt.c.wong@nokia.com | SP#41 completed. SP#38 WID approved | New 23.216
2215 | 410005 | Stage 3 for SRVCC in EPS | - | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080793 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 23.009, 24.008, New 24.301
2216 | 410006 | MME to MSC interface for SRVCC | - | 3 | Rel-8 | C4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080793 | - | Nokia Siemens Networks | Giorgi Gulbani | CP#43 completed | 23.003, 23.008, New (29.274, 29.277, 29.280)
2217 | 360020 | Voice Call Continuity for CDMA2000 1X | SAES-VCC_1X | 2 | Rel-8 | S2 | 2007-06-25 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | -
2218 | 350031 | SAE impacts on IMS | SAES-SA_IMS | 2 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | -
2219 | 390036 | CS Fallback in EPS | SAES-CSFB | 2 | Rel-8 | S2,C1,C4 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | SP-080097 | - | T-Mobile, Vodafone | sabine.demel@t-mobile.at, chris.pudney@vodafone.com | CP#43 completed | -
2220 | 400001 | Stage 2 for CS Fallback in EPS | - | 3 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080097 | - | T-Mobile, Vodafone | sabine.demel@t-mobile.at, chris.pudney@vodafone.com | SP#40 completed | New (23.272, 23.401)
2221 | 400102 | CT1 part of Stage 3 for CS Fallback in EPS | - | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080791 | - | NEC | yannick.lair@nectech.fr | CP#43 completed | 24.007, 24.008, 24.011, 29.018, New (24.301, 24.801, 29.118)
2222 | 400003 | CT4 part of Stage 3 for CS Fallback in EPS | - | 3 | Rel-8 | C4 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080791 | - | NEC | yannick.lair@nectech.fr | CP#42 completed | 23.007, 23.008, 29.274, New 29.277
2223 | 390039 | System enhancements for the use of IMS services in local breakout | SAES-IMS_LBO | 2 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080090 | - | Telecom Italia | mario.madella@telecomitalia.it | SP#40 completed | 23.228, 23.221, 23.203
2224 | 390010 | EPC Data Definitions | EPC-OAM | 2 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | - | - | - | - | SP#43 completed | -
2225 | 380037 | EPC Network Resource Model (NRM) Integration Reference Point (IRP) | - | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070737 | - | Huawei | WANG, Xuelong | SP#43 completed | New (32.751, 32.752, 32.753, 32.755)
2226 | 390011 | Performance measurements for EPC | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2009-03-12 17:00 | 100% | SP-080061 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#43 completed | New 32.426
2227 | 380038 | EPC Charging | EPC-CH | 2 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070736 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#43 completed | 32.240, 32.296, 32.251, 32.252, 32.298, 32.299
2228 | 400104 | Domain Name System Procedures for Evolved Packet System (DEPS) | SAES-DEPS | 2 | Rel-8 | C4 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080280 | - | TeliaSonera | jouni.korhonen@teliasonera.com | CP#43 completed | 23.003, New 29.303
2229 | 410007 | InterWorking Function (IWF) between MAP based and Diameter based interfaces | SAES-MAP2Diam | 2 | Rel-8 | C4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080644 | - | Huawei | liming49985@huawei.com | CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam) | New 29.305
2230 | 390021 | CT6 aspects of SAE | - | 2 | Rel-8 | C6 | 2008-03-07 08:00 | 2011-06-03 17:00 | 100% | CP-080164 | - | Nokia | Rune Lindholm | CP#44 completed core specification | -
2231 | 390121 | Core specification for CT6 aspects of SAE | - | 3 | Rel-8 | C6 | 2008-03-07 08:00 | 2009-05-29 17:00 | 100% | CP-080164 | - | Nokia | Rune Lindholm | CP#44 completed (specified Network Measurement Results collection via USAT) | 31.102, 31.111
2232 | 420018 | Test interworking of LTE Terminals with the USIM | SAES-USIM_LTE-Test | 3 | Rel-8 | C6 | 2008-12-05 08:00 | 2010-12-10 17:00 | 100% | CP-100598 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#50 completed. Steering of Roaming test cases have been introduced. Remaining issues CSG display testing (Provide Local Information, Call Control for EPS/PDN, Event Download (Access Technology Change - Multiple Access Technologies) | 31.121, 31.124
2233 | 490015 | Test interworking of IP Multimedia Services Identity Module (ISIM) terminals with IP Multimedia Subsystem (IMS) | SAES-ISIM_IMS_Test | 3 | Rel-8 | C6 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100602 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#52 completed. Linked to R5 UID_1273 Provisioning of IP-based multimedia services (24.229, 31.103), R8 UID_390021 CT6 aspects of SAE, UID_420018 Test interworking of LTE Terminals with the USIM, R UID_450018 Testing SMS over IMS in E-UTRAN (34.229). | 31.121, 31.124, New TS 31.134
2234 | 390018 | Issues for CT1 TR 24.801 | - | 2 | Rel-8 | C1 | 2007-01-04 15:00 | 2008-12-05 17:00 | 100% | CP-080068 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.801
2235 | 390019 | Issues for CT3 TR 29.804 | - | 2 | Rel-8 | C3 | 2007-02-05 08:00 | 2008-09-12 17:00 | 100% | CP-080068 | - | Ericsson | j.javier.pastor@ericsson.com | CP#41 completed | 29.804
2236 | 390020 | Deleted - Issues for CT4 TR 29.803 | - | 2 | Rel-8 | C4 | 2007-01-04 15:00 | 2008-09-12 17:00 | 100% | CP-080068 | - | Huawei | - | CP#41 Work stopped and continued in Normative specifications | 29.803
2237 | 350029 | Deleted (covered by 380068): Functions and procedures for SAE to support LCS | SAES-SA-FP_LCS | 2 | Rel-8 | S2 | 2008-03-03 08:00 | 2008-03-03 08:00 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | -
2238 | 350032 | Deleted (covered by 380064): SAE aspects of Emergency Calls | SAES-SA-EmCall | 2 | Rel-8 | S2 | 2008-03-03 08:00 | 2008-03-03 08:00 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - | Public Safety (I-A)
2239 | 340019 | Deleted - CT aspects of SAES | SAES-St3 | 2 | Rel-8 | C3,C1,C4 | 2007-09-04 17:00 | 2008-03-14 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | -
2240 | 350019 | Deleted - CT1 aspects of SAES | - | 3 | Rel-8 | C1 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | -
2241 | 340052 | Deleted - Interoperability | SAES-St3-interop | 3 | Rel-8 | C1 | 2008-03-14 17:00 | 2008-03-14 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | -
2242 | 350020 | Deleted - CT3 aspects of SAES | - | 3 | Rel-8 | C3 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | CP-060675 | - | - | - | SP#37 stopped | -
2243 | 350021 | Deleted - CT4 aspects of SAES | - | 3 | Rel-8 | C4 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | CP-060676 | - | - | - | SP#37 stopped | 29.803
2244 | 340021 | Deleted - UE to EPC NAS signalling (incl. MBMS and QoS aspects) | SAES-St3-sig | 3 | Rel-8 | C1 | 2008-03-14 17:00 | 2008-03-14 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | -
2245 | 340027 | Deleted - User and Control plane protocols | SAES-St3-prot | 3 | Rel-8 | C4 | 2007-09-21 17:00 | 2007-09-21 17:00 | 100% | CP-060676 | - | - | - | SP#37 stopped | -
2246 | 340037 | Deleted - Architecture enhancements for non-3GPP accesses | SAES-non_3GPP | 2 | Rel-8 | S2 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | SP-060926 | - | Motorola | Irfan.Ali@motorola.com | SP#34 stopped. Replaced by UID_350027 and its children | 23.402
2247 | 320030 | Deleted - Stage 2 of architecture for the 3GPP System Architecture Evolution | SAES-St2 | 2 | Rel-8 | S2 | 2007-10-02 17:00 | 2007-10-02 17:00 | 100% | SP-060926 | - | Vodafone | chris.pudney@vodafone.com | SP#34 stopped. Replaced by UIDs 340018 and 340037. (SP#34 report discussion of SP-060917.) | 23.002, 23.060, 23.107, 23.203, 23.228, 23.234, 23.246, 23.271, 23.279
2248 | 350023 | Deleted - SA aspects of System Architecture Evolution | SAES-SA | 2 | Rel-8 | S2 | 2006-04-12 08:00 | 2007-10-01 17:00 | 100% | - | - | - | - | SP#34 stopped | -
2249 | 450022 | Conformance Test Aspects – Mobility management based on DSMIPv6 (Dual-Stack Mobile IPv6) | DSMIPv6_UEConTest | 1 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-09-17 17:00 | 100% | RP-090754 | RP-100738 | Qualcomm | Lena Chaponniere (lchaponn@qualcomm.com) | RP#49 completed. Testing for CT1's UID_360022 (24.303) under Rel-8 Feature SAES | 36.508, 36.523-1, 36.523-2, 36.523-3
2250 | 370025 | IMS Centralized Service control | ICSRA | 1 | Rel-8 | S1,S2,C1,C3,C4,IETF | 2005-11-01 16:12 | 2014-12-05 17:00 | 95% | SP-070924 | - | AT&T | Randolph Wohlert (rwohlert@tri.sbc.com) | CP#46 completed | -
2251 | 380039 | Stage 1 for ICS Requirement and Architecture | - | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-12 17:00 | 100% | SP-070924 | - | AT&T | Randolph Wohlert (rwohlert@tri.sbc.com) | SP#39 completed | 22.101
2252 | 380040 | Stage 2 for ICS Requirement and Architecture | ICSRA-St2 | 2 | Rel-8 | S2 | 2007-12-14 08:00 | 2008-06-05 17:00 | 100% | SP-070924 | - | Alcatel-Lucent | - | SP#40 completed | 23.292, 23.206
2253 | 400205 | Stage 3 for ICSRA – Protocol, Addressing, Subscriber Data | - | 2 | Rel-8 | C1,C3,C4,IETF | 2005-11-01 16:12 | 2014-12-05 17:00 | 95% | CP-091046 | - | Ericsson | sean.schneyer@ericsson.com | CP#46 completed | -
2254 | 400005 | CT1 aspects - Stage 3 for ICSRA | - | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-091046 | - | Ericsson | Sean Schneyer | CP#46 completed | 24.229, new (24.292, 24.286)
2255 | 521014 | (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns) | - | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2014-12-05 17:00 | 75% | CP-091046 | - | Roland Jesske | Roland Jesske | Submitted to IESG for publication | draft-ietf-salud-alert-info-urns
2256 | 521015 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 6871) | - | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2013-03-01 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#59 completed | RFC 6871 (was draft-ietf-mmusic-sdp-media-capabilities)
2257 | 521016 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7195) | - | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2014-06-13 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#64 complete | RFC 7195 (was draft-ietf-mmusic-sdp-cs)
2258 | 521017 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7006) | - | 3 | Rel-8 | C1-IETF | 2008-06-03 08:00 | 2013-12-06 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#62 completed | RFC7006 (was draft-ietf-mmusic-sdp-miscellaneous-caps)
2259 | 400006 | CT3 aspects - Stage 3 for ICSRA | - | 3 | Rel-8 | C3 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-091046 | - | Mavenir | Brett Wallis ( brett@mavenir.com) | CP#43 completed | new 29.292
2260 | 400007 | CT4 aspects - Stage 3 for ICSRA | - | 3 | Rel-8 | C4 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-091046 | - | Ericsson | Sean Schneyer | CP#42 completed | 23.003, 29.232, 23.018, 29.002
2261 | 521018 | (IETF) CT4 aspects - Stage 3 for ICSRA (RFC 7254) | - | 3 | Rel-8 | C4-IETF | 2005-11-01 16:12 | 2014-06-13 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#64 complete | RFC 7254 (was draft-montemurro-gsma-imei-urn)
2262 | 400105 | Deleted - Stage 3 for ICSRA – I1 interface | - | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-09-12 17:00 | 100% | CP-080492 | - | Huawei | xupeili@huawei.com | CP#41 work stopped | 24.293
2263 | 370059 | IMS Multimedia Telephony and Supplementary Services | IMSTSS | 1 | Rel-8 | S1,S5,C1,C3,C4,IETF | 2007-05-02 08:00 | 2014-12-05 17:00 | 95% | - | - | - | - | SP#43 completed | -
2264 | 370060 | General aspects of IMS Sup Services | IMSSS-Gal | 2 | Rel-8 | S1,C1,C3,C4 | 2007-09-03 08:00 | 2009-03-06 17:00 | 100% | SP-070691 | - | Ericsson | Susana Sabater | CP#43 completed | -
2265 | 370023 | Service and Capability for Core IMS - inclusion of TISPAN requirements | TISCAPR8 | 3 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-14 17:00 | 100% | SP-070691 | - | Ericsson | Susana Sabater | SP#39 completed | 22.228, 22.115, 22.101
2266 | 380001 | Documentation of TISPAN R1 and R2 in CT1 | REDOC_TIS-C1 | 3 | Rel-8 | C1 | 2007-11-28 08:00 | 2008-09-12 17:00 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#41 completed | 24.141, 24.147, 24.173, 24.229, 24.247, 24.341, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.616, 24.623, 24.628, 24.629, 24.647, 24.654
2267 | 380002 | Documentation of TISPAN R1 and R2 in CT3 | REDOC_TIS-C3 | 3 | Rel-8 | C3 | 2007-11-28 08:00 | 2009-03-06 17:00 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#43 completed | 29.162, 29.163, 29.658
2268 | 380003 | Documentation of TISPAN R1 and R2 in CT4 | REDOC_TIS-C4 | 3 | Rel-8 | C4 | 2007-11-28 08:00 | 2008-09-12 17:00 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#41 completed | 29.228, 29.229
2269 | 370062 | IMS Multimedia Telephony Service | IMS-MMTel | 2 | Rel-8 | S1,S5 | 2007-09-10 08:00 | 2009-03-12 17:00 | 100% | - | - | - | - | SP#43 completed | -
2270 | 370024 | Merging TISPAN MMTel [requirements] for Common IMS | TMMTEL | 3 | Rel-8 | S1 | 2007-09-10 08:00 | 2007-12-07 17:00 | 100% | SP-070569 | - | Nokia Siemens Networks | - | SP#38 completed | 22.173
2271 | 380041 | Multimedia Telephony Service and Supplementary Services (MMTel) offline Charging | MMTel-CH | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-080848 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | CP#43 completed | 32.275, 32.298/299
2272 | 380006 | Call Completion on Busy Subscriber (CCBS)/Call Completion on Non-Reachable (CCNR) on IMS | CCBS_CCNR | 2 | Rel-8 | C1,C3,IETF | 2007-05-02 08:00 | 2013-06-14 17:00 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | -
2273 | 380007 | CT1 part of Stage 3 CCBS_CCNR | - | 3 | Rel-8 | C1 | 2007-05-02 08:00 | 2009-03-06 17:00 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | 24.642, 24.229, 24.173
2274 | 380008 | CT3 part of Stage 3 CCBS_CCNR | - | 3 | Rel-8 | C3 | 2007-05-02 08:00 | 2008-12-05 17:00 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#42 completed | 29.163
2275 | 521019 | (IETF) Stage 3 CCBS_CCNR [RFC 6910 (was draft-ietf-bliss-call-completion)] | - | 3 | Rel-8 | C1-IETF,C3-IETF | 2007-05-02 08:00 | 2013-06-14 17:00 | 100% | CP-080215 | - | Roland Jesske | - | CP#60 completed | RFC 6910 (was draft-ietf-bliss-call-completion)
2276 | 390058 | Flexible Alerting | FA | 2 | Rel-8 | S1,C1 | 2008-01-30 08:00 | 2009-03-06 17:00 | 100% | CP-080219 | - | Nortel | milanpa@nortel.com | CP#43 completed | -
2277 | 390059 | Stage 1 FA | - | 3 | Rel-8 | S1 | 2008-01-30 08:00 | 2008-06-05 17:00 | 100% | - | - | Telecom Italia | - | SP#40 completed | 22.173
2278 | 390015 | Stage 3 FA | - | 3 | Rel-8 | C1 | 2008-01-30 08:00 | 2009-03-06 17:00 | 100% | CP-080219 | - | Nortel | milanpa@nortel.com | CP#43 completed | 24.239, 24.173
2279 | 380009 | Communication Wait on IMS | CW_IMS | 2 | Rel-8 | C1,C3,IETF | 2007-06-22 08:00 | 2014-12-05 17:00 | 83% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | -
2280 | 380010 | CT1 part of Stage 3 CW-IMS | - | 3 | Rel-8 | C1 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | 24.615, 24.229, 24.173
2281 | 521020 | (IETF) Stage 3 CW-IMS (salud-alert-info-urns) | - | 3 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2014-12-05 17:00 | 75% | CP-080214 | - | Roland Jesske | Roland Jesske | Submitted to IESG for publication | draft-ietf-salud-alert-info-urns
2282 | 380011 | CT3 part of Stage 3 CW-IMS | - | 3 | Rel-8 | C3 | 2007-11-30 08:00 | 2008-12-04 17:00 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#42 completed | 29.163
2283 | 370103 | IMS Charging | - | 2 | Rel-8 | S5 | 2007-09-17 08:00 | 2009-03-12 17:00 | 100% | SP-070621 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#39 completed | 32.260, 32.298
2284 | 370003 | Add Interconnection Border Control Function (IBCF) to IMS Charging | - | 3 | Rel-8 | S5 | 2007-09-17 08:00 | 2008-03-12 17:00 | 100% | SP-070621 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#39 completed | 32.260, 32.298
2285 | 380042 | Advice of Charge (AoC) support in IMS Charging | - | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070739 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#43 completed | 32.240, 32.260, 32.296, 32.298, 32.299, new 32.280
2286 | 390035 | 3GPP2 Input to Common IMS | CIMS_3GPP2, IMS_Common | 1 | Rel-8 | S1,S2,S3,C1,C3,C4 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | TSG#42 completed | -
2287 | 390050 | Stage 1 CIMS_3GPP2 | - | 2 | Rel-8 | S1 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#40 completed | 22.228, 22.173, 22.101, 22.153
2288 | 390051 | Stage 2 CIMS_3GPP2 | - | 2 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#40 completed | 23.002, 23.141, 23.203, 23.167, 23.228
2289 | 390052 | Security CIMS_3GPP2 | - | 2 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#42 completed [issues addressed under UID_370078 (IMS-Sec)] | 33.141, 33.203, 33.210
2290 | 390113 | Stage 3 CIMS_3GPP2 | REDOC_3GPP2 | 2 | Rel-8 | C1,C3,C4 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | - | -
2291 | 390013 | Stage 3 CIMS_3GPP2 (CT1) | - | 3 | Rel-8 | C1 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 23.218, 24.141, 24.147, 24.173, 24.229, 24.238, 24.247, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.629, 24.930
2292 | 390026 | Stage 3 CIMS_3GPP2 (CT3) | - | 3 | Rel-8 | C3 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 29.163, 29.212, 29.213, 29.214
2293 | 390027 | Stage 3 CIMS_3GPP2 (CT4) | - | 3 | Rel-8 | C4 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 29.228, 29.229, 29.328, 29.329
2294 | 350005 | IMS Enhancements for support of Packet Cable access | PktCbl | 1 | Rel-8 | S2,S3,C1,C3,C4 | 2006-12-06 08:00 | 2008-05-30 17:00 | 100% | - | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#40 completed | -
2295 | 350008 | IMS Enhancements for Cable Client Types and Deployment Models | PktCbl-Deploy | 2 | Rel-8 | S2,C1 | 2007-02-05 08:00 | 2008-05-30 17:00 | 100% | SP-070105 | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#40 completed | -
2296 | 350009 | Architecture aspects of PktCbl-Deploy | - | 3 | Rel-8 | S2 | 2007-02-05 08:00 | 2007-12-06 17:00 | 100% | SP-070105 | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | SP#38 completed | 23.228
2297 | 350010 | CT1 aspects of PktCbl-Deploy | - | 3 | Rel-8 | C1 | 2007-03-26 08:00 | 2008-05-30 17:00 | 100% | CP-070122 | - | Cablelabs | D.Hancock@CableLabs.com | CP#40 completed | -
2298 | 350011 | IMS Inter-working aspects in Support of Cable Regulatory requirements | PktCbl-Intw | 2 | Rel-8 | S2,C1,C3 | 2007-02-05 08:00 | 2008-03-14 17:00 | 100% | SP-070107 | - | Cablelabs | B.McKibben@CableLabs.com | CP#39 completed | -
2299 | 350012 | Architecture aspects of PktCbl-Interwork | - | 3 | Rel-8 | S2 | 2007-02-05 08:00 | 2007-09-14 17:00 | 100% | SP-070107 | - | Cablelabs | B.McKibben@CableLabs.com | SP#37 completed | 23.228
2300 | 350013 | CT1,CT3 aspects of PktCbl-Interwork | - | 3 | Rel-8 | C1,C3 | 2007-03-26 08:00 | 2008-03-14 17:00 | 100% | CP-070575 | - | Cablelabs | D.Hancock@CableLabs.com | CP#39 completed | 24.229
2301 | 340008 | IMS Enhancements for Security Requirements in Support of Cable Deployments | PktCbl-Sec | 2 | Rel-8 | S3,C1,C3,C4 | 2006-12-06 08:00 | 2008-05-30 17:00 | 100% | SP-060933 | - | Cablelabs | s.dotson@cablelabs.com | CP#40 completed | -
2302 | 350033 | SA3 aspects of PktCbl-Sec | - | 3 | Rel-8 | S3 | 2006-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-060933 | - | Cablelabs | s.dotson@cablelabs.com | SP#39 completed | 33.203, 33.210, 33.220
2303 | 350006 | CT1 aspects of PktCbl-Sec | - | 3 | Rel-8 | C1 | 2007-03-26 08:00 | 2008-05-30 17:00 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#40 completed | 24.229
2304 | 380029 | CT3 aspects of PktCbl-Sec | - | 3 | Rel-8 | C3 | 2007-03-26 08:00 | 2007-11-30 17:00 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#38 completed | 29.163
2305 | 350007 | CT4 aspects of PktCbl-Sec | - | 3 | Rel-8 | C4 | 2007-03-26 08:00 | 2008-03-14 17:00 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#39 completed | 29.228, 29.229, 23.008
2306 | 360012 | IMS System enhancements for corporate network access | IMS_Corp | 1 | Rel-8 | S2,S1,C1,C4,IETF | 2007-06-22 08:00 | 2014-12-05 17:00 | 89% | SP-080095 | - | Orange | Delphin Barankanira | CP#47 completed | -
2307 | 390049 | SA1 aspects of IMS_Corp | - | 2 | Rel-8 | S1 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080095 | - | Telecom Italia | - | SP#40 completed | -
2308 | 360014 | SA2 aspects of IMS_Corp | - | 2 | Rel-8 | S2 | 2007-06-22 08:00 | 2008-09-18 17:00 | 100% | SP-080095 | - | Orange | Delphin Barankanira | no Stage 2 impacts | 23.228
2309 | 390022 | CT1 aspects of IMS_Corp | - | 2 | Rel-8 | C1 | 2008-03-07 08:00 | 2010-03-19 17:00 | 100% | CP-080220 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | 24.229, 24.503
2310 | 531002 | (IETF) CT1 aspects of IMS_Corp (vanelburg-dispatch-private-network-ind) | - | 2 | Rel-8 | C1-IETF | 2011-06-29 13:00 | 2014-12-05 17:00 | 75% | CP-080220 | - | Keith Drage | Keith Drage (drage@alcatel-lucent.com) | in RFC Ed-queue | draft-vanelburg-dispatch-private-network-ind
2311 | 390023 | CT4 aspects of IMS_Corp | - | 2 | Rel-8 | C4 | 2008-02-26 16:36 | 2008-12-05 17:00 | 100% | CP-080220 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#42 completed | 29.228, 29.229, 23.003, 23.008, 29.433
2312 | 380069 | Maintenance of TISPAN documentation | MAINTISP | 1 | Rel-8 | S2,C1,C3,C4,IETF | 2007-07-02 08:00 | 2014-06-13 17:00 | 100% | - | - | - | - | SP#40 completed | -
2313 | 380005 | Maintenance of TISPAN R2 | MAINT_R2 | 2 | Rel-8 | C1,C3,C4 | 2007-11-09 08:00 | 2008-03-07 17:00 | 100% | CP-080229 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#39 completed | 24.406, 24.407, 24.410, 24.411, 24.423, 24.430, 24.447, 24.451, 24.454, 24.503, 24.505, 24.508, 24.516, 24.528, 24.529, 29.412, 29.421, 29.433, 29.458, 29.527, 29.624
2314 | 521021 | Deleted - (IETF) Maintenance of TISPAN R2 (avasarala-dispatch-comm-div-notification) | MAINT_R2_IETF | 2 | Rel-8 | C1-IETF | 2007-11-09 08:00 | 2014-06-13 17:00 | 100% | CP-080229 | - | Andrew Allen | - | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification
2315 | 380043 | Documentation of TISPAN NGN R1 and R2 in 3GPP SA2 | IMS_Comm_Doc | 2 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-06-05 17:00 | 100% | SP-070823 | - | Nokia Siemens Networks | jozsef.varga@nsn.com | SP#40 completed | 23.228, 23.204, 23.167
2316 | 380044 | Maintenance of TISPAN release 2 common IMS | IMS_Comm_Mtce8 | 2 | Rel-8 | S2 | 2007-07-02 08:00 | 2007-12-06 17:00 | 100% | SP-070916 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | SP#38 completed | 23.506, 23.507,23.517, 23.521
2317 | 390056 | IMS Service Continuity | IMS-Cont | 1 | Rel-8 | S2,S1,C1 | 2008-03-12 08:00 | 2009-05-29 17:00 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | CP#44 completed | -
2318 | 390072 | Stage 1 IMS Service Continuity | - | 2 | Rel-8 | S1 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | SP#40 completed | -
2319 | 390057 | Stage 2 IMS Service Continuity | - | 2 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | SP#40 completed | 23.237, 23.292
2320 | 400011 | Stage 3 IMS Service Continuity | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-05-29 17:00 | 100% | CP-080491 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#44 completed | 24.237, 24.229, 24.216
2321 | 370078 | Security Enhancements for IMS | IMS-Sec | 1 | Rel-8 | S3,C1,C4 | 2006-09-19 14:36 | 2009-03-06 17:00 | 100% | SP-070496 | - | Ericsson | Bengt.Sahlin@ericsson.com | CP#43 completed | -
2322 | 360017 | Stage 2 for IMS-Sec | - | 2 | Rel-8 | S3 | 2007-03-01 08:00 | 2008-12-11 17:00 | 100% | SP-070496 | - | Ericsson | Bengt.Sahlin@ericsson.com | SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards | 33.203, 33.141, 33.803
2323 | 390054 | CT1 part of Stage 3 for IMS-Sec | - | 2 | Rel-8 | C1 | 2006-09-19 14:36 | 2008-12-05 17:00 | 100% | - | - | Ericsson | - | CP#42 completed | -
2324 | 390154 | CT4 part of Stage 3 for IMS-Sec | - | 2 | Rel-8 | C4 | 2007-06-07 08:00 | 2009-03-06 17:00 | 100% | - | - | Ericsson | - | CP#43 completed | -
2325 | 380012 | CT1 part of Network Attachment Subsystem (NASS) Bundled Authentication | NBA | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2009-03-06 17:00 | 100% | CP-070781 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 24.229
2326 | 380013 | CT4 part of Network Attachment Subsystem (NASS) Bundled Authentication | NBA-CT4 | 2 | Rel-8 | C4 | 2007-11-14 08:00 | 2008-05-30 17:00 | 100% | CP-070781 | - | Alcatel-Lucent | - | CP#40 completed | 29.229, 29.228, 23.008
2327 | 34046 | IMS initiated and controlled PSS and MBMS User Service | IMS_PSS_MBMS_US | 1 | Rel-8 | S4,S3,IETF | 2008-03-12 08:00 | 2011-09-21 17:00 | 100% | SP-080201 | - | FT, Ericsson | olle.franceschi@ericsson.com | SP#39 WID approved | -
2328 | 34146 | SA4, SA3 part of IMS initiated and controlled PSS and MBMS User Service | - | 2 | Rel-8 | S4,S3 | 2008-03-12 08:00 | 2008-03-12 08:00 | 100% | SP-080201 | - | FT, Ericsson | olle.franceschi@ericsson.com | SP#43 completed | 26.234, 26.346, 33.246, New 26.237
2329 | 521022 | (IETF) IMS initiated and controlled PSS and MBMS User Service (RFC 6080) | - | 2 | Rel-8 | S4-IETF | 2008-03-12 08:00 | 2011-09-21 17:00 | 100% | SP-080201 | - | Ericsson | - | SP#53/IETF#81 completed | RFC 6080 (was draft-ietf-sipping-config-framework)
2330 | 713024 | Multimedia interworking between IMS and CS networks | MIW-IMS | 1 | Rel-8 | C3,C4 | 2005-09-23 08:00 | 2008-12-05 17:00 | 100% | CP-070729 | - | Vodafone | nico.gabriele@vodafone.com | CP#42 completed | -
2331 | 7013 | Stage 1 and 2 defined in earlier Releases | - | 2 | Rel-8 | S2 | 2005-09-23 08:00 | 2005-11-30 17:00 | 100% | - | - | Vodafone | nico.gabriele@vodafone.com | SP#31 Moved from FS section Feb 2006 | -
2332 | 7014 | Stage 3 of MW-IMS | MIW-IMS-St3 | 2 | Rel-8 | C3 | 2005-09-23 08:00 | 2007-11-30 17:00 | 100% | CP-070096 | - | Vodafone | nico.gabriele@vodafone.com | Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021 | 29.863, 29.163
2333 | 380021 | Stage 3 for MW-IMS, MONA extension | - | 2 | Rel-8 | C3 | 2007-11-05 08:00 | 2008-12-05 17:00 | 100% | CP-070729 | - | Vodafone | Christer.Holmberg@ericsson.com | CP#42 completed | 29.863, 29.163
2334 | 380022 | Mn interface (MGCF – IM MGW) | - | 2 | Rel-8 | C4 | 2007-11-21 08:00 | 2008-12-05 17:00 | 100% | CP-070729 | - | Vodafone | Christer.Holmberg@ericsson.com | CP#42 completed | 29.332
2335 | 360029 | IMS Stage 3 IETF Protocol Alignment - phase 2 | IMSProtoc2 | 1 | Rel-8 | C1,IETF | 2007-06-22 08:00 | 2014-12-05 17:00 | 90% | CP-080794 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | -
2336 | 360129 | CT1 aspects of IMS Stage 3 IETF Protocol Alignment - phase 2 | - | 2 | Rel-8 | C1 | 2007-06-22 08:00 | 2009-03-06 17:00 | 100% | CP-080794 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 23.218, 24.229, 24.930
2337 | 521023 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-bakker-sipping-3gpp-ims-xml-body-handling) | - | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2012-12-07 17:00 | 100% | CP-080794 | - | Andrew Allen | - | CP#58 completed. ietf-draft discontinued. Documented within 3GPP | draft-bakker-sipping-3gpp-ims-xml-body-handling
2338 | 521024 | (IETF) IMS Stage 3 IETF Protocol Alignment (RFC 6544) | - | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2012-06-15 17:00 | 100% | CP-080794 | - | Keith Drage | - | CP#56 completed | RFC 6544 (was draft-ietf-mmusic-ice-tcp)
2339 | 521025 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-ietf-salud-alert-info-urns) | - | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2014-12-05 17:00 | 75% | CP-080794 | - | Roland Jesske | Roland Jesske | Submitted to IESG for publication | draft-ietf-salud-alert-info-urns
2340 | 380014 | Interworking between User-to-User Signalling (UUS) and SIP | UUSIW | 1 | Rel-8 | C1,C3,IETF | 2007-11-30 08:00 | 2014-12-05 17:00 | 85% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#43 completed | -
2341 | 380015 | CT1 part of Stage 3 MGCF UUSIW | - | 2 | Rel-8 | C1 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#42 completed | 24.279, 24.229
2342 | 521026 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui) | - | 2 | Rel-8 | C1-IETF,C3-IETF | 2007-11-30 08:00 | 2014-12-05 17:00 | 90% | CP-070782 | - | Roland Jesske | Roland Jesske | Submitted to IESG for publication | draft-ietf-cuss-sip-uui
2343 | 551001 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn) | - | 2 | Rel-8 | C1-IETF,C3-IETF | 2011-03-17 13:00 | 2014-12-05 17:00 | 75% | CP-070782 | - | Keith Drage | Keith Drage (drage@alcatel-lucent.com) | Submitted to IESG for publication | draft-ietf-cuss-sip-uui-isdn
2344 | 380016 | CT3 part of Stage 3 MGCF UUSIW | - | 2 | Rel-8 | C3 | 2007-11-30 08:00 | 2009-03-12 17:00 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#43 completed | 29.163
2345 | 380018 | Support of Overlap signalling | Overlap | 1 | Rel-8 | C3,C1,C4 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | -
2346 | 380019 | Stage 3 Overlap (CT1) | - | 2 | Rel-8 | C1 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | 24.229
2347 | 380020 | Stage 3 Overlap (CT3) | - | 2 | Rel-8 | C3 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | 29.163
2348 | 380120 | Stage 3 Overlap (CT4) | - | 2 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#42 completed | 29.228, 29.229
2349 | 380035 | AS/MRFC Stage 2 and 3 | MRFC_TS | 1 | Rel-8 | C1,IETF | 2007-11-14 08:00 | 2012-06-15 17:00 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | Triggered by Study UID_7048 (MRFC) | -
2350 | 380135 | AS/MRFC Stage 2 | - | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2008-12-05 17:00 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | CP#42 completed | 23.218
2351 | 380235 | AS/MRFC Stage 3 | - | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2008-12-05 17:00 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | CP#42 completed | 24.229, 24.147, 24.247
2352 | 521027 | (IETF) AS/MRFC Stage 2 and 3 (RFC 6505) | - | 2 | Rel-8 | C1-IETF | 2007-11-14 08:00 | 2012-06-15 17:00 | 100% | CP-070784 | - | Keith Drage | - | CP#56 completed | RFC 6505 (was draft-ietf-mediactrl-mixer-control-package)
2353 | 400012 | IMS Restoration Procedures | IMS_RP | 1 | Rel-8 | C4,C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 | -
2354 | 400026 | IMS Restoration Procedures (CT4) | - | 2 | Rel-8 | C4 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed | 23.380, 29.228, 29.229, 29.230, 23.008
2355 | 400027 | IMS Restoration Procedures (CT1) | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed | 24.229
2356 | 410003 | IMS Application Server Service Data Descriptions for AS interoperability | IMS_ASIO | 1 | Rel-8 | C4 | 2008-09-12 17:00 | 2009-03-06 17:00 | 100% | CP-080451 | - | Alcatel-Lucent | nhberry@alcatel-lucent.com | CP#43 completed. Triggered by UID_360030 (FS_IMS_ASIO) | 29.328, 29.329, 29.364
2357 | 340030 | I-WLAN Network Selection Principle (NSP) | IWLANNSP | 1 | Rel-8 | S1,C1,C6 | 2007-06-14 17:00 | 2009-03-06 17:00 | 100% | SP-060932 | - | Telefónica O2 | chris.friel@O2.com | CP#43 completed | - | WLAN
2358 | 390024 | Stage 1 for I-WLAN NSP | - | 2 | Rel-8 | S1 | 2007-06-14 17:00 | 2007-06-14 17:00 | 100% | SP-060932 | - | Telefónica O2 | chris.friel@O2.com | SP#36 completed | 22.234 | WLAN
2359 | 390025 | CT1 part of Stage 3 for I-WLAN NSP | - | 2 | Rel-8 | C1 | 2008-03-07 08:00 | 2009-03-06 17:00 | 100% | CP-080217 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | CP#43 completed | 24.234 | WLAN
2360 | 390125 | CT6 part of Stage 3 for I-WLAN NSP | - | 2 | Rel-8 | C6 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | CP-080217 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | CP#42 completed | 31.102, 31.111 | WLAN
2361 | 370049 | Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 1 | Rel-8 | S2,C1 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | SP-070701 | - | Orange | xiaobao.chen@orange-ftgroup.com | CP#43 completed | - | WLAN
2362 | 380045 | Stage 2 for Mobility between 3GPP-WLAN Interworking and 3GPP Systems | - | 2 | Rel-8 | S2 | 2007-09-14 08:00 | 2008-06-05 17:00 | 100% | SP-070701 | - | Orange | xiaobao.chen@orange-ftgroup.com | SP#40 completed | new 23.327 | WLAN
2363 | 400013 | CT1 aspects of Mobility between 3GPP-WLAN Interworking and 3GPP Systems | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080320 | - | Orange | reina.nader@orange-ftgroup.com | CP#43 completed | 24.303, new 24.327 | WLAN
2364 | 460006 | Conformance Test Aspects – Mobility between 3GPP WLAN Interworking and 3GPP Systems | IWLAN_Mob_UEConTest | 1 | Rel-8 | R5 | 2009-12-04 08:00 | 2010-09-17 17:00 | 100% | RP-091349 | RP-100740 | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | RP#49 completed. Testing for Rel-8 UID_400013 CT1 aspects of mobility between 3GPP WLAN Interworking and 3GPP Systems (24.327) | 34.108, 34.123-1, 34.123-2, 34.123-3 | WLAN
2365 | 7042 | Enhancements for Voice Group Call Service (VGCS) Applications (EVA) | EVA | 1 | Rel-8 | S1,C1,C4,G2 | 2006-03-15 08:00 | 2009-09-18 17:00 | 100% | SP-070904 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | CP#45 completed | -
2366 | 320021 | SA1 aspects of EVA | - | 2 | Rel-8 | S1 | 2006-03-15 08:00 | 2006-12-06 17:00 | 100% | SP-070904 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#38 completed | 42.068
2367 | 370019 | VGCS/VBS and GPRS Interactions | - | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-21 17:00 | 100% | SP-070653 | - | Huawei | Ling Liu | SP#39 completed | 42.068, 42.069
2368 | 320019 | CT1 aspects of EVA | - | 2 | Rel-8 | C1 | 2006-06-02 08:00 | 2009-09-18 17:00 | 100% | CP-060260 | - | Nortel | milanpa@nortel.com | CP#45 completed | 43.068, 44.068
2369 | 320020 | CT4 aspects of EVA | - | 2 | Rel-8 | C4 | 2006-06-02 08:00 | 2007-11-30 17:00 | 100% | CP-060260 | - | Nortel | - | CP#38 completed | 29.002
2370 | 52148 | GERAN2 aspects of EVA | - | 2 | Rel-8 | G2 | 2006-06-30 08:00 | 2008-02-22 17:00 | 100% | GP-071855 | - | Nortel | frank.billenkamp@nortel.com | GP#37 completed | 44.018, 48.008
2371 | 31081 | Personal Network Management | PNM | 1 | Rel-8 | S1,C1,S3 | 2005-07-11 08:00 | 2009-03-06 17:00 | 100% | SP-080327 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed | -
2372 | 7012 | Stage 1 for PNM | - | 2 | Rel-8 | S1 | 2005-07-11 08:00 | 2006-07-31 17:00 | 100% | SP-080327 | - | Vodafone | armin.toepfer@vodafone.com | SP#31 completed | 22.259
2373 | 350050 | Stage 2 for PNM | - | 2 | Rel-8 | C1 | 2007-03-26 08:00 | 2008-12-05 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#42 completed | 23.259
2374 | 350041 | Stage 3 for PNM | - | 2 | Rel-8 | C1,C4 | 2007-03-26 08:00 | 2009-03-06 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#43 completed | -
2375 | 350001 | CT1 aspects of Stage 3 PNM | - | 3 | Rel-8 | C1 | 2007-03-26 08:00 | 2009-03-06 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#43 completed | 24.259, 24.229
2376 | 350002 | Deleted - CT4 aspects of Stage 3 PNM | - | 3 | Rel-8 | C4 | 2007-03-26 08:00 | 2008-12-05 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#42 no impact on CT4 specs | -
2377 | 340010 | Key establishment between a UICC hosting device and a remote device | - | 2 | Rel-8 | S3 | 2006-12-06 08:00 | 2007-10-30 17:00 | 100% | SP-060839 | - | Ericsson | Vesa.Lehtovirta@ericsson.com | SP#37 completed | 33.259
2378 | 350049 | Deleted - Actual Requirements of PNM | - | 2 | Rel-8 | C1 | 2007-03-26 08:00 | 2007-03-26 08:00 | 100% | - | - | Ericsson | - | SP#37 stopped | -
2379 | 330005 | eCall Data Transfer | EData | 1 | Rel-8 | S1,C1 | 2006-09-28 08:00 | 2009-03-06 17:00 | 100% | SP-060678 | - | Airbiquity | rrobinson@airbiquity.com | SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2) | - | Public Safety (I-A)
2380 | 370081 | eData Requirements | - | 2 | Rel-8 | S1 | 2006-09-28 08:00 | 2008-03-12 17:00 | 100% | SP-060678 | - | Airbiquity | rrobinson@airbiquity.com | SP#39 completed | 22.101, 22.105 | Public Safety (I-A)
2381 | 400014 | Transfer of data during an emergency call | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080316 | - | T-Mobile | Dieter Jacobsohn | CP#43 completed | 24.008 | Public Safety (I-A)
2382 | 34042 | eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution | eCall_Phase2 | 1 | Rel-8 | S4 | 2007-12-06 08:00 | 2009-09-24 17:00 | 100% | SP-070756 | - | Airbiquity | lhong@airbiquity.com & rrobinson@airbiquity.com | SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData) | 26.267, 26.268, 26.269, 26.967, 26.969 | Public Safety (I-A)
2383 | 450001 | eCall Conformance Testing | eCall_MSTest | 1 | Rel-8 | G3new | 2009-09-04 08:00 | 2010-09-03 17:00 | 100% | GP-091098 | - | Ericsson, Qualcomm | Vikrant Jain (vikrantj@qualcomm.com) | GP#47 completed. GP#43 WID approved. Testing for Rel-8 eCall_Phase2 (UID_34042) and EData (UID_330005) | 51.010-1, 51.010-2 | Public Safety (I-A)
2384 | 450023 | Conformance Test Aspects – non-modem procedures of eCall sessions in UTRA | UMTS_eCall_UEConTest | 1 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | RP-090952 | RP-100489 | Ericsson, Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#48 completed. Testing for Rel-8 eCall_Phase2 (UID_34042) and Edata (UID_330005) | 34.108, 34.123-1, 34.123-2, 34.123-3 | Public Safety (I-A)
2385 | 380060 | IP Interconnection of Services | IPinterc | 1 | Rel-8 | S1,S2,S5,C3 | 2006-08-16 08:00 | 2009-03-06 17:00 | 100% | SP-080565 | - | Telefónica O2 | chris.friel@O2.com | SP#43 completed | -
2386 | 380061 | Stage 1 for IPinterc | - | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-080565 | - | Telefónica O2 | chris.friel@O2.com | SP#39 completed. | 22.101, 22.228
2387 | 7005 | System enhancements for interconnection interfaces between two IMSs | IMS_NNI | 2 | Rel-8 | S2,S5,C3 | 2006-08-16 08:00 | 2009-03-06 17:00 | 100% | SP-080554 | - | Telecom Italia | Mario Madella (mario.madella@telecomitalia.it) | CP#43 completed | -
2388 | 360024 | Stage 2 for IMS_NNI | - | 3 | Rel-8 | S2 | 2007-06-22 08:00 | 2007-12-06 17:00 | 100% | SP-080554 | - | Telecom Italia | Mario Madella (mario.madella@telecomitalia.it) | SP#38 completed | 23.002, 23.228
2389 | 360011 | IMS inter-operator service interconnection interface | FBI2-IOPSI | 3 | Rel-8 | C3 | 2007-06-01 08:00 | 2009-03-06 17:00 | 100% | CP-080578 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | CP#43 completed | 29.865, 29.165
2390 | 330011 | Charging harmonization for NGN between 3GPP and ATIS-TMOC | FBI2-TISP2-CH | 3 | Rel-8 | S5 | 2006-09-28 08:00 | 2006-12-07 17:00 | 100% | SP-060545 | - | Amdocs | yishai.brown@amdocs.com | SP#34 completed | 32.297
2391 | 7007 | Deleted - Protocol impact of FBI for TISPAN R2 | FBI2-TISP2-c1 | 3 | Rel-8 | C1 | 2006-08-16 08:00 | 2007-03-15 17:00 | 100% | - | - | Ericsson | - | SP#38 stopped | -
2392 | 7006 | Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8 | FBI2-TISP2-s2 | 3 | Rel-8 | S2 | 2007-11-30 17:00 | 2007-11-30 17:00 | 100% | - | - | Nokia Siemens Networks | - | SP#36 stopped | -
2393 | 360025 | Support of (G)MSC-S – (G)MSC-S Nc Interface based on the SIP-I protocol | SIP_Nc | 1 | Rel-8 | C4,C3 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#43 completed. Stage 1 in Feature UID_380060 (IPinterc). CP#40 updated WID CP-070517=>CP-080282 | -
2394 | 410002 | Stage 1 for SIP_Nc (covered by Feature IPinterc) | - | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-070871 | - | Telefónica O2 | chris.friel@O2.com | 22/07/08 Created. Stage 1 for SIP_Nc (covered by SA1 Feature UID_380060 Ipinterc) | 22.101, 22.228
2395 | 360026 | SIP-I based circuit-switched core network; Stage 2 | SIP_Nc-St2 | 2 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#42 completed | 23.231, 23.153, 23.205
2396 | 360027 | Application of SIP-I Protocols to Circuit Switched (CS) core network architecture; Stage 3 | SIP_Nc-St3 | 2 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#42 completed | 29.231, 29.232, 29.332
2397 | 360028 | Interworking between the 3GPP CS domain with SIP-I as signalling protocol and other networks | - | 2 | Rel-8 | C3 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | CP-080282 | - | Nokia Siemens Networks | Thomas.Belling@nsn.com | CP#43 completed. CP#42 target 12/08=>03/09 | 29.235, 23.172, 23.202, 29.007, 29.163, 29.414
2398 | 370051 | Earthquake and Tsunami Warning System | ETWS | 1 | Rel-8 | S1,S2,C1,C4,G2 | 2007-09-10 08:00 | 2009-05-15 17:00 | 100% | SP-070815 | - | NTT DoCoMo | kitaharar@nttdocomo.co.jp | SP#43 Larger scope Feature UID_380057 (PWS) moved to Rel-9 | - | Public Safety (I-A)
2399 | 370052 | Stage 1 for ETWS | - | 2 | Rel-8 | S1 | 2007-09-10 08:00 | 2008-03-12 17:00 | 100% | SP-070815 | - | NTT DoCoMo | kitaharar@nttdocomo.co.jp | SP#39 completed | 22.168 | Public Safety (I-A)
2400 | 380056 | SA2 aspects of ETWS | - | 2 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-09-18 17:00 | 100% | SP-070815 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#41 completed | 23.828, 23.401 | Public Safety (I-A)
2401 | 400015 | CT1 aspects of ETWS | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080951 | - | NTT DoCoMo | yamashitahi@s1.nttdocomo.co.jp | CP#42 completed | 23.041 | Public Safety (I-A)
2402 | 410021 | CT4 aspects of ETWS | - | 2 | Rel-8 | C4 | 2008-09-26 13:00 | 2008-12-05 17:00 | 100% | CP-080951 | - | NTT DoCoMo | yamashitahi@s1.nttdocomo.co.jp | CP#42 completed | 29.168 | Public Safety (I-A)
2403 | 430045 | ETWS primary notification message definition in GERAN | - | 2 | Rel-8 | G2 | 2009-03-12 08:00 | 2009-05-15 17:00 | 100% | SP-090154 | - | Ericsson | claes-goran.persson@ericsson.com | SP#44 completed with CT1 help (GERAN2 LS_in SP-090154) | 44.018, 44.060 | Public Safety (I-A)
2404 | 440011 | Conformance Test Aspects – UMTS Earthquake and Tsunami Warning System (ETWS) FDD | ETWS_UMTS_UEConTestFDD | 1 | Rel-8 | R5 | 2009-05-29 08:00 | 2010-03-12 17:00 | 100% | RP-090467 | RP-100068 | NTT DoCoMo | Makoto Ito (itohm@nttdocomo.co.jp) | RP#47 completed. Testing for Rel-8 ETWS UID_370051 | 34.108, 34.123-1, 34.123-2 | Public Safety (I-A)
2405 | 380059 | In Case of Emergency numbers storage and easy access on UICC | ICE | 1 | Rel-8 | S1,C6 | 2007-03-13 08:00 | 2009-03-06 17:00 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed (ICE Graphics not included in Rel-8) | -
2406 | 380159 | Stage 1 for ICE | - | 2 | Rel-8 | S1 | 2007-03-13 08:00 | 2008-03-12 17:00 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | SP#39 Stage 1 completed | 22.030, 22.101
2407 | 380259 | CT6 aspects of ICE | - | 2 | Rel-8 | C6 | 2007-03-13 08:00 | 2009-03-06 17:00 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed (ICE Graphics not in Rel-8 / not explicitly in SA1 WID either) | 31.102
2408 | 330006 | Local Charging Zone Requirements | LCZR | 1 | Rel-8 | S1 | 2006-09-28 08:00 | 2008-03-12 17:00 | 100% | SP-060482 | - | China Mobile | liuhongyfw@chinamobile.com | SP#39 Stage 1 completed | 22.115
2409 | 340029 | Customized Alerting Tone (CAT) service | CAT | 1 | Rel-8 | S1,C1,C3,C4 | 2006-12-06 08:00 | 2009-09-18 17:00 | 100% | SP-070122 | - | China Mobile | fenglingjuan@chinamobile.com | CP#45 completed | -
2410 | 370028 | Stage 1 for CAT | - | 2 | Rel-8 | S1 | 2006-12-06 08:00 | 2007-09-20 17:00 | 100% | SP-070122 | - | China Mobile | fenglingjuan@chinamobile.com | - | 22.182
2411 | 370029 | TISPAN requirements for customized multimedia information services | TISCMI | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-10 17:00 | 100% | SP-070880 | - | China Mobile | fenglingjuan@chinamobile.com | SP#38 completed | 22.182
2412 | 390014 | IMS CAT Supplementary Service | CAT-SS | 2 | Rel-8 | C1,C3 | 2008-03-12 08:00 | 2009-09-18 17:00 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | - | -
2413 | 390114 | IMS CAT SS | - | 3 | Rel-8 | C1 | 2008-04-21 08:00 | 2008-12-04 17:00 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | CP#42 completed | 24.182
2414 | 390071 | CAT solution for voice and video call in CS domain | - | 3 | Rel-8 | C3 | 2008-03-12 08:00 | 2009-09-18 17:00 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | CP#45 completed. Triggered by Study UID_360031 (TR 29.882) | 29.163
2415 | 410010 | CAT Service in 3GPP CS domain | CAT-3G_CS | 2 | Rel-8 | C4,C1 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | - | 23.205, 23.231, 29.002
2416 | 410110 | CT4 part of CAT Service in 3GPP CS domain | - | 3 | Rel-8 | C4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | CP#43 completed. Triggered by Study UID_360031 (TR 29.882) | 23.205, 23.231, 29.002
2417 | 410015 | CT1 part of CAT Service in 3GPP CS domain | - | 3 | Rel-8 | C1 | 2008-09-12 08:00 | 2008-12-05 17:00 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | CP#42 completed. Triggered by Study UID_360031 (TR 29.882) | 24.008, 23.014
2418 | 340031 | Service-Level Interworking for Messaging Services | MESSIW | 1 | Rel-8 | S1,S2,C3,C1 | 2007-03-26 17:00 | 2009-03-06 17:00 | 100% | SP-070816 | - | Huawei | ling.liu@huawei.com; duanxiaoqin@huawei.com | CP#43 completed | -
2419 | 350047 | Stage 1 for MESSIW | - | 2 | Rel-8 | S1 | 2007-03-26 17:00 | 2007-03-26 17:00 | 100% | SP-070816 | - | Huawei | ling.liu@huawei.com | SP#35 completed | 22.105, 22.340
2420 | 350048 | Stage 2 for MESSIW | - | 2 | Rel-8 | S2 | 2007-04-26 08:00 | 2008-03-07 17:00 | 100% | SP-070816 | - | Huawei | patrice.hede@huawei.com | SP#39 completed | 23.811, 23.204
2421 | 400016 | CT3 part of Stage 3 for MESSIW | - | 2 | Rel-8 | C3 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080773 | - | Huawei | xupeili@huawei.com | CP#43 completed | 29.311
2422 | 400017 | CT1 part of Stage 3 for MESSIW | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080773 | - | Huawei | xupeili@huawei.com | CP#42 completed | 24.229
2423 | 340044 | Multimedia Priority Service | PRIOR | 1 | Rel-8 | S1,C1,C3,C4 | 2006-06-08 08:00 | 2009-09-18 17:00 | 100% | SP-060780 | - | Telcordia | jgarraha@telcordia.com | CP#45 completed | - | Public Safety (I-A)
2424 | 320023 | Service Requirements for PRIOR | PRIOR-EMR | 2 | Rel-8 | S1 | 2006-06-08 08:00 | 2007-12-06 17:00 | 100% | SP-060780 | - | Telcordia | jgarraha@telcordia.com | SP#38 completed | New 22.153 | Public Safety (I-A)
2425 | 340012 | CT1 part of Stage 3 for PRIOR | - | 2 | Rel-8 | C1 | 2006-12-01 08:00 | 2009-09-18 17:00 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#45 completed | 24.229 | Public Safety (I-A)
2426 | 370021 | CT4 part of Stage 3 for PRIOR | - | 2 | Rel-8 | C4 | 2007-09-21 08:00 | 2009-03-06 17:00 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 23.008, 29.228, 29.229 | Public Safety (I-A)
2427 | 370020 | Deleted - Stage 3 for PRIOR | - | 2 | Rel-8 | C3 | 2007-09-21 08:00 | 2009-05-29 17:00 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2) | 29.212, 29.213, 29.214, 29.163 | Public Safety (I-A)
2428 | 360010 | Open Service Access (OSA) Rel-8 | OSA8 | 1 | Rel-8 | S1,C5 | 2007-08-23 08:00 | 2008-05-30 17:00 | 100% | SP-070692 | - | Orange | Song Dong | SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A). | -
2429 | 360004 | OSA Stage 1 - Service Requirements | - | 2 | Rel-8 | S1 | 2007-08-23 08:00 | 2008-03-12 17:00 | 100% | - | - | Orange, AePONA | Song Dong | SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A). | 22.127
2430 | 370034 | OSA Stage 1 - NGN Service Requirement | OSA8-IMS | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-14 17:00 | 100% | SP-070692 | - | Orange | Song Dong | SP#40 maintenance & new OSA work moved to OMA | 22.127
2431 | 360005 | Rel-8 OSA Stage 2/3 enhancements | - | 2 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | SP#40 maintenance & new OSA work moved to OMA | 23.198, 29.198, 29.199
2432 | 370012 | Deleted - Ensure Parlay-X composable with identity management frameworks, in particular Liberty Alliance | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | CP#40: Work moved to OMA | existing 29.199-xy
2433 | 370013 | Parlay-X Content Management web service (store/manage meta-data) | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-21
2434 | 370014 | Parlay-X Policy web service | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-22
2435 | 370015 | Parlay-X Terminal status web service | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-08
2436 | 370016 | Deleted - Identify communication format used by a particular application | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | CP#40: Work moved to OMA | existing 29.199-xy
2437 | 380047 | Deleted - Security on User Profile Management - reuse GUP API (22.127 CR 0084 S1-071794) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2438 | 380048 | Deleted - Privacy on Subscriber Identity (Liberty Alliance, OASIS) (22.127 CR 0085 S1-071835) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2439 | 380049 | Deleted - Topology Hiding (22.127 CR 0086 S1-071838) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2440 | 380050 | Deleted - Subscriber event notification (22.127 CR 0087 S1-071836) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2441 | 380051 | Deleted - Event notification (22.127 CR 0088 S1-071762) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2442 | 380052 | Deleted - Access policy (22.127 CR 0089 S1-071763) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2443 | 380053 | Deleted - API usage accounting (22.127 CR 0090 S1-071792) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework
2444 | 380054 | Presence alignment with OMA and IETF (22.127 CR 0092 S1-071764) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-14/13
2445 | 380055 | Deleted - Service identification (22.127 CR 0095 S1-071837) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | existing 29.199-xy
2446 | 390067 | Framework Enterprise Operator (Service Subscription function) | - | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-03
2447 | 390068 | Mobility Emergency Location | - | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-06
2448 | 390069 | Connectivity Manager SCF | - | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-10
2449 | 390070 | PAM Presence Agent | - | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-14
2450 | 360032 | Paging Permission with Access Control (PPACR) | PPACR | 1 | Rel-8 | S1,C1 | 2007-06-12 08:00 | 2008-12-05 17:00 | 100% | SP-070501 | - | NTT DoCoMo | Morita Takashi | CP#42 completed. Triggered by Study UID_330016 (PPAC). | -
2451 | 370084 | Stage 1 for PPACR | PPACR-S1 | 2 | Rel-8 | S1 | 2007-06-12 08:00 | 2007-09-14 17:00 | 100% | SP-070501 | - | NTT DoCoMo | Morita Takashi | SP#37 completed | 22.011
2452 | 380017 | Stage 3 for PPACR (CT1) | PPACR-CT1 | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2008-12-05 17:00 | 100% | CP-070783 | - | NTT DoCoMo | - | CP#42 completed | 24.008, 23.122, 24.301
2453 | 490017 | Conformance Test Aspects – Paging Permission with Access Control (PPAC) | PPAC_UEConTest | 1 | Rel-8 | R5 | 2010-09-17 08:00 | 2010-12-10 17:00 | 100% | RP-100806 | RP-101074 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#50 completed | UTRA 34.108, 34.123-1, 34.123-2, 34.123-3
2454 | 380063 | Charging for multi-phases services | CHRGMPH | 1 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-080053 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | SP#39 Stage 1 completed | 22.115
2455 | 380070 | Stage 1 for CHRGMPH | CHRGMPH-s1 | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-080053 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | SP#39 completed | 22.115
2456 | 380065 | Home NodeB / eNodeB | HomeNB | 1 | Rel-8 | S1,C1,C4 | 2007-12-06 08:00 | 2009-03-06 17:00 | 100% | SP-070952 | - | Vodafone | John Watson | CP#43 completed | - | HNB
2457 | 380066 | Stage 1 for Home NodeB / eNodeB | HomeNB-S1 | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-070952 | - | Vodafone | John Watson | SP#39 completed | 22.011, 22.115 | HNB
2458 | 420019 | Support of Closed Subscriber Group (CSG) | - | 2 | Rel-8 | C4 | 2008-12-05 08:00 | 2009-03-06 17:00 | 100% | - | - | CT#42 | Hannu Hietalahti | CP#43 completed. SP#42 SP-080874 22.011CR0141 confirmed Requirement to support roaming subscribers with CSG home network subscription but did NOT confirmed requirement for home network independent support of roamers in CSG | 29.002, 29.272, 23.008, 23.003 | HNB
2459 | 410012 | CSG and Idle Mode Mobility for LTE Home eNodeB | HomeNB-LTE | 2 | Rel-8 | C1 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080498 | - | Huawei | zhang.peng@huawei.com | CP#43 completed | 23.122, new (24.285, 24.301, 24.801) | HNB
2460 | 410013 | CSG and Idle Mode Mobility for 3G Home NodeB | HomeNB-3G | 2 | Rel-8 | C1 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080792 | - | Qualcomm | Osok Song | CP#43 completed | 23.122, 24.008, new 24.285 | HNB
2461 | 390033 | UTRA HNB | HNB | 1 | Rel-8 | RP,S5 | 2008-03-07 08:00 | 2009-06-04 17:00 | 100% | - | - | - | - | SP#44 completed | - | HNB
2462 | 400053 | Support of UTRA HNB | HNB-supp | 2 | Rel-8 | R2 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | RP-080752 | RP-090040 | Huawei | Yang Xudong (yangxudong@huawei.com) | RP#43 completed | 25.304, 25.306, 25.331, new 25.367 | HNB
2463 | 400054 | UTRAN Architecture for 3G HNB | HNB-arch | 2 | Rel-8 | R3 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | RP-080487 | RP-090042 | Alcatel-Lucent | Martin Warner (mw15@alcatel-lucent.com) | RP#42 completed | 25.401, 25.410, 25.412, 25.413, 25.414, 25.415, new (25.467, 25.468, 25.469) | HNB
2464 | 390034 | FDD Home NodeB RF requirements | HNB-RF | 2 | Rel-8 | R4 | 2008-03-07 08:00 | 2009-03-06 17:00 | 100% | RP-080971 | RP-090041 | Motorola | Ying Cai (yingcai@motorola.com) | RP#43 completed | 25.104, 25.141, new 25.967 | HNB
2465 | 420037 | 3G Home NodeB OAM&P Type 1 Management Interface | HNB-3G_OAM | 2 | Rel-8 | S5 | 2008-12-11 08:00 | 2009-06-04 17:00 | 100% | SP-080708 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#44 completed. Complements work in BroadBand Forum | new (32.581, 32.582, 32.583, 32.584) | HNB
2466 | 430022 | UTRA HNB – UE Conformance Testing | HNB-UEConTest | 1 | Rel-8 | R5 | 2009-03-06 08:00 | 2010-06-04 17:00 | 100% | - | - | - | - | RP#48 FDD completed. Testing for Feature UID_390033 UTRA HNB | - | HNB
2467 | 430023 | Conformance Test Aspects – UTRA HNB (FDD) | HNB-UEConTestFDD | 2 | Rel-8 | R5 | 2009-03-06 08:00 | 2010-06-04 17:00 | 100% | RP-090023 | RP-100482 | Huawei | Trica Li (trica_li@huawei.com) | RP#48 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 | HNB
2468 | 350015 | Lawful Interception in the 3GPP Rel-8 | LI8 | 1 | Rel-8 | S3 | 2007-03-12 08:00 | 2009-03-12 17:00 | 100% | SP-070238 | - | BMWI, Verizon | berthold.wilhelm@bnetza.de, ron_ryan@verizon.net | SP#43 completed | 33.106, 33.107, 33.108
2469 | 390046 | Generic Bootstrapping Architecture Push Function | GBAPush | 1 | Rel-8 | S3,C1,C4 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | SP-080133 | - | Ericsson | Rolf Blom | CP#43 completed | -
2470 | 390146 | SA3 part of GBAPush (33.223) | - | 2 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-05 17:00 | 100% | SP-080133 | - | Ericsson | Rolf Blom | SP#42 completed 33.223 as Rel-8. TS 33.224 moved to Rel-9 under new UID_420039 | 33.223
2471 | 390246 | CT1 part of GBAPush | - | 2 | Rel-8 | C1 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | CP-090112 | - | Ericsson | Rolf Blom | CP#43 completed | 24.109
2472 | 390346 | CT4 part of GBAPush | - | 2 | Rel-8 | C4 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | CP-090112 | - | Ericsson | Rolf Blom | CP#43 completed | 29.109
2473 | 34045 | Requirements and Test methods for Wideband Terminals | RETEM_WB_T | 1 | Rel-8 | S4 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080004 | - | FT, Ericsson | stephane.ragot@orange-ftgroup.com, wanqing.shi@sonyericsson.com | SP#42 completed. SP#39 WID approved. | 26.131, 26.132
2474 | 34043 | Extending PSS and MBMS User Services for optimized Mobile TV | PSS_MBMS_OMTV | 1 | Rel-8 | S4 | 2007-12-06 08:00 | 2008-12-11 17:00 | 100% | SP-070757 | - | Ericsson | thorsten.lohmar@ericsson.com | SP#42 completed. SP#38 WID approved. | 26.234, 26.346, 26.946
2475 | 400028 | Encoding formats, transport formats and media description signalling for interworking, QoE, and other enhancements to MTSI-MHI | MTSI_eMHI | 1 | Rel-8 | S4,C3,C4 | 2007-12-06 08:00 | 2009-03-12 17:00 | 100% | SP-080443 | - | Ericsson, Qualcomm | olle.franceschi@ericsson.com, nleung@qualcomm.com | TSG#43 completed | -
2476 | 34041 | MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size | MTSI_eMHI-DRASIS | 2 | Rel-8 | S4 | 2007-12-06 08:00 | 2009-03-12 17:00 | 100% | SP-080246 | - | Qualcomm, Samsung | nleung@qualcomm.com & kyunghun.jung@samsung.com | SP#43 completed | 26.114
2477 | 400018 | CT3 part of Enhancement of interworking between MTSI and CS networks | - | 2 | Rel-8 | C3 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#43 completed | 29.163
2478 | 400020 | CT4 part of Enhancement of interworking between MTSI and CS networks | - | 2 | Rel-8 | C4 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#43 completed | 29.332
2479 | 400019 | Deleted - CT1 part of Enhancement of interworking between MTSI and CS networks | - | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-12 17:00 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#42 stopped (No CT1-impact). WID updated CP-080422=>CP-080774 | -
2480 | 340063 | Rel-8 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM8 | 1 | Rel-8 | S5,C1,C4,IETF | 2007-06-07 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | OAM8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI | TR 30.818
2481 | 340064 | Rel-8 Network Infrastructure Management | OAM8-NIM | 2 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | - | -
2482 | 35051 | Telecom Management Methodology | - | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-03-12 17:00 | 100% | SP-070296 | - | Ericsson | thomas.tovinger@ericsson.com | SP#43 completed | 32.155, 32.153
2483 | 35053 | Advanced Alarming on Itf-N | - | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-06-12 17:00 | 100% | SP-070492 | - | Nokia Siemens Networks | SUERBAUM, Clemens | SP#40 completed | 32.121, 32.122, 32.123
2484 | 35056 | CN CS Bearer Transport Network (BTN) relative NRM | - | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-06-12 17:00 | 100% | SP-070300 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#40 completed | 32.632, 32.633, 32.635
2485 | 390016 | Alignment with eTOM and M.3060 architectural concepts | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080068 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#42 completed | 32.101/2, 32-series
2486 | 400030 | IRP SOAP Solution Sets | - | 3 | Rel-8 | S5 | 2008-06-05 08:00 | 2009-03-12 17:00 | 100% | SP-090148 | - | Ericsson | edwin.tse@ericsson.com | SP#43 completed | 32.111-7, 32.617, 32.417, 32.367, 32.347, 32.111-1, 32.111-2, 32.111-3, 32.111-5, 32.307, 32.317, 32.341, 32.342, 32.343, 32.345, 32.361, 32.362, 32.363, 32.365, 32.411, 32.412, 32.413, 32.415, 32.611, 32.612, 32.613, 32.615, 32.625
2487 | 450052 | Create missing specifications for IRP XML definitions | - | 3 | Rel-8 | S5 | 2009-09-24 08:00 | 2009-12-04 17:00 | 100% | SP-090553 | - | ZTE | Shuqiang Huang (huangsq@zte.com.cn) | SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x) | new (32.125, 32.355, 32.505, 32.535), 32.150, 32.153, 32.335
2488 | 370002 | Deleted - End point modelling for reference point | - | 3 | Rel-8 | S5 | 2007-09-17 08:00 | 2008-12-11 17:00 | 100% | SP-070618 | - | Motorola | Yizhi Yao (yzyao@motorola.com) | SP#41 Work stopped. Contributions related to E-UTRAN/EPC to be submitted to UID_380036 E-UTRAN NRM IRP/ UID_380037 EPC NRM IRP | 32.152, 32.62/3/4x, 32.73x
2489 | 340065 | Rel-8 Performance Management | OAM8-PM | 2 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-03-12 17:00 | 100% | - | - | - | Li Jian (lijian@chinamobile.com) | - | -
2490 | 35061 | IP bearer network Performance measurement definitions | - | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-12-11 17:00 | 100% | SP-070301 | - | China Mobile | lilianyuan@chinamobile.com | SP#42 completed | 32.321, 32.322, 32.323, 32.325
2491 | 360001 | HSUPA performance measurements | - | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-12-11 17:00 | 100% | SP-070835 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#42 completed | 32.405
2492 | 360002 | Key Performance Indicators (KPIs) for UMTS and GSM | - | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-03-12 17:00 | 100% | SP-070299 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#43 completed | 32.410
2493 | 340066 | Rel-8 Trace Management | OAM8-Trace | 2 | Rel-8 | C1,C4,IETF | 2008-03-07 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | - | -
2494 | 11067 | CT1 part of Service Level Tracing in IMS | - | 3 | Rel-8 | C1 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 completed | 24.323, 24.229
2495 | 521028 | (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug) | - | 3 | Rel-8 | C1-IETF | 2008-03-07 08:00 | 2012-12-07 17:00 | 100% | CP-080315 | - | Peter Dawes | peter.dawes@vodafone.com | CP#58 Removed from Rel-8, Rel-9 and Rel-10 (Not completed internet-draft) | Rel-11 remains draft-dawes-dispatch-debug
2496 | 531003 | (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event) | - | 3 | Rel-8 | C1-IETF | 2008-03-07 08:00 | 2011-12-09 17:00 | 100% | CP-080315 | - | Peter Dawes | peter.dawes@vodafone.com | CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug | draft-dawes-sipping-debug-event
2497 | 400022 | CT4 part of Service Level Tracing in IMS | - | 3 | Rel-8 | C4 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 completed | 29.228, 29.229
2498 | 400021 | Deleted - CT3 part of Service Level Tracing in IMS | - | 3 | Rel-8 | C3 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 stopped (No CT3-impact) | -
2499 | 350016 | Rel-8 Charging Management small Enhancements | CH8 | 1 | Rel-8 | S5 | 2006-03-16 08:00 | 2008-12-11 17:00 | 100% | - | - | - | - | CH8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI | TR 30.818
2500 | 350038 | Online charging correlation | - | 2 | Rel-8 | S5 | 2006-03-16 08:00 | 2007-12-14 17:00 | 100% | SP-070077 | - | Orange | Chahine, Rony | SP#38 completed | 32.296
2501 | 360003 | SMS online charging | - | 2 | Rel-8 | S5 | 2007-06-07 08:00 | 2007-12-14 17:00 | 100% | SP-070293 | - | Vodafone | Gavin.Wong@vodafone.com | SP#38 completed | 32.240, 32.299, new 32.274
2502 | 410045 | Introduce Online Charging from SMS-SC into the SMS Charging Specifications | - | 2 | Rel-8 | S5 | 2008-09-18 08:00 | 2008-12-11 17:00 | 100% | SP-080463 | - | Acision | erik.gebler@acision.com | SP#42 completed. Linked to SA2 UID 32081 (Support of SMS over IP networks) and CT4 UID 340016 (Routeing of MT-SMS via the HPLMN). | 32.274, 32.299
2503 | 380046 | Deleted - WLAN Offline Charging | - | 2 | Rel-8 | S5 | 2008-01-07 08:00 | 2008-12-11 17:00 | 100% | SP-070750 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#42 stopped | 32.252, 32.298, 32.299
2504 | 380024 | Conferencing enhancements for Mp interface | eMp | 1 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | -
2505 | 380025 | Stage 2 for eMp | - | 2 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | 23.333
2506 | 380026 | Stage 3 for eMp | - | 2 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | 29.333
2507 | 320014 | Contact Manager for 3GPP UICC applications | eUPHBOOK | 1 | Rel-8 | C6 | 2006-06-22 08:00 | 2008-12-05 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#42 completed. CP#40: WID updated CP-070622=>CP-080382. aka Enhanced USIM phonebook | -
2508 | 320015 | Requirements for Contact Manager | eUPHBOOK-St1 | 2 | Rel-8 | C6 | 2006-06-22 08:00 | 2007-12-21 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#38 completed | 21.111
2509 | 350046 | External interface for eUPHBOOK | eUPHBOOK-Ext_Spec | 2 | Rel-8 | C6 | 2007-05-07 08:00 | 2008-03-07 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#39 completed | new 31.220
2510 | 370004 | Internal interface for eUPHBOOK | eUPHBOOK-Int_Spec | 2 | Rel-8 | C6 | 2007-05-07 08:00 | 2008-12-05 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#42 completed | new 31.221
2511 | 320016 | Deleted - Implementation of eUPHBOOK | eUPHBOOK-St23 | 2 | Rel-8 | C6 | 2007-06-21 17:00 | 2007-06-21 17:00 | 100% | CP-060355 | - | Giesecke & Devrient | Claus Dietze | SP#33 stopped | 31.102
2512 | 20068 | Rel-8 LTE – 3G Long Term Evolution - Evolved Packet System RAN part | LTE | 1 | Rel-8 | RP,S5 | 2006-09-25 08:00 | 2009-03-12 17:00 | 100% | RP-080747 | RP-080741 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#43 completed. Role model for SAE/LTE system wide project management by SA2 in SP-060166 | LTE 36.300, 36.938
2513 | 330018 | LTE – Physical Layer | LTE-Phys | 2 | Rel-8 | R1 | 2006-09-25 08:00 | 2008-03-07 17:00 | 100% | RP-080747 | RP-080741 | NTT DoCoMo | Sadayuki Abeta | RP#39 completed | 36.201, 36.211, 36.212, 36.213, 36.214, 25.215, 25.225
2514 | 330019 | LTE – Radio Interface Layer 2 and 3 Protocol Aspect | LTE-L23 | 2 | Rel-8 | R2 | 2006-09-25 08:00 | 2008-12-05 17:00 | 100% | RP-080747 | RP-080741 | Nokia Siemens Networks | benoist.sebire@nokia.com | RP#42 completed | 36.302, 36.304, 36.306, 36.314, 36.321, 36.322, 36.323, 36.331, 25.302, 25.304, 25.331
2515 | 330020 | LTE – eUTRAN Interfaces | LTE-interfaces | 2 | Rel-8 | R3 | 2006-09-25 08:00 | 2008-12-05 17:00 | 100% | RP-080747 | RP-080741 | Ericsson | Martin Israelsson | RP#42 completed | 36.401, 36.410, 36.411, 36.412, 36.413, 36.414, 36.420, 36.421, 36.422, 36.423, 36.424, 25.413
2516 | 330021 | LTE – Evolved UTRA and UTRAN RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing | LTE-RF | 2 | Rel-8 | R4 | 2006-09-25 08:00 | 2008-12-05 17:00 | 100% | RP-080747 | RP-080741 | Nokia Siemens Networks | Tuomo Saynajakangas | RP#42 completed. RP#47 abandoned draft 36.801, 36.803, 36.804 | 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.942, 25.123, 25.133
2517 | 370046 | LTE – FDD repeaters | LTE-Repeaters | 2 | Rel-8 | R4 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | RP-070749 | RP-090037 | Powerwave Technologies, Andrew Wireless | ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com | RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report) | 36.106, 36.143, 25.113
2518 | 390001 | E-UTRAN Data Definitions | E-UTRAN-OAM | 2 | Rel-8 | S5 | 2007-09-17 08:00 | 2009-03-12 17:00 | 100% | - | - | - | - | SP#43 completed | -
2519 | 370001 | Subscriber and Equipment Trace for E-UTRAN and EPC | - | 3 | Rel-8 | S5 | 2007-09-17 08:00 | 2009-03-12 17:00 | 100% | SP-070617 | - | Ericsson | robert.petersen@ericsson.com | SP#43 completed | 32.421, 2.422, 32.423, 2.441, 32.442, 32.443, 32.445
2520 | 380036 | E-UTRAN Network Resource Model (NRM) Integration Reference Point (IRP) | - | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070738 | - | Ericsson | ELMDAHL, Per | SP#43 completed | new (32.761, 32.762, 32.763, 32.765)
2521 | 390002 | Performance measurements for E-UTRAN | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2009-03-12 17:00 | 100% | SP-080062 | - | Motorola, Huawei | Yizhi Yao (yzyao@motorola.com) | SP#43 completed | new 32.425
2522 | 390003 | Key Performance Indicators (KPIs) for E-UTRAN | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2009-03-12 17:00 | 100% | SP-080063 | - | Ericsson | ulf.hubinette@ericsson.com | SP#43 completed | new (32.450, 32.451)
2523 | 390004 | Self-Organizing Networks (SON) | LTE_SON-OAM | 2 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080275 | - | Vodafone | GOMPAKIS, Panagiotis | SP#42 completed (WT UID_390007 moved to Rel-9) | - | SON
2524 | 390104 | SON Concepts and requirements | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080275 | - | Vodafone | GOMPAKIS, Panagiotis | SP#42 completed | new 32.500
2525 | 390005 | Self-Establishment of eNBs, including automated Software Management | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080849 | - | Nokia Siemens Networks | SUERBAUM, Clemens | SP#42 completed | new (32.501, 32.502, 32.503, 32.531, 32.532, 32.533)
2526 | 390006 | SON Automatic Neighbour Relations (ANR) List Management | - | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080066 | - | Ericsson | edwin.tse@ericsson.com | SP#42 completed | 32.761, 32.762, 32.763, 32.765, new 32.511
2527 | 25029 | Rel-8 LTE – Terminal Conformance Test Specification | LTE-UEConTest | 1 | Rel-8 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | Testing for Feature UID_20068 (LTE) | -
2528 | 25041 | 3G LTE – Terminal Protocol Conformance Test Specifications | LTE-UEConTest_SIG | 2 | Rel-8 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | RP-080647 | RP-091060 | NEC, Motorola | david.lecompte@nectech.fr, Jacob.John@motorola.com | RP#46 completed | 36.521-1, 36.521-2, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3
2529 | 25042 | LTE – Terminal Radio Transmission and Reception Conformance Test Specifications | LTE-UEConTest_RF | 2 | Rel-8 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | RP-080601 | RP-091059 | Agilent | andrea_leonardi@agilent.com | RP#46 completed. RP#50 TR 36.903 v100 for Approval | 36.521-1, 36.521-2, 36.521-3, new TR 36.903
2530 | 350040 | Rel-8 Improvements of the Radio Interface | RInImp8 | 1 | Rel-8 | RP | 2007-03-05 08:00 | 2009-03-06 17:00 | 100% | - | - | - | - | - | -
2531 | 350034 | UMTS 1500 MHz | RInImp8-UMTS1500 | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2007-09-14 17:00 | 100% | RP-070078 | RP-070526 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#37 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121
2532 | 350035 | UMTS 700 MHz FDD | RInImp8-UMTS700 | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-05-30 17:00 | 100% | RP-070127 | RP-080260 | Nokia | Tuomo Saynajakangas | RP#40 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121
2533 | 410018 | UMTS 1880 MHz TDD | RInImp9-UMTS1880TDD | 2 | Rel-8 | R4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | RP-080757 | RP-090044 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#43 completed | 25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.307
2534 | 380074 | UMTS 2300 MHz TDD LCR | RInImp8-UMTS2300TDD | 2 | Rel-8 | R4 | 2007-12-17 08:00 | 2008-09-12 17:00 | 100% | RP-071016 | RP-080517 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#41 completed. RP#47 abandoned draft 25.828 | 25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.306, 25.331, 34.122
2535 | 350037 | Further Improved Minimum Performance Requirements for HSDPA UE (FDD) - Two-Branch Interference Cancellation | RInImp8-2BIC | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-03-07 17:00 | 100% | RP-070254 | RP-080041 | AT&T | Marc Grant | RP#39 completed | 25.101
2536 | 370032 | CS Voice Service over HSPA | RInImp8-CsHspa | 2 | Rel-8 | R2 | 2007-07-19 08:00 | 2008-03-07 17:00 | 100% | RP-070765 | RP-080042 | Nokia Siemens Networks | woonhee.hwang@nsn.com | RP#39 completed | 25.323, 25.331, 25.322
2537 | 370033 | Performance requirements for 15 code reception with 16QAM/QPSK (FDD) | RInImp8-Hsdpa15codes | 2 | Rel-8 | R4 | 2007-06-11 15:00 | 2008-03-07 17:00 | 100% | RP-070745 | RP-080043 | Vodafone | tim.frost@vodafone.com | RP#39 completed | 25.101
2538 | 350036 | Deleted - UMTS 2300 MHz FDD/TDD | RInImp8-UMTS2300 | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-09-12 17:00 | 100% | RP-070128 | RP-080515 | AT&T | Marc Grant | RP#41 stopped | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121
2539 | 25125 | Rel-8 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-8 | R5 | 2007-06-01 08:00 | 2008-12-05 17:00 | 100% | - | - | - | - | 05/08: Linked to Feature UID_20028 (RInImp) | -
2540 | 25050 | Conformance Test Aspects – CS Voice Service over HSPA | RInImp8-CsHspa_UEConTest | 2 | Rel-8 | R5 | 2007-06-01 08:00 | 2008-09-12 17:00 | 100% | RP-080160 | RP-080542 | Huawei | baoyi@huawei.com | RP#41 completed | 34.108, 34.123-1, 34.123-2, 34.123-3
2541 | 400055 | Conformance Test Aspects – Performance requirements for 15 code reception with 16QAM/QPSK (FDD) | RInImp8-UEConTest_ Hsdpa15codes | 2 | Rel-8 | R5 | 2008-03-07 17:00 | 2008-12-05 17:00 | 100% | RP-080311 | RP-080818 | Ericsson | Mikael.Ziren@Ericsson.com | RP#42 completed | 34.121-1, 34.121-2
2542 | 370035 | Rel-8 RAN improvements | - | 1 | Rel-8 | RP | 2007-06-04 08:00 | 2009-05-29 17:00 | 100% | - | - | - | - | - | -
2543 | 360013 | Combination of 64QAM and MIMO for HSDPA (FDD) | RANimp-64QamMimoHsdpa | 2 | Rel-8 | R1 | 2007-06-04 08:00 | 2008-09-12 17:00 | 100% | RP-070500 | RP-080518 | Ericsson | Johan.Bergman@ericsson.com | RP#41 completed | 25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141
2544 | 370036 | Improved L2 for uplink | RANimp-UplinkL2dataRates | 2 | Rel-8 | R2 | 2007-09-14 08:00 | 2008-05-30 17:00 | 100% | RP-070717 | RP-080265 | Ericsson | Janne.Peisa@ericsson.com | RP#40 completed. Linked to UID_370037 Enhanced Uplink for CELL_FACH State in FDD | 25.319, 25.301, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, 25.427
2545 | 370037 | Enhanced Uplink for CELL_FACH State in FDD | RANimp-UplinkEnhState | 2 | Rel-8 | R2 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | RP-070677 | RP-080804 | Nokia Siemens Networks | markus.wimmer@nsn.com | RP#42 completed. Linked to UID_370036 Improved L2 for uplink | 25.309, 25.211, 25.214, 25.321, 25.331, 25.423, 25.433
2546 | 370038 | Enhanced UE Discontinuous Reception (DRX) for FDD | RANimp-DRX | 2 | Rel-8 | R2 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | RP-070679 | RP-080520 | Nokia | luis.barreto@nokia.com | RP#41 completed. Continuation of Rel-7 work item "Continuous connectivity for packet data users" UID_20046. | 25.306, 25.308, 25.321, 25.331, 25.423
2547 | 370039 | Enhancements for Serving Radio Network Subsystem (SRNS) Relocation Procedure | RANimp-SrnsReloc | 2 | Rel-8 | R3 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | RP-070759 | RP-080521 | Nokia Siemens Networks | masatoshi.nakamata@nsn.com | RP#41 completed. Linked to UID_370040 Enhancements for FDD HSPA Evolution | 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.214, 25.133
2548 | 370040 | Enhancements for FDD HSPA Evolution | RANimp-HSPAEvo | 2 | Rel-8 | R3,R2 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | RP-080830 | RP-080805 | Nokia Siemens Networks | masatoshi.nakamata@nsn.com | RP#42 completed. Triggered by Rel-7 Study on Scope of future FDD HSPA Evolution (UID_20065) TR 25.999 | 25.401, 25.413, 25.420, 25.423, 25.427, 25.433, 25.446, 25.301, 25.346
2549 | 380075 | 64QAM for 1.28 Mcps TDD HSDPA | RANimp-64Qam1.28TDD | 2 | Rel-8 | R1 | 2007-12-04 08:00 | 2008-12-05 17:00 | 100% | RP-070924 | RP-080806 | ZTE | zfmail@zte.com.cn | RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.102, 25.105, 25.123, 25.142, 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433
2550 | 380076 | Enhanced CELL_FACH state in 1.28 Mcps TDD | RANimp-EnhState1.28TDD | 2 | Rel-8 | R2 | 2007-12-04 08:00 | 2008-12-05 17:00 | 100% | RP-071038 | RP-080807 | ZTE | zhang.yincheng@zte.com.cn | RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.123, 25.221, 25.222, 25.224, 25.301, 25.302, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.401, 25.423, 25.425, 25.433, 25.435
2551 | 390028 | Continuous Connectivity for packet data users for 1.28 Mcps TDD | RANimp-LCRCPC | 2 | Rel-8 | R1 | 2008-03-07 08:00 | 2009-05-29 17:00 | 100% | RP-080085 | RP-090394 | TD Tech | chenying@td-tech.com | RP#44 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.929, 25.308, 25.319
2552 | 390029 | HSPA VoIP to WCDMA/GSM CS continuity | RANimp-HSPAVoIP | 2 | Rel-8 | R2 | 2008-03-07 08:00 | 2009-03-06 17:00 | 100% | RP-080749 | RP-090050 | Nokia | Simone.Provvedi@nokia.com | RP#43 completed | 25.331, 25.413
2553 | 390030 | HS-DSCH Serving Cell Change Enhancements | RANimp-HSDSCH | 2 | Rel-8 | R2 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | RP-080227 | RP-080811 | Ericsson | henrik.enbuske@ericsson.com | RP#42 completed | 25.101, 25.104, 25.133, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433
2554 | 400050 | MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | RANimp-MIMOLCR | 2 | Rel-8 | R1,R4 | 2008-01-24 11:12 | 2009-05-29 17:00 | 100% | RP-080485 | RP-090313 | CATT | wangke@datangmobile.cn | RP#43 completed | 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.102, 25.105, 25.142
2555 | 400052 | Dual-Cell HSDPA operation on adjacent carriers | RANimp-DCHSDPA | 2 | Rel-8 | R1,R4 | 2008-11-17 08:00 | 2009-05-29 17:00 | 100% | RP-080490 | RP-080814 | Ericsson | johan.bergman@ericsson.com | RP#42 completed. Triggered by UID_390032 Study on Dual-Cell HSDPA (withdrawn TR 25.825 v100). | 25.101, 25.104, 25.133, 25.141, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433
2556 | 25126 | Rel-8 RAN improvements - UE Conformance Testing | - | 1 | Rel-8 | R5 | 2008-05-30 08:00 | 2010-09-17 17:00 | 100% | - | - | - | - | Linked to Feature UID_20029 (RANimp) | -
2557 | 410020 | Conformance Test Aspects – Combination of 64QAM and MIMO for HSDPA (FDD) | RANimp-UEConTest_64QamMimoHsdpa | 2 | Rel-8 | R5 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | RP-080759 | RP-091058 | Ericsson | leif.mattisson@ericsson.com | RP#46 completed. Testing for UID_360013 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2
2558 | 400056 | Conformance Test Aspects – Improved L2 for uplink | RANimp-UEConTest_UplinkL2dataRates | 2 | Rel-8 | R5 | 2008-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-080606 | RP-090712 | Ericsson | leif.mattisson@ericsson.com | RP#45 completed. Testing for UID_370036 | 34.108, 34.123-1, 34.123-2, 34.123-3
2559 | 440010 | Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates | RANimp-UEConTest_ImprovedL2LCRTDD | 2 | Rel-8 | R5 | 2009-05-29 08:00 | 2010-09-17 17:00 | 100% | RP-090491 | RP-100737 | CATT | Xiaozhong Chen (chenxiaozhong@datangmobile.cn) | RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink | 34.108, 34.123-1, 34.123-2, 34.123-3
2560 | 400057 | Conformance Test Aspects – 64QAM for 1.28 Mcps TDD HSDPA | RANimp-UEConTest_64Qam1.28TDD | 2 | Rel-8 | R5 | 2008-05-30 08:00 | 2009-05-29 17:00 | 100% | RP-080334 | RP-090415 | ZTE | ma.zijiang@zte.com.cn | RP#44 completed. Testing for UID_380075 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
2561 | 420015 | Conformance Test Aspects – Dual-Cell HSDPA operation on adjacent carriers | RANimp-UEConTest_DCHSDPA | 2 | Rel-8 | R5 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | RP-080996 | RP-100479 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#48 completed. Testing for UID_400052 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2562 | 430024 | Conformance Test Aspects – Enhanced Uplink for CELL_FACH State in FDD | RANimp-UEConTest_EnhancedRACHCellFACHState | 2 | Rel-8 | R5 | 2009-03-06 08:00 | 2010-06-04 17:00 | 100% | RP-090152 | RP-100483 | Nokia | jarkko.hellsten@nokia.com | RP#48 completed. Testing for UID_370037 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2563 | 430028 | Conformance Test Aspects – Receiver Type3i | RANimp-UEConTest_ReceiverType3i | 2 | Rel-8 | R5 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090010 | RP-091066 | Qualcomm | Ashok Kumar Narayanaswamy (anarayan@qualcomm.com) | RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD | 34.108, 34.121-1, 34.121-2
2564 | 440009 | Conformance Test Aspects – Enhanced CELL_FACH State in LCR TDD | RANimp-UEConTest_EnhancedCellFACHStateLCRTDD | 2 | Rel-8 | R5 | 2009-05-30 08:00 | 2010-09-17 17:00 | 100% | RP-090490 | RP-100735 | CATT | Xiaozhong Chen (chenxiaozhong@datangmobile.cn) | RP#49 completed. Testing for UID_380076 | 34.108, 34.123-1, 34.123-2, 34.123-3
2565 | 450024 | Conformance Test Aspects – Continuous Connectivity for packet data users for 1.28 Mcps TDD | RANimp-UEConTest_CPCLCRTDD | 2 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-09-17 17:00 | 100% | RP-090751 | RP-100739 | ZTE | huang.he4@zte.com.cn | RP#49 completed. Testing for UID_390028 | 34.108, 34.123-1, 34.123-2, 34.123-3
2566 | 450025 | Conformance Test Aspects – MIMO for 1.28 Mcps TDD | RANimp-UEConTest_MIMOLCRTDD | 2 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | RP-100120 | RP-100660 | ZTE | huang.chun2@zte.com.cn | PR#48 completed. Testing for UID_400050 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
2567 | 450026 | Conformance Test Aspects – HS-DSCH Serving Cell Change Enhancements | HSDSCH_UEConTest | 2 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | RP-090756 | RP-100077 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#47 completed. Testing for UID_390030 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2568 | 360008 | 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast | MBSFN-DOB | 1 | Rel-8 | R1 | 2007-06-04 08:00 | 2008-12-05 17:00 | 100% | RP-081124 | RP-080218 | Ericsson | Lars.Lindbom@ericsson.com | RP#42 completed. WID updated RP-070493=>RP-081124 (changed WI title "MBSFN Downlink Optimized Broadcast (DOB) 3.84 Mcps TDD" => "3.84Mcps TDD MBSFN Integrated Mobile Broadcast"). | 25.102, 25.105, 25.123, 25.201, 25.221, 25.222, 25.223, 25.224, 25.304, 25.306, 25.331, 25.346, 25.402, 25.433
2569 | 440008 | Conformance Test Aspects – 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast | MBSFN_IMB_UEConTest | 1 | Rel-8 | R5 | 2009-05-30 08:00 | 2010-03-19 17:00 | 100% | RP-090583 | RP-100070 | IPwireless | Phil Young (pyoung@ipwireless.com) | RP#47 completed. Testing for Rel-8 MBSFN-DOB UID_360008 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
2570 | 50583 | GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 1 | Rel-8 | GP,G1,C1,G3new | 2006-09-08 08:00 | 2011-11-25 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed. GP#52 completed MS conformance testing | 44.018, 44.060, 45.002, 45.008, 45.010, 48.008, 48.018, 51.010
2571 | 51583 | G1 part of GERAN support for GERAN - 3G Long Term Evolution interworking | - | 2 | Rel-8 | G1 | 2006-09-08 08:00 | 2009-02-20 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed | 43.055, 43.129, 43.246, 45.002, 45.008, 45.010
2572 | 52583 | G2 part of GERAN support for GERAN - 3G Long Term Evolution interworking | - | 2 | Rel-8 | G2 | 2006-09-08 08:00 | 2009-02-20 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed | 44.018, 44.060, 48.008, 48.018
2573 | 53583 | CT1 part of GERAN support for GERAN - 3G Long Term Evolution interworking | - | 2 | Rel-8 | C1 | 2006-09-08 08:00 | 2009-02-20 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | - | 24.008
2574 | 54583 | Testing for GERAN support for GERAN - 3G Long Term Evolution interworking | - | 2 | Rel-8 | G3new | 2006-09-08 08:00 | 2011-11-25 17:00 | 100% | GP-061757 | - | Renesas Mobile | deepa.kamath@renesasmobile.com | GP#52 completed | 51.010
2575 | 55586 | U-TDOA Enhancement | GUTEN | 1 | Rel-8 | GP | 2007-05-18 08:00 | 2007-11-16 17:00 | 100% | GP-070865 | - | TruePosition | Terry Brooks (terri.brooks@trueposition.com) | GP#36 completed U-TDOA (Uplink Time Difference of Arrival) | 43.059, 45.008, 48.071
2576 | 50587 | GAN Enhancements | GANENH | 1 | Rel-8 | GP | 2007-05-15 15:24 | 2009-09-04 17:00 | 100% | GP-071484 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#37 completed. GP#43 completed Testing | -
2577 | 50588 | Update to GAN specifications | GANENH-SPEC | 2 | Rel-8 | GP | 2007-08-31 08:00 | 2008-02-22 17:00 | 100% | GP-071560 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#37 completed | 43.318, 44.318
2578 | 53089 | Update TS 51.010 Mobile Station (MS) Conformance Specification for GAN Enhancements | GANENH-MStest | 2 | Rel-8 | G3new | 2007-05-15 15:24 | 2009-09-04 17:00 | 100% | GP-071563 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#43 completed | 51.010
2579 | 50591 | AoIP (A-interface over IP) | AoIP | 1 | Rel-8 | GP,S4,C4,C1,C3 | 2000-01-03 08:00 | 2008-12-11 17:00 | 100% | GP-081361 | - | China Mobile, Ericsson | wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com | GP#40/TSG#42 completed . Triggered by TR 43.903 Study on A-interface over IP (AINTIP) UID_50589. | -
2580 | 400041 | GERAN aspects of AoIP | - | 2 | Rel-8 | GP | 2000-01-03 08:00 | 2008-11-21 17:00 | 100% | GP-081362 | - | China Mobile, Ericsson | wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com | GP#40 completed. GP#39 updated WID GP-080901=>GP-081362. | 48.001, 48.002, 48.008, 48.020, 49.008, 48.103
2581 | 400042 | Media Requirements for CS over IP based User Plane | AoIP-CSoIP | 2 | Rel-8 | S4 | 2007-12-05 08:00 | 2008-12-11 17:00 | 100% | SP-080444 | - | China Mobile, Ericsson | Karl.Hellwig@Ericsson.com | SP#42 completed | 26.102, 26.103, 26.202
2582 | 400024 | Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 2 | Rel-8 | C4,C1,C3 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | -
2583 | 400324 | CT4 part of Core Network Impacts for A-Interface User Plane over IP | - | 3 | Rel-8 | C4 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 23.205, 23.153, 23.231, 29.232
2584 | 400124 | CT1 part of Core Network Impacts for A-Interface User Plane over IP | - | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 23.009
2585 | 400224 | CT3 part of Core Network Impacts for A-Interface User Plane over IP | - | 3 | Rel-8 | C3 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 29.007
2586 | 51147 | New multicarrier BTS class | MCBTS | 1 | Rel-8 | G1 | 2007-08-31 08:00 | 2008-08-29 17:00 | 100% | GP-071542 | - | Alcatel-Lucent | thomas.bitzer@alcatel-lucent.de | GP#39 completed | 45.005, 45.050, 51.021
2587 | 38001 | Support for Additional Navigation Satellite Systems (ANSS) for LCS | ANSS | 1 | Rel-8 | S1,G2,R2 | 2008-05-16 08:00 | 2008-12-11 17:00 | 100% | GP-081784 | - | Qualcomm | Mungal Dhanda | GP#40 completed | -
2588 | 420038 | Stage 1 for ANSS for LCS | - | 2 | Rel-8 | S1 | 2008-12-11 08:00 | 2008-12-11 17:00 | 100% | - | - | - | - | SP#42 completed by 22.071 CR0077 | 22.071
2589 | 38101 | GERAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS | - | 2 | Rel-8 | G2 | 2008-05-16 08:00 | 2008-11-21 17:00 | 100% | GP-081784 | - | Qualcomm | Mungal Dhanda | GP#40 completed | 43.059, 44.031, 49.031, 44.071, 48.031, 51.010
2590 | 400051 | RAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS | RANimp-ANSS | 2 | Rel-8 | R2 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | RP-080346 | RP-080813 | Qualcomm | Etienne Chaponniere (echaponn@qualcomm.com) | RP#42 WI closed at 95%. Considers Rel-9 performance requirements | 25.305, 25.306, 25.331, 25.413, 25.423, 25.433, 25.453
2591 | 51149 | Conformance testing for the Latency Reductions feature | CTLATRED | 1 | Rel-8 | G1,G3new | 2008-02-22 08:00 | 2010-03-05 17:00 | 100% | GP-080367 | - | Ericsson | mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com | GP#45 completed | -
2592 | 53090 | MS conformance testing for the Latency Reductions feature | CTLATRED-MStest | 2 | Rel-8 | G3new | 2008-02-22 08:00 | 2010-03-05 17:00 | 100% | GP-080368 | - | Ericsson | hakan.e.grunditz@ericsson.com | GP#45 completed | 51.010
2593 | 51150 | BTS conformance testing for the Latency Reductions feature | CTLATRED-BTStest | 2 | Rel-8 | G1 | 2008-02-22 08:00 | 2009-02-20 17:00 | 100% | GP-080369 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#41 completed | 51.021
2594 | 53091 | MS conformance testing of changes introduced by WI "Support of Packet-switched Handover for GERAN A/Gb mode" | PSHCT-MStest | 1 | Rel-8 | G3new | 2008-02-22 08:00 | 2008-11-21 17:00 | 100% | GP-080411 | - | Rohde & Schwarz | Franz.Segerer@ROHDE-SCHWARZ.COM | GP#40 completed | 51.010
2595 | 320001 | (Small) Technical Enhancements and Improvements for Rel-8 | TEI8 | 1 | Rel-8 | SP,CP,RP,GP | 2007-01-01 08:00 | 2008-12-11 17:00 | 100% | - | - | - | - | SP#42 completed | -
2596 | 521029 | (IETF) (Small) Technical Enhancements and Improvements for Rel-8 | TEI8_IETF | 1 | Rel-8 | C1-IETF | 2007-01-01 08:00 | 2012-09-07 17:00 | 100% | - | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#57 completed | RFC 6714 (was draft-ietf-simple-msrp-cema)
2597 | 400025 | Test - (Small) Technical Enhancements and Improvements for Rel-8 | TEI8_Test | 1 | Rel-8 | R5,G3new | 2007-03-07 11:12 | 2010-12-24 17:00 | 100% | - | - | - | - | - | -
2598 | 31067 | Deleted - All-IP Network | AIPN | 1 | Rel-8 | S1 | 2004-06-28 08:00 | 2006-03-15 17:00 | 100% | SP-050181 | - | NTT DoCoMo | c.masyu@nttdocomo.co.jp | SP#38 stopped. 25/07/08 Moved UID_31059 Study on All-IP Network (FS_AIPN/was AIPFS) to Rel-7 out of the stopped Rel-8 Feature UID_31067 Deleted - All-IP Network (AIPN) | -
2599 | 31068 | Deleted - Stage 1 | - | 2 | Rel-8 | S1 | 2004-06-28 08:00 | 2006-03-15 17:00 | 100% | SP-050181 | - | NTT DoCoMo | c.masyu@nttdocomo.co.jp | 22.258 withdrawn, superseded by 22.278 (UID 320022). SP#38 stopped | 22.258
2600 | 340032 | Deleted - was Rel-7 - LCS for 3GPP Interworking WLAN | LCS4_IWLAN | 1 | Rel-8 | S2 | 2007-09-28 17:00 | 2007-09-28 17:00 | 100% | SP-060818 | - | LG Electronics | dhshim@lge.com | SP#35 stopped | 23.234, 23.271, 23.167 | WLAN
2601 | 330010 | Deleted - never approved- FBI Phase 2 | FBI2 | 1 | Rel-8 | S2 | 2007-09-28 17:00 | 2007-09-28 17:00 | 100% | - | - | Nokia Siemens Networks | - | SP#38 stopped | -
2602 | 330007 | Deleted -Enhancements to BS30 Bearer service for Videotelephony | BS30 | 1 | Rel-8 | S1 | 2007-03-15 17:00 | 2007-03-15 17:00 | 100% | SP-060484 | - | 3 | andre.jarvis@three.co.uk | SP#38 stopped (no support) | 22.002, 22.004, 22.101, 22.105, 24.008
2603 | 370055 | Deleted - IMS Enhancements Rel-8 | IMS8 | 1 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-14 17:00 | 100% | - | - | Telecom Italia | - | SP#38 stopped | -
2604 | 400023 | Deleted - Contact Manager Conformance Test specifications | eUPHBOOK-Test | 1 | Rel-8 | C6 | 2008-06-02 08:00 | 2010-03-19 17:00 | 100% | CP-080430 | - | Comprion, Gemalto | Udo Willenbrink, Jacques Seif | CP#47 work stopped/abandoned | -
2605 | 400123 | Deleted - Contact Manager for 3GPP UICC applications test specifications | - | 2 | Rel-8 | C6 | 2008-06-02 08:00 | 2010-03-19 17:00 | 100% | CP-080430 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#47 work stopped/abandoned | 31.320 (external interface for communication with the ME)
2606 | 400223 | Deleted - Contact Manager API for Java™ Card test specification | - | 2 | Rel-8 | C6 | 2008-06-02 08:00 | 2010-03-19 17:00 | 100% | CP-080430 | - | Gemalto | jacques.seif@gemalto.com | CP#47 work stopped/abandoned | 31.321 (internal interface (API))
2607 | 53092 | Deleted - MS conformance testing of Support of Conversational Services in A/Gb mode via the PS domain | SCSAGBCT-MStest | 1 | Rel-8 | G3new | 2008-02-25 08:00 | 2009-09-04 17:00 | 100% | GP-080330 | - | Nokia | arsi.heino@nokia.com | GP#43 work stopped/abandoned (completion 0%) | 51.010
2608 | 0 | Release 8 Studies | - | 1 | Rel-8 | CP,GP,RP,SP | 2005-10-07 08:00 | 2010-11-12 17:00 | 100% | - | - | - | - | - | -
2609 | 7026 | Study on Customised Alerting Tone (CAT) Requirements | FS_CAT | 1 | Rel-8 | S1 | 2005-10-07 08:00 | 2006-09-14 17:00 | 100% | SP-060474 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | Spin-off Rel-8 Feature Customized Alerting Tone (CAT) Service UID_340029 | 22.982
2610 | 7027 | Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) | FS_M2M | 1 | Rel-8 | S1 | 2005-11-04 08:00 | 2007-03-08 17:00 | 100% | SP-050527 | - | Siemens | Juergen Merkel | SP#35 completed. Spin-off SA3 Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M (UID_370053). SP#40 Spin-off new Feature UID_410030 (NIMTC) | 22.868 | MTC, M2M
2611 | 31089 | Study on Network Composition | FS_NetComp | 1 | Rel-8 | S1 | 2005-12-07 08:00 | 2007-12-12 17:00 | 100% | SP-060478 | - | Nokia Siemens Networks | joerg.swetina@neclab.eu | SP#38 completed | 22.980
2612 | 320024 | Study on Requirements of IMS Multimedia Conferencing | FS_IMSconf | 1 | Rel-8 | S1 | 2006-06-08 08:00 | 2007-09-12 17:00 | 100% | SP-060479 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | SP#37 completed. Spin-off New Feature UID_370026 Value-Added Services for Short Message Service (VAS4SMS) | 22.948
2613 | 320025 | Study on support of a Public Warning System | FS_PWS | 1 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-14 17:00 | 100% | SP-080054 | - | T-Mobile | mark.younge@t-mobile.com | SP#39 completed. Spin-off Rel-9 Feature UID_380057 (PWS) | 22.968 | Public Safety (I-A)
2614 | 330016 | Study on Paging Permission with Access Control | FS_PPAC | 1 | Rel-8 | S1 | 2006-09-28 08:00 | 2007-09-20 17:00 | 100% | SP-060785 | - | NTT DoCoMo | Katsuhiro NOGUCHI (noguchi@nttdocomo.co.jp) | SP#37 completed. Spin-off new Feature UID_370084 (PPACR) | 22.908
2615 | 340033 | Study on Non-3GPP access Network Selection Principles (NSP) | FS_N3GtoNSP | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2008-06-05 17:00 | 100% | SP-080318 | - | Telefónica O2 | chris.friel@O2.com | SP#38 completed. Spin-off New Feature UID_380062 (N3GTONSP). SP#40 WID updated SP-060930=>SP-080318. TR re-approved with new # 22.812=>22.912 | 22.912
2616 | 340034 | Study on Value Added Services for Short Message Service | FS_VAS4SMS | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2007-12-07 17:00 | 100% | SP-060786 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | SP#38 completed. Spin-off New Feature UID_370026 (VAS4SM) | 22.942
2617 | 340035 | Study on Service continuity between mobile and WLAN networks | FS_SMLSWLAN | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2007-12-06 17:00 | 100% | SP-060936 | - | NEC | joerg.swetina@neclab.eu | SP#38 completed | 22.937 | WLAN
2618 | 370086 | Study on Services Alignment and Migration | FS_ServAl | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#39 completed. Spin-off Rel-9 Feature UID_330017 Services Alignment and Migration (ServAl) | 22.983
2619 | 32085 | Study on 3GPP System Architecture Evolution | FS_SAE | 1 | Rel-8 | S2,S3 | 2004-12-03 08:00 | 2009-03-12 17:00 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#43 completed | -
2620 | 32086 | Stage 2 Interim conclusion for RAN Work to start | - | 2 | Rel-8 | S2 | 2004-12-03 08:00 | 2008-09-18 17:00 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.882
2621 | 32087 | Stage 2 study on 3GPP architectural development | - | 2 | Rel-8 | S2 | 2006-01-09 08:00 | 2008-09-18 17:00 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.882
2622 | 7024 | Security study for Inter-access mobility between non-3GPP and 3GPP system | - | 2 | Rel-8 | S3 | 2007-09-03 08:00 | 2009-03-12 17:00 | 100% | SP-070163 | - | Nokia | dajiang.zhang@nokia.com | SP#43 completed | 33.821, 33.822
2623 | 320028 | Study on Stage 2 aspects of IMS Service Brokering | FS_ISB_ST2 | 1 | Rel-8 | S2 | 2006-06-19 08:00 | 2008-09-18 17:00 | 100% | SP-060443 | - | Telcordia | raquel@research.telcordia.com | SP#41 completed. No spin-off activity proposed. [Note: IMS Service Brokering enhancements UID_31088 moved back from R8 to R7 to give a home to 22228CR0036_(Rel-7)_S1-051232. Hence, Rel-7 ISB has Stage 1 only (and is misaligned with Rel-7 Stages 2/3.] | 23.810
2624 | 7049 | Study on IMS utilizing multicast bearer services | FS_MLTICAST-IMS | 1 | Rel-8 | S2 | 2006-03-22 08:00 | 2007-12-06 17:00 | 100% | SP-060148 | - | Nokia Siemens Networks | - | SP#38 completed | 23.847
2625 | 350051 | Study on Multimedia Session Continuity | FS_MMSC | 1 | Rel-8 | S2 | 2007-04-26 08:00 | 2008-06-05 17:00 | 100% | SP-070818 | - | LG Electronics | - | SP#40 completed | 23.893
2626 | 380034 | Study on centralized IMS service control | FS_ICS | 1 | Rel-8 | S2,S1 | 2006-10-23 08:00 | 2008-03-12 17:00 | 100% | SP-070494 | - | Ericsson | peter.bleckert@ericsson.com | SP#39 completed | -
2627 | 370087 | Study on centralized IMS services requirements | FS_ICS-S1 | 2 | Rel-8 | S1 | 2007-03-05 08:00 | 2008-03-12 17:00 | 100% | SP-070494 | - | NEC | joerg.swetina@neclab.eu | SP#39 completed | 22.892
2628 | 330012 | Study on centralized IMS services control | FS_IMS_CSC | 2 | Rel-8 | S2 | 2006-10-23 08:00 | 2008-03-12 17:00 | 100% | SP-070494 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#39 completed | 23.892
2629 | 380078 | Study on Architecture of IMS based Customized Alerting Tone (CAT) | FS_CAT-St2 | 1 | Rel-8 | S2 | 2007-12-04 08:00 | 2008-09-18 17:00 | 100% | SP-070905 | - | China Mobile | WANG, Jing (wangjing@chinamobilecom) | SP#41 completed as Rel-8 | 23.872
2630 | 380085 | Study on Home (e)NodeB Security | FS_HNB_Sec | 1 | Rel-8 | S3 | 2007-12-20 08:00 | 2009-03-12 17:00 | 100% | SP-070783 | - | Huawei | yangyanmei@huawei.com | SP#43 completed. Linked to RAN4 Study on 3G Home NodeB/eNodeB (UID_350039) and to SA5 Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB (UID_360007) | 33.820 | HNB
2631 | 360015 | Study on Transferring of emergency call data – in-band modem solution | eCALLIBMS | 1 | Rel-8 | S4 | 2006-12-07 08:00 | 2007-12-12 17:00 | 100% | SP-060935 | - | Airbiquity | lhong@airbiquity.com | SP#38 completed. Spin-off WID UID_34042 (eCall_Phase2) | 26.967 | Public Safety (I-A)
2632 | 35065 | Study on Element Operations Systems Function (EOSF) definition | OAM7-NIM- EOSF | 1 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-06-12 17:00 | 100% | SP-070307 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#40 completed. WID updated SP-050608=>SP-070307 | 32.819
2633 | 35074 | Study on SA5 MTOSI XML Harmonization | OAM8-NIM-XML | 1 | Rel-8 | S5 | 2006-05-10 08:00 | 2007-09-12 17:00 | 100% | SP-070305 | - | Nortel | jduguay@nortel.com | SP#37 completed. WID updated SP-050295=>SP-070305 | 32.818
2634 | 320006 | Study on Common Profile Storage (CPS) Framework of User Data for network services and management | OAM7-CPS | 1 | Rel-8 | S5 | 2006-07-03 08:00 | 2007-06-07 17:00 | 100% | SP-060263 | - | T-Mobile | istvan.aba@t-mobile.at | SP#36 completed. Spin-off New Feature UID_400034 User Data Convergence (UDC) | 32.808
2635 | 340036 | Study on Management for LTE and SAE | FS_OAM_LTE_SAE | 1 | Rel-8 | S5 | 2006-12-07 08:00 | 2008-12-11 17:00 | 100% | SP-060753 | - | Ericsson | robert.petersen@ericsson.com | SP#42 completed | 32.816
2636 | 350004 | Study on Charging Aspects of 3GPP System Evolution | FS_SAEcharg | 1 | Rel-8 | S5 | 2007-04-02 08:00 | 2007-12-06 17:00 | 100% | SP-070174 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#38 completed | 32.820
2637 | 7048 | Study on AS-MRFC media server control protocol | MRFC | 1 | Rel-8 | C1 | 2006-03-22 08:00 | 2008-06-13 17:00 | 100% | CP-060180 | - | Hewlett-Packard | mark.syrett@hp.com | CP#40 completed. Spin-off New Feature UID_380035 (MRFC_TS) | 24.880
2638 | 350018 | Study on IMS Restoration Procedures | FS_IMS_RP | 1 | Rel-8 | C4 | 2007-03-26 08:00 | 2008-05-30 17:00 | 100% | CP-070031 | - | Ericsson | german.blanco@ericsson.com | CP#40 completed. Spin-off WID UID_400012 (IMS_RP) | 23.820
2639 | 360030 | Study on IMS Application Server Service Data Descriptions for AS interoperability | FS_IMS_ASIO | 1 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | CP-070685 | - | Alcatel-Lucent | Jean-Jacques Trottin | CP#41 completed. Linked to SA5 Study on Common Profile Storage framework UID_320006. Spin-off WID UID_410003 (IMS_ASIO) | 29.864
2640 | 360031 | Study on Customized Alerting Tone (CAT) solution for voice and video call in CS domain | FS_CAT_VVC_CS | 1 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | CP-070518 | - | China Mobile | zhanghao@chinamobile.com | CP#41 completed. Spin-off WID under Feature CAT UID_340029 | 29.882
2641 | 380023 | Study on InterWorking Function between MAP based and Diameter based interfaces | FS_MAP2Diam | 1 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-070760 | - | Huawei | liming49985@huawei.com | CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005 | 29.805
2642 | 370041 | Study on Scope of future HSPA Evolution for 1.28 Mcps TDD | FS_RAN-LCRTDDHSPAEvo | 1 | Rel-8 | R1 | 2007-09-14 08:00 | 2008-05-30 17:00 | 100% | RP-070748 | RP-080290 | RITT | Xu Fei | RP#40 completed | 25.824
2643 | 370042 | Study on Synchronized E-DCH for UTRA FDD | FS_RAN-UplinkSync | 1 | Rel-8 | R1 | 2007-09-14 08:00 | 2008-03-07 17:00 | 100% | RP-070678 | RP-080068 | Nokia Siemens Networks | Karri.Ranta-aho@nsn.com | RP#39 completed | 25.823
2644 | 360016 | Study on Improved network controlled mobility between LTE and 3GPP2/mobile WiMAX radio technologies | FS_RAN-LTEmob | 1 | Rel-8 | R4 | 2007-06-04 08:00 | 2007-12-03 17:00 | 100% | RP-070511 | RP-070827 | Motorola | hao.bi@Motorola.com | RP#38 completed | 36.938
2645 | 350039 | Study on 3G Home NodeB/eNodeB | FS_RAN-HNBeNB | 1 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-05-30 17:00 | 100% | RP-070257 | RP-080289 | Motorola | howard.thomas@motorola.com | RP#40 completed | 25.820 | HNB
2646 | 50589 | Study on A-interface over IP | AINTIP | 1 | Rel-8 | GP | 2007-08-31 08:00 | 2008-02-22 17:00 | 100% | GP-071562 | - | China Mobile, Ericsson | paul.schliwa-bertling@ericsson.com | GP#37 completed. Spin-off implementation Feature AoIP (A-interface over IP) UID_50591 | 43.903
2647 | 50590 | Study on Multi-User Reusing-One-Slot | MUROS | 1 | Rel-8 | GP | 2007-11-16 08:00 | 2010-11-12 17:00 | 100% | GP-072033 | - | Nokia Siemens Networks | juergen.hofmann@nsn.com | GP#48 completed as Rel-8. Spin-off implementation WI UID_420002 VAMOS (Voice services over Adaptive Multi-user channels on One Slot) | 45.914
2648 | 51148 | Study on Optimized Transmit Pulse Shape for Downlink EGPRS2-B | WIDER | 1 | Rel-8 | G1 | 2007-11-16 08:00 | 2010-05-21 17:00 | 100% | GP-072026 | - | Research In Motion, Nokia Siemens Networks | jdwyer@RIM.COM and eddie.riddington@nsn.com | GP#46 completed | 45.913
2649 | 350017 | Deleted - Study on Mobility between 3GPP-WLAN Interworking and 3GPP Systems | FS_SM3GWLAN | 1 | Rel-8 | S2 | 2007-03-20 08:00 | 2008-09-18 17:00 | 100% | SP-070106 | - | Orange | - | SP#41 stopped. Draft TR 23.827 content implemented in TS 23.327. | withdrawn 23.827 | WLAN
2650 | 370044 | Deleted - equals 340035 -FS on Service continuity between mobile and WLAN networks | FSSCMobToW | 1 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-14 17:00 | 100% | SP-070557 | - | BT | mike.meyerstein@bt.com | SP#39 stopped | 22.937
2651 | 380068 | Deleted - Study on Evaluation of LCS Control Plane Solution for EPS | FS_LCS_EPS | 1 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-05-30 17:00 | 100% | SP-070819 | - | SiRF | - | SP#40 spin-off Feature UID_400038 (LCS_CPS_EPS). SP#40 FS stopped | 23.891
2652 | 380080 | Deleted - Study on HS-PDSCH serving cell change enhancements | FS_RAN-HSPDSCH | 1 | Rel-8 | R4 | 2007-12-17 08:00 | 2008-03-07 17:00 | 100% | RP-071044 | RP-080070 | Qualcomm | - | RP#39 stopped (no TR produced). Spin-off HS-DSCH Serving Cell Change Enhancements (UID_39003) | none
2653 | 390032 | Deleted - Study on Dual-Cell HSDPA operation | FS_RAN-DCHS | 1 | Rel-8 | R1 | 2007-08-15 08:00 | 2009-03-06 17:00 | 100% | RP-080228 | RP-090066 | Qualcomm | Josef Blanz | RP#43 stopped (draft TR 25.825 v100 withdrawn). Conclusions in RP-090318 (RAN1 findings of the UTRA Multi-Carrier Evolution study). RP#42 New WI approved on Dual-Cell HSDPA operation on adjacent carriers (UID_400052) | withdrawn 25.825 v100
2654 | 0 | Release 7 Features | - | 1 | Rel-7 | CP,GP,RP,SP | 2005-05-02 08:00 | 2007-12-06 17:00 | 100% | - | - | - | - | - | -
2655 | 732097 | Identification of Communication Services in IMS | ServID | 1 | Rel-7 | S2,S1,C1,S5 | 2005-05-02 08:00 | 2007-09-14 17:00 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | WID approved SP#28. WID updated SP#32 | -
2656 | 32106 | TR on ServID | - | 2 | Rel-7 | S2 | 2005-05-02 08:00 | 2006-03-21 17:00 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | - | 23.816
2657 | 32107 | Stage 1,2 of ServID | - | 2 | Rel-7 | S1,S2 | 2005-11-11 08:00 | 2006-05-31 17:00 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | - | 22.228, 23.228, 23.203
2658 | 320010 | Stage 3 of ServID | - | 2 | Rel-7 | C1 | 2006-03-31 08:00 | 2007-03-15 17:00 | 100% | CP-060259 | - | Ericsson | christer.holmberg@ericsson.com | CP#32 approved WID | 23.218, 24.229
2659 | 7035 | Charging of ServID | - | 2 | Rel-7 | S5 | 2006-03-31 08:00 | 2007-09-14 17:00 | 100% | SP-060293 | - | Orange | alain.bibas@orange-ft.com | - | 32.260, 32.298, 32.299
2660 | 32116 | Supporting Globally Routable User Agent URIs in IMS | GRUU | 1 | Rel-7 | S2,S1,C1 | 2005-11-14 08:00 | 2007-06-15 17:00 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | SP#29 approved WID | -
2661 | 7009 | Deleted - TR on GRUU | - | 2 | Rel-7 | S2 | 2005-11-14 08:00 | 2006-09-14 17:00 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | Abandoned | -
2662 | 7010 | Stage 1,2 of GRUU | - | 2 | Rel-7 | S1,S2 | 2006-07-03 08:00 | 2006-09-29 17:00 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | SP#29 approved WID | 22.228, 23.228, 23.218, 24.229
2663 | 320011 | Stage 3 of GRUU | - | 2 | Rel-7 | C1 | 2006-06-02 08:00 | 2007-06-15 17:00 | 100% | CP-060358 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#32 approved WID | 24.229
2664 | 7038 | Multimedia Telephony Service for IMS | MTSI | 1 | Rel-7 | S1,C1,S4 | 2006-02-01 08:00 | 2007-06-15 | 100% | SP-060224 | - | Ericsson | peter.bleckert@ericsson.com | - | -
2665 | 7039 | Stage 1 of MTSI | MTSI-REQ | 2 | Rel-7 | S1 | 2006-02-01 08:00 | 2006-09-29 17:00 | 100% | SP-060224 | - | Ericsson | peter.bleckert@ericsson.com | - | 22.173
2666 | 7037 | Stage 3 of MTSI | - | 2 | Rel-7 | C1 | 2006-03-10 08:00 | 2007-06-14 17:00 | 100% | CP-060257 | - | Ericsson | christer.holmberg@ericsson.com | - | 24.173
2667 | 7040 | Media handling and interaction in MTSI | MTSI-MHI | 2 | Rel-7 | S4 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | SP-060225 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.114
2668 | 7023 | Deleted - duplicates UID7039 - IMS Multimedia Telephony Service | MMTEL | 2 | Rel-7 | S1 | 2007-06-15 | 2007-06-15 | 100% | SP-050387 | - | Ericsson | peter.bleckert@ericsson.com | - | 22.173
2669 | 350147 | Multimedia Telephony Service for IMS (MTSI) - UE Conformance Testing | MTSI-UEConTest | 1 | Rel-7 | R5 | 2007-09-19 08:00 | 2009-03-12 17:00 | 100% | RP-080605 | RP-090056 | Ericsson, Motorola | Leif.Mattisson@ericsson.com, Jacob.John@motorola.com | RP#43 completed. Linked UID_7038 (MTSI) | 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2
2670 | 377001 | TISPAN requirements for Multimedia Telephony with PSTN/ISDN simulation services | TMMTEL7 | 1 | Rel-7 | S1 | 2007-09-18 08:00 | 2007-12-06 17:00 | 100% | SP-070568 | - | - | - | - | 22.273 (EI 181 002 maintenance)
2671 | 387001 | Maintenance of TISPAN release 1 common IMS | MCIMSTR1 | 1 | Rel-7 | S2 | 2007-07-02 08:00 | 2008-03-07 17:00 | 100% | SP-070915 | - | Ericsson | Raymond Forbes | - | http://www.3gpp.org/specs/TISPAN-IMS-ansfer.htm
2672 | 387002 | SA1 aspects of MCIMSTR1 | MCIMSTR1-S1 | 2 | Rel-7 | S1 | 2007-09-18 08:00 | 2007-12-06 17:00 | 100% | SP-070915 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | - | 22.173, 22.273
2673 | 387003 | SA2 aspects of MCIMSTR1 | MCIMSTR1-S2 | 2 | Rel-7 | S2 | 2007-09-18 08:00 | 2007-12-06 17:00 | 100% | SP-070915 | - | Ericsson | Raymond Forbes | - | 23.406, 23.417, 23.508,23.509, 23.511
2674 | 380072 | SA1,SA2 part of Maintenance of TISPAN release 1 common IMS | IMS_Comm_Mtce7 | 2 | Rel-7 | S2,S1 | 2007-07-02 08:00 | 2007-12-06 17:00 | 100% | SP-080501 | - | BT, Ericsson | Dick Knight, Raymond Forbes | SP#38 completed | 22.173, 22.273, 22.401, 23.406, 23.417, 23.508, 23.509, 23.511
2675 | 380004 | Maintenance of TISPAN R1 | MAINT_R1 | 2 | Rel-7 | C1,C3,C4 | 2007-11-09 08:00 | 2008-03-07 17:00 | 100% | CP-080211 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#39 completed | 24.404, 24.405, 24.406, 24.407, 24.408, 24.410, 24.411, 24.416, 29.421, 24.423, 24.428, 24.429, 29.433, 24.441, 24.403, 29.427, 24.430, 29.412
2676 | 32045 | PS domain and IMS impacts for supporting IMS Emergency calls (EMC1) | EMC1 | 1 | Rel-7 | S2,S1,C1,C4,IETF | 2000-09-18 08:00 | 2011-12-09 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | EMC1 | Public Safety (I-A)
2677 | 1314 | Service Requirements for IP-based emergency calls | - | 2 | Rel-7 | S1 | 2000-09-18 08:00 | 2004-06-25 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 22.101 | Public Safety (I-A)
2678 | 32046 | Study on Stage 2 for IMS-level solution | - | 2 | Rel-7 | S2 | 2003-02-26 08:00 | 2005-09-16 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.867 | Public Safety (I-A)
2679 | 32080 | Study on Stage 2 for GPRS-level solution | - | 2 | Rel-7 | S2 | 2004-10-14 08:00 | 2005-12-08 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.867 | Public Safety (I-A)
2680 | 32100 | Stage 2 Specification Phase - IMS-level | - | 2 | Rel-7 | S2 | 2005-09-05 08:00 | 2006-06-09 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.060, 23.167, 23.203, 23.221, 23.228, 23.234, 23.271, 23.406 | Public Safety (I-A)
2681 | 32101 | Deleted - Stage 2 Specification Phase - GPRS-level | - | 2 | Rel-7 | S2 | 2007-03-02 17:00 | 2007-03-02 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | - | Public Safety (I-A)
2682 | 1653 | Emergency Call Enhancements for IP& PS Based Calls – stage 3 | - | 2 | Rel-7 | C1,C4,IETF | 2006-01-09 08:00 | 2011-12-09 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | - | Public Safety (I-A)
2683 | 1315 | CT1 IMS aspects to support IMS Emergency sessions | - | 3 | Rel-7 | C1 | 2006-01-09 08:00 | 2007-06-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 24.229 | Public Safety (I-A)
2684 | 521030 | (IETF) CT1 IMS aspects to support IMS Emergency sessions | - | 3 | Rel-7 | C1-IETF | 2006-01-09 08:00 | 2011-12-09 17:00 | 100% | CP-050529 | - | Keith Drage | - | CP#54 completed | RFC 6442 (was draft-ietf-sipcore-location-conveyance) | Public Safety (I-A)
2685 | 13028 | Deleted - CT3 IMS aspects to support IMS Emergency sessions | - | 3 | Rel-7 | C3 | 2006-05-08 08:00 | 2006-09-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | Cancelled for Rel-7 and there is no corresponding Rel-8 WI | 29.163 | Public Safety (I-A)
2686 | 13031 | Deleted - CT3 PS domain aspects to support IMS Emergency sessions | - | 3 | Rel-7 | C3 | 2006-05-08 08:00 | 2006-09-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | Cancelled for Rel-7 and there is no corresponding Rel-8 WI | 29.061 | Public Safety (I-A)
2687 | 1646 | CT1 PS domain aspects to support IMS Emergency sessions | - | 3 | Rel-7 | C1 | 2006-01-09 08:00 | 2007-06-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 24.008, 24.234 | Public Safety (I-A)
2688 | 14026 | CT4 PS domain aspects to support IMS Emergency sessions | EMC1-GPRSc4 | 3 | Rel-7 | C4 | 2006-01-09 08:00 | 2007-06-01 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 29.060 | Public Safety (I-A)
2689 | 11065 | IMS Support of Conferencing | IMSconf | 1 | Rel-7 | C1 | 2005-11-04 08:00 | 2007-03-15 17:00 | 100% | CP-070120 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#35 revised WID | 24.147, 24.229
2690 | 34033 | Performance Characterization of VoIMS over HSDPA\EUL channels | VoIMS-PCVoIMS | 1 | Rel-7 | S4 | 2005-03-15 08:00 | 2007-12-06 17:00 | 100% | SP-050089 | - | Alcatel-Lucent | mcgowan@alcatel-lucent.com | - | 26.935
2691 | 31062 | WLAN-UMTS Interworking Phase 2 | WLAN2, WLAN-SC | 1 | Rel-7 | S1,S2 | 2004-01-05 08:00 | 2005-06-07 08:00 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | Created at SP#27 because of WLAN items belonging to Rel-7 | 33.234 (SP-36 SA3 CRs approved) | WLAN
2692 | 31057 | Stage 1 on Session Continuity | - | 2 | Rel-7 | S1 | 2004-01-05 08:00 | 2004-06-11 17:00 | 100% | - | - | - | - | - | 22.234 | WLAN
2693 | 32096 | Stage 2 on Session Continuity: covered by SAE | - | 2 | Rel-7 | S2 | 2005-06-07 08:00 | 2005-06-07 08:00 | 100% | - | - | - | - | - | - | WLAN
2694 | 32110 | WLAN Interworking – Private Network access from WLAN 3GPP IP Access | WLANPNA | 1 | Rel-7 | S2,C1,C3,C4 | 2005-10-10 08:00 | 2006-09-26 17:00 | 100% | SP-050489 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | - | - | WLAN
2695 | 32111 | WLAN-PNA - Stage 2 | WLANPNA-st2 | 2 | Rel-7 | S2 | 2005-10-10 08:00 | 2006-06-23 17:00 | 100% | SP-050489 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | Approved at SP#29 | 23.234, 33.234 | WLAN
2696 | 11059 | WLAN-PNA - Stage 3 | WLANPNA-st3 | 2 | Rel-7 | C1,C3,C4 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | - | WLAN
2697 | 11064 | CT1 aspets for WLAN-PNA | - | 3 | Rel-7 | C1 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | 24.234 | WLAN
2698 | 13027 | CT3 aspets for WLAN-PNA | - | 3 | Rel-7 | C3 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | 29.161 | WLAN
2699 | 14024 | Deleted - CT4 aspets for WLAN-PNA | - | 3 | Rel-7 | C4 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | CT4#31; no impacts identified, therefore completed. CP-32 stopped | 29.234 | WLAN
2700 | 32092 | Enhancements to support QoS provisioning over 3GPP/WLAN Interworking | WLANQOS | 1 | Rel-7 | S2,C4,C1 | 2005-03-14 08:00 | 2007-03-09 17:00 | 100% | SP-050682 | - | Samsung | - | Moved from FS section Feb 06. SP-30 updated WID | - | WLAN
2701 | 7015 | Deleted - TR on support of QoS on WLAN | - | 2 | Rel-7 | S2 | 2005-03-14 08:00 | 2006-01-31 17:00 | 100% | SP-050682 | - | Samsung | - | SP#32 stopped | 23.836 | WLAN
2702 | 7016 | Stage 2 on support of QoS over 3GPP/WLAN interworking | - | 2 | Rel-7 | S2 | 2006-02-01 08:00 | 2006-06-30 17:00 | 100% | SP-050682 | - | Samsung | - | SP#30 updated WID | 23.234 | WLAN
2703 | 14028 | Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking | - | 2 | Rel-7 | C4 | 2006-09-22 08:00 | 2007-03-09 17:00 | 100% | CP-060418 | - | Huawei | zhang.peng@huawei.com | CP#33 approved WID | 29.234, 23.008 | WLAN
2704 | 340005 | Stage 3 CT1 on support of QoS over 3GPP/WLAN Interworking | - | 2 | Rel-7 | C1 | 2006-09-04 08:00 | 2006-11-30 17:00 | 100% | CP-060418 | - | Huawei | zhang.peng@huawei.com | CP#33 approved WID | 24.234 | WLAN
2705 | 32079 | Location Services enhancements | LCS3 | 1 | Rel-7 | S1,S2,GP,C4,R2 | 2004-06-28 08:00 | 2007-12-17 17:00 | 100% | SP-040682 | - | - | - | - | -
2706 | 32093 | Stage 2 for LCS3 (including IMS emergency location aspects) | - | 2 | Rel-7 | S2 | 2004-12-31 08:00 | 2006-09-15 17:00 | 100% | SP-050119 | - | SiRF | brodilitz@sirf.com | SP#27 approved WID | 23.271
2707 | 50558 | LCS Enhancements related to Location-Based Services | LCS3-LBS | 2 | Rel-7 | GP | 2005-01-03 08:00 | 2007-08-31 17:00 | 100% | GP-050265 | - | SiRF | kjudge@sirf.com | - | 43.059, 44.031, 48.008, 49.031
2708 | 14025 | CT4 aspects for LCS UEPos-LBS | LCS3-UEPos-LBS | 2 | Rel-7 | C4 | 2006-01-02 08:00 | 2006-12-01 17:00 | 100% | CP-050240 | - | SiRF | brodilitz@sirf.com | - | 24.030, 24.080, 29.002
2709 | 20042 | UE positioning - Velocity | LCS3-UEPos-Velocity | 2 | Rel-7 | R2 | 2005-03-15 08:00 | 2006-09-15 17:00 | 100% | RP-050300 | RP-060459 | SiRF | BRodilitz@SiRF.com | - | 25.305, 25.331, 25.410, 25.413, 25.453
2710 | 20012 | Inclusion of Uplink TDOA UE positioning method in the UTRAN specifications | LCS3-UEPos-UTDOA | 2 | Rel-7 | R2 | 2004-09-15 08:00 | 2007-12-17 17:00 | 100% | RP-040387 | RP-070797 | TruePosition | Robert Gross (rgross@polariswireless.com) | - | 25.305, 25.453, new TS 25.111
2711 | 31052 | LCS for 3GPP Interworking WLAN | LCS3-IWLAN | 2 | Rel-7 | S1,S2 | 2004-06-28 08:00 | 2007-03-02 17:00 | 100% | SP-060291 | - | Telcordia | Mike Loushine | - | - | WLAN
2712 | 32077 | FS on 3GPP system to WLAN Interworking with LCS | LCS3-IWLAN-FSs1 | 3 | Rel-7 | S1 | 2004-06-28 08:00 | 2006-06-30 17:00 | 100% | SP-060291 | - | Telcordia | Mike Loushine | - | new TR 22.935
2713 | 32108 | Deleted - Study of work on an LCS architecture for I-WLAN. | LCS3-IWLAN-FSs2 | 3 | Rel-7 | S2 | 2006-06-26 08:00 | 2007-03-02 17:00 | 100% | SP-060291 | - | LG Electronics | dhshim@lge.com ; phede@lge.com | SP#41 TR withdrawn. All work transferred to specs | 23.837
2714 | 340007 | Stage 2 for LCS architecture for I-WLAN | - | 3 | Rel-7 | S2 | 2006-10-23 08:00 | 2007-03-02 17:00 | 100% | SP-060818 | - | LG Electronics | dhshim@lge.com ; phede@lge.com | - | 23.234, 23.271, 23.167
2715 | 20030 | Deleted - UE positioning Rel-7 | LCS3-UEpos | 2 | Rel-7 | RP | 2004-09-15 08:00 | 2007-12-17 17:00 | 100% | - | - | - | - | - | -
2716 | 31084 | MBMS Enhancements | MBMSE | 1 | Rel-7 | S1,R1,C3 | 2005-07-11 08:00 | 2007-11-30 17:00 | 100% | SP-050389 | - | China Mobile | liuhongyfw@chinamobile.com | - | -
2717 | 340041 | Stage 1 of MBMSE | - | 2 | Rel-7 | S1 | 2005-07-11 08:00 | 2005-12-08 17:00 | 100% | SP-050389 | - | China Mobile | liuhongyfw@chinamobile.com | - | 22.146, 22.246, 22.228
2718 | 340042 | MBMS FDD Physical layer Enhancements | MBMSE-RANPhysFDD | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070226 | RP-070290 | Ericsson | Lars.Lindbom@ericsson.com | - | 25.211, 25.212, 25.213, 25.101, 25.104, 25.331, 25.433, 25.346, 25.306
2719 | 340043 | MBMS TDD Physical layer Enhancements | MBMSE-RANPhysTDD | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070241 | RP-070291 | IPWireless | Nicholas Anderson | - | 25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123
2720 | 350022 | MBMS Low Chip Rate TDD Physical Layer Enhancement | MBMSE-RANPhysLCRTDD | 2 | Rel-7 | R1 | 2007-03-16 08:00 | 2007-09-10 17:00 | 100% | RP-070253 | RP-070292 | RITT | Lin Hui | - | 25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123
2721 | 340046 | MBMS Mz interface | MBMSMz | 2 | Rel-7 | C3 | 2006-12-04 08:00 | 2007-11-30 17:00 | 100% | CP-070109 | - | Huawei | Deng Tingting (ttdeng@huawei.com) | - | 29.061
2722 | 400058 | MBMS - UE Conformance Testing | MBMSE_UEConTest | 1 | Rel-7 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | Linked to Rel-7 Feature UID_31084 (MBMSE) | -
2723 | 25049 | Conformance Test Aspects – MBMS TDD Physical layer Enhancements – MBSFN for HCR and VHCR TDD | MBMSE-RANPhysTDD_UEConTest | 2 | Rel-7 | R5 | 2007-06-01 08:00 | 2008-09-12 17:00 | 100% | RP-080155 | RP-080541 | IPWireless | tspeight@ipwireless.com | RP#41 completed | 34.108, 34.122, 34.123-1/2/3
2724 | 400059 | Conformance Test Aspects – MBMS LCR TDD Physical Layer Enhancement | MBMSE-RANPhysLCRTDD_UEConTest | 2 | Rel-7 | R5 | 2008-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-080318 | RP-090715 | CATT | chenxiaozhong@datangmobile.cn | RP#45 completed | 34.108, 34.123-1
2725 | 400060 | Conformance Test Aspects – MBSFN for FDD | MBMSE-UEConTest_RANPhysFDD | 2 | Rel-7 | R5 | 2008-05-30 08:00 | 2009-12-04 17:00 | 100% | RP-080336 | RP-091214 | Huawei | Xiang Li (trica_li@huawei.com) | RP#46 completed | 34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2726 | 34038 | MBMS User Service Extensions | MBMSUSE | 1 | Rel-7 | S4 | 2005-12-07 08:00 | 2007-06-07 17:00 | 100% | SP-050838 | - | Ericsson | Thorsten.Lohmar@ericsson.com | - | 26.346, 26.946
2727 | 31051 | Advanced Global Navigation Satellite System (AGNSS) concept | LCS3-AGNSS | 1 | Rel-7 | S1,S2,GP,R2 | 2004-06-28 08:00 | 2007-08-31 17:00 | 100% | SP-040681 | - | Alcatel | Michel.monnerat@thalesaleniaspace.com | - | -
2728 | 50551 | Stage 1/2 for Towards AGNSS Concept | AGNSS | 2 | Rel-7 | S1,S2 | 2007-02-16 08:00 | 2007-02-16 17:00 | 100% | SP-040681 | - | Alcatel | richard.couty@space.alcatel.fr | - | 22.071, 23.271
2729 | 50548 | Towards AGNSS Concept | AGNSS-GP | 2 | Rel-7 | GP | 2004-06-28 08:00 | 2007-08-31 17:00 | 100% | GP-042677 | - | Alcatel | richard.couty@space.alcatel.fr | GP#36 completed | 43.030, 43.059, 44.031, 44.035, 44.071, 48.008, 48.018, 48.031, 49.031
2730 | 20050 | Global Navigation Satellite System (GNSS) in UTRAN | LCS3-GNSS-UTRAN | 2 | Rel-7 | R2 | 2005-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-060211 | RP-070482 | France Telecom | alain.abinakhoul@francetelecom.com | - | 25.305, 25.331, 25.306, 25.413, 25.423, 25.433, 25.453, 25.302, 25.215, 25.401, 25.402, 25.450, 25.452
2731 | 50581 | A-GPS Minimum Performance | GAGR | 1 | Rel-7 | G1,G3 | 2006-04-28 08:00 | 2007-08-31 17:00 | 100% | GP-060834 | - | Spirent | richard.catmur@spirentcom.com | - | 45.005, 51.010
2732 | 31048 | Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM | USSD-USIM | 1 | Rel-7 | S1,C6 | 2004-03-05 08:00 | 2005-08-12 17:00 | 100% | SP-040104 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | -
2733 | 31060 | Stage 1 for USSD message delivery and transfer to USIM | - | 2 | Rel-7 | S1 | 2004-03-18 08:00 | 2004-10-15 17:00 | 100% | SP-040104 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | 22.090
2734 | 43008 | Alignment with requirements regarding USSD usage | - | 2 | Rel-7 | C6 | 2004-03-05 08:00 | 2005-08-12 17:00 | 100% | TP-040069 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | 31.111, 31.115, 31.130
2735 | 31063 | Combinational Services | CSICS | 1 | Rel-7 | S1,S2,C1,S4 | 2005-01-17 08:00 | 2006-03-06 17:00 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | -
2736 | 31064 | Stage 1 for CSICS | - | 2 | Rel-7 | S1 | 2005-01-17 08:00 | 2005-06-09 17:00 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | 22.279
2737 | 32084 | Stage 2 for CSICS | - | 2 | Rel-7 | S2 | 2005-01-17 08:00 | 2005-07-15 17:00 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | 23.279
2738 | 11054 | Stage 3 for CSICS CN aspects | - | 2 | Rel-7 | C1 | 2005-05-02 08:00 | 2006-03-06 17:00 | 100% | CP-060105 | - | Vodafone | peter.dawes@vodafone.com | - | 24.879, 24.279, 24.229, 24.008
2739 | 34031 | Stage 3 for codec aspects | CSICS-Codec | 2 | Rel-7 | S4 | 2005-03-15 08:00 | 2005-12-07 17:00 | 100% | SP-050091 | - | Ericsson | Per.Frojdh@ericsson.com | - | 26.141, 26.235
2740 | 31065 | CAMEL Trunk Triggers | TTCAMEL | 1 | Rel-7 | S1,C4 | 2004-12-17 13:00 | 2005-12-05 12:00 | 100% | SP-040743 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | - | -
2741 | 31066 | Stage 1 for CAMEL Trunk Triggers | - | 2 | Rel-7 | S1 | 2004-12-17 13:00 | 2005-12-05 12:00 | 100% | SP-040743 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | - | 22.078
2742 | 14017 | CAMEL Trunk Originated Trigger Detection Points | CamelR7 | 2 | Rel-7 | C4 | 2004-12-17 13:00 | 2005-12-05 12:00 | 100% | NP-040550 | - | Nortel | David Hutton (dhutton@nortel.com) | - | -
2743 | 31088 | IMS Service Brokering enhancements | ISB | 1 | Rel-7 | S1 | 2005-12-07 08:00 | 2006-03-13 17:00 | 100% | SP-050830 | - | Telcordia | jbakker@telcordia.com | No CR submitted in rel-8 (according to CR database). | 22.228
2744 | 320027 | Stage 1 for ISB | ISB-s1 | 2 | Rel-7 | S1 | 2005-12-07 08:00 | 2006-03-13 17:00 | 100% | SP-050830 | - | Telcordia | jbakker@telcordia.com | No Rel-8 changes | 22.228
2745 | 11045 | Enhancements of VGCS for public authority officials | EVGCS | 1 | Rel-7 | S1,C1,C4,G2 | 2004-08-27 08:00 | 2007-06-15 17:00 | 100% | SP-040304 | - | - | - | Moved from Rel-6 UID_50563 Enhancements of VGCS in public networks for communication of public authority officials | 43.068, 44.068, 24.008, 29.002
2746 | 31061 | Stage 1 for Enhancements of VGCS for public authority officials | - | 2 | Rel-7 | S1 | 2004-08-27 08:00 | 2004-08-27 08:00 | 100% | SP-040304 | - | Siemens | joerg.swetina@neclab.eu | Voice Group Call Service | 42.068, 43.068
2747 | 11056 | Architecture and protocol aspects | - | 2 | Rel-7 | C1,C4 | 2004-08-27 08:00 | 2007-06-15 17:00 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 44.068
2748 | 11062 | CT1 aspects of EVGCS | - | 3 | Rel-7 | C1 | 2004-08-27 08:00 | 2007-06-15 17:00 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 44.068, 24.008
2749 | 14022 | CT4 aspects of EVGCS | - | 3 | Rel-7 | C4 | 2004-08-27 08:00 | 2006-03-10 17:00 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 29.002
2750 | 752076 | GERAN2 aspects of EVGCS | - | 2 | Rel-7 | G2 | 2004-08-27 08:00 | 2007-02-16 17:00 | 100% | GP-071855 | - | Siemens | kenneth.isaacs@roke.co.uk | - | -
2751 | 11055 | Improvements of VGCS for parallel use of services | IVGCS | 1 | Rel-7 | S1 | 2005-03-15 08:00 | 2007-03-15 17:00 | 100% | SP-070167 | - | - | - | Voice Group Call Service | -
2752 | 31070 | Service Requirements for VGCS improvements | - | 2 | Rel-7 | S1 | 2005-03-15 08:00 | 2005-06-08 17:00 | 100% | SP-070167 | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 42.068
2753 | 32090 | Stage 2 modifications for VGCS improvements | - | 2 | Rel-7 | C1 | 2005-12-01 08:00 | 2007-03-14 17:00 | 100% | NP-050141 | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 43.068
2754 | 11057 | Protocol aspects | - | 2 | Rel-7 | C1 | 2005-12-01 08:00 | 2007-03-15 17:00 | 100% | NP-050141 | - | T-Mobile | Dieter Jacobsohn | Previous name (before CT32) was Architecture and protocol aspects | 44.068
2755 | 11063 | CT1 aspects of IVGCS | - | 3 | Rel-7 | C1 | 2005-12-01 08:00 | 2007-03-15 17:00 | 100% | CP-070118 | - | T-Mobile | - | - | 43.068, 44.068
2756 | 14023 | Deleted - CT4 aspects of IVGCS | IVGCS-St3-c4 | 3 | Rel-7 | C4 | 2007-03-09 17:00 | 2007-03-09 17:00 | 100% | NP-050141 | - | T-mobile | - | CT4#33 stage 2 solution is still open. ... | 29.002
2757 | 31071 | Open Service Access (OSA) Rel-7 | OSA7 | 1 | Rel-7 | S1,C5 | 2005-03-15 08:00 | 2007-06-08 17:00 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | -
2758 | 31172 | OSA Service Broker | OSA7-SB | 2 | Rel-7 | S1,C5 | 2005-03-15 08:00 | 2006-12-01 17:00 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | -
2759 | 31072 | Service Requirements for OSA Service Broker | - | 3 | Rel-7 | S1 | 2005-03-15 08:00 | 2005-06-08 17:00 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | 22.127
2760 | 43011 | Stage 2 OSA API Service Brokering | - | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | - | 23.198
2761 | 7017 | Stage 3 OSA API Service Brokering | - | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | - | 29.198-16
2762 | 15039 | Rel-7 OSA Stage 2/3 enhancements | - | 2 | Rel-7 | C5 | 2006-04-28 08:00 | 2007-06-08 17:00 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | CP#34 updated WID CP-060607=>CP-070200 | 29.198/9, 23.198
2763 | 7018 | Parlay X Message Broadcast Web Service | - | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | ETRI | - | - | 29.199-15, 23.198
2764 | 7019 | Parlay X Geocoding Web Service | - | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | ETRI | - | - | 29.199-16, 23.198
2765 | 7020 | Parlay X Application driven QoS Web Service | - | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | BT | - | - | 29.199-17, 23.198
2766 | 340001 | Parlay-X Device Capabilities and Configuration | - | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-06-08 17:00 | 100% | CP-070200 | - | Telenor | - | - | 29.199-18, 23.198
2767 | 340002 | Parlay-X Multimedia Streaming Session Management Web Service | - | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | Telenor | - | - | 29.199-19, 23.198
2768 | 340003 | Parlay-X Multimedia Multicast Control Web Service | - | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | ETRI | - | - | 29.199-20, 23.198
2769 | 340004 | OSA API Conference Call Control SCF | - | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | Ericsson | - | - | 29.198-04-5, 23.198
2770 | 31053 | Selective Disabling of UE Capabilities | SDoUE | 1 | Rel-7 | S1,S2,C1 | 2005-01-24 14:07 | 2007-06-15 17:00 | 100% | SP-050182 | - | Motorola | - | Moved from FS section Feb 06 | -
2771 | 32088 | Stage 1 of SDoUE | SDoUE-CR | 2 | Rel-7 | S1 | 2005-01-24 14:07 | 2006-12-08 17:00 | 100% | SP-050182 | - | Motorola | - | Moved from FS section Feb 06 | 22.011
2772 | 32089 | Deleted - TR on different possible architectures | SDoUE-FS | 2 | Rel-7 | S2 | 2005-03-21 08:00 | 2005-12-16 17:00 | 100% | SP-050182 | - | Vodafone | Gavin.Wong@vodafone.com | Moved from FS section Feb 06. Abandoned at SP-30 | 23.805 abandonned at SP-30; descendant C1 24.305
2773 | 7036 | Stage 3 of SDoUE | - | 2 | Rel-7 | C1 | 2006-03-10 08:00 | 2007-06-15 17:00 | 100% | CP-070121 | - | Ericsson | christian.herrero@ericsson.com | - | 24.305
2774 | 7041 | Network selection enhancements (NSP) | NSP | 1 | Rel-7 | S1 | 2006-03-15 08:00 | 2007-06-15 17:00 | 100% | SP-060220 | - | O2 | chris.friel@O2.com | - | -
2775 | 320012 | Stage 1 of NSP | NSP-TS | 2 | Rel-7 | S1 | 2006-03-15 08:00 | 2006-12-06 17:00 | 100% | SP-060220 | - | O2 | chris.friel@O2.com | - | 22.101, 22.011, 23.122, 24.008, 25.304, 31.102, 45.008
2776 | 320013 | Procedural aspects of NSP | NSP-CR | 2 | Rel-7 | C1 | 2006-06-02 08:00 | 2007-06-15 17:00 | 100% | CP-060357 | - | Motorola | Andrew Howell | - | 23.122, 24.008, 31.102
2777 | 25048 | Network selection enhancements (NSP) - UE Conformance Testing | NSP-CR_UEConTest | 1 | Rel-7 | R5 | 2007-06-01 08:00 | 2008-12-05 17:00 | 100% | RP-080135 | RP-080819 | Nokia | jarkko.hellsten@nokia.com | RP#42 completed. Testing for Feature UID_7041 (NSP-CR) | 34.108, 34.123-1, 34.123-2, 34.123-3
2778 | 32064 | Access Class Barring and Overload Protection | ACBOP | 1 | Rel-7 | S2,C1 | 2004-03-15 08:00 | 2006-09-08 17:00 | 100% | SP-040338 | - | Vodafone | chris.pudney@vodafone.com | - | 23.898
2779 | 32065 | TR on Stage 2 | - | 2 | Rel-7 | S2 | 2004-03-15 08:00 | 2005-03-31 17:00 | 100% | SP-040338 | - | NTT DoCoMo | Jean-Jacques Davidian (davidian@docomo.fr) | - | 23.898
2780 | 11048 | Stage 3 CN aspects of ACBOP | - | 2 | Rel-7 | C1 | 2005-06-06 08:00 | 2006-01-31 17:00 | 100% | - | - | - | - | - | 24.008
2781 | 20010 | Deleted - Potential impact on Iu interface Overload functionality | - | 2 | Rel-7 | RP | 2004-03-15 08:00 | 2004-03-15 08:00 | 100% | - | - | - | - | - | 25.413
2782 | 20009 | Deleted - Extra ACBOP information in RAN | - | 2 | Rel-7 | RP | 2004-03-15 08:00 | 2004-03-15 08:00 | 100% | - | - | - | - | - | 25.331
2783 | 50117 | Deleted - Extra ACBOP information in GERAN | - | 2 | Rel-7 | GP | 2006-09-08 17:00 | 2006-09-08 17:00 | 100% | - | - | - | - | - | 44.018
2784 | 32074 | System enhancements for Fixed Broadband access to IMS | FBI | 1 | Rel-7 | S2,S3,S5,C1,C3,C4,IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | SP-060145 | - | - | - | - | -
2785 | 7001 | TISPAN Rel 1 related aspects | FBI-TIS1 | 2 | Rel-7 | S2,S3,C1,C3,C4,IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | - | - | - | - | - | -
2786 | 32075 | Stage 2 of FBI for TISPAN R1 | - | 3 | Rel-7 | S2 | 2004-10-14 08:00 | 2006-03-08 17:00 | 100% | - | - | - | - | - | -
2787 | 11050 | Protocol impact of FBI for TISPAN R1 | - | 3 | Rel-7 | S3,C1,C3,C4,IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | -
2788 | 521031 | (IETF) CT aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C1-IETF,C3-IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | NP-040618 | - | Roland Jesske | - | CP#54 completed | RFC 6432 (was draft-jesske-dispatch-update3326-reason-responses)
2789 | 11060 | CT1 aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C1 | 2003-11-05 08:00 | 2006-11-30 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | 24.819, 24.229
2790 | 13025 | CT3 aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C3 | 2003-11-05 08:00 | 2006-12-08 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | 29.163, 29.209
2791 | 14020 | CT4 aspects of FBI for TISPAN R1 | FBI-TIS1-st3-c4 | 4 | Rel-7 | C4 | 2006-01-13 08:00 | 2007-03-09 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | CT4#32: a set of CRs on FBI for cable labs | 29.229
2792 | 33027 | Security Enhancements for FBI | FBI-ISE | 3 | Rel-7 | S3 | 2005-06-28 08:00 | 2005-12-08 17:00 | 100% | SP-050395 | - | Ericsson | Bengt.Sahlin@ericsson.com | Duplicated entry ("ACCSEC2", "Access Security Enhancements", SP-040865) deleted by A.Sultan | 33.203
2793 | 7002 | PacketCable Related aspects | FBI-PCBL | 2 | Rel-7 | S2,S5,C1 | 2006-02-01 08:00 | 2007-03-14 17:00 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | - | -
2794 | 7003 | Stage 1,2 of FBI for PacketCable | - | 3 | Rel-7 | S2 | 2006-02-01 08:00 | 2006-12-15 17:00 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | - | 22.228, 23.228
2795 | 7004 | Protocol impact of FBI for PacketCable | - | 3 | Rel-7 | C1 | 2006-05-01 08:00 | 2007-03-14 17:00 | 100% | - | - | - | - | - | -
2796 | 7032 | SA5 Charging aspects of FBI for PacketCable | FBI-PCBL-CH | 3 | Rel-7 | S5 | 2006-03-31 08:00 | 2006-12-07 17:00 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | 03/2006 SP#31 WID approved | 32.240, 32.260, 32.298, 32.299
2797 | 32081 | Support of SMS over generic 3GPP IP access | SMSIP | 1 | Rel-7 | S2,C4,C1 | 2004-10-14 08:00 | 2007-06-14 17:00 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID (removed MMS) | - | WLAN
2798 | 32094 | FS on SMSIP | - | 2 | Rel-7 | S2 | 2004-10-14 08:00 | 2005-06-13 17:00 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID | 23.804 | WLAN
2799 | 32095 | Stage 2 for SMSIP | - | 2 | Rel-7 | S2 | 2005-06-08 08:00 | 2006-09-15 17:00 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID | 23.204 | WLAN
2800 | 310001 | Stage 3 for SMSIP | SMSIP-St3 | 2 | Rel-7 | C4,C1 | 2005-06-08 08:00 | 2007-06-14 17:00 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | - | WLAN
2801 | 310002 | CT1 aspects for SMSIP | - | 3 | Rel-7 | C1 | 2005-06-08 08:00 | 2007-06-14 17:00 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | 23.040, 24.229 | WLAN
2802 | 310003 | CT4 aspects for SMSIP | SMSIP-St3-c4 | 3 | Rel-7 | C4 | 2005-06-08 08:00 | 2007-06-01 17:00 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | 23.008, 29.002 | WLAN
2803 | 32082 | Evolution of Policy Control and Charging | PCC | 1 | Rel-7 | S2,S5,C3,C1 | 2004-10-14 08:00 | 2007-11-30 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID adding SA5 charging. 23.125 will be discontinued from Rel-7. | -
2804 | 32102 | Deleted - TR for PCC | - | 2 | Rel-7 | S2 | 2004-10-14 08:00 | 2005-12-29 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-30: S2 has no intention for TR completion | 23.803
2805 | 32103 | Stage 2 for PCC | - | 2 | Rel-7 | S2 | 2005-07-04 08:00 | 2006-09-15 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7. | 23.203
2806 | 32109 | Evolution of policy control and flow based bearer level charging | - | 2 | Rel-7 | S2 | 2006-08-01 08:00 | 2006-12-29 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7. | 23.207, 23.002, 23.228
2807 | 7033 | SA5 Charging aspects of PCC | PCC-CH | 2 | Rel-7 | S5 | 2006-03-31 08:00 | 2007-06-15 17:00 | 100% | SP-060217 | - | Orange | alain.bibas@orange-ft.com | SP-31 updated WID with SA5 charging. | 32.250, 32.251, 32.298, 32.299
2808 | 13029 | Gx reference point for Policy and Charging Control | PCC-Gx | 2 | Rel-7 | C3 | 2005-12-02 08:00 | 2007-11-30 17:00 | 100% | CP-060434 | - | Siemens | Thomas.Belling@nsn.com | - | 29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208)
2809 | 13030 | Rx reference point for PCC CT3 aspects | PCC-Rx | 2 | Rel-7 | C3,C1 | 2005-12-02 08:00 | 2007-11-30 17:00 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | WID approved at CP#30, Revised at CP#31, Revised at CP#33 | -
2810 | 310006 | PCC-Rx CT3 aspects | PCC-Rx-c3 | 3 | Rel-7 | C3 | 2005-12-02 08:00 | 2007-11-30 17:00 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | - | 29.213, 29.214 (not progressed to Rel-7: 29.209, 29.211)
2811 | 7008 | PCC-Rx CT1 aspects | PCC-Rx-Gx-c1 | 3 | Rel-7 | C1 | 2005-12-02 08:00 | 2007-06-15 17:00 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | - | 24.229
2812 | 32091 | Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC | 1 | Rel-7 | S2,S1,S5,C1,C4 | 2004-12-31 08:00 | 2007-06-15 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | WID approved SP#27; updated SP#28; updated SP#32 | - | WLAN
2813 | 32104 | TR for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S2 | 2004-12-31 08:00 | 2005-12-08 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 23.806 | WLAN
2814 | 31085 | Stage 1 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S1 | 2005-03-17 08:00 | 2005-09-28 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 22.101 | WLAN
2815 | 32105 | Stage 2 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S2 | 2005-09-06 08:00 | 2006-09-08 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 23.206 | WLAN
2816 | 35079 | SA5 Charging for Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC-CH | 2 | Rel-7 | S5 | 2006-03-17 08:00 | 2007-06-14 17:00 | 100% | SP-060292 | - | Orange | alain.bibas@orange-ft.com | 03/2006 SP#31 WID approved | 32.250, 32.260 | WLAN
2817 | 11058 | Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | C1,C4 | 2006-02-01 08:00 | 2007-06-15 17:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - | WLAN
2818 | 11066 | CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 3 | Rel-7 | C1 | 2006-02-01 08:00 | 2007-06-15 17:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 24.206, 24.216 | WLAN
2819 | 14027 | CT4 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC-St3-c4 | 3 | Rel-7 | C4 | 2006-06-09 08:00 | 2007-03-09 17:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 23.003 | WLAN
2820 | 13032 | Deleted - CT3 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 3 | Rel-7 | C3 | 2006-11-02 08:00 | 2006-11-02 08:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 29.163 | WLAN
2821 | 7046 | One Tunnel solution for optimization of Packet Data Traffic | OPTUNEL | 1 | Rel-7 | S2 | 2006-03-27 08:00 | 2007-10-31 17:00 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | - | -
2822 | 320002 | Deleted - Study on Stage 2 for One Tunnel solution | OPTUNEL-Study | 2 | Rel-7 | S2 | 2006-03-27 08:00 | 2006-09-15 17:00 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | TR for Info SP-33. SP-34: S2 Report intention to discontinue TR | 23.809
2823 | 340013 | One Tunnel Deployment Guideline | OPTUNEL-Guide | 2 | Rel-7 | S2 | 2006-10-23 08:00 | 2007-10-31 17:00 | 100% | SP-060819 | - | Huawei | lan.liu@huawei.com | - | 23.919
2824 | 320003 | Stage 2 specification for One Tunnel solution | OPTUNEL-Stage2 | 2 | Rel-7 | S2 | 2006-09-11 08:00 | 2006-12-15 17:00 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | - | 23.060
2825 | 320029 | CSI Terminating Session handling | CSItermS | 1 | Rel-7 | S2,C1 | 2006-06-08 08:00 | 2007-06-15 17:00 | 100% | SP-060437 | - | Samsung | Osok Song | Triggered by the abandoned Study UID_32117 | -
2826 | 340014 | Stage 2 of CStermS | - | 2 | Rel-7 | S2 | 2006-06-08 08:00 | 2007-03-02 17:00 | 100% | SP-060437 | - | Samsung | Osok Song | - | 23.279
2827 | 340015 | Stage 3 of CStermS | - | 2 | Rel-7 | C1 | 2006-12-14 08:00 | 2007-06-15 17:00 | 100% | CP-070239 | - | Samsung | chenho.chin@samsung.com | CP-34 approved WID. CP-35 updated WID | 24.229, 24.279
2828 | 340011 | Deleted - duplicated with UID 340015 -Stage 3 CSI Terminating Session handling | - | 2 | Rel-7 | C1 | 2007-03-09 17:00 | 2007-03-09 17:00 | 100% | CP-060647 | - | Samsung | chenho.chin@samsung.com | CP-34 approved WID | 24.229, 24.179, 24.279
2829 | 33022 | Liberty Alliance and 3GPP Security Interworking | LibSec | 1 | Rel-7 | S3 | 2005-03-10 08:00 | 2006-11-30 17:00 | 100% | SP-050145 | - | Nokia | Silke.Holtmanns@nokia.com | WID approved SP#27. | 33.980
2830 | 33023 | Trust Requirements for Open Platforms in 3GPP | TrustOP | 1 | Rel-7 | S3 | 2005-01-03 08:00 | 2006-11-30 17:00 | 100% | SP-040863 | - | Nokia | Silke.Holtmanns@nokia.com | WID approved SP#26. | 33.905
2831 | 33024 | Development of UEA2 and UIA2 | AlgUEA2 | 1 | Rel-7 | S3 | 2004-12-01 08:00 | 2005-12-09 17:00 | 100% | SP-040864 | - | TeliaSonera | per.christoffersson@teliasonera.com | WID approved SP#26, Dependant on Funding Availability. | 35.919, 35.215, 35.216, 35.217, 35.218
2832 | 33026 | Lawful Interception in the 3GPP Rel-7 architecture | LI-7A | 1 | Rel-7 | S3 | 2005-06-28 08:00 | 2005-12-08 17:00 | 100% | SP-050237 | - | BMWI | berthold.wilhelm@regtp.de | - | 33.106, 33.107, 33.108
2833 | 33028 | Key establishment between a UICC and a terminal | KeyEstUTerm | 1 | Rel-7 | S3 | 2005-12-07 08:00 | 2006-09-28 17:00 | 100% | SP-050780 | - | Gemalto | mireille.pauliac@gemplus.com | - | 33.110
2834 | 330008 | NDS Authentication Framework Extension for Transport Layer Security | NDSAFTLS | 1 | Rel-7 | S3 | 2006-09-28 08:00 | 2006-12-06 17:00 | 100% | SP-060507 | - | Nokia | tiina.s.koskinen@nokia.com | TLS profile is moved to Rel-8 | 33.310
2835 | 732030 | Security enhancements | SEC7 | 1 | Rel-7 | S3,C1,C4 | 2005-09-12 08:00 | 2006-11-30 17:00 | 100% | - | - | - | - | - | -
2836 | 732031 | HTTPS connection between a UICC and a NAF | SEC7-HSUN | 2 | Rel-7 | S3,C1 | 2005-09-12 08:00 | 2005-09-12 17:00 | 100% | SP-050573 | - | Gemalto | JSeif@axalto.com, mireille.pauliac@gemplus.com | - | 33.918, 33.222, 24.109
2837 | 732032 | 2G GBA: 2G SIM usage in 3GPP GAA framework | SEC7-2GGBA | 2 | Rel-7 | S3 | 2005-09-12 08:00 | 2005-12-05 17:00 | 100% | SP-050576 | - | Nokia | Silke.Holtmanns@nokia.com | - | 33.920, 33.220
2838 | 732033 | Generic Authentication Architecture usage extensions and optimizations | SEC7-GAA2 | 2 | Rel-7 | S3 | 2005-09-12 08:00 | 2006-11-30 17:00 | 100% | SP-060429 | - | Nokia | Silke.Holtmanns@nokia.com | 33.223 goes to R8 | 33.220, 29.109, 24.109, (33.223 goes to R8)
2839 | 32034 | SS7 TCAP security Gateway | SEC7-NDS-TCAPsec | 2 | Rel-7 | S3,C4 | 2005-09-12 08:00 | 2006-08-14 17:00 | 100% | SP-050579 | - | Siemens | marc.blommaert.ext@nsn.com | - | -
2840 | 310004 | SA3 aspects of SEC7-NDS-TCAPsec | SEC7-NDS-TCAPsec-SA3 | 3 | Rel-7 | S3 | 2005-09-12 08:00 | 2006-03-10 17:00 | 100% | SP-050579 | - | Siemens | marc.blommaert.ext@nsn.com | - | 33.204
2841 | 310005 | TCAPsec Gateway | SEC7-TCAP | 3 | Rel-7 | C4 | 2006-04-03 08:00 | 2006-08-14 17:00 | 100% | CP-060170 | - | Siemens | Ulrich.wiehe@gksag.de | - | 29.204, 29.002
2842 | 711052 | IMS Stage 3 IETF Protocol Alignment | IMSProtoc | 1 | Rel-7 | C1 | 2004-12-10 08:00 | 2007-03-14 17:00 | 100% | CP-060101 | - | - | - | TR 24.930: Signalling flows for the session setup in the IM CN subsystem based on Session Initiation Protocol (SIP) | 24.930
2843 | 7043 | Interoperability between VGCS/VBS and A/Gb flexibility | VGCSFlex | 1 | Rel-7 | C1,C4 | 2006-03-22 08:00 | 2007-03-09 17:00 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | Voice Group Call Service | -
2844 | 7044 | CT1 aspects of VGCSFlex | - | 2 | Rel-7 | C1 | 2006-03-22 08:00 | 2006-10-30 17:00 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 43.069
2845 | 7045 | CT4 aspects of VGCSFlex | VGCSFlex-c4 | 2 | Rel-7 | C4 | 2006-03-22 08:00 | 2007-03-09 17:00 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | - | 29.002
2846 | 13023 | DIAMETER on the GGSN Gi interface | DIAMGi | 1 | Rel-7 | C3 | 2004-09-10 08:00 | 2006-12-08 17:00 | 100% | CP-060431 | - | Vodafone | Nico.Gabriele@vodafone.com | - | 29.061
2847 | 13022 | DIAMETER on the PDG Wi interface | DIAMWi | 1 | Rel-7 | C3 | 2004-09-10 08:00 | 2006-12-08 17:00 | 100% | CP-060432 | - | Vodafone | Nico.Gabriele@vodafone.com | - | 29.161
2848 | 13033 | Interworking between the 3GPP CS domain with BICC or ISUP as signalling protocol and external SIP-I networks | ExtSIPI | 1 | Rel-7 | C3 | 2006-09-22 08:00 | 2008-07-22 17:00 | 100% | CP-070101 | - | Siemens | Thomas.Belling@nsn.com | - | 29.164
2849 | 340047 | PDU multiplexing at Nb Interface with IP transport | NbIPMux | 1 | Rel-7 | C3 | 2006-12-04 08:00 | 2008-07-22 17:00 | 100% | CP-070105 | - | Alcatel-Lucent | Jean.Rzeznik@alcatel-lucent.fr | - | 29.414
2850 | 14012 | Mp (MRFC - MRFP) interface | Mp | 1 | Rel-7 | C4,C1 | 2006-02-13 08:00 | 2007-06-08 17:00 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | -
2851 | 11061 | CT1 aspects of Mp | - | 2 | Rel-7 | C1 | 2006-02-13 08:00 | 2006-02-13 17:00 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | 24.229
2852 | 13026 | Deleted - CT3 aspects of Mp | - | 2 | Rel-7 | C3 | 2006-09-22 08:00 | 2006-09-22 17:00 | 100% | - | - | Ericsson | philip.hodges@ericsson.com | CP#34: CT3 not involved in Mp interface definition | 29.162
2853 | 320009 | Procedures description | Mp-PROCc4 | 2 | Rel-7 | C4 | 2006-06-02 08:00 | 2007-03-09 17:00 | 100% | CP-070246 | - | Huawei | Chencheng@huawei.com | - | 23.333
2854 | 14021 | Stage 3 for Mp (MRFC - MRFP) interface | Mp-St3c4 | 2 | Rel-7 | C4 | 2006-02-13 08:00 | 2007-06-08 17:00 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | 29.333
2855 | 340016 | Routeing of MT-SMS via the HPLMN | SMSviaH | 1 | Rel-7 | C4,C1 | 2006-12-01 08:00 | 2007-03-09 17:00 | 100% | CP-070032 | - | Vodafone | Nick.Russell@vodafone.com | WID approved in CP#34 | 23.040, 29.002
2856 | 350003 | Mobile Termination whilst the MS is moving to another MSC | MTmovMS | 1 | Rel-7 | C4 | 2007-03-09 08:00 | 2007-05-31 17:00 | 100% | CP-070334 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | - | 23.008, 23.012, 23.018, 23.078, 23.079, 29.002
2857 | 743009 | ISIM API for Java Card | APIJAVA | 1 | Rel-7 | C6 | 2005-03-14 08:00 | 2007-07-27 17:00 | 100% | CP-050145 | - | Sun | Sebastian Hans | - | 31.103, 102 241
2858 | 440042 | Rel-7 (U)SIM API Testing (TS 31.213) | USIM_API_Test | 1 | Rel-7 | C6 | 2009-05-30 08:00 | 2010-03-19 17:00 | 100% | CP-090450 | - | Sagem Orga | gerrit.hartbrod@sagem-orga.com | CP#47 completed. Update of Rel-6 (U)SIM API for Java Card Testing UID_43007 under Rel-6 UICC/USIM enhancements and interworking UID_1800 | 31.213
2859 | 330001 | High speed interface between the UICC and the ME | HSI | 1 | Rel-7 | C6 | 2006-09-22 08:00 | 2007-11-30 17:00 | 100% | CP-070259 | - | Gemalto | jacques.seif@GEMALTO.COM | Following ETSI publication of TS 102 600, expected to be completed at CT6 meeting 45 | 31.101
2860 | 34030 | Video Codec Performance Requirements | VICPer | 1 | Rel-7 | S4 | 2005-01-03 08:00 | 2007-06-07 17:00 | 100% | SP-040836 | - | Siemens | juergen.pandel@siemens.com | - | 26.234, 26.235, 26.346, 26.140, 26.902
2861 | 34032 | Dynamic and Interactive Multimedia Scenes | DIMS | 1 | Rel-7 | S4 | 2005-03-15 08:00 | 2007-06-07 17:00 | 100% | SP-050195 | - | Streamezzo | gaelle.martin-cocher@streamezzo.com | - | 26.140, 26.142, 26.234, 26.244, 23.346
2862 | 34034 | 3G-324M Video Telephony Call Setup Times Improvements | VTCSTI | 1 | Rel-7 | S4 | 2005-06-08 08:00 | 2006-09-27 17:00 | 100% | SP-050404 | - | Vodafone | edward.hall@vodafone.co.uk | - | 26.911
2863 | 34035 | Optimizations for Multimedia Telephony over IMS | OMTIMS | 1 | Rel-7 | S4 | 2005-09-28 08:00 | 2005-09-28 08:00 | 100% | SP-060226 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.235, 26.236
2864 | 34037 | Deleted - Characterisation of Adaptive Jitter Management Performance for VoIP Services | OMTIMS-CAJMP | 2 | Rel-7 | S4 | 2005-09-28 08:00 | 2005-09-28 08:00 | 100% | SP-050432 | - | Lucent | dhuo@lucent.com | SP-35 stopped | -
2865 | 34036 | End-to-End Multimedia Services Performance Metrics | E2EMSPM | 1 | Rel-7 | S4 | 2005-09-28 08:00 | 2007-03-15 17:00 | 100% | SP-050433 | - | China Mobile | zhangyanyf@chinamobile.com | - | 26.944
2866 | 34039 | Packet Switched Streaming Enhancements | PSSe | 1 | Rel-7 | S4 | 2006-06-08 08:00 | 2007-06-07 17:00 | 100% | SP-060361 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.234, 26.244
2867 | 35041 | Rel-7 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM7 | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-26 15:53 | 100% | - | - | Huawei | Christian.Toche@huawei.com | OAM7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI | TR 30.817
2868 | 35042 | Rel-7 Network Infrastructure Management | OAM7-NIM | 2 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | - | - | - | - | - | -
2869 | 35044 | Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050302 | - | Motorola | - | - | 32.731/2/3/5, 32.631/2/3/5
2870 | 35046 | Co-operative Element Management interface (CO-OP) (Study + Implementation) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050304 | - | Motorola | - | - | 32.806, 32.814, 32.101
2871 | 35047 | Network Management (NM) Itf-N performance criteria | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050305 | - | China Mobile | - | - | 32.811
2872 | 35048 | Delta synchronization between IRP Manager and IRP Agent (Study + Implementation) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050306 | - | Siemens | - | - | 32.391/2/3/5
2873 | 35049 | Subscription Management (SuM) IRP Solution Sets | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-060739 | - | Ericsson | - | - | 32.307/317/607/667/665, 32.101, 32.175
2874 | 35050 | Integration Reference Point (IRP) Security Management | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050308 | - | Huawei | Christian.Toche@huawei.com | - | 32.372/3/5, 32.111,32.30x,32.32x,32.33x,32.34x,32.35x,32.36x,32.41x,32.60x,32.61x,32.66x
2875 | 35052 | Partial suspension of Itf-N during maintenance/testing (Study + Implementation) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050310 | - | Siemens | - | - | 32.381/2/3/5
2876 | 35054 | Deleted - Management of Legacy Equipment | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-15 17:00 | 100% | SP-050312 | - | Siemens | - | Request to TSG#35 to STOP the WI | new 32.xxx
2877 | 35055 | Deleted - Rules for Vendor Specific Extensions | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050313 | - | Siemens | - | Request to TSG#35 to STOP the WI | 32.62n; For n = 1 to 5
2878 | 35064 | Backward and Forward Compatibility of IRP systems | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050630 | - | Ericsson | - | - | 32.154
2879 | 35071 | Repeater Network Resource Model (NRM) definition | - | 3 | Rel-7 | S5 | 2006-02-13 08:00 | 2006-12-07 17:00 | 100% | SP-050731 | - | China Mobile | - | - | 32.721/2/3/5
2880 | 35072 | UTRAN radio channel power monitoring | - | 3 | Rel-7 | S5 | 2006-02-13 08:00 | 2007-03-15 17:00 | 100% | SP-050733 | - | China Mobile | - | - | 32.405, 32.64n; For n = 1 to 5
2881 | 340009 | Notification XML Schema | - | 3 | Rel-7 | S5 | 2006-12-07 08:00 | 2007-03-15 17:00 | 100% | SP-060754 | - | Huawei | Christian.Toche@huawei.com | 12/2006 SP#34 WID approved | New 32.325/345/365/415, CR to 32.335/615/665
2882 | 35043 | Rel-7 Performance Management | OAM7-PM | 2 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | - | - | - | - | - | -
2883 | 35057 | Performance measurements definition for CN CS | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050315 | - | China Mobile | - | - | 32.407, 32.408
2884 | 35058 | Enhancement UTRAN performance measurements definition | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050316 | - | China Mobile | - | - | 32.405
2885 | 35059 | Add TDD specific counters in Performance measurement | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050317 | - | CATT | - | - | 32.405
2886 | 35060 | ATM bearer network Performance measurements | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050318 | - | ZTE | - | - | No impact on 32.404, 32.405, 32.406, 32.407
2887 | 35069 | Performance measurements definition for IMS | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050631 | - | China Mobile | - | - | 32.404,32.409,32.437, 32.632/3/4/5
2888 | 35073 | HSDPA performance measurements | - | 3 | Rel-7 | S5 | 2006-02-13 08:00 | 2007-06-14 17:00 | 100% | SP-060379 | - | China Mobile | - | - | 32.405
2889 | 35039 | Rel-7 Trace Management | OAM7-Trace | 2 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-26 15:53 | 100% | SP-050628 | - | Vodafone | - | - | -
2890 | 35040 | End-to-end Service Level tracing for IMS | - | 3 | Rel-7 | S5 | 2005-11-11 08:00 | 2007-03-15 17:00 | 100% | SP-050627 | - | Vodafone | - | 07/2005: OMA (Stage 1), Stage 2/3 SA5, CT1/3/4 | 32.101, 32.421, 32.422, 32.423
2891 | 35062 | Trace record content for UTRAN TDD | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050628 | - | Nokia | - | - | 32.421, 32.422, 32.423
2892 | 35063 | IRP for Subscriber and Equipment Trace Management | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050629 | - | Nokia | - | - | 32.441, 32.442, 32.443, 32.445, 32.632, 32.633, 32.635
2893 | 11046 | Deleted - SIP enhancements for trace | - | 3 | Rel-7 | C1 | 2007-06-15 17:00 | 2007-06-26 15:53 | 100% | - | - | - | - | combined with UID 11067 | -
2894 | 35070 | Deleted - duplicated with UID 35063 - IRP for Subscriber and Equipment Trace Management | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-15 17:00 | 100% | SP-050629 | - | Nokia | - | - | 32.421,32.422,32.423. 3 new 32.4x1,2,3
2895 | 320007 | Rel-7 Charging Management small Enhancements | CH7 | 1 | Rel-7 | S5 | 2006-05-22 08:00 | 2007-06-14 17:00 | 100% | - | - | Orange | alain.bibas@orange-ft.com | CH7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI | TR 30.817
2896 | 320008 | Alternate Charged Party (ACP) for IMS | CH7-IMS-ACP | 2 | Rel-7 | S5 | 2006-05-22 08:00 | 2007-06-14 17:00 | 100% | SP-060442 | - | Lucent | njmazzarella@alcatel-lucent.com | - | 32.240, 32.260, 32.298, 32.299
2897 | 330004 | Align 3GPP Charging with OMA PoC Enabler Release 2.0 | CH7-PoC | 2 | Rel-7 | S5 | 2006-09-28 08:00 | 2007-06-14 17:00 | 100% | SP-060546 | - | Siemens | Gerald.Goermer@nsn.com | 09/2006 SP#33 WID approved | 32.240, 32.272, 32.299, 32.298
2898 | 2468 | Multiple-Input Multiple-Output (MIMO) antennas | MIMO | 1 | Rel-7 | R1,R5 | 2003-03-14 08:00 | 2008-03-07 17:00 | 100% | RP-030192 | - | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037and RP-070531 | 25.876, 25.996
2899 | 21006 | MIMO - Physical layer | MIMO-Phys | 2 | Rel-7 | R1 | 2003-09-12 08:00 | 2007-03-15 17:00 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037 | 25.211, 25.212, 25.213, 25.214, 25.215, 25.221
2900 | 22003 | MIMO - Layer 2,3 aspects | MIMO-L23 | 2 | Rel-7 | R2 | 2003-09-12 08:00 | 2007-03-15 17:00 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037 | 25.876
2901 | 23008 | MIMO - Iub/Iur Protocol Aspects | MIMO-IurIub | 2 | Rel-7 | R3 | 2003-03-14 08:00 | 2007-03-15 17:00 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037 | -
2902 | 24008 | MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing | MIMO-RF | 2 | Rel-7 | R4 | 2003-12-12 08:00 | 2007-09-17 17:00 | 100% | RP-030192 | RP-070531 | Alcatel-Lucent | ngm@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070531 | -
2903 | 25036 | UE Conformance Testing for Multiple Input Multiple Output antennas (MIMO) | MIMO-UEConTest | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-03-07 17:00 | 100% | - | - | Qualcomm | svora@qualcomm.com | BB place holder for a number of RAN5 Tasks | -
2904 | 25037 | Conformance Test Aspects – Multiple Input Multiple Output Antennas (MIMO) for FDD | MIMO-UEConTest_FDD | 3 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-03-07 17:00 | 100% | - | - | Qualcomm | svora@qualcomm.com | - | TS 34.108, TS 34.109, TS 34.121-1, TS 34.121-2, TS 34.123-1, TS 34.123-2, TS 34.123-3
2905 | 20028 | Rel-7 Improvements of the Radio Interface | - | 1 | Rel-7 | RP,GP | 2004-09-15 08:00 | 2007-06-04 17:00 | 100% | - | - | - | - | Generic feature | -
2906 | 20060 | Extended UMTS 1.7/2.1 GHz | RInImp-UMTS1721Ext | 2 | Rel-7 | R4 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060180 | RP-060681 | Ericsson | johan.skold@ericsson.com | RP#34 completed. Introduction of Band X (Extended UMTS 1.7/2.1 GHz) in 25.307 | 25.806, 25.101, 25.104, 25.133, 24.141, 25.331, 25.306, 25.307, 25.423, 25.461, 25.463, 34.121
2907 | 20067 | UMTS 2.6 GHz 7.68 Mcps TDD | RInImp-UMTS26VHCRTDD | 2 | Rel-7 | R4 | 2006-06-15 08:00 | 2006-09-15 17:00 | 100% | RP-060349 | RP-060451 | IPWireless | Shin Horng Wong (shwong@ipwireless.com) | RP#33 completed | 25.102, 25.105, 25.123, 25.113, 25.142, 34.124
2908 | 20021 | UMTS 2.6 GHz | RInImp-UMTS2600 | 2 | Rel-7 | R4 | 2004-09-15 08:00 | 2005-06-14 17:00 | 100% | RP-040397 | RP-050184 | Nokia | jussi.numminen@nokia.com | RP#28 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121
2909 | 20025 | UMTS 2.6 GHz TDD | RInImp-UMTS2600TDD | 2 | Rel-7 | R4 | 2004-12-15 08:00 | 2005-12-14 17:00 | 100% | RP-040553 | RP-050661 | IPWireless | Shin Horng Wong (shwong@ipwireless.com) | RP#30 completed | 25.102, 25.105, 25.113, 25.123, 25.142, 25.331, 25.942, 25.306, 25.307, 34.122, 34.124
2910 | 20027 | UMTS 900 MHz | RInImp-UMTS900 | 2 | Rel-7 | R4 | 2004-12-15 08:00 | 2005-12-14 17:00 | 100% | RP-040541 | RP-050662 | Nortel | Yannick Li (yli@nortelnetworks.com) | RP#30 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121
2911 | 20043 | UMTS 1700 MHz | RInImp-UMTS1700 | 2 | Rel-7 | R4 | 2005-03-15 08:00 | 2005-12-14 17:00 | 100% | RP-050385 | RP-050824 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#30 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 34.121
2912 | 20024 | UE Antenna Performance Evaluation Method and Requirements | RInImp-UEAnt | 2 | Rel-7 | R4,GP | 2004-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-050122 | RP-070281 | TeliaSonera | Christian.Bergljung@TeliaSonera.com | RP#36 completed | 25.101, new TR (25.914, 25.963)
2913 | 20045 | Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2) | RInImp-HSPerf-Type3 | 2 | Rel-7 | R4 | 2005-03-15 | 2005-03-15 | 100% | RP-050362 | RP-060015 | Cingular | Marc Grant | RP#27 completed | 25.101
2914 | 20062 | Additional minimum UE performance requirement for non-HSDPA channels based on type 1 enhanced receiver (Rx Diversity) | RInImp-RxDiv | 2 | Rel-7 | R4 | 2005-09-15 08:00 | 2006-12-15 17:00 | 100% | - | - | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | - | 25.101
2915 | 20048 | Additional minimum UE performance requirement for DL physical channels in support of DCH/HS-DSCH operation based on type 1 enhanced receiver (RX-Diversity) | RInImp-RxDiv-DCH | 3 | Rel-7 | R4 | 2005-09-15 08:00 | 2006-06-14 17:00 | 100% | RP-060185 | RP-060235 | Cingular | Marc Grant | RP#32 completed | 25.101
2916 | 7028 | Additional minimum UE performance requirement for downlink physical channels in support of MTCH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-RxDiv-MBMS | 3 | Rel-7 | R4 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060183 | RP-060678 | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | RP#34 completed | 25.101
2917 | 7029 | Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-RxDiv-EDCH | 3 | Rel-7 | R4 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060184 | RP-060679 | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | RP#34 completed | 25.101
2918 | 20049 | Deleted Improved support of gaming over HSDPA/EDCH | RInImp-Gaming | 2 | Rel-7 | R2 | 2005-12-15 08:00 | 2006-12-15 17:00 | 100% | - | RP-060680 | Cingular | Don Zelmer (dz1069@att.com) | RP#34 stopped. SR in RP-060680 | -
2919 | 20047 | Deleted (not approved at PCG) - UMTS 2.6 GHz FDD DL External | RInImp-UMTS2600Ext | 2 | Rel-7 | R4 | 2005-09-15 08:00 | 2005-09-15 08:00 | 100% | - | - | T-mobile | han.van.bussel@t-mobile.de | This item was conditionnaly approved pending decision of PCG#16 who decided not to approve it | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121
2920 | 25025 | Rel-7 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-7 | R5 | 2005-11-11 08:00 | 2008-09-12 17:00 | 100% | - | - | - | - | Linked to Feature UID_20028 (RInImp) | -
2921 | 25007 | UE Conformance Test for UMTS 2600 MHz | RInImp-UMTS2600_Test | 2 | Rel-7 | R5 | 2005-11-11 08:00 | 2006-06-02 17:00 | 100% | - | - | Nokia | Aleksi.Heino@nokia.com | RP#32 completed | 34.108, 34.121
2922 | 25008 | UE Conformance Test for UMTS 900 MHz (band VIII) | RInImp-UMTS900_Test | 2 | Rel-7 | R5 | 2005-11-11 08:00 | 2006-06-02 17:00 | 100% | - | - | Qualcomm | hanye@qualcomm.com | RP#32 completed | 34.108, 34.121
2923 | 25013 | Conformance Test Aspects – Improved Performance of HSDPA Receiver type 3 | RInImp-HSPerf-Type3_Test | 2 | Rel-7 | R5 | 2006-03-10 08:00 | 2006-12-01 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | RP#34 completed | 34.121, 34.108
2924 | 25020 | UE antenna Over The Air (OTA) conformance testing | RInImp-UEAnt_Test | 2 | Rel-7 | R5 | 2006-09-20 08:00 | 2008-09-12 17:00 | 100% | RP-060486 | RP-080535 | Nokia | Aleksi.Heino@nokia.com | RP#41 completed (GERAN aspects might need to be included later) | 34.114
2925 | 25015 | UE conformance testing for FDD Inter-Band Operation | RInImp-InterBand_Test | 2 | Rel-7 | R5 | 2006-06-02 08:00 | 2006-12-01 17:00 | 100% | - | - | NEC, Motorola | Jacob.John@motorola.com | RP#34 completed | 34.108, 34.123-1, 34.123-2, 34.123-3
2926 | 25028 | Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz | RInImp-UEConTest_UMTS1721Ext | 2 | Rel-7 | R5 | 2006-12-01 08:00 | 2007-06-01 17:00 | 100% | RP-060676 | RP-070312 | Motorola | carolyn.taylor@motorola.com | RP#36 completed | 34.108, 34.121-1, 34.121-2
2927 | 25039 | Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-UEConTest_RxDivEDCH | 2 | Rel-7 | R5 | 2007-06-01 08:00 | 2007-12-07 17:00 | 100% | RP-070414 | RP-070810 | Motorola | carolyn.taylor@motorola.com | RP#38 completed | -
2928 | 25040 | Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of MTCGH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-UEConTest_RxDivMBMS | 2 | Rel-7 | R5 | 2007-06-01 08:00 | 2008-03-07 17:00 | 100% | RP-070381 | RP-080056 | Ericsson | leif.mattisson@ericsson.com | RP#39 completed | 34.121-1, 34.121-2
2929 | 20029 | Rel-7 RAN improvements | - | 1 | Rel-7 | RP,S5 | 2004-12-15 | 2007-06-15 17:00 | 100% | - | - | - | - | Generic feature | -
2930 | 20026 | Optimization of channelisation code utilisation for 1.28 Mcps TDD | RANimp-RABSE-CodOptLCRTDD | 2 | Rel-7 | R1 | 2004-12-15 | 2006-12-15 17:00 | 100% | RP-040552 | RP-060682 | UTStarcom | Ka Leong Lo (kaleong.lo@UTSTAR.COM) | RP#34 completed | -
2931 | 20031 | Delay optimization for procedures applicable to CS and PS Connections | RANimp-DelayOpt | 2 | Rel-7 | R2 | 2005-03-15 08:00 | 2006-09-15 17:00 | 100% | RP-050386 | RP-060453 | Nokia | juho.pirskanen@nokia.com | RP#33 completed | 25.815, 25.321, 25.322, 25.331
2932 | 20132 | Improved support of IMS Realtime Services using HSDPA/HSUPA | RANimp-IMSRealTime | 2 | Rel-7 | R2 | 2005-03-15 | 2005-12-14 17:00 | 100% | RP-050160 | RP-050667 | Cingular | Don Zelmer (dz1069@att.com) | RP#30 completed | -
2933 | 20033 | UE Performance Requirements for MBMS (TDD) | MBMS-RAN-RF-TDD | 2 | Rel-7 | R4 | 2005-03-15 08:00 | 2006-06-15 17:00 | 100% | RP-050156 | RP-060477 | IPwireless | shwong@ipwireless.com | RP#32 completed | 25.102, 25.123
2934 | 20046 | Continuous connectivity for packet data users | RANimp-CPC | 2 | Rel-7 | R1 | 2005-03-14 08:00 | 2007-03-15 17:00 | 100% | RP-050870 | RP-070033 | Siemens | Joern.Krause@siemens.com | RP#35 completed | 25.903, 25.201, 25.211, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433, 25.101, 25.133
2935 | 7030 | Extended WCDMA Cell Range | RANimp-ExtCell | 2 | Rel-7 | R3 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060212 | RP-060685 | Ericsson | Muhammad Kazmi | RP#34 completed | 25.133, 25.423, 25.425, 25.433, 25.435, 25.453, 25.331
2936 | 7031 | 7.68 Mcps TDD Enhanced Uplink | RANimp-VHCRTDD-EDCH | 2 | Rel-7 | R1 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | nanderson@ipwireless.com | RP#34 completed | 25.201, 25.202, 25.221, 25.222, 25.223, 25.224, 25.225, 25.331, 23.321, 25.306, 25.302, 25.401, 25.420, 25.423, 25.427, 25.433, 25.102, 25.105, 25.142
2937 | 330009 | Enhanced CELL_FACH State in FDD | RANimp-EnhState | 2 | Rel-7 | R2 | 2006-09-25 08:00 | 2007-06-04 17:00 | 100% | RP-070245 | RP-070286 | Nokia | juho.pirskanen@nokia.com | RP#36 completed | 25.308, 25.304, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425,
2938 | 340038 | 64QAM for HSDPA (FDD) | RANimp-64QamDownlink | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070223 | RP-070287 | Ericsson | Johan.Bergman@ericsson.com | RP#36 completed | 25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141
2939 | 340039 | Improved L2 support for high data rates | RANimp-L2DataRates | 2 | Rel-7 | R2 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070242 | RP-070289 | Ericsson | Janne.Peisa@ericsson.com | RP#36 completed | 25.301, 25.308,25.306, 25.321, 25.322, 25.331, 25.433, 25.435, 25.423, 25.425, 25.999
2940 | 340040 | Introduction of 16QAM in HSUPA (FDD) | RANimp-16QamUplink | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-060844 | RP-070288 | Nokia | Karri.Ranta-aho@nsn.com | RP#36 completed | 25.319, 25.101, 25.104, 25.133, 25.141, 25.211, 25.212, 25.213, 25.214, 25.306, 25.321, 25.331, 25.423, 25.433
2941 | 20066 | Interface to control Tower Mounted Amplifiers (TMAs) | RANImp-TMA | 2 | Rel-7 | R3,S5 | 2006-06-02 08:00 | 2007-06-15 17:00 | 100% | RP-060418 | RP-070140 | Vodafone | alexej.kulakov@vodafone.com | RP#35 completed | -
2942 | 20166 | RAN3 part of Interface to control Tower Mounted Amplifiers (TMAs) | - | 3 | Rel-7 | R3 | 2006-06-02 08:00 | 2007-03-16 17:00 | 100% | RP-060418 | RP-070140 | Vodafone | alexej.kulakov@vodafone.com | RP#35 completed | -
2943 | 340045 | OAM aspects to Interface to control TMAs | RANImp-TMA-OAM | 3 | Rel-7 | S5 | 2007-01-26 08:00 | 2007-06-15 17:00 | 100% | - | - | Vodafone | Adrian.Neal@vodafone.com | SP#36 completed | 32.642, 32.643, 32.645 – Align with RAN 25.466
2944 | 25026 | Rel-7 RAN improvements - UE Conformance Testing | - | 1 | Rel-7 | R5 | 2006-09-20 08:00 | 2009-09-18 17:00 | 100% | - | - | - | - | Linked to Feature UID_20029 (RANimp) | -
2945 | 25021 | Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink | RANimp-UEConTest_EDCHTDH | 2 | Rel-7 | R5 | 2006-09-20 08:00 | 2008-09-12 17:00 | 100% | RP-060484 | RP-080536 | IPWireless | tspeight@ipwireless.com | RP#41 completed | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
2946 | 25031 | Conformance Test Aspects – 64QAM for HSDPA (FDD) | RANimp-UEConTest_64QamDownlink | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-03-03 17:00 | 100% | RP-071319 | RP-080059 | Ericsson | leif.mattisson@ericsson.com | RP#39 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2947 | 25032 | Conformance Test Aspects – 16QAM for HSUPA (FDD) | RANimp-UEConTest_16QamUplink | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-05-30 17:00 | 100% | RP-070022 | RP-080281 | Motorola | carolyn.taylor@motorola.com | RP#40 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2948 | 25033 | Conformance Test Aspects – Improved L2 support for high data rates | RANimp-UEConTest_L2DataRates | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-05-30 17:00 | 100% | RP-070020 | RP-080256 | Ericsson | leif.mattisson@ericsson.com | RP#40 completed | 34.108, 34.123-1, 34.123-2, 34.123-3
2949 | 25034 | Conformance Test Aspects – Continuous connectivity for packet data users | RANimp-UEConTest_CPC | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-05-30 17:00 | 100% | RP-070023 | RP-080282 | Nokia | jarkko.hellsten@nokia.com | RP#40 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3
2950 | 25035 | Conformance Test Aspects – Enhanced CELL_FACH state in FDD | RANimp-UEConTest_EnhancedCellFACHState | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2009-09-18 17:00 | 100% | RP-080730 | RP-090711 | Nokia | jarkko.hellsten@nokia.com | RP#45 completed | 34.108, 34.123-1, 34.123-2, 34.123-3
2951 | 20014 | 7.68 Mcps TDD option | VHCRTDD | 1 | Rel-7 | R1,R2,R3,R4,R5 | 2004-09-15 08:00 | 2007-09-14 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | -
2952 | 20015 | VHCRTDD: Stage 2 | VHCRTDD-Stage2 | 2 | Rel-7 | R1 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | 25.202
2953 | 20016 | VHCRTDD: Physical Layer | VHCRTDD-Phys | 2 | Rel-7 | R1 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | 25.221, 25.222, 25.223, 25.224,25.225
2954 | 20017 | VHCRTDD: Layer 2 and layer 3 protocol aspects | VHCRTDD-L23 | 2 | Rel-7 | R2 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | drichards@ipwireless.com | RP#31 completed | 25.301, 25.302, 25.305, 25.306, 25.321, 25.331
2955 | 20018 | VHCRTDD: UTRAN Iub/Iur Protocol Aspects | VHCRTDD-IurIub | 2 | Rel-7 | R3 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Peter Legg (plegg@ipwireless.com) | RP#31 completed | 25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435
2956 | 20019 | VHCRTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | VHCRTDD-RF | 2 | Rel-7 | R4 | 2004-09-15 08:00 | 2006-06-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Shin Horng Wong (shwong@ipwireless.com) | RP#32 completed | 25.102, 25.105, 25.123, 25.133, 25.142
2957 | 25027 | Conformance Test Aspects - 7.68 Mcps TDD | VHCRTDD-UEConTest | 2 | Rel-7 | R5 | 2006-09-20 08:00 | 2007-09-14 17:00 | 100% | RP-060482 | RP-070307 | IPWireless | tspeight@ipwireless.com | RP#37 completed | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
2958 | 20035 | 3.84 Mcps TDD Enhanced Uplink | EDCHTDD | 1 | Rel-7 | RP | 2005-03-15 | 2006-09-15 17:00 | 100% | RP-050100 | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | -
2959 | 20036 | EDCHTDD: Stage 2 | EDCHTDD-Stage2 | 2 | Rel-7 | R2 | 2005-03-15 | 2006-06-15 17:00 | 100% | - | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | -
2960 | 20037 | EDCHTDD: Physical Layer | EDCHTDD-Phys | 2 | Rel-7 | R1 | 2005-03-15 | 2006-09-15 17:00 | 100% | - | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | 25.201, 25.221,25.222, 25.223, 25.224, 25.225
2961 | 20038 | EDCHTDD: Layer 2 and 3 Protocol Aspects | EDCHTDD-L23 | 2 | Rel-7 | R2 | 2005-03-15 | 2006-09-15 17:00 | 100% | - | RP-060462 | IPwireless | drichards@ipwireless.com | RP#33 completed | 25.301, 25.302, 25.306, 25.321, 25.331
2962 | 20039 | EDCHTDD: UTRAN Iub/Iur Protocol Aspects | EDCHTDD-IurIub | 2 | Rel-7 | R3 | 2005-03-15 | 2006-09-15 17:00 | 100% | - | RP-060462 | Interdigital | jim.miller@interdigital.com | RP#33 completed | 25.401, 25.420, 25.423, 25.427, 25.430, 25.433, 25.435
2963 | 20040 | EDCHTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | EDCHTDD-RF | 2 | Rel-7 | R4 | 2005-03-15 08:00 | 2006-09-15 17:00 | 100% | - | RP-060462 | IPwireless | Shin Horng Wong (shwong@ipwireless.com) | RP#33 completed | 25.102, 25.105, 25.123, 25.142
2964 | 20055 | 1.28 Mcps TDD Enhanced Uplink | LCRTDD-EDCH | 1 | Rel-7 | R1,R2,R3,R4,R5 | 2006-03-15 08:00 | 2008-09-12 17:00 | 100% | RP-060202 | RP-070296 | CATT | Haijing Hu | RP#35 completed | -
2965 | 20056 | 1.28 Mcps TDD Enhanced Uplink: Physical Layer | LCRTDD-EDCH-Phys | 2 | Rel-7 | R1 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | - | RP-070038 | CATT | Ke Wang | RP#35 completed | 25.201, 25.221, 25.222, 25.223, 25.224, 25.225
2966 | 20057 | 1.28 Mcps TDD Enhanced Uplink: Layer 2 and 3 Protocol Aspects | LCRTDD-EDCH-L23 | 2 | Rel-7 | R2 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | - | RP-070038 | CATT | Haiyang Quan | RP#35 completed | 25.301, 25.302, 25.306, 25.321, 25.331
2967 | 20058 | 1.28 Mcps TDD Enhanced Uplink: UTRAN Iub/Iur Protocol Aspects | LCRTDD-EDCH-IubIur | 2 | Rel-7 | R3 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | - | RP-070038 | CATT | Yincheng Zhang | RP#35 completed | 25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435
2968 | 20059 | 1.28 Mcps TDD Enhanced Uplink: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | LCRTDD-EDCH-RF | 2 | Rel-7 | R4 | 2006-03-15 08:00 | 2007-06-15 17:00 | 100% | - | RP-070296 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#36 completed | 25.102, 25.105, 25.123, 25.142
2969 | 350146 | 1.28 Mcps TDD Enhanced Uplink - UE Conformance Testing | LCRTDD-EDCH-UEConTest | 2 | Rel-7 | R5 | 2007-09-20 08:00 | 2008-09-12 17:00 | 100% | RP-070724 | RP-080539 | CATT | chenxiaozhong@datangmobile.cn | RP#41 completed | 34.108, 34.122, 34.123-1/2/3
2970 | 490016 | Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD | LCRTDD_MB_MF_UEConTest | 1 | Rel-7 | R5 | 2010-09-17 08:00 | 2011-09-16 17:00 | 100% | RP-100805 | RP-110968 | CATR | Ms Jun Chen (chenjun@catr.cn) | RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD. | UTRA 34.108, 34.123-1, 34.123-2, 34.123-3
2971 | 50118 | MS Antenna Performance Evaluation Method and Requirements | APEMR | 1 | Rel-7 | GP | 2005-01-28 08:00 | 2007-11-16 17:00 | 100% | GP-050284 | - | TeliaSonera | Ulf.Tegth@teliasonera.com | GP#36 completed for R7 | 25.914, 25.144, 45.005
2972 | 50119 | Lower 700 MHz Inclusion in the GERAN Specifications | GSM710 | 1 | Rel-7 | GP | 2005-01-03 08:00 | 2006-06-30 17:00 | 99% | GP-050543 | - | UTC | dcotton@mtview.union-tel.com | - | -
2973 | 51138 | Inclusion of the 698 – 746 MHz band into GERAN core specifications | GSM710-core | 2 | Rel-7 | G1 | 2005-01-03 08:00 | 2005-06-30 17:00 | 100% | - | - | - | - | Completed | 24.008, 43.022, 44.018, 44.118, 45, 001, 45.005,
2974 | 53184 | Aspects of GSM710 | GSM-710-test | 2 | Rel-7 | G1,G3new | 2005-08-31 13:00 | 2006-06-30 17:00 | 100% | - | - | - | - | - | -
2975 | 53084 | G1 aspects of GSM710 | - | 3 | Rel-7 | G1 | 2005-08-31 13:00 | 2006-06-30 17:00 | 100% | - | - | - | - | - | 51.021
2976 | 55094 | G3 aspects of GSM710 | - | 3 | Rel-7 | G3new | 2005-08-31 13:00 | 2006-06-30 17:00 | 100% | - | - | - | - | - | 51.010
2977 | 50564 | Support of Conversational Services in A/Gb mode via the PS domain | SCSAGB | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-061501 | - | Ericsson | gunnar.hedby@ericsson.com | Originally started Nov. 2003 as GP-030443 | -
2978 | 52143 | Minimise the transfer delay between the SGSN and the MS | SCSAGB-MTD | 2 | Rel-7 | GP | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-061501 | - | Ericsson | gunnar.hedby@ericsson.com | - | -
2979 | 51137 | Definition of radio resource management functionality for Support of Conversational Services in A/Gb mode via the PS domain | SCSAGB-RRM | 2 | Rel-7 | G1 | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-061502 | - | Ericsson | gunnar.hedby@ericsson.com | - | -
2980 | 52144 | Support of Conversational Services in A/Gb mode via the PS domain – RLC Non-Persistent mode | SCSAGB-RLCNP | 2 | Rel-7 | G2 | 2006-06-30 08:00 | 2006-11-17 17:00 | 100% | GP-061503 | - | Ericsson | gunnar.hedby@ericsson.com | - | 43.955, 43.064, 44.060, 45.001, 45.002, 45.003, 45.005, 45.010, 51.010, 51.021
2981 | 52138 | Deleted- Radio Channel Support | SCSAGB-RCHS | 2 | Rel-7 | G2 | 2006-07-17 17:00 | 2006-07-17 17:00 | 100% | GP-051166 | - | Ericsson | gunnar.hedby@ericsson.com | - | -
2982 | 52139 | Deleted- Modifications to FLO | SCSAGB-FLO | 2 | Rel-7 | G2 | 2006-07-17 17:00 | 2006-07-17 17:00 | 100% | GP-051165 | - | Ericsson | gunnar.hedby@ericsson.com | - | -
2983 | 50565 | Addition of new frequency band to GSM (T-GSM810) | TGSM810 | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-050945 | - | Huawei | chende@huawei.com | - | 45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060, 51.010-1, 51.021
2984 | 50566 | Changes to core specification | TGSM810-Core | 2 | Rel-7 | GP | 2005-04-08 08:00 | 2005-09-02 17:00 | 100% | GP-050946 | - | Huawei | chende@huawei.com | - | 45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060
2985 | 55092 | Changes to MS testing specification | TGSM810-MStest | 2 | Rel-7 | G3new | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-050947 | - | Huawei | chende@huawei.com | - | 51010-1
2986 | 53082 | Changes to BTS testing specification | TGSM810-BTStest | 2 | Rel-7 | G1 | 2005-04-08 08:00 | 2005-11-11 17:00 | 100% | GP-050948 | - | Huawei | chende@huawei.com | - | 51021
2987 | 50567 | Handover of dedicated and shared resources while in Dual Transfer Mode | HODSRDTM | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2006-11-17 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | GP#30 completed. Started at GP#24 | -
2988 | 55093 | GERAN2 part of Handover of dedicated and shared resources while in Dual Transfer Mode | HODSRDTM-G2 | 2 | Rel-7 | G2 | 2005-04-08 08:00 | 2006-06-30 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | GP#30 completed | 43.055, 44.018, 44.060
2989 | 55095 | Deleted - MS Conformance Testing | HODSRDTM-MStest | 2 | Rel-7 | G3new | 2005-04-08 08:00 | 2006-11-17 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | Stopped, no work done. 12/2008 Marked as stopped ("deleted") | 51-010
2990 | 53083 | Deleted - BTS conformance testing | HODSRDTM-BTStest | 2 | Rel-7 | G1 | 2005-04-08 08:00 | 2006-11-17 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | Stopped, no work done. 12/2008 Marked as stopped ("deleted") | 51.026
2991 | 50569 | Mobile Station Receive Diversity (DARP Phase II) | MSRD2 | 1 | Rel-7 | GP | 2005-11-11 08:00 | 2007-11-16 17:00 | 100% | GP-061491 | - | Nokia | kent.pedersen@nokia.com | GP#36 completed | -
2992 | 50571 | Performance Requirements for Mobile Station Receive Diversity, DARP Phase II | MSRD2-PerfReq | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-02-16 17:00 | 100% | GP-060115 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 45.005
2993 | 50572 | Capability signalling of Mobile Station Receive Diversity, DARP Phase II | MSRD2-CapSig | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-02-16 17:00 | 100% | GP-060116 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 24.008
2994 | 50573 | Test Scenarios for Mobile Station Receive Diversity, DARP Phase II | MSRD2-TestSc | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-02-16 17:00 | 100% | GP-060117 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 45.005
2995 | 50570 | MS conformance test of DARP Phase II (MSRD) | MSRD2-Msconf | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-11-16 17:00 | 100% | GP-060114 | - | Nokia | kent.pedersen@nokia.com | GP#36 completed | 51.010
2996 | 50579 | Downlink Dual Carrier | GDCDL | 1 | Rel-7 | GP | 2006-01-20 08:00 | 2009-09-04 17:00 | 100% | GP-061331 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#35 completed | -
2997 | 51139 | Downlink Dual Carrier Stage 2 | GDCDL-Stage2 | 2 | Rel-7 | G1 | 2006-01-20 08:00 | 2006-06-30 17:00 | 100% | GP-060484 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#30 completed | 43.055, 43.064
2998 | 52142 | Downlink Dual Carrier Stage 3 | GDCDL-Stage3 | 2 | Rel-7 | G1 | 2006-01-20 08:00 | 2007-08-31 17:00 | 100% | GP-060485 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#35 completed | 24.008, 44.018, 44.060, 45.001, 45.002, 45.005, 45.008
2999 | 53086 | Downlink Dual Carrier – MS Conformance Test | GDCDL-MStest | 2 | Rel-7 | G3new | 2006-01-20 08:00 | 2009-09-04 17:00 | 100% | GP-060486 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#43 completed | 51.010
3000 | 50580 | Support of SIGTRAN in GERAN | GSIGT | 1 | Rel-7 | GP | 2006-01-20 08:00 | 2006-06-30 17:00 | 100% | GP-060450 | - | Ericsson | peter.ostrup@ericsson.com | GP#30 completed | 48.001, 48.006, 43.059, 49.031
3001 | 50582 | Latency Reductions | LATRED | 1 | Rel-7 | GP | 2006-06-30 08:00 | 2007-08-31 17:00 | 100% | GP-061519 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021
3002 | 52145 | Improved Ack/Nack reporting | LATRED-ACKNAR | 2 | Rel-7 | G2 | 2006-06-30 08:00 | 2007-08-31 17:00 | 100% | GP-061520 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021
3003 | 52146 | Reduced TTI | LATRED-REDTTI | 2 | Rel-7 | G2 | 2006-06-30 08:00 | 2007-08-31 17:00 | 100% | GP-061521 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021
3004 | 52147 | PS Handover between GERAN/UTRAN mode and GAN Mode | GUGAN | 1 | Rel-7 | G2 | 2006-06-30 08:00 | 2007-02-16 17:00 | 100% | GP-061349 | - | Ericsson | John.Diachina@Ericsson.com | GP#33 completed | 43.318, 44.318, 43.129, 25.306, 24.008, 44.060, 25.331, 51.010
3005 | 50584 | Higher Uplink performance for GERAN Evolution | HUGE | 1 | Rel-7 | GP | 2006-09-08 08:00 | 2011-05-20 17:00 | 100% | GP-071083 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#39 completed | -
3006 | 51140 | Stage 2 for HUGE | HUGE-Stage2 | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2007-09-07 17:00 | 100% | GP-061902 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#35 completed | 43.055, 43.064
3007 | 51141 | Layer 1 Support for HUGE | HUGE-Layer1 | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2008-02-22 17:00 | 100% | GP-061903 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#37 completed | 45.001, 45.002, 45.003, 45.004, 45.008
3008 | 52149 | Layer 2/3 Support for HUGE | HUGE-Layer23 | 2 | Rel-7 | G2 | 2006-09-08 08:00 | 2007-08-31 17:00 | 100% | GP-061904 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#35 completed | 24.008, 44.018, 44.060
3009 | 51142 | Performance requirements for HUGE | HUGE-Perfreq | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2008-08-29 17:00 | 100% | GP-061905 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#39 completed | 45.005
3010 | 51143 | BTS Conformance Test for HUGE | HUGE-BTStest | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2009-09-04 17:00 | 100% | GP-061907 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#43 completed | 51.021
3011 | 53087 | MS Conformance Test for HUGE | HUGE-Mstest | 2 | Rel-7 | G3new | 2006-09-08 08:00 | 2011-05-20 17:00 | 100% | GP-061906 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#50 completed | 51.010
3012 | 50121 | REduced symbol Duration, Higher Order modulation and Turbo coding (RED HOT) for downlink | REDHOT | 1 | Rel-7 | GP | 2006-11-17 08:00 | 2011-05-20 17:00 | 100% | GP-071080 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#38 completed | -
3013 | 51144 | Stage 2 for REDHOT | REDHOT-Stage2 | 2 | Rel-7 | G1 | 2006-11-17 08:00 | 2007-08-31 17:00 | 100% | GP-062489 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#35 completed | 43.055, 43.064
3014 | 51145 | Stage 3 for REDHOT | REDHOT-Stage3 | 2 | Rel-7 | G1 | 2006-11-17 08:00 | 2008-05-16 17:00 | 100% | GP-062490 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#38 completed | 24.008, 44.018, 44.060, 45.001, 45.002, 45.003, 45.004, 45.005, 45.008
3015 | 51146 | BTS Conformance Tests for REDHOT | REDHOT-BTStest | 2 | Rel-7 | G1 | 2006-11-17 08:00 | 2009-05-15 17:00 | 100% | GP-062492 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#42 completed | 51.021
3016 | 53088 | MS Conformance Tests for REDHOT | REDHOT-Mstest | 2 | Rel-7 | G3new | 2006-11-17 08:00 | 2011-05-20 17:00 | 100% | GP-062491 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#50 completed | 51.010
3017 | 60110 | (Small) Technical Enhancements and Improvements for Rel-7 | TEI7 | 1 | Rel-7 | SP,CP,RP,GP | 2007-03-26 17:00 | 2007-03-26 17:00 | 100% | - | - | - | - | - | -
3018 | 25030 | Test - (Small) Technical Enhancements and Improvements for Rel-7 | TEI7_Test | 1 | Rel-7 | R5 | 2006-06-02 08:00 | 2007-11-28 17:00 | 100% | - | - | - | - | - | -
3019 | 32113 | Deleted - PS domain and IMS support for IMS Emergency sessions | IMS-EMER | 1 | Rel-7 | S2 | 2006-06-23 17:00 | 2006-09-21 14:31 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271
3020 | 32114 | Deleted - IMS aspects to support IMS Emergency sessions | - | 2 | Rel-7 | S2 | 2006-06-23 17:00 | 2006-09-21 14:31 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271
3021 | 32115 | Deleted - PS domain aspects to support IMS Emergency sessions | - | 2 | Rel-7 | S2 | 2006-06-23 17:00 | 2006-09-21 14:31 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271
3022 | 32005 | Deleted - IMS Local services | IMSLocal | 1 | Rel-7 | S2 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | - | - | - | 23.228
3023 | 32019 | Deleted - Stage 2 | - | 2 | Rel-7 | S2 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | - | - | DAB - Not yet required in SA2 as it exists in previous releases | -
3024 | 11035 | Deleted - Stage 3 for IMS Local services | - | 2 | Rel-7 | C1 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | -
3025 | 32078 | Deleted - IMS Phase 3 | - | 1 | Rel-7 | S2 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | - | - | - | -
3026 | 701216 | Deleted - Improvements of Radio Interface | - | 1 | Rel-7 | RP | 2004-09-15 08:00 | 2004-09-15 08:00 | 100% | - | - | - | - | Stage 2 description of Interim conclusion | -
3027 | 14018 | Deleted: Generic User Profile Phase 2 | - | 1 | Rel-7 | C4 | 2005-08-08 13:48 | 2006-06-30 17:00 | 100% | - | - | - | - | Created at TSG#27 by A. Sultan because of the move to Rel-7 of "Common Objects". | -
3028 | 42003 | Deleted - Stage 3 - Common objects | - | 1 | Rel-7 | C4 | 2005-08-08 13:48 | 2006-06-30 17:00 | 100% | TP-020275 | - | - | - | No progress in CN4#26. This have to be moved to Rel-7. It was deleted from WID | 24.241
3029 | 0 | Release 7 Studies | - | 1 | Rel-7 | CP,GP,RP,SP | 2004-06-28 08:00 | 2007-09-17 17:00 | 100% | - | - | - | - | - | -
3030 | 31082 | Study on Multimedia Telephony Capabilities for IMS | MITE | 1 | Rel-7 | S1 | 2005-07-11 08:00 | 2006-07-31 17:00 | 100% | SP-050387 | - | Ericsson | peter.bleckert@ericsson.com | Spin-off Feature UID_7038 (MTSI) | 22.973
3031 | 31050 | Study on Behaviour of Multi system UEs | BMSU | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-12-15 17:00 | 100% | SP-050502 | - | Qualcomm | dwilliams@qualcomm.com | - | 22.936
3032 | 31055 | Study on Combining CS calls and IMS sessions | IRTSD-CS_IMS | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-03-17 17:00 | 100% | SP-040467 | - | TeliaSonera | robert.frank@teliasonera.com | - | 22.979
3033 | 31059 | Study on All-IP Network | FS_AIPN | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-03-16 17:00 | 100% | SP-040303 | - | NTT DoCoMo | Shin-ichi Isobe (isobes@nttdocomo.co.jp) | 07/08 Moved to Rel-7 as Study out of stopped Rel-8 Feature UID_31067 All-IP Network (AIPN) | 22.978
3034 | 31075 | Study on Videotelephony teleservice | VidTel | 1 | Rel-7 | S1 | 2005-03-01 08:00 | 2006-01-17 17:00 | 100% | SP-050506 | - | T-Mobile | michael.kurz@t-mobile.at | - | 22.903
3035 | 31073 | Study on Network Selection Principles | NetSel | 1 | Rel-7 | S1 | 2005-03-15 08:00 | 2005-12-08 17:00 | 100% | SP-050227 | - | O2 | chris.friel@O2.com | Spin-off Feature Network selection enhancements (NSP-CR) UID_7041 | 22.811
3036 | 31041 | Study on Multimedia Priority Service | PRIOR-MM | 1 | Rel-7 | S1 | 2003-03-28 08:00 | 2006-06-30 17:00 | 100% | SP-060329 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | Spin-off Feature PRIOR UID_340044 | 22.953 | Public Safety (I-A)
3037 | 31083 | Study on Transferring of emergency Call data | eCALL | 1 | Rel-7 | S1 | 2005-07-11 08:00 | 2006-03-31 17:00 | 100% | SP-050388 | - | Motorola | jian.j.wu@motorola.com | - | 22.967 | Public Safety (I-A)
3038 | 32073 | Study on Enhancement of E2E QoS | QoS7 | 1 | Rel-7 | S2 | 2004-06-28 08:00 | 2005-09-15 17:00 | 100% | SP-040326 | - | Huawei | Robert Jaksa | - | 23.802
3039 | 35066 | Study on SOAP/HTTP IRP Solution Sets | OAM7-NIM-XML | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050610 | - | Nortel | Suzèle Lariven (lariven@nortel.com) | SP#34 completed | 32.809
3040 | 35067 | Study on Itf-N Implementation Conformance Statement (ICS) template | OAM7-NIM-ICS | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050609 | - | China Mobile | Li Yewen (liyewen@chinamobile.com) | SP#35 completed | 32.812
3041 | 35068 | Study on IRP Information Model | OAM7-NIM-IM | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050611 | - | Motorola | trevor.pirt@motorola.com | SP#35 completed | 32.810
3042 | 7034 | Study on Bandwidth Saving at Nb Interface with IP transport | BSNbIP | 1 | Rel-7 | C3 | 2006-03-10 08:00 | 2007-03-09 17:00 | 100% | CP-060438 | - | Siemens | Thomas.Belling@siemens.com | Moved to FS at CT32 (in line with slides) | 29.814
3043 | 14019 | Study on Routeing of MT-SMS via the HPLMN | SMS7 | 1 | Rel-7 | C4 | 2005-10-07 08:00 | 2006-12-01 17:00 | 100% | CP-060701 | - | Vodafone | Nick.Russell@vodafone.com | Previously known as "Study of a SMS Centre for MT SMS" | 23.840
3044 | 7025 | Feasibility Study on the TCAPsec Gateway concept | FS_SEC7-TCAP | 1 | Rel-7 | C4 | 2005-10-28 08:00 | 2006-03-10 17:00 | 100% | CP-050687 | - | Siemens | Ulrich.wiehe@gksag.de | TR 29.800 content moved to TS 29.204 under implementation WI UID_310005 TCAPsec Gateway | 29.800
3045 | 7050 | Study on using M2PA in 3GPP network | FS-M2PA | 1 | Rel-7 | C4 | 2006-03-22 08:00 | 2007-06-08 17:00 | 100% | CP-060698 | - | China Mobile | zhaoyuyi@chinamobile.com | - | 29.801
3046 | 320018 | Study on Support of (G)MSC-S - (G)MSC-S Nc Interface based on the SIP-I protocol | NcSIP | 1 | Rel-7 | C4,C3 | 2006-05-15 08:00 | 2007-09-14 17:00 | 100% | CP-070034 | - | Vodafone | david.hutton@vodafone.com | - | 29.802
3047 | 330002 | CT4 aspects of NcSIP | - | 2 | Rel-7 | C4 | 2006-05-15 08:00 | 2007-06-01 17:00 | 100% | CP-070034 | - | Vodafone | david.hutton@vodafone.com | - | 29.802
3048 | 330003 | CT3 aspects of NcSIP | - | 2 | Rel-7 | C3 | 2006-05-15 08:00 | 2007-09-14 17:00 | 100% | CP-070034 | - | Ericsson | ragnar.huslende@ericsson.com | - | 29.802
3049 | 20023 | Study on Evolved UTRA and UTRAN | RANFS-Evo | 1 | Rel-7 | RP | 2004-12-15 08:00 | 2006-09-15 17:00 | 100% | RP-040461 | RP-060472 | NTT DoCoMo | nakamurata@NTTDOCOMO.CO.JP | RP#33 (Sep 2006) completed. SR in RP-060472 | 25.912
3050 | 20034 | Study on Performance Evaluation of the UE behaviour in high speed trains with speeds up to 350 kmph | RANFS-HSTrains | 1 | Rel-7 | R4 | 2005-03-15 | 2006-06-15 17:00 | 100% | RP-050146 | RP-060412 | Vodafone | Mike.vogel@vodafone.com,tim.frost@vodafone.com | RP#32 (Jun 2006) completed. SR in RP-060412 | none
3051 | 20041 | Study on UTRA Tower Mounted Amplifier (FDD) | RANFS-TMA | 1 | Rel-7 | R4 | 2005-06-15 08:00 | 2006-03-14 17:00 | 100% | RP-050387 | RP-060035 | Ericsson | Klas.Sjerling@ericsson.com | RP#31 (Mar 2006) completed. SR in RP-060035 | 25.818
3052 | 20044 | Study on Continuous connectivity for packet data users | RANFS-cont-packet | 1 | Rel-7 | R1 | 2005-03-15 08:00 | 2005-09-14 17:00 | 100% | RP-050391 | RP-050427 | Siemens | joerg.gustrau@siemens.com | RP#29 (Sep 2006) completed. SR in RP-050427 | none
3053 | 20051 | Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN | RANFS-MBMSImp | 1 | Rel-7 | R2 | 2005-12-15 08:00 | 2006-12-15 17:00 | 100% | RP-050746 | RP-060692 | LG Electronics | leego@lge.com | RP#34 completed | 25.905
3054 | 20052 | Deleted - Study on Performance Improvements in Small Cells using HSDPA/EDCH | SMALLCELLS | 1 | Rel-7 | R1,R4 | 2005-12-15 08:00 | 2006-06-15 17:00 | 100% | RP-050782 | RP-060263 | Cingular | Marc Grant | RP#32 (Jun 2006) stopped at 0% completion | none | Small cell
3055 | 20053 | Study on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD) | RANFS-IC | 1 | Rel-7 | R4 | 2005-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-050880 | RP-070499 | Cingular | Marc Grant | RP#36 (May 2007) completed. SR in RP-070499 | 25.963
3056 | 20065 | Study on Scope of future FDD HSPA Evolution | RANFS-HSPAEvo | 1 | Rel-7 | RP | 2006-03-15 08:00 | 2007-09-17 17:00 | 100% | RP-060217 | RP-070533 | Cingular | Don Zelmer (dz1069@att.com) | RP#37 (Sep 2007) completed. SR in RP-070533 | 25.999
3057 | 330013 | Study on Dynamically reconfiguring a FDD UE receiver to reduce power consumption when desired Quality of Service is met | FSUEPow | 1 | Rel-7 | R4 | 2007-06-22 17:00 | 2007-06-22 17:00 | 100% | RP-060641 | RP-070534 | Nokia | Chris.callender@nokia.com, tiina.s.koskinen@nokia.com | RP#37 (Sep 2007) completed. SR in RP-070534 | 25.906
3058 | 50568 | Study on Future GERAN Evolution | FGE | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2007-02-16 17:00 | 100% | GP-051052 | - | Nokia | eddie.riddington@nokia.com | GP#33 completed | 45.912
3059 | 50120 | Study on GAN Enhancements | EGAN | 1 | Rel-7 | GP | 2007-08-31 17:00 | 2007-08-31 17:00 | 100% | GP-062298 | - | T-Mobile | janne.linkola@t-mobile.com | GP#35 completed | 43.902
3060 | 31054 | Deleted - Study on IMS with real time services deployment | IRTSD | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-09-12 17:00 | 100% | SP-040465 | - | - | - | - | -
3061 | 31077 | Deleted - Covered by SI - Personal Network (PN) and Personal Area Network (PAN) | PNPAN | 1 | Rel-7 | S1 | 2005-12-08 17:00 | 2005-12-20 15:24 | 100% | SP-050386 | - | Vodafone | armin.toepfer@vodafone.com | - | -
3062 | 31087 | Deleted - Study on Customised Alerting Tone (CAT) Requirements (was duplicated) | - | 1 | Rel-7 | S1 | 2006-06-30 17:00 | 2006-06-30 17:00 | 100% | SP-050607 | - | - | - | Awaiting MCC SA3 input | -
3063 | 732028 | Deleted - IMS security extensions (covered by UID33027) | IMS-SE | 1 | Rel-7 | S3 | 2005-12-08 17:00 | 2005-12-08 17:00 | 100% | SP-050395 | - | Ericsson | Bengt.Sahlin@ericsson.com | - | -
3064 | 32029 | Deleted - Study on applicability of GALILEO for LCS | Galileo | 1 | Rel-7 | S2 | 2005-06-30 17:00 | 2005-06-30 17:00 | 100% | SP-020541 | - | - | - | - | -
3065 | 32058 | Deleted - TR on Stage 2 | - | 2 | Rel-7 | S2 | 2005-06-30 17:00 | 2005-06-30 17:00 | 100% | - | - | - | - | - | -
3066 | 50095 | Deleted - GERAN review of the TR | - | 2 | Rel-7 | GP | 2005-06-30 17:00 | 2005-06-30 17:00 | 100% | - | - | - | - | - | -
3067 | 32076 | Deleted - Study on Stage 2 (IMS services using CS bearers) | IRTSD-IMSCS | 1 | Rel-7 | S2 | 2004-06-28 08:00 | 2005-09-12 17:00 | 100% | SP-040479 | - | Nortel | Mark Watson | SP-30: S2 has no intention for TR completion | 23.899
3068 | 32099 | Deleted - VoIMS bearer related enhancements | VoIMS | 1 | Rel-7 | S2 | 2006-07-21 17:00 | 2006-07-21 17:00 | 100% | - | - | - | - | Created by MCC to group all VoIMS related items, after consultation of chairs | -
3069 | 32098 | Deleted - Study on enhancement of radio performance for VoIMS | - | 2 | Rel-7 | S2 | 2006-07-21 17:00 | 2006-07-21 17:00 | 100% | SP-050351 | - | Nortel | Laurence Lautier (lautierl@nortel.com) | WID approved SP#28. SA2#52 stopped | 23.807
3070 | 32112 | Deleted - Study on IMS enhancements and optimizations for real time communication. | IMS-RT | 1 | Rel-7 | S2 | 2005-10-10 08:00 | 2007-06-01 17:00 | 100% | SP-050492 | - | Ericsson | stephen.terrill@ericsson.com | abandoned at 65% | 23.818
3071 | 32117 | Deleted - Study on Terminating Session handling | CSIterm | 1 | Rel-7 | S2 | 2006-01-09 08:00 | 2006-12-29 17:00 | 100% | SP-050811 | - | Samsung | - | SP#32 Jun 2006 Study abandoned => spin-off Implementation work UID_320029 | 23.819
3072 | 34040 | Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) | - | 1 | Rel-7 | S4 | 2007-06-22 17:00 | 2007-06-22 17:00 | 100% | SP-060935 | - | Airbiquity | lhong@airbiquity.com | SP-38 stopped | 26.967 | Public Safety (I-A)
3073 | 35045 | Deleted - Study on IRP usage scenarios | OAM-Study | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050303 | - | Lucent | - | - | 32.8xy
3074 | 360009 | Deleted - Study on Interference Cancellation for UTRA FDD UE (covered by UID 20053) | RANFS-InterfCanc | 1 | Rel-7 | R4 | 2007-03-28 08:00 | 2007-03-28 17:00 | 100% | - | - | - | - | Deleted. Same as FS on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD) | -
3075 | 50552 | Deleted - Study on enhanced support of Video Telephony | VIDGER | 1 | Rel-7 | GP | 2006-06-30 17:00 | 2006-06-30 17:00 | 100% | GP-042221 | - | Ericsson | stefan.g.eriksson@ericsson.com | FS CLOSED at G#28 (no input) | -
3076 | 0 | Release 6 Features | - | 1 | Rel-6 | NP,GP,RP,SP,TP | 2002-06-28 17:00 | 2005-12-30 17:00 | 100% | - | - | - | - | - | -
3077 | 1216 | Rel-6 Improvements of Radio Interface | - | 1 | Rel-6 | R2,R4,R5 | 2000-08-14 08:00 | 2006-12-01 17:00 | 100% | - | - | - | - | - | -
3078 | 20032 | Improved support of IMS Realtime Services using HSDPA/EDCH | RInImp-IMSRealTime | 2 | Rel-6 | R2 | 2005-03-15 | 2005-12-14 17:00 | 100% | - | - | Cingular | Don Zelmer (dz1069@att.com) | - | -
3079 | 24006 | Improving Receiver Performance Requirements for the FDD UE | RInImp-UERecPerf | 2 | Rel-6 | R4 | 2002-03-08 08:00 | 2003-09-19 17:00 | 100% | - | - | Intel | shimon.moshavi@INTEL.COM | - | 25.101
3080 | 24004 | Base station classification for FDD | RInImp-BSClass-FDD | 2 | Rel-6 | R4 | 2000-08-14 08:00 | 2002-12-04 17:00 | 100% | - | - | - | - | - | -
3081 | 1476 | FDD Base station classification | - | 3 | Rel-6 | R4 | 2000-08-14 08:00 | 2002-12-04 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | 25.104, 25.141
3082 | 24007 | UMTS-850 | RInImp-UMTS850 | 2 | Rel-6 | R4 | 2002-12-06 08:00 | 2003-12-12 17:00 | 100% | - | - | Cingular | Don Zelmer (dz1069@att.com) | Introduction of UMTS850 (Band V) in 25.307 | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331, 25.942
3083 | 24009 | DS-CDMA introduction in the 800 MHz band | RInImp-UMTS800 | 2 | Rel-6 | R4 | 2003-03-14 08:00 | 2003-12-12 17:00 | 100% | - | - | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | Introduction of UMTS800 in 25.307 | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331
3084 | 24010 | UMTS 1.7/2.1 GHz | RInImp-UMTS1721 | 2 | Rel-6 | R4 | 2003-03-14 08:00 | 2003-03-14 08:00 | 100% | - | - | Nokia | jussi.numminen@NOKIA.COM | Introduction of UMTS1700/2100 (Band IV) | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331
3085 | 25010 | Conformance Test Aspects – UMTS 1.7/2.1 GHz Band | RInImp-UMTS1721_Test | 2 | Rel-6 | R5 | 2006-03-10 08:00 | 2006-12-01 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | TS34.121, TS34.108
3086 | 24013 | Improved Receiver Performance Requirements for HSDPA | RInImp-HSPerf | 2 | Rel-6 | R4,R5 | 2003-09-19 08:00 | 2006-06-09 17:00 | 100% | - | - | Nokia | jussi.numminen@NOKIA.COM | - | -
3087 | 20011 | Improved Minimum Performance Requirements for HSDPA UE categories 7 and 8 | RInImp-HSPerf-10code | 3 | Rel-6 | R4 | 2004-09-15 | 2006-06-09 17:00 | 100% | - | - | Nokia | jussi.numminen@nokia.com | Approved at RP#25 as RP-040375 | 25.101
3088 | 25001 | Testing of Improved Minimum Performance for HSDPA | RInImp-HSPerf-10Code_Test | 3 | Rel-6 | R5 | 2003-09-19 08:00 | 2006-03-16 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3
3089 | 24014 | Performance Requirements of Receive Diversity for HSDPA | RInImp-HSPerf-RxDiv | 3 | Rel-6 | R4 | 2003-12-15 | 2005-06-07 17:00 | 100% | - | - | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | - | 25.101
3090 | 25002 | Testing of Performance of Receiver diversity for HSDPA | RInImp-HSPerf-RxDiv_Test | 3 | Rel-6 | R5 | 2003-09-19 08:00 | 2006-03-16 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3
3091 | 3 | Rel-6 RAN Feasibility Studies | - | 1 | Rel-6 | RP | 2000-08-14 08:00 | 2005-03-14 17:00 | 100% | - | - | - | - | - | -
3092 | 23007 | FS of the improved access to UE measurement data for CRNC to support TDD RRM | RANimp-RRMopt-FSUEMsD | 2 | Rel-6 | R3 | 2002-12-06 08:00 | 2003-12-18 17:00 | 100% | - | - | Interdigital | jim.miller@interdigital.com | - | 25.801, 25.423
3093 | 1506 | FS on Radio link performance enhancements | RInImp-Rlperf | 2 | Rel-6 | R1 | 2000-08-14 08:00 | 2004-09-14 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | Study finished at RP#25 | 25.899
3094 | 21000 | FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD | RInImp-IfIsMLCR | 2 | Rel-6 | R1 | 2001-12-14 08:00 | 2003-09-19 17:00 | 100% | - | - | Samsung | Li Xiao Qiang (xqli@samsung.co.kr) | - | 25.888
3095 | 21003 | FS for the analysis of OFDM for UTRAN enhancement | RInImp-FSOFDM | 2 | Rel-6 | R1 | 2002-06-10 08:00 | 2004-06-14 17:00 | 100% | - | - | Nortel | Sarah Boumendil | - | 25.892
3096 | 21004 | FS on Uplink Enhancements for Dedicated Transport Channels | RInImp-FSUpDTrCh | 2 | Rel-6 | R1 | 2002-09-06 08:00 | 2004-03-12 17:00 | 100% | - | - | Nokia | Karri.Ranta-aho@nsn.com | - | 25.896
3097 | 21005 | FS on Analysis on Higher Chip Rates for UTRA TDD evolutions | RInImp-FSVHCRTDD | 2 | Rel-6 | R1 | 2002-09-06 08:00 | 2004-09-14 17:00 | 100% | - | - | IPWireless | mbeale@ipwireless.com | Study finished at RP#25 | 25.895
3098 | 24011 | FS on Low Output Powers for general purpose FDD BSs | RInImp-FSLoPw | 2 | Rel-6 | R3 | 2003-06-13 08:00 | 2004-03-12 17:00 | 100% | - | - | Telefónica | Ana Burgos (burgos_a@tsm.es) | - | 25.807
3099 | 21007 | FS on Uplink enhancements for UTRA TDD | RInImp-FSUpEnhTDD | 2 | Rel-6 | R1 | 2003-06-06 08:00 | 2005-03-14 17:00 | 100% | - | - | Interdigital | Marian.Rudolf@InterDigital.com | - | 25.804
3100 | 24005 | FS on UE antenna efficiency test methods performance requirements (2) | RInImp-UEAnTM2 | 2 | Rel-6 | R4 | 2002-03-08 08:00 | 2002-09-06 17:00 | 100% | - | - | Allgon | Alf Ahlström (alf.ahlstrom@pwav.com) | The RInImp-UEAnTM FS was re-opened at TSG RP#15 upon request from WG4 | -
3101 | 23006 | Deleted - FS on the evolution of the UTRAN architecture | RANimp-FSEvo | 2 | Rel-6 | R3 | 2002-09-09 08:00 | 2004-12-14 17:00 | 100% | - | - | Nokia | woonhee.hwang@nsn.com, Antti.Toskala@nokia.com | Study Closed, work will continue within the FS on evolved UTRA and UTRAN | -
3102 | 20003 | FDD Enhanced Uplink | EDCH | 1 | Rel-6 | R2,R1,R3,R4,R5 | 2004-03-15 | 2007-09-14 17:00 | 100% | - | - | Ericsson | Joakim Bergström | - | -
3103 | 20004 | FDD Enhanced Uplink - Stage 2 | EDCH-Stage2 | 2 | Rel-6 | R2 | 2004-03-15 08:00 | 2004-12-14 17:00 | 100% | - | - | - | - | - | 25.309
3104 | 20005 | FDD Enhanced Uplink - Physical Layer | EDCH-Phys | 2 | Rel-6 | R1 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | Nokia | Karri.Ranta-aho@nsn.com | - | 25.211, 25.212, 25.213, 25.214, 25.215
3105 | 20006 | FDD Enhanced Uplink - Layer 2 and 3 Protocol Aspects | EDCH-L23 | 2 | Rel-6 | R2 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | Ericsson | Joakim Bergström | - | 25.301, 25.302, 25.306, 25.321, 25.331
3106 | 20007 | FDD Enhanced Uplink - UTRAN Iub/Iur Protocol Aspects | EDCH-IurIub | 2 | Rel-6 | R3 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | Nortel | Saso Stojanovski | - | 25.401, 25.420, 25.423, 25.430, 25.433
3107 | 20008 | FDD Enhanced Uplink - RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | EDCH-RF | 2 | Rel-6 | R4 | 2004-03-15 | 2004-06-24 17:00 | 100% | - | - | Ericsson | thomas.unshelm@ericsson.com | - | 25.101, 25.104, 25.133, 25.141
3108 | 25003 | Conformance Test Aspects – FDD Enhanced Uplink | EDCH_Test | 2 | Rel-6 | R5 | 2005-06-03 08:00 | 2007-09-14 17:00 | 100% | - | - | Ericsson | Leif.Mattisson@ericsson.com | - | 34.108, 34.109, 34.121, 34.123-1, 34.123-2, 34.123-3
3109 | 9 | Rel-6 RAN improvements | - | 1 | Rel-6 | RP,S5 | 2002-09-09 08:00 | 2005-03-14 17:00 | 100% | - | - | - | - | Generic feature | -
3110 | 624 | RAB support enhancement | - | 2 | Rel-6 | R2 | 2003-03-14 08:00 | 2005-03-14 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | building block without particular end date | 25.862
3111 | 21008 | Optimization of downlink channelisation code utilisation | RANimp-RABSE-CodeOptFDD | 3 | Rel-6 | R1 | 2004-03-12 08:00 | 2005-03-14 17:00 | 100% | - | - | Nortel | Sarah Boumendil | - | -
3112 | 21009 | optimization of channelisation code utilisation for 3.84 Mcps TDD | RANimp-RABSE-CodOptTDD | 3 | Rel-6 | R1 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | IPWireless | Nicholas Anderson | WIDS modified in RP#26, RP-040551 | -
3113 | 20013 | HS-DPCCH ACK/NACK Enhancement | RANimp-RABSE-ACKNACK | 3 | Rel-6 | R1 | 2004-09-15 08:00 | 2004-12-14 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | Approved at RP#25 as RP-040390 | 25.212, 25.214, 24.331, 25.433
3114 | 23009 | Deleted - Iu enhancements for IMS support in RAN | RANimp-RABSE-IuEnhIMS | 3 | Rel-6 | R3 | 2003-03-14 08:00 | 2004-06-03 17:00 | 100% | - | - | Nortel | Philippe.Godin@nortelnetworks.com | Closed RP#24 due to the lack of progress | -
3115 | 23005 | Deleted - Improvement of RRM across RNS and RNS/BSS | RANimp-RRM1 | 3 | Rel-6 | R3 | 2003-12-05 17:00 | 2003-12-05 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | abandoned RP-23 | -
3116 | 20999 | Beamforming Enhancements | RANimp-BFE | 2 | Rel-6 | R1 | 2003-09-19 | 2003-12-19 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | - | 24.215, 25.423, 25.425, 25.433, 25.435
3117 | 23012 | Rel-6 RRM optimization for Iur and Iub | RANimp-RRMopt-UEMsD | 2 | Rel-6 | R3 | 2003-09-19 | 2004-03-12 17:00 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | -
3118 | 23014 | Improved access to UE measurement data for CRNC to support TDD RRM | - | 3 | Rel-6 | R3 | 2003-09-19 | 2004-03-12 17:00 | 100% | - | - | Interdigital | jim.miller@interdigital.com | - | 25.423
3119 | 23010 | Remote Control of Electrical Tilting Antennas | RANimp-TiltAnt | 2 | Rel-6 | R3,S5 | 2003-03-14 08:00 | 2004-09-16 17:00 | 100% | - | - | Vodafone | Andreas.Hauser@vodafone.com | - | -
3120 | 23015 | Tilting Antenna - RAN aspects | - | 3 | Rel-6 | R3 | 2003-03-14 08:00 | 2004-09-14 17:00 | 100% | - | - | Vodafone | Andreas.Hauser@vodafone.com | Finished at RP#25 | 25.460, 25.461, 25.462, 25.463
3121 | 35023 | OAM&P impacts | RANimp-TiltAnt-OAM | 3 | Rel-6 | S5 | 2004-02-27 08:00 | 2004-09-16 17:00 | 100% | S5-048270 | - | Vodafone | Adrian.Neal@vodafone.com | SP#25 09/2004 completed | 32.804, 32.64x
3122 | 23011 | Network Assisted Cell Change (NACC) from UTRAN to GERAN - network-side aspects | RANimp-NACC | 2 | Rel-6 | R3 | 2002-09-09 08:00 | 2004-06-15 17:00 | 100% | - | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | - | -
3123 | 32023 | Location Services enhancements 2 | LCS2 | 1 | Rel-6 | S2,S5,N4,R2,R4,R5,OMA | 2001-01-15 08:00 | 2004-12-16 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | -
3124 | 32024 | Improvement on Le interface | - | 2 | Rel-6 | S2,OMA | 2002-06-17 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | -
3125 | 32051 | Stage 2 for Improvement on Le interface | - | 3 | Rel-6 | S2 | 2002-06-17 08:00 | 2003-09-22 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271
3126 | 32053 | Stage 3 - impacts MLP (Mobile Location Protocol) | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | -
3127 | 32001 | Enhanced support for anonymity and user privacy | - | 2 | Rel-6 | S2,OMA | 2002-07-08 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | -
3128 | 32047 | Stage 2 for Enhanced support for anonymity and user privacy | - | 3 | Rel-6 | S2 | 2002-07-08 08:00 | 2003-06-27 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271
3129 | 32054 | Stage 3 - impacts MLP and RLP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | -
3130 | 32025 | Enhanced inter-GMLC interface | - | 2 | Rel-6 | S2,OMA | 2002-06-24 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | -
3131 | 32048 | Stage 2 for Enhanced inter-GMLC interface | - | 3 | Rel-6 | S2 | 2002-06-24 08:00 | 2003-09-05 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271
3132 | 32055 | Stage 3 - definition of RLP and PCP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | -
3133 | 32012 | Location Services support for IMS public identities | - | 2 | Rel-6 | S2,OMA | 2003-02-24 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | -
3134 | 32049 | Stage 2 for Location Services support for IMS public identities | - | 3 | Rel-6 | S2 | 2003-02-24 08:00 | 2004-01-23 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271
3135 | 32056 | OMA Stage 3 for Location Services support for IMS public identities - impacts MLP, RLP and PCP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | -
3136 | 32026 | New area event for location service triggering reports | - | 2 | Rel-6 | S2,N4,OMA | 2002-06-03 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | -
3137 | 32050 | Stage 2 for New area event for location service triggering reports | - | 3 | Rel-6 | S2 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271
3138 | 14015 | Stage 3 for UE-CN signalling | - | 3 | Rel-6 | N4 | 2003-10-09 08:00 | 2004-08-31 17:00 | 100% | SP-030127 | - | Nokia | - | Current stage 3 fullfills stage 2 | -
3139 | 32057 | Stage 3 for New area event for location service triggering reports - impacts MLP, RLP and PCP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | -
3140 | 20001 | UE positioning for Location Services enhancements 2 | LCS2-UEpos | 2 | Rel-6 | R2,R4,R5 | 2001-01-15 08:00 | 2004-09-14 17:00 | 100% | - | - | - | - | - | -
3141 | 2475 | Open SMLC-SRNC Interface within the UTRAN to support UTRAN Rel-4 positioning methods | LCS-Rel4Pos | 3 | Rel-6 | R2 | 2001-01-15 08:00 | 2003-09-19 17:00 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | - | 25.305, 25.401, 25.450, 25.452, 25.453
3142 | 24012 | A-GPS minimum performance specification | LCS-UEPos-AGPSPerf | 3 | Rel-6 | R4,R5 | 2003-06-06 08:00 | 2004-09-14 17:00 | 100% | - | - | AT&T Wireless | donglin.shen@attws.com | RP#25 completed (FDD) | new 25.171, 34.171 (testing)
3143 | 22002 | Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods | LCS2-UEpos-FSBlank | 3 | Rel-6 | R2 | 2002-07-01 08:00 | 2003-09-19 17:00 | 100% | - | - | Cambridge Positioning Systems | david.bartlett@cursor-system.com | RP#38 Work stopped | new TR 25.894
3144 | 2457 | Deleted - UE positioning enhancements - other methods | LCS2-UEpos-enh | 3 | Rel-6 | R2 | 2003-09-26 17:00 | 2003-09-26 17:00 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | RP#24 Work stopped | -
3145 | 35035 | LCS charging | LCS2-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-12-16 17:00 | 100% | SP-040778 | - | France Telecom | alain.bibas@orange-ft.com | SP#26 completed | new TS 32.271
3146 | 1571 | Rel-6 Security enhancements | SEC1, Rel-6 | 1 | Rel-6 | S3 | 2001-01-03 08:00 | 2004-11-26 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | SP#9 approved WID | -
3147 | 2026 | Enhanced HE control of security (including positive authentication reporting) | - | 2 | Rel-6 | S3 | 2001-01-03 08:00 | 2003-09-25 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | SP#9 approved WID S3-000490 (Enhanced home control of security by HE) | 33.102
3148 | 2027 | Deleted - SEC1 Stage 2 (Enhanced HE control of security) | - | 3 | Rel-6 | S3 | 2001-01-03 08:00 | 2002-06-14 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3149 | 33006 | Rel-6 Network Domain Security | SEC1-NDS | 3 | Rel-6 | S3 | 2002-06-17 08:00 | 2003-09-25 17:00 | 100% | SP-000420 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#9 approved WID S3-000606 (Network Domain Security) | 33.102, 33.103, 33.105
3150 | 33007 | Rel-6 IP network layer security (NDS/IP) | SEC1-NDS-IP | 4 | Rel-6 | S3 | 2002-06-17 08:00 | 2003-09-25 17:00 | 100% | SP-000420 | - | - | - | SP#9 approved WID S3-000626 (Access security for IP-based services) | 33.210
3151 | 33017 | Network Domain Security; Authentication Framework (NDS/AF) | SEC1-NDS-AF | 2 | Rel-6 | S3 | 2002-02-15 08:00 | 2004-02-13 17:00 | 100% | SP-030108 | - | Nokia | tommi.viitanen@nokia.com | SP#19 approved WID | 33.810
3152 | 33019 | Key Management of group keys for Voice Group Call Services | SECGKYV | 2 | Rel-6 | S3 | 2003-09-26 08:00 | 2004-11-26 17:00 | 100% | SP-030491 | - | Vodafone | benno.tietz@vodafone.com | - | 42.068, 43.068, 44.068, 42.069, 43.069, 44.069, 31.102, 24.008, 48.008, 42.009, 43.020, New TSs (55.236, 55.205) MILENAGE algorithms
3153 | 33020 | Network Domain Security; MAP application layer security (NDS/MAPsec) | MAPSEC | 1 | Rel-6 | S3 | 2004-07-06 08:00 | 2004-12-29 17:00 | 100% | SP-040280 | - | Vodafone | Peter.Howard@vodafone.com | SP#19 approved WID. Marked as closed 12/2008 (was marked 20% complete) | 33.200
3154 | 32021 | IMS Phase 2 | IMS2 | 1 | Rel-6 | S1,S2,S3,S5,NP,R5 | 2000-08-28 08:00 | 2007-09-14 17:00 | 100% | - | - | - | - | - | -
3155 | 14014 | Enhancements to the Cx and Sh interfaces | IMS2-CCR | 2 | Rel-6 | N4 | 2003-06-06 08:00 | 2004-08-31 17:00 | 100% | NP-030229 | - | - | - | Shared public user identities need to be solved. If email approval CR is accepted. Work 100% done.... | -
3156 | 25009 | Conformance Test Aspects – IMS Call Control Rel-6 enhancements | IMS2_CCR_Test | 2 | Rel-6 | R5 | 2006-03-10 08:00 | 2007-09-14 17:00 | 100% | - | - | Ericsson | Jacob.John@motorola.com, Leif.Mattisson@ericsson.com | - | 34.229-1, 34.229-2, 34.229-3, 34.108
3157 | 31025 | IMS Group Management | IMSGM | 2 | Rel-6 | S1 | 2002-03-14 08:00 | 2004-12-08 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | -
3158 | 31026 | Stage 1 - TS on IMS group management | - | 3 | Rel-6 | S1 | 2002-03-14 08:00 | 2002-12-09 17:00 | 100% | - | - | Nokia | juha.kalliokulju@nokia.com | - | -
3159 | 32036 | Stage 2 for IMS Group Management | - | 3 | Rel-6 | S2 | 2003-05-26 08:00 | 2003-12-31 17:00 | 100% | - | - | - | - | - | 23.228
3160 | 11036 | Stage 3 for IMS Group management (e.g. chat) | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-12-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Depends on CN decision on CPCP in Rel-6. Complete, if unresolved IETF dependencies are dropped (-> LS to CN plenary) | -
3161 | 11037 | IMS Conferencing | - | 2 | Rel-6 | N1 | 2002-11-04 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | -
3162 | 32037 | Stage 2 for IMS Conferencing | - | 3 | Rel-6 | S2 | 2002-11-04 08:00 | 2003-12-31 17:00 | 100% | - | - | - | - | - | 23.228
3163 | 32038 | Stage 3 for IMS Conferencing | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-12-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Depends on CN decision on IETF dependencies in Rel-6. Higher figure if CPCP is dropped (-> LS to CN plenary) | -
3164 | 31022 | IMS Messaging | IMSM | 2 | Rel-6 | S1 | 2002-03-14 08:00 | 2005-12-30 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | -
3165 | 31023 | TR on support of messaging in the IMS | IMSM-TR | 3 | Rel-6 | S1 | 2002-03-14 08:00 | 2002-12-09 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | New 22.940
3166 | 31034 | Stage 1 22.340 | IMSM-TS | 3 | Rel-6 | S1 | 2002-11-11 08:00 | 2002-12-11 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | 22.340
3167 | 31033 | CRs to 22.140 & 22.228 | IMSM-CR | 3 | Rel-6 | S1 | 2002-03-14 08:00 | 2003-03-17 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | 22.140,22.228
3168 | 32700 | Stage 2 for IMS Messaging | - | 3 | Rel-6 | S2 | 2002-11-04 08:00 | 2004-08-31 17:00 | 100% | - | - | - | - | - | 23.228
3169 | 11039 | Stage 3 for IMS Messaging | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-12-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | -
3170 | 60001 | SIP/SIMPLE Instant messaging | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-12-30 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040232 | -
3171 | 11040 | Additional SIP Capabilities support not covered by Rel-5 | - | 2 | Rel-6 | N1 | 2002-11-11 08:00 | 2005-06-17 17:00 | 100% | - | - | - | - | - | -
3172 | 32041 | Stage 2 for add SIP cap (e.g. forking) | - | 3 | Rel-6 | S2 | 2002-11-11 08:00 | 2004-02-20 17:00 | 100% | - | - | - | - | - | 23.228
3173 | 32042 | Stage 3 for Additional SIP Capabilities | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-09-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | -
3174 | 11052 | Procedured associated with IMS-ALG | - | 3 | Rel-6 | N1 | 2004-09-06 08:00 | 2005-06-17 17:00 | 100% | - | - | - | - | - | -
3175 | 11041 | Review additional SIP Capabilities against IMS | - | 2 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-09-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | -
3176 | 2048 | Interworking between IMS and IP networks | IMS-CCR-IWIP | 2 | Rel-6 | N3 | 2000-08-28 08:00 | 2004-12-08 17:00 | 100% | NP-020091 | - | BT | nigel.holland@bt.com | [DAB 14.02.02] - end date pushed back to March 2003 | 23.821, 29.061, 29.162
3177 | 13004 | Interworking for 3GPP_SIP and IETF_SIP | - | 3 | Rel-6 | N3 | 2000-08-28 08:00 | 2003-06-13 17:00 | 100% | - | - | Siemens | Thomas.Belling@nsn.com | [DAB - 20.08.03] - CN Part of TR Complete @ CN#20 | New 29.962
3178 | 13005 | Interworking for IPv6 to IPv4 | - | 3 | Rel-6 | N3 | 2000-08-28 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | 29.163
3179 | 11044 | Interworking for IPv6 to IPv4 (SIP / SDP aspects) | - | 3 | Rel-6 | N1 | 2004-05-11 08:00 | 2004-09-08 17:00 | 100% | - | - | - | - | - | -
3180 | 11017 | stage 3 of interworking with non-IMS IP networks | - | 3 | Rel-6 | N1 | 2001-03-14 08:00 | 2004-09-08 17:00 | 100% | - | - | - | - | - | -
3181 | 2047 | Interworking between IMS and CS networks | IMS-CCR-IWCS | 2 | Rel-6 | N3 | 2000-08-28 08:00 | 2004-03-18 17:00 | 100% | NP-030292 | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | [DAB - 25.05.04] - CN3 consider this work to be complete | 29.163, 29.061, 24.228, and New CN4 specification
3182 | 14001 | Mn interface (IM-MGW to MGCF) enhancements (CN4 Part) | IMS-CCR-Mn | 2 | Rel-6 | N4 | 2001-08-07 10:24 | 2004-09-01 17:00 | 100% | - | - | - | - | TISPAN issue is open | -
3183 | 31036 | Study of subscriber and operators relationship in IMS and related ISIM requirements for Rel 6” | - | 2 | Rel-6 | S1 | 2002-11-15 08:00 | 2002-12-12 17:00 | 100% | - | - | Nokia | juha.kalliokulju@nokia.com | - | -
3184 | 33012 | Lawful Interception in Rel-6 architecture | SEC1-LI, Rel-6 | 2 | Rel-6 | S3 | 2002-12-09 08:00 | 2003-12-18 17:00 | 100% | SP-030106 | - | Reg TP, Nortel | berthold.wilhelm@regtp.de, Ron Ryan | - | 33.106, 33.107, 33.108
3185 | 31042 | IMS Subscription and access scenarios | - | 2 | Rel-6 | S1 | 2002-12-16 08:00 | 2003-06-13 17:00 | 100% | - | - | TeliaSonera | FRANK, Robert | - | 22.800
3186 | 35032 | IMS charging | IMS2-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-12-16 17:00 | 100% | SP-030049 | - | Ericsson | Patrik TEPPO | SP#26 12/2004 completed | 32.260
3187 | 11051 | IMS Management objects | - | 2 | Rel-6 | N1 | 2004-09-03 08:00 | 2005-11-04 17:00 | 100% | NP-040494 | - | - | - | - | 24.167
3188 | 32027 | Deleted - Stage 2 of IMS Phase 2 | - | 2 | Rel-6 | S2 | 2003-09-19 17:00 | 2003-09-19 17:00 | 100% | SP-020544 | - | - | - | - | -
3189 | 32063 | 3GPP Enablers for services like Push to Talk over Cellular (PoC) | PoC | 1 | Rel-6 | S2,S4,S5 | 2003-09-08 08:00 | 2005-06-09 17:00 | 100% | SP-030384 | - | Ericsson | Shabnam Sultana | - | -
3190 | 32068 | Feasibility Study on 3GPP Enablers for services like Push to Talk over Cellular (PoC) | - | 2 | Rel-6 | S2 | 2003-09-08 08:00 | 2004-11-30 17:00 | 100% | SP-030384 | - | Ericsson | Shabnam Sultana | - | 23.979
3191 | 60002 | Dependencies on OMA PoC | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-02-28 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040232 | -
3192 | 34029 | Selection of one or more PoC codec(s) for PoC | - | 2 | Rel-6 | S4 | 2004-09-13 08:00 | 2004-12-16 17:00 | 100% | - | - | - | - | Completed | 26.235, 26.236
3193 | 35036 | PoC charging | PoC-CH | 2 | Rel-6 | S5 | 2004-09-27 08:00 | 2005-06-09 17:00 | 100% | SP-050032 | - | Siemens | Gerald.Goermer@nsn.com | SP#28 06/2005 completed | 32.272
3194 | 32062 | Study on Interworking aspects and migration scenarios for IPv4 based IMS Implementations | IPv4IMS | 1 | Rel-6 | S2 | 2003-09-08 08:00 | 2004-06-25 17:00 | 100% | SP-040327 | - | Siemens | Alexander Milinski | - | 23.981
3195 | 11032 | Interoperability and Commonality between IMS using different IP-connectivity Networks | IMSCOOP | 1 | Rel-6 | S2 | 2002-09-16 08:00 | 2003-12-12 17:00 | 100% | - | - | - | - | - | 23.864
3196 | 32028 | Stage 2 for Interoperability | - | 2 | Rel-6 | S2 | 2002-09-16 08:00 | 2003-09-30 17:00 | 100% | SP-020543 | - | Nokia | balazs.bertenyi@nsn.com | No contributions assumed that no more will be done in 3GPP hence work may need to be done in 3GPP2 | 23.864
3197 | 32061 | Stage 2 for commonality | - | 2 | Rel-6 | S2 | 2002-09-16 08:00 | 2003-09-19 17:00 | 100% | SP-020543 | - | Nokia | balazs.bertenyi@nsn.com | - | 23.864
3198 | 11033 | Stage 3 for Interoperability and Commonality between IMS using different IP-connectivity Networks | - | 2 | Rel-6 | N1 | 2002-10-14 08:00 | 2003-12-12 17:00 | 100% | NP-020572 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | -
3199 | 1365 | Support of Push Services | PUSH | 1 | Rel-6 | S1 | 2001-01-03 08:00 | 2004-02-27 17:00 | 100% | SP-000669 | - | NTT Comware | Yoshinori Kitada | Changed from FS to actual support of Push | 23.976
3200 | 31004 | Stage 1 for Support of Push Services | - | 2 | Rel-6 | S1 | 2001-01-03 08:00 | 2002-06-14 17:00 | 100% | - | - | - | - | - | -
3201 | 32701 | TR 23.976 on Push Architecture | - | 2 | Rel-6 | S2 | 2002-11-11 08:00 | 2004-02-27 17:00 | 100% | SP-030126 | - | Research In Motion | Nick Alfano | - | 23.976
3202 | 42009 | Rel-6 Multimedia Messaging (MMS) enhancements | MMS6 | 1 | Rel-6 | T2,S1,S4,S5,OMA | 2002-08-15 08:00 | 2005-12-07 17:00 | 100% | TP-030175 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | -
3203 | 42010 | Definition of service requirements for MMS6 | MMS6-SR | 2 | Rel-6 | S1 | 2002-11-15 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | - | 22.140
3204 | 31031 | Definition of service requirements charging | - | 3 | Rel-6 | S1 | 2002-11-15 08:00 | 2003-12-19 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140
3205 | 42011 | Technical realization of MMS6 | - | 2 | Rel-6 | T2 | 2002-09-06 08:00 | 2004-12-10 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 23.140
3206 | 42012 | OMA dependencies | - | 2 | Rel-6 | OMA | 2003-08-15 08:00 | 2005-04-29 17:00 | 100% | - | - | - | - | - | OMA specs
3207 | 42013 | MMS formats and codecs for MMS6 | MMS6-Codec | 2 | Rel-6 | S4 | 2002-08-15 08:00 | 2005-12-07 17:00 | 100% | - | - | Nokia | roberto.castagno@nokia.com | - | 26.140, 26.936
3208 | 42014 | Handling of private addressing schemes in MMS | - | 2 | Rel-6 | T2 | 2003-12-10 08:00 | 2004-12-10 17:00 | 100% | TP-030299 | - | T-Mobile | Steffen.Habermann@T-MOBILE.DE | - | 23.140
3209 | 35034 | MMS charging | MMS6-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | SP-040778 | - | - | - | SP#25 09/2004 completed | 32.270
3210 | 42015 | Deleted - FS Multiple MMS Relay/Server Architecture | - | 2 | Rel-6 | T2 | 2004-12-10 17:00 | 2004-12-10 17:00 | 100% | TP-030301 | - | Telefónica Móviles | Juan Gorospe (gorospe_j@tsm.es) | originally it was intended to create a FS TR but most likely the work will become an Annex of 23.140 | probably Annex to 23.140
3211 | 42005 | Rel-6 MExE enhancements | MEXE6 | 1 | Rel-6 | T2 | 2002-03-08 08:00 | 2003-06-06 17:00 | 100% | - | - | - | - | - | -
3212 | 42006 | MExE Rel-6 Improvements and Investigations | MEXE6-ENHANC | 2 | Rel-6 | T2 | 2002-03-08 08:00 | 2003-03-12 17:00 | 100% | TP-020017 | - | TTPCom | Lars Brenk ( (lsb_ttpcom@HOTMAIL.COM) | - | -
3213 | 42007 | MExE Run-Time Independent Framework Feasibility Study | MEXE6-RTIF | 2 | Rel-6 | T2 | 2002-03-08 08:00 | 2003-06-06 17:00 | 100% | TP-020086 | - | Nokia Siemens Networks | balazs.bertenyi@nokia.com | - | 22.857
3214 | 2062 | Subscription Management | SuM | 1 | Rel-6 | S5 | 2002-09-20 08:00 | 2005-03-17 17:00 | 100% | SP-040763 | - | T-Mobile | istvan.aba@t-mobile.at | SP#27 03/2005 completed | 32.140/1, 32.171/2/5, 32.803
3215 | 2499 | Presence Capability | PRESNC | 1 | Rel-6 | S1,S2,S3,S4,N1,N3,N4,OMA | 2001-03-19 08:00 | 2005-12-07 17:00 | 100% | SP-010064 | - | Motorola | Mark Cataldo | merged "Presence Service Enhancements" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date | -
3216 | 2501 | Stage 1 for Presence Capability | - | 2 | Rel-6 | S1 | 2001-03-19 08:00 | 2003-07-18 17:00 | 100% | SP-010064 | - | Motorola | Mark Cataldo | TP#16 moved Stage 1 to Rel-6 TS 22.141 (existed already in Rel-5) | 22.141
3217 | 2502 | Stage 2 for Presence Capability | - | 2 | Rel-6 | S2 | 2001-09-12 08:00 | 2002-09-20 17:00 | 100% | SP-010517 | - | Nokia | balazs.bertenyi@nsn.com | - | 23.002, 24.229, New 23.141
3218 | 2503 | Stage 3 for Presence Capability | - | 2 | Rel-6 | N1,N4 | 2002-04-01 08:00 | 2004-12-08 17:00 | 100% | NP-040492 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Dependency to 2 IETF drafts, no known work at the moment | New N1 (24.141, 24.841), N4 (29.002, 29.228, 29.230, 29.328)
3219 | 13018 | Stage 3 (CN3 Part Pk interface) | - | 2 | Rel-6 | N3 | 2002-04-01 08:00 | 2005-03-11 17:00 | 100% | NP-040492 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 29.061, 29.161
3220 | 34025 | Media Codecs and Formats for IMS Messaging and Presence | PRESNC-COFIMP | 2 | Rel-6 | S4 | 2003-06-12 08:00 | 2005-12-07 17:00 | 100% | SP-030212 | - | Nokia | harri.honko@nokia.com | - | 26.141, 26.936
3221 | 2504 | Security aspects of Presence Capability | - | 2 | Rel-6 | S3 | 2002-08-26 08:00 | 2002-12-12 17:00 | 100% | SP-020514 | - | Ericsson | krister.boman@erv.ericsson.se | SP#17 approved WID S3-020429 | -
3222 | 60003 | SIMPLE Presence | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-03-31 17:00 | 100% | SP-040232 | - | - | OMA-LIAISON@mail.openmobilealliance.org | SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables | -
3223 | 50056 | Enhanced A/Gb feasibility study | AGbEnFS | 1 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | GP-022565 | - | Vodafone | jose-luis.carrizo@vodafone.co.uk | - | None
3224 | 50057 | Feasibility study on A/Gb enhancements | AGbEnFS-FS | 2 | Rel-6 | G2 | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | GP-022565 | - | Vodafone | jose-luis.carrizo@vodafone.co.uk | - | None
3225 | 50080 | Requirements for the support of conversational services | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None
3226 | 50084 | Identification of the different building blocks for the provision of conversational services on the existing A/Gb protocol stack | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None
3227 | 50093 | Outline of impact and feasibility of these building blocks and their different solutions | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None
3228 | 50081 | Impact on 3GPP architecture and requirement to co-ordinatge with other TSGs (CN, SA) | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None
3229 | 50082 | Standardisation effort | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None
3230 | 50083 | Dependency to other features of Enhanced A/Gb feasibility study | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None
3231 | 50063 | Flexible Layer One for GERAN | FLOGER | 1 | Rel-6 | GP,S3 | 2000-01-03 08:00 | 2004-06-25 17:00 | 100% | GP-021018 | - | Nokia | benoist.sebire@nokia.com | - | -
3232 | 50064 | Realisation of a Flexible Layer One | FLOGER-Real | 2 | Rel-6 | GP | 2000-01-03 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3233 | 50065 | Technical Report on Realisation of a Flexible Layer One | - | 3 | Rel-6 | GP | 2002-04-19 08:00 | 2004-02-06 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3234 | 51002 | Architecture in 45.001 and 43.051 | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3235 | 51003 | Multiplexing in 45.002 | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3236 | 51004 | Channel Coding in 45.003 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3237 | 51005 | Performance Requirements in 45.005 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3238 | 51006 | Radio subsystem link control in 45.008 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3239 | 52071 | Requirements in 44.004 | - | 3 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | -
3240 | 52072 | Signalling and protocol support for a Flexible Layer One | FLOGER-SigPro | 2 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-06-25 17:00 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | -
3241 | 52073 | Modifications to RLC/MAC in 44.060 and 44.160 | - | 3 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-06-25 17:00 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | -
3242 | 52074 | Modifications to RRC in 44.118 and 44.018 | - | 3 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-06-25 17:00 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | -
3243 | 52075 | Security for a Flexible Layer One | FLOGER-SecFLO | 2 | Rel-6 | S3,G2 | 2002-04-19 08:00 | 2003-08-29 17:00 | 100% | GP-021021 | - | Nokia | benoist.sebire@nokia.com | - | -
3244 | 52076 | Ciphering in 44.060, 44.160, 44.018, 44.118 | - | 3 | Rel-6 | S3,G2 | 2002-04-19 08:00 | 2003-08-29 17:00 | 100% | GP-021021 | - | Nokia | benoist.sebire@nokia.com | - | 44.060, 44.160, 44.018, 44.118
3245 | 55077 | Deleted - GERAN MS Conformance test for the Flexible Layer One - DELETE | FLOGER-Msconf | 2 | Rel-6 | G4,G5 | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | GP-021022 | - | Nokia | benoist.sebire@nokia.com | - | -
3246 | 55078 | Deleted at TSG #27 - MS Test in 51.010 | - | 3 | Rel-6 | G4,G5 | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | - | - | Nokia | benoist.sebire@nokia.com | - | -
3247 | 55079 | Deleted - GERAN BTS Conformance test for the Flexible Layer One - DELETE | FLOGER-BTSconf | 2 | Rel-6 | G3new | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | GP-021023 | - | Nokia | benoist.sebire@nokia.com | - | -
3248 | 53080 | Deleted at TGS #27 - BTS Test in 51.021 - DELETE | - | 3 | Rel-6 | G3new | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | - | - | Nokia | benoist.sebire@nokia.com | - | -
3249 | 50041 | Uplink TDOA feasibility study | TDOAF | 1 | Rel-6 | GP | 2001-11-30 08:00 | 2002-06-28 17:00 | 100% | GP-012794 | - | TruePosition | Bob Gross (rlgross@trueposition.com) | - | 45.811
3250 | 2544 | Multimedia Broadcast and Multicast Service | MBMS | 1 | Rel-6 | S1,S2,S3,S4,S5,N1,N3,R2,R4,R5,T1,GP,G2,G3new | 2001-05-11 08:00 | 2008-03-07 17:00 | 100% | - | - | - | - | SP#13 Title renamed | -
3251 | 2545 | Stage 1 for Multimedia Broadcast and Multicast Service | - | 2 | Rel-6 | S1 | 2001-05-11 08:00 | 2002-04-01 17:00 | 100% | - | - | - | - | - | 22.146, 22.101
3252 | 32002 | Stage 2 for Multimedia Broadcast and Multicast Service | - | 2 | Rel-6 | S2 | 2001-09-24 08:00 | 2004-03-17 17:00 | 100% | SP-010516 | - | - | - | - | -
3253 | 32702 | TR on MBMS Architectural Study | - | 3 | Rel-6 | S2 | 2001-09-24 08:00 | 2002-08-23 17:00 | 100% | - | - | - | - | - | 23.846
3254 | 32703 | Stage 2 MBMS Specification Work | - | 3 | Rel-6 | S2 | 2002-08-19 08:00 | 2004-03-17 17:00 | 100% | - | - | - | - | - | 23.246
3255 | 11030 | Support of the MBMS in CN protocols | - | 2 | Rel-6 | N1 | 2002-06-18 08:00 | 2004-12-08 17:00 | 100% | NP-040493 | - | - | - | - | -
3256 | 13015 | Gmb interface for MBMS (CN3 part) | - | 2 | Rel-6 | N3 | 2003-08-29 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | 29.061
3257 | 33008 | Security aspects of MBMS | - | 2 | Rel-6 | S3 | 2002-07-01 08:00 | 2005-03-18 17:00 | 100% | SP-020514 | - | 3 | adrian.escott@three.co.uk | SP#17 approved WID S3-020433 | New 33.246
3258 | 35038 | MBMS Charging | MBMS-CH | 2 | Rel-6 | S5 | 2005-01-11 08:00 | 2005-06-09 17:00 | 100% | SP-040779 | - | - | - | SP#28 completed | 32.273
3259 | 31045 | MBMS User Services | - | 2 | Rel-6 | S1,S4 | 2003-05-13 08:00 | 2006-03-16 17:00 | 100% | - | - | - | - | - | -
3260 | 31044 | Stage 1 for MBMS User Services | - | 3 | Rel-6 | S1 | 2003-05-13 08:00 | 2004-04-01 17:00 | 100% | - | - | - | - | - | 22.246
3261 | 34026 | Definition of MBMS user services, media codecs, formats and transport/application protocols using MBMS | MBMS-TSMBMS | 3 | Rel-6 | S4 | 2003-06-12 08:00 | 2006-03-16 17:00 | 100% | SP-030674 | - | Nokia | igor.curcio@nokia.com | - | 26.346, 26.936, 26.946
3262 | 2481 | Introduction of MBMS in RAN | MBMS-RAN | 2 | Rel-6 | R2,R4 | 2002-01-01 | 2005-09-14 17:00 | 100% | - | - | Nokia | juho.pirskanen@nokia.com | - | -
3263 | 20022 | Introduction of MBMS in RAN (physical & upper layers, access network interfaces) | - | 3 | Rel-6 | R2 | 2002-01-01 | 2004-12-14 17:00 | 100% | - | - | Nokia | juho.pirskanen@nokia.com | - | 25.346, 25.304, 25.321, 25.322, 25.323
3264 | 20020 | UE Performance Requirements for MBMS | MBMS-RAN-RF | 3 | Rel-6 | R4 | 2004-09-15 | 2005-09-14 17:00 | 100% | RP-040370 | - | Ericsson | Torgny.Palenius@ericsson.com | RP#25 approved WID RP-040370 | 25.101, 25.133
3265 | 25024 | MBMS UE Conformance Testing | MBMS-UEConTest | 2 | Rel-6 | R5,T1 | 2006-03-10 08:00 | 2008-03-07 17:00 | 100% | - | - | - | - | - | -
3266 | 25014 | RF/RRM Conformance Test Aspects – MBMS (FDD) | MBMS-RAN-RF_Test | 3 | Rel-6 | R5,T1 | 2006-06-02 08:00 | 2008-03-07 17:00 | 100% | - | - | Ericsson | leif.mattisson@ericsson.com | - | 34.108, 34.109, 34.121-1, 34.121-2
3267 | 25022 | Conformance Test Aspects - MBMS for 3.84 Mcps and 7.68 Mcps TDD | MBMS-UEConTest_TDH | 3 | Rel-6 | R5,T1 | 2006-09-20 08:00 | 2007-12-07 17:00 | 100% | - | - | IPWireless | Timothy Speight (tspeight@ipwireless.com) | - | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
3268 | 25023 | Signalling Conformance Test Aspects – MBMS for LCR TDD | MBMS-UEConTest_SIGTDL | 3 | Rel-6 | R5,T1 | 2006-09-20 08:00 | 2007-12-07 17:00 | 100% | - | - | Datang | zhaojian@datangmobile.cn | - | 34.108, 34.123-1, 34.123-2, 34.123-3
3269 | 25011 | Conformance Test Aspects – MBMS | MBMS_Test | 3 | Rel-6 | R5,T1 | 2006-03-10 08:00 | 2007-09-14 17:00 | 100% | - | - | Qualcomm | Shubhang Vora (svora@qualcomm.com) | - | 34.108, 34.123-1, 34.123-2, 34.123-3
3270 | 25038 | Conformance Test Aspects - 1.28 Mcps TDD MBMS RF/RRM | MBMS-UEConTest_RFTDL | 3 | Rel-6 | R5,T1 | 2007-06-01 08:00 | 2007-12-07 17:00 | 100% | - | - | Datang | chenxiaozhong@datangmobile.cn | - | 34.108, 34.109, 34.122
3271 | 50085 | Support of MBMS in GERAN | MBMS-GERAN | 2 | Rel-6 | GP,G2,G3new | 2001-08-30 08:00 | 2005-01-28 17:00 | 100% | GP-022566 | - | - | - | - | -
3272 | 50086 | MBMS Impact on the logical and physical channels | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3273 | 52085 | MBMS Re-synchronisation at cell change | - | 3 | Rel-6 | G2 | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3274 | 50098 | Simultaneous support of MBMS services | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3275 | 50099 | Simultaneous support of MBMS and non-MBMS services | - | 3 | Rel-6 | GP | 2001-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3276 | 50100 | MBMS Resynchronization at cell change | - | 3 | Rel-6 | GP | 2001-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3277 | 50087 | MBMS Decision making process between point-to-point or point-to-multipoint configurations | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3278 | 50088 | MBMS channel allocations procedures to multiple MSs | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3279 | 50089 | MBMS Changes to the Gb interface | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3280 | 50090 | GERAN specific changes to the Iu-ps interface for MBMS | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3281 | 50091 | Interaction between MBMS and Iu-flex | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3282 | 50092 | MBMS Security aspects | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3283 | 53081 | MBMS-GERAN - MS conformance tests | - | 3 | Rel-6 | G3new | 2002-01-25 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | -
3284 | 55091 | Deleted - MS conformance tests - G5 | - | 3 | Rel-6 | G5 | 2003-06-27 17:00 | 2003-06-27 17:00 | 100% | - | - | - | - | - | -
3285 | 31006 | Speech Recognition and Speech Enabled Services | SRSES | 1 | Rel-6 | S1,S2,S4,OMA | 2001-10-08 08:00 | 2005-12-30 17:00 | 100% | SP-010572 | - | - | - | - | -
3286 | 31007 | Speech Enabled Services Based on Distributed Speech Recognition (DSR) | DSR | 2 | Rel-6 | S1 | 2001-10-08 08:00 | 2002-03-15 17:00 | 100% | SP-010581 | - | Qualcomm | Dwilliams@qualcomm.com | - | 22.977, 22.941, 23.207, 22.243
3287 | 32999 | TR on Architectural impacts | - | 2 | Rel-6 | S2 | 2003-05-12 08:00 | 2004-03-02 17:00 | 100% | - | - | - | - | - | 23.877
3288 | 34700 | Codec Work to Support Speech Recognition Framework for Automated Voice Services | SRSES-Codec | 2 | Rel-6 | S4 | 2002-10-15 08:00 | 2004-12-16 17:00 | 100% | SP-020687 | - | Motorola | David Pearce (bdp003@motorola.com) | - | 26.235, 26.236, 26.243, 26.177, 26.943
3289 | 60004 | Multimodal support | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-12-30 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | -
3290 | 11021 | Deleted - SES codec negotiation at Session Description Protocol (SDP) | - | 2 | Rel-6 | N1 | 2003-06-04 17:00 | 2003-06-04 17:00 | 100% | - | - | - | - | Abandoned NP-23 | -
3291 | 31008 | Generic User Profile Rel-6 | GUP | 1 | Rel-6 | S1,S3,N4 | 2001-10-08 08:00 | 2005-03-03 17:00 | 100% | SP-040515 | - | - | - | - | -
3292 | 31009 | Stage 1 - Requirements for Generic User Profile | - | 2 | Rel-6 | S1 | 2001-10-08 08:00 | 2003-05-30 17:00 | 100% | - | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 22.240, 22.228
3293 | 32008 | Stage 2 - Architecture | - | 2 | Rel-6 | S2 | 2002-01-28 08:00 | 2003-06-06 17:00 | 100% | SP-020539 | - | Nokia | harri.o.koskinen@nokia.com | - | 23.240
3294 | 42002 | Stage 2 - Data Description Method | - | 2 | Rel-6 | N4 | 2002-12-05 08:00 | 2005-03-03 17:00 | 100% | TP-020275 | - | T-Mobile | kurt.bischinger@t-mobile.at | TR approved in CN#26 | 23.241
3295 | 14008 | Stage 3 - Network | - | 2 | Rel-6 | N4 | 2003-05-19 08:00 | 2005-03-03 17:00 | 100% | - | - | - | - | - | 29.240
3296 | 33009 | Security aspects of GUP | - | 2 | Rel-6 | S3 | 2002-07-16 08:00 | 2003-09-18 17:00 | 100% | SP-030109 | - | Lucent | Bradley Owen (bvowen@lucent.com) | SP#19 approved WID | 33.102, 33.203, 33.210
3297 | 31010 | Digital Rights Management | DRM | 1 | Rel-6 | S1,OMA | 2001-10-08 08:00 | 2004-05-28 17:00 | 100% | SP-010577 | - | - | - | Foreseen start and completion dates introduced by MCC (no indication at all on the WID) | -
3298 | 31011 | Requirements for Digital Rights Management | - | 2 | Rel-6 | S1 | 2001-10-08 08:00 | 2002-06-13 17:00 | 100% | - | - | Openwave | nicholas.wood@openwave.com | - | -
3299 | 60005 | Stage 2 for Digital Rights Management | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-05-28 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | -
3300 | 60006 | Stage 3 for Digital Rights Management | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-05-28 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | -
3301 | 33001 | Security for Digital Rights Management | - | 2 | Rel-6 | OMA | 2002-06-17 08:00 | 2003-03-03 17:00 | 100% | - | - | - | - | SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17 | -
3302 | 31037 | Deleted - Monitoring of Stages 2 and 3 progress (actual work to be done by OMA) | - | 2 | Rel-6 | S1 | 2003-03-21 17:00 | 2003-03-21 17:00 | 100% | - | - | - | - | Replaced by UID 60005 and 60006 | -
3303 | 31012 | WLAN-UMTS Interworking Rel-6 | WLAN | 1 | Rel-6 | S1,S2,S3,S5,N1,N3,N4,T3 | 2000-01-03 08:00 | 2005-09-22 17:00 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | - | - | WLAN
3304 | 31020 | Technical Report on WLAN-UMTS Interworking | WLAN-TR | 2 | Rel-6 | S1 | 2000-01-03 08:00 | 2003-06-13 17:00 | 100% | SP-030712 | - | T-mobile | Mark.Younge@t-mobile.com | - | 22.934 | WLAN
3305 | 31035 | Stage 1 for WLAN-UMTS Interworking Rel-6 | WLAN-TS | 2 | Rel-6 | S1 | 2003-01-06 08:00 | 2004-06-11 17:00 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | - | 22.101, 22.105 | WLAN
3306 | 32018 | Architecture Definition for scenarii 2 and 3 | - | 2 | Rel-6 | S2 | 2002-03-25 08:00 | 2004-05-31 17:00 | 100% | SP-020542 | - | - | - | - | 23.234 | WLAN
3307 | 32704 | Security aspects of WLAN-UMTS Interworking | - | 2 | Rel-6 | S3 | 2002-09-30 08:00 | 2003-03-21 17:00 | 100% | SP-020514 | - | Ericsson, BT | luis.lopez-soria@ece.ericsson.se, colin.blanchard@bt.com | SP#17 approved WID S3-020451 | 21.133, 33.106, 33.107, 33.108, 33.200, 33.203, 33.210, New 33.234 | WLAN
3308 | 14013 | Stage 3 - CN4 aspects | WLAN-IW | 2 | Rel-6 | N4 | 2003-05-23 08:00 | 2004-09-01 17:00 | 100% | NP-030490 | - | Nokia | raquel.rodriguez@nokia.com | WID approved at CN#19 | 29.234, 29.061 | WLAN
3309 | 13019 | Stage 3 - CN3 aspects (Wi Interface for Scenario 3) | - | 2 | Rel-6 | N3 | 2003-05-23 08:00 | 2004-09-30 17:00 | 100% | - | - | - | - | - | 29.161 | WLAN
3310 | 11042 | Stage 3 for scenario 2 | - | 2 | Rel-6 | N1 | 2003-05-23 08:00 | 2004-09-08 17:00 | 100% | NP-030490 | - | - | - | - | - | WLAN
3311 | 11047 | Stage 3 for scenario 3 | - | 2 | Rel-6 | N1 | 2003-05-23 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | - | WLAN
3312 | 35033 | WLAN charging | WLAN-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2005-09-22 17:00 | 100% | SP-030048 | - | Nokia | Benni ALEXANDER | - | 32.252 | WLAN
3313 | 43010 | USIM enhancements for WLAN Interworking | - | 2 | Rel-6 | T3 | 2003-09-05 08:00 | 2005-03-04 17:00 | 100% | TP-030185 | - | Axalto | Jabellan@axalto.com | - | 31.102 | WLAN
3314 | 31015 | Priority Service | PRIOR1 | 1 | Rel-6 | S1 | 2002-05-30 08:00 | 2003-09-26 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | - | Public Safety (I-A)
3315 | 31016 | Feasibility Study on Priority Service | PRIOR-FS | 2 | Rel-6 | S1 | 2002-06-14 08:00 | 2002-06-14 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | 22.950 | Public Safety (I-A)
3316 | 31017 | Stage 1 - Requirements for Priority Service | PRIOR-SR | 2 | Rel-6 | S1 | 2002-05-30 08:00 | 2003-09-17 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | - | Public Safety (I-A)
3317 | 31043 | Priority service implementation guide | - | 2 | Rel-6 | S1 | 2003-03-28 08:00 | 2003-09-26 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | 22.952 | Public Safety (I-A)
3318 | 31018 | Network Sharing | NTShar | 1 | Rel-6 | S1,S2,N1,R2,R5 | 2003-01-20 08:00 | 2006-03-10 17:00 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | -
3319 | 31019 | Technical Report on Network Sharing | NTShar-TR | 2 | Rel-6 | S1 | 2003-01-20 08:00 | 2003-12-19 17:00 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 22.951
3320 | 31038 | Stage 1 - CRs to implement Network Sharing | NTSharCR | 2 | Rel-6 | S1 | 2003-01-20 08:00 | 2003-12-19 17:00 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 22.011, 22.101, 22.115, 22.129
3321 | 32044 | Stage 2 for Network Sharing | - | 2 | Rel-6 | S2 | 2003-02-27 08:00 | 2004-07-30 17:00 | 100% | SP-030123 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 23.002, 23.060, 23.221, 23.236, new TS 23.251, TR 23.851
3322 | 11043 | Network sharing - stage 3 | - | 2 | Rel-6 | N1 | 2003-05-23 08:00 | 2004-12-08 17:00 | 100% | NP-040429 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 23.008, 23.122, 24.007, 24.008, 29.018
3323 | 22004 | Enhancement of the support of network sharing in the UTRAN | NTShar-UTRANEnh | 2 | Rel-6 | R2 | 2003-09-19 | 2003-09-19 | 100% | - | - | TeliaSonera | Anders.Dahlen@TeliaSonera.com | - | 25.401, 25.413, 25.331, 25.304
3324 | 25004 | Conformance Test Aspects – Network Sharing | NTShar-UTRANEnh_Test | 2 | Rel-6 | R5 | 2005-03-11 08:00 | 2006-03-10 17:00 | 100% | - | - | TeliaSonera | Niklas.Wiren@TeliaSonera.com | - | 34.108, 34.123-1, 34.123-2, 34.123-3
3325 | 32016 | QoS Improvements | QoS1 | 1 | Rel-6 | S2,N3 | 2002-07-15 08:00 | 2004-12-08 17:00 | 100% | SP-010719 | - | Nokia | - | - | 23.107, 23.207, 23.221
3326 | 32017 | FS on Dynamic Policy control enhancements for end-to-end QoS | - | 2 | Rel-6 | S2 | 2002-07-15 08:00 | 2004-04-23 17:00 | 100% | SP-020540 | - | Nortel | Claire Mousset | - | 23.917 withdrawn (Contents all in 23.207)
3327 | 32059 | Definition of the Gq interface | - | 2 | Rel-6 | S2 | 2003-07-01 08:00 | 2004-04-23 17:00 | 100% | SP-030306 | - | - | Janne Rinne | - | 23.207
3328 | 13016 | Gq interface specification for Dynamic Policy control enhancements – Stage 3 | - | 2 | Rel-6 | N3 | 2003-08-29 08:00 | 2004-12-08 17:00 | 100% | NP-030198 | - | Nokia | Anna.Sillanpaai@nokia.com | [DAB - 25.05.04] - Delayed to Sept - possibly Dec 2004 | 29.207, 29.208, 29.209
3329 | 33002 | Subscriber certificates | SEC1-SC | 1 | Rel-6 | S3,S2,N1,N4,T3,OMA | 2002-02-25 08:00 | 2004-12-08 17:00 | 100% | SP-010622 | - | Nokia | valtteri.niemi@nokia.com | SP#14 approved WID | -
3330 | 32705 | Stage 1 of Subscriber certificates | - | 2 | Rel-6 | S3 | 2002-02-25 08:00 | 2002-09-12 17:00 | 100% | SP-010622 | - | Nokia | valtteri.niemi@nokia.com | - | New (33.220, 33.221, 33.222, 33.246, 33.919)
3331 | 32706 | Architecture review | - | 2 | Rel-6 | S2 | 2002-10-14 08:00 | 2002-11-14 17:00 | 100% | - | - | Nokia | - | - | -
3332 | 14504 | Stage 3 for Subscriber certificates | - | 2 | Rel-6 | N4,T3 | 2003-09-19 08:00 | 2004-11-30 17:00 | 100% | NP-030399 | - | Nokia | Lauri Laitinen | Finished in CN4#26 | 23.003, 23.008, 29.109, 29.230, T3 31.102, 31.103, 31.111
3333 | 11049 | Stage 3 Ua & Ub interfaces | - | 2 | Rel-6 | N1 | 2003-11-03 08:00 | 2004-12-08 17:00 | 100% | - | - | Nokia | - | - | 24.109
3334 | 60007 | OMA dependencies on Subscriber certificates | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-06-08 17:00 | 100% | - | - | Nokia | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040420 | -
3335 | 15010 | Rel-6 Open Service Access (OSA) enhancements | OSA3 | 1 | Rel-6 | N5 | 2002-10-31 08:00 | 2005-03-10 17:00 | 100% | NP-040351 | - | Alcatel | Chelo.Abarca@alcatel.fr | CN#25: Updated WID NP-040351 replaces NP-040144. | 22.127, 23.198, 29.198, 29.199, 29.998
3336 | 31040 | Scope of the Open Service Access Release 6 | - | 2 | Rel-6 | S1 | 2003-03-28 08:00 | 2003-06-27 17:00 | 100% | SP-030038 | - | - | - | - | -
3337 | 15038 | OSA Stage 2 | - | 2 | Rel-6 | N5 | 2004-08-13 08:00 | 2005-03-10 17:00 | 100% | - | - | - | - | Inherited by CN5 from SA2 at TSG#25 Sep 2004. SA2's 23.127 (OSA/VHE Stage 2) replaced from Rel-6 onwards by a new CN5 TS 23.198 (Stage 2 OSA-only). | 23.198 OSA Stage 2-ONLY replaces 23.127 (OSA/VHE) from Rel-6 onwards
3338 | 15026 | Multi Media Messaging function | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2004-09-10 17:00 | 100% | - | - | - | - | - | 29.198-15
3339 | 15028 | Policy management extensions | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2003-12-12 17:00 | 100% | - | - | - | - | - | 29.198, 29.998
3340 | 15029 | TS on Presence and Availability Management (from the PRESNC WI) | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2004-03-26 17:00 | 100% | - | - | - | - | N5#26: Split WI into TS & TR. | 29.198-14
3341 | 15032 | OSA interfaces at different levels of abstractions (Parlay X, Web services) | - | 2 | Rel-6 | N5 | 2003-07-14 08:00 | 2004-09-10 17:00 | 100% | - | - | - | - | - | 29.199
3342 | 15033 | Introduction of migration support mechanism | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2003-12-10 17:00 | 100% | - | - | - | - | - | 29.198, 29.998
3343 | 15036 | Framework Function for Federation | - | 2 | Rel-6 | N5 | 2003-02-03 08:00 | 2003-12-12 17:00 | 100% | - | - | - | - | - | 29.198, 29.998
3344 | 60008 | OMA potential overlaps with 3GPP OSA Stage 3 (Web services) | - | 2 | Rel-6 | OMA | 2003-12-18 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | TSG#25 Approved CN5 29.199 Parlay X Web services. Ongoing 3GPP/OMA co-ordination to avoid OMA producing conflicting/OVERLAPING specs (NP-040283/SP-040493). | -
3345 | 15037 | Deleted - TR on Presence and Availability Management (from the PRESNC WI) | - | 2 | Rel-6 | N5 | 2004-09-17 17:00 | 2004-09-17 17:00 | 100% | - | - | - | - | N5#26:TR Completion 09/04; consistent with CN1 delayed Rel-6 completion. | -
3346 | 50401 | Addition of frequency bands to GSM (TAPS) | TAPS | 1 | Rel-6 | GP | 2002-06-28 08:00 | 2005-01-28 17:00 | 100% | GP-022072 | - | Nokia | Torben Themsen | - | -
3347 | 50094 | Addition of frequency bands to GSM – Changes to core specs | TAPS-Specs | 2 | Rel-6 | G1 | 2002-11-15 08:00 | 2002-12-20 17:00 | 100% | GP-022073 | - | Nokia | Torben Themsen | - | -
3348 | 51102 | Changes to core specs | - | 3 | Rel-6 | G1 | 2002-11-15 08:00 | 2002-12-20 17:00 | 100% | GP-022073 | - | Nokia | Torben Themsen | - | -
3349 | 54102 | Deleted - Addition of frequency bands to GSM – Changes for conformance tests | TAPS-Conf | 2 | Rel-6 | G4 | 2002-06-28 08:00 | 2005-01-28 17:00 | 100% | GP-022074 | - | Nokia | Torben Themsen | - | -
3350 | 54103 | Deleted - 51.010-1 Add testing | - | 3 | Rel-6 | G4 | 2002-06-28 08:00 | 2005-01-28 17:00 | 100% | GP-022074 | - | Nokia | Torben Themsen | - | -
3351 | 50130 | Seamless support of streaming services in A/Gb mode | SSStrea | 1 | Rel-6 | GP,S3 | 2000-01-03 08:00 | 2005-06-17 17:00 | 100% | GP-022561 | - | Vodafone | José Luis Carrizo Martínez | - | -
3352 | 51131 | Identification of requirements for streaming | - | 2 | Rel-6 | G1 | 2003-06-27 08:00 | 2003-08-29 17:00 | 100% | GP-022564 | - | Vodafone | José Luis Carrizo Martínez | - | -
3353 | 51133 | Requirements for streaming | - | 3 | Rel-6 | G1 | 2003-06-27 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3354 | 51132 | Performance study of cell change mechanisms | - | 2 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | GP-022562 | - | Vodafone | José Luis Carrizo Martínez | - | -
3355 | 51134 | Performance of NACC | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3356 | 51135 | Performance of cell change in DTM for the PS domain | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3357 | 51136 | Handover for Seamless support of streaming services in A/Gb mode | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3358 | 52131 | Reduction of service interruption times and packet loss during mobility procedures | - | 2 | Rel-6 | G2 | 2003-06-27 08:00 | 2005-06-17 17:00 | 100% | GP-022563 | - | Vodafone | José Luis Carrizo Martínez | Completed at GERP#17 | -
3359 | 52133 | optimizations of existing mechanisms/procedures | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2003-11-21 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3360 | 52134 | Inter-system NACC | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2003-11-21 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3361 | 52135 | PS Handover (within GERAN and between GERAN and UTRAN) | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2005-06-17 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3362 | 52136 | Dependency to other features of Reduction of service interruption times and packet loss during mobility procedures | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2003-11-21 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | -
3363 | 54131 | Deleted - MS conformance testing for Seamless support of streaming services in A/Gb mode | - | 2 | Rel-6 | G3new | 2003-12-19 08:00 | 2004-01-30 17:00 | 100% | GP-023424 | - | Vodafone | José Luis Carrizo Martínez | Marked as stopped 10/2009 | -
3364 | 54132 | Deleted - MS conformance tests for Seamless support of streaming services in A/Gb mode | - | 3 | Rel-6 | G4,G5 | 2003-12-19 08:00 | 2004-01-30 17:00 | 100% | GP-023424 | - | Vodafone | José Luis Carrizo Martínez | Marked as stopped 10/2009 | -
3365 | 33013 | GERAN A/Gb mode security enhancements | - | 2 | Rel-6 | S3 | 2002-09-26 08:00 | 2005-01-28 17:00 | 100% | SP-030107 | - | Vodafone | peter.howard@vodafone.com | SP#19 approved WID | 33.102
3366 | 34300 | Performance characterisation of default codecs for PS conversational multimedia application | CODCAR | 1 | Rel-6 | S4 | 2002-09-13 08:00 | 2004-06-10 17:00 | 100% | SP-020433 | - | Nokia | pasi.s.ojala@nokia.com | - | 26.935
3367 | 31030 | Study on Privacy Capability | PrivCap | 1 | Rel-6 | S1 | 2003-11-10 08:00 | 2004-03-03 17:00 | 100% | SP-020579 | - | Lucent | Michael Boote (mboote@alcatel-lucent.com) | - | 22.949
3368 | 35010 | Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM6 | 1 | Rel-6 | S5 | 2002-09-12 08:00 | 2005-03-11 17:00 | 100% | SP-040766 | - | - | - | SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4. | -
3369 | 35011 | Principles, high level Requirements and Architecture | - | 2 | Rel-6 | S5 | 2002-09-12 08:00 | 2004-09-16 17:00 | 100% | SP-040767 | - | Motorola | - | SP#25 09/2004 completed | 32.101, 32.102
3370 | 35012 | Performance Management | - | 2 | Rel-6 | S5 | 2002-09-12 08:00 | 2004-12-16 17:00 | 100% | SP-040782 | - | Nortel | - | SP#26 12/2004 completed | 32.401, 32.403, 52.402, 32.411, 32.412, 32.413, 32.432, 32.435, 32.436
3371 | 35014 | Network Infrastructure Management | - | 2 | Rel-6 | S5 | 2002-09-12 08:00 | 2004-12-16 17:00 | 100% | SP-040789 | - | Ericsson | thomas.tovinger@ericsson.com | SP#26 12/2004 completed | 32.150/1/2, 32.805, 32.111-5, 32.313/4, 32.331/2/3/4/5, 32.341/2/3/4, 32.351/2/3/4, 32.361/2/3/4, 32.371/2/3/4, 32.804, 32.675, 32.690, 32.695, 32.71/2/3/4/5, 32.741/2/3/4/5
3372 | 35015 | Rel-6 Trace Management | OAM-Trace | 2 | Rel-6 | S5,N4,R3 | 2002-09-20 08:00 | 2005-03-11 17:00 | 100% | SP-040782 | - | Nokia | kari.t.ronka@nokia.com | SP#26 12/2004 SA5 completed 12/04. Signalling Based Trace Activation for IMS (SIP) moved to Rel-7. Reason: CN1 cannot complete 24.229 trace without IETF dependency => estimate 05/2005. | -
3373 | 35022 | Subscriber and UE trace management | - | 3 | Rel-6 | S5 | 2002-09-20 08:00 | 2004-12-16 17:00 | 100% | - | - | Nokia | kari.t.ronka@nokia.com | SP#26 12/2004 completed | 32.421, 32.422, 32.423, 52.008
3374 | 23013 | Subscriber and equipment trace in UTRAN | OAM-Trace-RAN | 3 | Rel-6 | R3 | 2003-06-06 08:00 | 2004-06-15 17:00 | 100% | - | - | Nortel | Yann Sehedi (sehedic@nortelnetworks.com) | - | 25.413, 25.420, 25.423
3375 | 14016 | Trace Management, Stage3 | - | 3 | Rel-6 | N4 | 2004-06-09 08:00 | 2005-03-11 17:00 | 100% | NP-040411 | - | Nokia | seppo.kauntola@nokia.com | - | 23.205, 29.232, 29.060, 29.002, 29.228
3376 | 35016 | Rel-6 Charging Management | CH | 1 | Rel-6 | S5,S2,N3 | 2002-11-21 08:00 | 2005-06-09 17:00 | 100% | SP-040773 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | SP#28 Target 09/2005 for WLAN Charging 32.252 | -
3377 | 35037 | Charging architecture and principles | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.240
3378 | 35024 | Charging Data Record (CDR) file format and transfer | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-03-18 17:00 | 100% | - | - | - | - | SP#23 03/2004 completed | 32.297
3379 | 35025 | CDR parameter description | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2005-06-09 17:00 | 100% | - | - | - | - | SP#28 06/2005 completed | 32.298
3380 | 35026 | Diameter charging applications | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.299
3381 | 35027 | Online Charging System (OCS) architecture study | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2003-09-18 17:00 | 100% | - | - | - | - | SP#21 09/2003 completed | 32.815
3382 | 35028 | OCS: Applications and interfaces | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-12-16 17:00 | 100% | - | - | - | - | SP#26 12/2004 completed | 32.296
3383 | 35017 | Charging Management for Bearer level | CH-BC | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | SP-030048 | - | Nokia | Benni ALEXANDER | SP#28 Target 09/2005 for WLAN Charging 32.252 | -
3384 | 35029 | CS domain charging | - | 3 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-03-18 17:00 | 100% | - | - | - | - | SP#23 03/2004 completed | 32.250
3385 | 35030 | PS domain charging | - | 3 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.251
3386 | 35031 | CDR transfer | - | 3 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.295
3387 | 35019 | Charging Management for the Service domain | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2005-06-09 17:00 | 100% | SP-040778 | - | Siemens | Gerald.Goermer@nsn.com | SP#26: Updated WID SP-040778 was SP-030050. Target completion 06/2005. Consisting of MMS-CH, LCS-CH, WLAN-CH, POC-CH, MBMS-CH | 32.252, 32.270, 32.271, 32.272
3388 | 32030 | Overall architectural aspects of IP flow based bearer level charging | CH-FBC | 2 | Rel-6 | S2,N3 | 2002-11-21 08:00 | 2005-03-11 17:00 | 100% | SP-040041 | - | - | - | - | 23.125
3389 | 32069 | Overall definition of FBC architecture | - | 3 | Rel-6 | S2 | 2002-11-21 08:00 | 2004-03-02 17:00 | 100% | - | - | - | - | - | -
3390 | 32070 | Study on providing policy control with FBC | - | 3 | Rel-6 | S2 | 2004-02-02 08:00 | 2004-07-30 17:00 | 100% | - | - | - | - | - | -
3391 | 13020 | Gx interface for flow based charging | - | 3 | Rel-6 | N3 | 2004-02-02 08:00 | 2004-12-08 17:00 | 100% | NP-040245 | - | Nokia | juha.a.rasanen@nokia.com | - | 29.210
3392 | 13021 | Rx interface for flow based charging | - | 3 | Rel-6 | N3 | 2004-02-02 08:00 | 2005-03-11 17:00 | 100% | NP-040339 | - | Nortel | Javier Gonzalez Gallego | - | 29.209
3393 | 1800 | Rel-6 UICC/USIM enhancements and interworking | USAT1 | 1 | Rel-6 | T3 | 2000-09-25 08:00 | 2005-03-10 17:00 | 100% | - | - | - | - | - | -
3394 | 1802 | UICC API | USAT1-API | 2 | Rel-6 | T3 | 2002-03-20 08:00 | 2005-03-10 17:00 | 100% | - | - | - | - | 8/3/2001: test spec is based on R99 core spec, so deleted from Workplan | -
3395 | 43001 | Rel-6 Java API Test specification | - | 3 | Rel-6 | T3 | 2002-03-20 08:00 | 2002-06-10 17:00 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | - | -
3396 | 43006 | 2G/3G Java Card™ API based applet interworking | - | 3 | Rel-6 | T3 | 2003-03-17 08:00 | 2004-03-05 17:00 | 100% | TP-030031 | - | Oberthur Card Systems | Stéphane Andrau | - | -
3397 | 43007 | (U)SIM API for Java Card Testing | - | 3 | Rel-6 | T3 | 2003-03-17 08:00 | 2005-03-10 17:00 | 100% | TP-040186 | - | Axalto | Christophe Begassat (cbegassat@axalto.com) | - | 31.213
3398 | 43003 | Deleted - Java API Test specification (TS 43.019 Rel-5) | - | 3 | Rel-6 | T3 | 2002-05-30 08:00 | 2003-06-09 17:00 | 100% | TP-020122 | - | Microelectrónica Española | Mario Pérez | MOVED to Rel-5 WP | -
3399 | 43004 | Rel-6 USIM toolkit enhancements | USAT1-API-MULTOS | 2 | Rel-6 | T3 | 2000-09-25 08:00 | 2005-03-04 17:00 | 100% | - | - | Aspects Software | Neil Livingston | - | -
3400 | 502031 | C SIM API | - | 3 | Rel-6 | T3 | 2000-09-25 08:00 | 2002-09-27 17:00 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | 31.101, 31.102, 31.103, 31.111, 31.113, new 31.115, 31.116
3401 | 502032 | Specification of C SIM API | - | 4 | Rel-6 | T3 | 2000-09-25 08:00 | 2002-09-27 17:00 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | -
3402 | 502033 | Test specification for C SIM API | - | 4 | Rel-6 | T3 | 2001-01-01 08:00 | 2001-09-28 17:00 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | -
3403 | 43009 | USIM application toolkit Conformance Test Specification for Mobile Equipments | - | 3 | Rel-6 | T3 | 2003-12-05 08:00 | 2005-03-04 17:00 | 100% | TP-030259 | - | Gemplus | Eric.laffont@gemplus.com | - | 31.124
3404 | 34022 | Packet Switched Streaming Services Rel-6 | PSSrel6 | 1 | Rel-6 | S4,S1 | 2002-11-18 08:00 | 2005-12-07 17:00 | 100% | SP-020685 | - | Ericsson | olle.franceschi@ericsson.com | - | -
3405 | 31039 | Stage 1 for Packet Switched Streaming Services Rel-6 | - | 2 | Rel-6 | S1 | 2002-11-18 08:00 | 2003-03-17 17:00 | 100% | SP-020685 | - | Ericsson | - | 2nd resp SA4 | 22.233
3406 | 34024 | Stage 3 for Packet Switched Streaming Services Rel-6 | PSSrel6-Stage3 | 2 | Rel-6 | S4 | 2002-12-13 08:00 | 2005-12-07 17:00 | 100% | SP-020685 | - | Ericsson | olle.franceschi@ericsson.com | TR tbc by Sept. 05 | 26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936
3407 | 34023 | AMR-WB extension for high audio quality | AMRWB+ | 1 | Rel-6 | S4 | 2002-12-13 08:00 | 2005-12-07 17:00 | 100% | SP-030083 | - | Nokia | janne.m.vainio@nokia.com | TR tbc by Sept. 05 | 26.290, 26.304, 26.273, 26.274, 26.412, 26.936
3408 | 34027 | Codec Enhancements for Packet Switched Conversational Multimedia Applications | CEPSCM | 1 | Rel-6 | S4 | 2004-03-16 08:00 | 2004-12-16 17:00 | 100% | SP-040066 | - | Nokia | miska.hannuksela@nokia.com | - | 26.235, 26.236
3409 | 34028 | 3G-324M Improvements | 3G-324MI | 1 | Rel-6 | S4 | 2004-03-16 08:00 | 2004-12-16 17:00 | 100% | SP-040067 | - | Ericsson | bo.burman@ericsson.com | - | 26.111, 26.911
3410 | 51101 | Single Antenna Receiver Interference Cancellation (SAIC) | SAIC | 1 | Rel-6 | GP,G1 | 2002-11-15 08:00 | 2004-06-25 16:22 | 100% | GP-023400 | - | Cingular | Marc Grant | - | 45.903
3411 | 12006 | Enhancement of dialled service for CAMEL | EDCAMEL | 1 | Rel-6 | S1,N2,N4 | 2003-03-28 08:00 | 2003-12-31 17:00 | 100% | SP-020818 | - | Samsung | craig.bishop@samsung.com | - | 22.078
3412 | 12007 | Stages 2 and 3 for Enhancement of dialled service for CAMEL | - | 2 | Rel-6 | N2,N4 | 2003-03-28 08:00 | 2003-12-31 17:00 | 100% | NP-030153 | - | Samsung | Richard Brook | - | 23.008, 23.016, 23.018, 23.078, 29.002, 29.078
3413 | 32060 | Study on Bandwidth and resource savings in CS networks | BARS | 1 | Rel-6 | S2 | 2003-06-01 08:00 | 2004-06-16 17:00 | 100% | SP-030308 | - | - | - | - | 23.977
3414 | 50600 | Multiple TBF in A/Gb mode | MULTBF | 1 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2005-01-28 17:00 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | GP#17 Nov 2003 Moved from Rel-5 UID_50058 MULTBF (Only Multiple TBF Concept paper produced in Rel-5) | -
3415 | 50601 | Multiple TBF in A/Gb mode - Core | MULTBF-Agbmode | 2 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | - | -
3416 | 50602 | Multiple TBF Concept paper | - | 3 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | - | - | - | - | - | -
3417 | 50603 | Multiple TBF Stage 2 (43.064) CRs | - | 3 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | - | - | - | - | - | -
3418 | 50604 | Multiple TBF Stage 3 (44.060) CRs | - | 3 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | - | - | - | - | - | -
3419 | 50605 | Deleted - Multiple TBF in A/Gb mode – MS testing | MULTBF-Testing | 2 | Rel-6 | G3new | 2005-01-28 17:00 | 2005-01-28 17:00 | 100% | GP-022098 | - | Ericsson | gunnar.mildh@era.ericsson.se | - | -
3420 | 50096 | Alignment between the test-regimes for GERAN capable MS | ALTERE | 1 | Rel-6 | G3new | 2003-08-29 08:00 | 2005-09-02 17:00 | 100% | GP-032236 | - | Ericsson | anthony.toubassi@sonyericsson.com | - | -
3421 | 50097 | Determine the controversial test cases in the different test regimes and align them with 3GPP GERAN test specifications. Such test cases to be added to TS 51.010. | ALTERE-TC | 2 | Rel-6 | G3new | 2003-08-29 08:00 | 2005-09-02 17:00 | 100% | - | - | - | - | - | -
3422 | 50444 | Addition of U-TDOA in the CS domain | UTDOACS | 1 | Rel-6 | GP | 2003-11-21 08:00 | 2004-04-23 17:00 | 100% | GP-032773 | - | TruePosition | Bob Gross, Rhys Robinson (rlgross@trueposition.com) | Completed, except for potential LMU performance specs | -
3423 | 50445 | Addition of U-TDOA in the PS domain | UTDOAPS | 1 | Rel-6 | GP | 2003-06-27 08:00 | 2004-11-12 17:00 | 100% | GP-032774 | - | TruePosition | Bob Gross, Rhys Robinson (rlgross@trueposition.com) | - | -
3424 | 50101 | Downlink Advanced Receiver Performance | DARP | 1 | Rel-6 | GP | 2003-11-21 08:00 | 2005-09-02 17:00 | 100% | GP-041966 | - | Nokia | tommy.bysted@nokia.com | - | -
3425 | 50102 | DARP test scenarios | DARP-TS | 2 | Rel-6 | GP | 2003-11-21 08:00 | 2004-08-27 17:00 | 100% | GP-041967 | - | Nokia | tommy.bysted@nokia.com | - | -
3426 | 50103 | DARP for GMSK modulated voice services | DARP-GMSK | 2 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | GP-041968 | - | Nokia | tommy.bysted@nokia.com | - | -
3427 | 50104 | Performance requirements in 45.005 for DARP for GMSK modulated voice services | DARP-GMSK-Perf | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | -
3428 | 50105 | Radio subsystem link control in 45.008 for DARP for GMSK modulated voice services | DARP-GMSK-LC | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | -
3429 | 50106 | DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE | 2 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | GP-041969 | - | Nokia | tommy.bysted@nokia.com | - | -
3430 | 50107 | Performance requirements in 45.005 for DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE-Perf | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | -
3431 | 50108 | Radio subsystem link control in 45.008 for DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE-LC | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | -
3432 | 50115 | DARP Capability signalling | DARP-CAPSIG | 2 | Rel-6 | GP | 2003-11-21 08:00 | 2004-11-12 17:00 | 100% | GP-041970 | - | Nokia | tommy.bysted@nokia.com | - | -
3433 | 50116 | GERAN MS Conformance test for DARP | ARP-ConfTest | 2 | Rel-6 | G3new | 2004-08-27 08:00 | 2005-09-02 17:00 | 100% | GP-041971 | - | Nokia | tommy.bysted@nokia.com | - | -
3434 | 50109 | Reduction of PS service interruption in Dual Transfer Mode | PSintDTM | 1 | Rel-6 | G2 | 2003-11-21 08:00 | 2005-06-24 17:00 | 100% | GP-032548 | - | Siemens | toby.proctor@roke.co.uk | - | -
3435 | 50110 | Use case and requirement definition | PSintDTM-Req | 2 | Rel-6 | G2 | 2003-11-21 08:00 | 2004-04-23 17:00 | 100% | GP-032549 | - | Siemens | toby.proctor@roke.co.uk | - | -
3436 | 50111 | Performance Study of Current Procedures | PSintDTM-Perf | 2 | Rel-6 | G2 | 2003-11-21 08:00 | 2004-04-23 17:00 | 100% | GP-032550 | - | Siemens | toby.proctor@roke.co.uk | - | -
3437 | 50112 | Reduction of service interruption times and packet loss during Dual Transfer Mode and mobility procedures | PSintDTM-Reduct | 2 | Rel-6 | G2 | 2004-04-23 08:00 | 2004-11-12 17:00 | 100% | GP-032551 | - | Siemens | toby.proctor@roke.co.uk | - | -
3438 | 50113 | Deleted - MS Conformance testing - Reduction of PS service interruption in DTM | PSintDTM-ConfMS | 2 | Rel-6 | G3new | 2004-06-25 08:00 | 2005-06-24 17:00 | 100% | - | - | - | - | - | -
3439 | 50114 | Deleted - BTS Conformance testing - Reduction of PS service interruption in DTM | PSintDTM-ConfBTS | 2 | Rel-6 | G3new | 2005-06-24 17:00 | 2005-06-24 17:00 | 100% | - | - | - | - | - | -
3440 | 12008 | CAMEL prepay interworking with SCUDIF | SCCAMEL | 1 | Rel-6 | N4,N3,S1 | 2003-12-08 08:00 | 2004-10-05 10:24 | 100% | NP-030584 | - | Nokia | Keijo.Palviainen@Nokia.Com | - | 22.078, 23.078, 29.078, 29.002, 23.172
3441 | 31046 | Circuit Switched Video and Voice Service Improvements | CS_VSS | 1 | Rel-6 | S2,N1 | 2004-01-12 08:00 | 2005-09-02 17:00 | 100% | SP-040331 | - | Vodafone | John Watson | - | -
3442 | 31047 | Deleted - Stage 1 - Requirements | - | 2 | Rel-6 | S1 | 2004-01-12 08:00 | 2004-10-14 17:00 | 100% | SP-040331 | - | Vodafone | John Watson | - | 22.101
3443 | 32071 | Stage 2 Study on architecture alternatives | - | 2 | Rel-6 | S2 | 2004-01-12 08:00 | 2004-12-16 17:00 | 100% | SP-040331 | - | Vodafone | chris.pudney@vodafone.com | - | 23.903
3444 | 32072 | Deleted - Stage 2 description on Redial | - | 2 | Rel-6 | S2 | 2004-05-03 08:00 | 2004-12-16 17:00 | 100% | SP-040331 | - | Vodafone | chris.pudney@vodafone.com | - | -
3445 | 11053 | Switching between voice and video call - Redial solution | - | 2 | Rel-6 | N1 | 2005-01-03 08:00 | 2005-06-17 17:00 | 100% | SP-040331 | - | Vodafone | - | - | 23.009, 24.008
3446 | 52137 | Deleted - CS_VSS - GERAN2 Part | - | 2 | Rel-6 | G2 | 2005-09-02 17:00 | 2005-09-02 17:00 | 100% | SP-040331 | - | Vodafone | - | - | -
3447 | 13017 | Deleted - CS_VSS - CN3 Part | - | 2 | Rel-6 | N3 | 2004-10-14 17:00 | 2004-10-14 17:00 | 100% | SP-040331 | - | Vodafone | - | - | -
3448 | 13024 | Reorganisation of CS Data Specifications | CS Data | 1 | Rel-6 | N3 | 2004-11-19 08:00 | 2004-12-08 17:00 | 100% | NP-040563 | - | Siemens | Thomas.Belling@nsn.com | Created at TSG#27 as 100 % complete | 23.910, 29.007, New 23.202
3449 | 50553 | Generic Access to A/Gb Interface (GAAI) | GAAI | 1 | Rel-6 | GP | 2004-06-25 08:00 | 2006-01-20 17:00 | 100% | GP-042247 | - | Motorola | - | - | -
3450 | 50544 | FS on GAAI | GAAG | 2 | Rel-6 | GP | 2004-06-25 08:00 | 2004-08-27 17:00 | 100% | GP-041592 | - | Motorola | - | Feasibility Study | 43.901
3451 | 50554 | GAAI – Stage 2 | GAAI-Stage2 | 2 | Rel-6 | GP | 2004-08-27 08:00 | 2005-04-08 17:00 | 100% | - | - | Ericsson | jari.vikberg@ericsson.com | - | 43.318
3452 | 50555 | GAAI – Stage 3 | GAAI-Stage3 | 2 | Rel-6 | GP | 2004-08-27 08:00 | 2005-04-08 17:00 | 100% | - | - | - | - | - | 44.318
3453 | 50556 | MS Conformance Test for GAAI | GAAI-CT | 2 | Rel-6 | GP | 2004-08-27 08:00 | 2006-01-20 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | -
3454 | 50559 | Support of PS Handover for GERAN A/Gb mode | SPSHAGB | 1 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051160 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB- Originally Started Nov 2003 as GP-030443 | -
3455 | 50560 | Stage 2 for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-Stage2 | 2 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051161 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-Stage2 | 43.129
3456 | 50561 | PS handover for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-PSHO | 2 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051162 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-PSH | -
3457 | 50562 | Definition of radio resource management functionality for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-RRM | 2 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051163 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-RRM | -
3458 | 33018 | Study on (U)SIM Security Reuse by Peripheral Devices on Local Interfaces | - | 1 | Rel-6 | S3 | 2003-07-03 08:00 | 2003-12-26 17:00 | 100% | SP-030341 | - | Toshiba | Raziq Yaqub (ryaqub@tari.toshiba.com) | SP#20 approved WID | 33.817
3459 | 33021 | Study on Security for early IMS | SEC-IMS | 1 | Rel-6 | S3 | 2004-10-01 08:00 | 2005-03-28 17:00 | 100% | SP-040691 | - | Vodafone | Peter.Howard@vodafone.com | SP#24 approved WID. SP#46 withdrawn TR 33.978 from Rel-8 onwards | 33.978
3460 | 60111 | (Small) Technical Enhancements and Improvements for Rel-6 | TEI6 | 1 | Rel-6 | SP,CP,RP,GP | 2006-06-02 08:00 | 2006-06-02 08:00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 6 CR not related to any feature and with very limited impact on the system. Moved in from Stoyan/Testing WP | -
3461 | 25019 | Test - (Small) Technical Enhancements and Improvements for Rel-6 | TEI6_Test | 1 | Rel-6 | R5,T1 | 2006-06-02 08:00 | 2008-05-06 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 4 conformance testing | 34.108,34.121-1/2,34.122,34.123-1/2/3
3462 | 31029 | Deleted - Study of Feature Interactions Requirements | FINTER | 1 | Rel-6 | S1 | 2004-09-16 17:00 | 2004-09-16 17:00 | 100% | SP-020578 | - | - | - | SP#25 stopped | -
3463 | 50563 | Deleted EVGCS - Enhancements of VGCS in public networks for communication of public authority officials | - | 1 | Rel-6 | GP,G2 | 2005-08-25 08:00 | 2005-09-02 17:00 | 100% | GP-041837 | - | Siemens | kenneth.isaacs@roke.co.uk | GP#26 moved to Rel-7 as UID_11045 Enhancements of VGCS in public networks for communication of public authority officials | 44.018, 44.068, 48.008
3464 | 50500 | Deleted SCSAGB - Support of Conversational Services in A/Gb mode via the PS domain | - | 1 | Rel-6 | GP,N1 | 2003-11-21 17:00 | 2004-02-19 17:00 | 100% | GP-030443 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | - | -
3465 | 50501 | Deleted - Creation of a TR | SCSAGB-TR | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030444 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | - | -
3466 | 50502 | Deleted - Stage 2 | SCSAGB-Stage2 | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030445 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Started | -
3467 | 50503 | Deleted - Radio Channel Support | SCSAGB-RCS | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030446 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | -
3468 | 50504 | Deleted SCSAGB-RRM - Definition of radio resource management functionality | - | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030447 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | -
3469 | 50505 | Deleted - replaced by 50561 - PS Handover | SCSAGB-PSH | 2 | Rel-6 | GP,N1 | 2003-11-24 08:00 | 2004-02-19 17:00 | 100% | GP-030448 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Started | -
3470 | 50506 | Deleted SCSAGB-FLO - Modifications to FLO | - | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030449 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | -
3471 | 2 | Deleted - Rel-6 Evolutions of the transport in the UTRAN (ETRAN) | - | 1 | Rel-6 | RP | 2003-12-31 17:00 | 2003-12-31 17:00 | 100% | - | - | Alcatel | Francois Courau | Generic feature ETRAN | -
3472 | 0 | Release 5 Features | - | 1 | Rel-5 | NP,GP,RP,SP,TP | 2000-01-03 08:00 | 2001-03-29 17:00 | 100% | - | - | - | - | - | -
3473 | 625 | IP transport in the UTRAN | ETRAN-IPtrans | 1 | Rel-5 | R3 | 2000-07-17 08:00 | 2002-03-29 17:00 | 100% | - | - | Alcatel | Nicolas Drevon | - | -
3474 | 2455 | Feasibility study on SS7 signalling transportation in the core network with SCCP-User Adaptation (SUA) | FS_SS7IP | 1 | Rel-5 | N4 | 2001-03-12 08:00 | 2001-12-21 17:00 | 100% | NP-010460 | - | - | - | - | 29.903
3475 | 2476 | High Speed Downlink Packet Access | HSDPA | 1 | Rel-5 | R2,R5 | 2001-04-02 08:00 | 2007-03-09 17:00 | 100% | - | - | Motorola | Ravi Kuchibhotla | - | -
3476 | 2477 | Physical Layer for High Speed Downlink Packet Access | HSDPA-Phys | 2 | Rel-5 | R1 | 2001-04-05 08:00 | 2002-03-29 17:00 | 100% | RP-010262 | - | Motorola | Amitabha Ghosh (qa0047@email.mot.com) | - | -
3477 | 2478 | Layer 2 and 3 aspects | HSDPA-L23 | 2 | Rel-5 | R2 | 2001-04-05 08:00 | 2002-03-29 17:00 | 100% | - | - | Motorola | Ravi Kuchibhotla | - | -
3478 | 2479 | Iub/Iur protocol aspects - for High Speed Downlink Packet Access | HSDPA-IubIur | 2 | Rel-5 | R3 | 2001-04-02 08:00 | 2002-03-29 17:00 | 100% | RP-010262 | - | Motorola | Mike Diesen | - | -
3479 | 2480 | RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | HSDPA-RF | 2 | Rel-5 | R4 | 2001-04-09 08:00 | 2003-06-06 17:00 | 100% | RP-010262 | - | Motorola | Howard Benn | - | -
3480 | 25000 | Conformance Testing of HSDPA | HSDPA_Test | 2 | Rel-5 | R5 | 2003-09-19 08:00 | 2006-09-22 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3
3481 | 25012 | Conformance Testing of HCR TDD HSDPA | HSDPA_HCRTDD_Test | 2 | Rel-5 | R5 | 2006-03-10 08:00 | 2007-03-09 17:00 | 100% | - | - | IPWireless | drichards@ipwireless.com | - | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3
3482 | 501216 | Rel-5 Improvements of Radio Interface | - | 1 | Rel-5 | RP | 2000-08-14 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | -
3483 | 1471 | Base station classification for TDD | RInImp-BSClass | 2 | Rel-5 | R4 | 2000-08-14 08:00 | 2002-06-14 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | -
3484 | 1477 | TDD Base station classification | RInImp-BSClass-TDD | 3 | Rel-5 | R4 | 2000-08-14 08:00 | 2002-03-08 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | -
3485 | 24002 | Base Station Classification for 1.28 Mcps TDD option | RInImp-BSClass-LCRTDD | 3 | Rel-5 | R4 | 2001-06-15 08:00 | 2002-06-14 17:00 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | - | -
3486 | 2469 | Enhancement on the DSCH hard split mode | RInImp-DSCHhsp | 2 | Rel-5 | R1 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Samsung | Jaeyoel KIM | - | -
3487 | 1217 | Hybrid ARQ II/III | RInImp-HARQ | 2 | Rel-5 | R2 | 2000-08-21 08:00 | 2001-12-28 17:00 | 100% | - | - | Siemens | armin.sitte@siemens.com | Stopped at RP#14; work on this task was performed as part of High Speed Downlink Packet Access feature | -
3488 | 1221 | FS on USTS | RInImp-USTS | 2 | Rel-5 | R1 | 2000-08-14 08:00 | 2001-12-21 17:00 | 100% | - | - | SK Telecom | D. Kim | - | -
3489 | 1997 | FS on UE antenna efficiency test method performance requirements | RInImp-UEAnTM | 2 | Rel-5 | R4 | 2000-09-25 08:00 | 2001-09-14 17:00 | 100% | - | - | Allgon | O. Edvardsson | - | -
3490 | 2494 | FS on the re-introduction of the downlink SIR measurement | RInImp-SIR | 2 | Rel-5 | R4 | 2001-03-12 08:00 | 2001-12-14 17:00 | 100% | - | - | Ericsson | Torgny.Palenius@ericsson.com | - | -
3491 | 2493 | FS on mitigating the effect of CPICH interference at the UE | RInImp-CPICH_Intf | 2 | Rel-5 | R4 | 2001-03-19 08:00 | 2002-03-08 17:00 | 100% | - | - | Intel | shimon.moshavi@INTEL.COM | - | -
3492 | 1839 | Deleted - Conformance Test Spec. improvements in Radio Interface | - | 2 | Rel-5 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3493 | 2210 | Deleted - Testing improvement of inter-frequency and inter-system measurement | - | 3 | Rel-5 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3494 | 2211 | Deleted - Testing Hybrid ARQ II/III | - | 3 | Rel-5 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3495 | 500009 | Rel-5 RAN improvements | - | 1 | Rel-5 | RP | 2001-03-16 08:00 | 2007-03-09 17:00 | 100% | - | - | - | - | - | -
3496 | 656 | RRM optimization for Iur and Iub | RANimp-RRMopt | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-06-04 17:00 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | -
3497 | 23000 | Iur common transport channel efficiency optimization | RANimp-RRMopt-ctc | 3 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Shahrokh Amirijoo | - | -
3498 | 23001 | Iur neighbouring cell reporting efficiency optimization | RANimp-RRMopt-ncr | 3 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Shahrokh Amirijoo | - | -
3499 | 23002 | FS Introduction of direct transport bearers between SRNC and Node-B | RAN-imp-RRMopt-DTB | 3 | Rel-5 | R3 | 2001-06-15 08:00 | 2002-06-04 17:00 | 100% | - | - | Ericsson | Risto Sepponen | FS was closed and introduction of WI not agreed at RAN #16 | -
3500 | 2488 | RL Timing Adjustment | RANimp-RLTA | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Elena Voltolina | - | -
3501 | 2489 | Separation of resource reservation and radio link activation | RANimp-SepRR | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | -
3502 | 23003 | FS SRNS Relocation Procedure Enhancement | RANimp-SRNS | 2 | Rel-5 | R3 | 2001-06-15 08:00 | 2002-09-03 17:00 | 100% | - | - | Nokia | Olivier Guyot | - | -
3503 | 2490 | FS Improvement of Radio Resource Management across RNS and RNS/PSS | RANimp-ImpRRM | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2001-12-21 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | FS was closed and WI was introduced at RAN #14 | -
3504 | 2491 | Re-arrangements of Iub transport bearers | RANimp-TTPS | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | -
3505 | 22000 | RAB support enhancement for Rel-5 | RANimp-RABSE5 | 2 | Rel-5 | R2 | 2001-04-02 08:00 | 2002-06-28 17:00 | 100% | - | - | Nokia | Juha Mikola | RFC 3095 context relocation | -
3506 | 25005 | Testing of ROHC performance | RANimp-RABSE5_Test | 2 | Rel-5 | R5 | 2005-09-09 08:00 | 2007-03-09 17:00 | 100% | - | - | Nokia | jarkko.hellsten@nokia.com | - | 34.108, 34.123-1, 34.123-2, 34.123-3
3507 | 21001 | Beamforming requirements for UE | RANimp-BFR-UE | 2 | Rel-5 | R1 | 2001-09-21 08:00 | 2001-12-14 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | - | -
3508 | 21002 | Support of Site Selection Diversity Transmission in UTRAN | RANimp-SSDT | 2 | Rel-5 | R1 | 2001-12-14 08:00 | 2002-06-04 17:00 | 100% | - | - | NEC | - | RP-020356 | -
3509 | 2472 | Node B Synchronisation for 1.28 Mcps TDD | RANimp-NBSLCR | 2 | Rel-5 | R1 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | CATT | Jinling HU | - | -
3510 | 2102 | Deleted - Conformance Test Aspects - RAN Improvements | - | 2 | Rel-5 | T1 | 2002-01-01 08:00 | 2004-03-01 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3511 | 2222 | Deleted - Testing Radio access bearer support enhancements | - | 3 | Rel-5 | T1 | 2002-01-01 08:00 | 2002-09-02 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3512 | 41010 | Deleted - General changes to TS34.121 and TS34.122 corresponding to release 5 | RANimp-test, TEI5 | 3 | Rel-5 | T1 | 2003-03-03 08:00 | 2004-03-01 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34.121, 34.122
3513 | 23004 | UTRAN Sharing in Connected Mode | NETSHARE | 1 | Rel-5 | R3 | 2001-12-03 08:00 | 2002-09-03 17:00 | 100% | - | - | Ericsson | Martin Israelsson | Formerly 'Shared Network support in connected mode', renamed at RAN #16. | -
3514 | 1273 | Provisioning of IP-based multimedia services | IMS | 1 | Rel-5 | S1,S2,S3,S5,NP,T3,T1,R5 | 2000-01-03 08:00 | 2006-12-01 17:00 | 100% | SP-000216 | - | Openwave | Mark Cataldo | - | -
3515 | 1274 | Call control and roaming to support IMS in UMTS | IMS-CCR | 2 | Rel-5 | S2,R5 | 2000-01-03 08:00 | 2006-12-01 17:00 | 100% | SP-010339 | - | Lucent | Liz Daniel | - | -
3516 | 1633 | Stage 1 for Call control and roaming to support IMS in UMTS | - | 3 | Rel-5 | S1 | 2000-02-21 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | Issues include e.g.: Roaming requirements, Requirements on supplementary services, Interworking requirements | 22.228
3517 | 1514 | Stage 2 (Architecture and Main flows) | - | 3 | Rel-5 | S2 | 2000-04-14 08:00 | 2001-03-23 17:00 | 100% | SP-000289 | - | Lucent | Liz Daniel | Issues include e.g.: Mobile IP, RAB selection principles, Optimized VoIP bearer mechanisms, SIP multimedia protocol | 23.228
3518 | 1296 | Impact on MM/CC/SM | IMS-CCR-IWMM | 3 | Rel-5 | N1 | 2000-08-28 08:00 | 2002-03-08 17:00 | 100% | NP-010434 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Per 26/2-02: This is understood to be the PCO & TFT CRs which CN1 provides to TSGN #15 for approval. If this is correct understanding, then the task is 100 % complete. | -
3519 | 2233 | SIP Call Control protocol for the IMS | - | 3 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | NP-010643 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | TSGN_10 approved the change:CN1 - SA2 SIP joint meeting spotted one more place for improvement: work tasks with ID 1998 and 1278 are actually subtasks under of single CN1 WT. One WI has been approved for the CN1 WT with title "SIP Call Control protocol | 24.228, 24.229, 23.218
3520 | 1998 | IMS signalling flows | - | 4 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | 24.228 | 24.228
3521 | 1278 | IMS stage 3 | - | 4 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | 24.229 | 24.229
3522 | 2255 | IMS Session Handling; stage 2 | - | 4 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | 23.218 | 23.218
3523 | 25006 | Conformance Test Aspects – IMS Call Control | IMS-CCR_Test | 3 | Rel-5 | R5 | 2005-03-11 08:00 | 2006-12-01 17:00 | 100% | - | - | Motorola | Jacob.John@motorola.com | - | 34.108, 34.229-1, 34.229-2, 34.229-3
3524 | 10004 | Main IETF dependencies | - | 3 | Rel-5 | NP | 2000-01-03 08:00 | 2002-06-14 17:00 | 100% | - | - | Lucent | - | - | -
3525 | 2521 | IETF: RFC 3261 (Session Initiation Protocol) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | -
3526 | 2523 | IETF: RFC 3262 (Reliability of provisional responses) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | -
3527 | 2522 | IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3528 | 2524 | IETF: RFC 3323 (SIP extensions for caller identity and privacy) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3529 | 2525 | IETF: RFC 3313 (SIP extensions for media authorization) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3530 | 11000 | IETF: RFC 3265 (specific event notification) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | -
3531 | 11001 | IETF: RFC editor Queue (refer method) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | Lucent | - | - | -
3532 | 11002 | IETF: RFC editor Queue (DHCP options for SIP servers) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3533 | 11004 | IETF: RFC 3267 (AMR and AMR WB RTP and SDP) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | -
3534 | 11005 | IETF: RFC 3266 (IPv6 support within SDP) | - | 4 | Rel-5 | N1 | 2000-01-03 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | -
3535 | 11022 | IETF: RFC 3311 (The Update method) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3536 | 11023 | IETF: RFC 3324 (Network Asserted Identity) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3537 | 11024 | IETF: RFC editor Queue (Various 3GPP Private Extensions) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | -
3538 | 1290 | Addressing | - | 4 | Rel-5 | S2 | 2000-10-09 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | - | -
3539 | 1291 | Architectural issues | - | 5 | Rel-5 | S2 | 2000-10-09 08:00 | 2001-08-31 17:00 | 100% | - | - | - | - | - | -
3540 | 1292 | Impact on HSS | - | 5 | Rel-5 | N4 | 2000-11-15 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | Covered by 29.228 & 29228 | -
3541 | 2530 | Service Examples (Work stopped) | IMS-Sex | 4 | Rel-5 | S1 | 2001-04-17 08:00 | 2002-06-14 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.928
3542 | 2531 | IMS Framework Report (work stopped) | IMS-FrWk | 5 | Rel-5 | S1 | 2001-04-17 08:00 | 2002-06-14 17:00 | 100% | - | - | SBC | Randolph Wohlert (rwohlert@tri.sbc.com) | - | 22.941
3543 | 1298 | Access Security for IMS | IMS-ASEC | 2 | Rel-5 | S3,T3 | 2001-10-08 08:00 | 2002-06-28 17:00 | 100% | SP-010323 | - | Ericsson | krister.boman@emw.ericsson.se | - | -
3544 | 43000 | IMS impacts on UICC (ISIM application) | - | 3 | Rel-5 | T3 | 2001-10-08 08:00 | 2002-06-21 17:00 | 100% | TP-010251 | - | Vodafone | Jeremy Norris | - | 33.102, New TS 31.103
3545 | 11014 | Deleted - SIP extensions for Integrity protection | - | 3 | Rel-5 | N1 | 2001-12-17 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | CN1 is not aware of any requirements and is not doing anything on this task | -
3546 | 2574 | Security Aspects of Requirement for Network Configuration Independence | SEC1-NCI | 2 | Rel-5 | S3 | 2001-07-02 08:00 | 2001-12-28 17:00 | 100% | SP-010324 | - | AT&T Wireless | hugh.shieh@attws.com | Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C | 33.203
3547 | 1299 | IMS Lawful Interception | IMS-LI | 2 | Rel-5 | S3 | 2000-09-04 08:00 | 2002-03-29 17:00 | 100% | SP-010621 | - | Reg TP | berthold.wilhelm@regtp.de | SP#17 completed | 33.106, 33.107, New 33.108
3548 | 35007 | Charging and OAM&P for IMS | IMS-OAM | 2 | Rel-5 | S5 | 2000-12-25 08:00 | 2002-06-12 17:00 | 100% | SP-010461 | - | - | - | - | 32-series
3549 | 2036 | Multimedia codecs and protocols for conversational PS services | IMS-CODEC | 2 | Rel-5 | S4 | 2000-07-26 08:00 | 2002-09-27 17:00 | 100% | SP-000398 | - | Toshiba, Nokia | B. Aronson (Toshiba), pasi.s.ojala@nokia.com | - | 26.235, 26.236
3550 | 2039 | Codecs | - | 3 | Rel-5 | S4 | 2000-07-26 08:00 | 2002-03-14 17:00 | 100% | SP-000398 | - | - | - | - | 26.235, 26.236
3551 | 34020 | Transport protocols | - | 3 | Rel-5 | S4 | 2002-03-12 08:00 | 2002-03-12 17:00 | 100% | - | - | Nokia | P. Ojala | - | 26.236
3552 | 34006 | recommendation for QoS parameter values for various media types | - | 3 | Rel-5 | S4 | 2001-12-31 08:00 | 2002-09-27 17:00 | 100% | - | - | - | - | - | -
3553 | 11025 | IETF: RFC 3310 (HTTP Digest Authentication using AKA) | - | 3 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | - | - | - | -
3554 | 11026 | IETF: RFC 3329 (Security mechanism agreement for SIP connections) | - | 3 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | - | - | - | -
3555 | 32003 | SIP message compression | - | 2 | Rel-5 | S2 | 2001-09-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3556 | 32004 | Stage 2 for SIP message compression | - | 3 | Rel-5 | S2 | 2001-09-24 08:00 | 2001-10-26 17:00 | 100% | - | - | - | - | - | -
3557 | 11015 | Compression signalling | - | 3 | Rel-5 | N1 | 2001-09-28 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3558 | 10001 | Stage 3 description of IMS interfaces | - | 2 | Rel-5 | NP | 2001-03-14 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | -
3559 | 1286 | Cx interface (HSS to CSCF) | - | 3 | Rel-5 | N4 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | NP-010626 | - | - | - | - | -
3560 | 14997 | Mp interface (MRFC - MRFP) enhancements | - | 3 | Rel-5 | N4 | 2001-03-14 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | [DAB 08-03-02] - No work required in CN4 | -
3561 | 11016 | Mw interface (CSCF to P-CSCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3562 | 11018 | Mr interface (CSCF to MRF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-03-29 17:00 | 100% | - | - | - | - | - | -
3563 | 14003 | Dx interface (I-CSCF to SLF) | - | 3 | Rel-5 | N4 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | CN4#11 30/11/01: No inputs received in CN4... | -
3564 | 13001 | Go interface (GGSN to PCF) | - | 3 | Rel-5 | N3 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | [DAB - 23/05/03] - 100 % complete | -
3565 | 11019 | ISC (IMS Service Control) Interface | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3566 | 14006 | Sh interface (HSS to AS) | - | 3 | Rel-5 | N4 | 2002-02-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | CN4#11 30/11/01: No inputs received in CN4... | -
3567 | 14998 | Si interface (HSS to IM-SSF) | - | 3 | Rel-5 | N4 | 2002-01-16 13:00 | 2002-08-30 17:00 | 100% | - | - | - | - | SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete) | -
3568 | 11020 | Gm interface (UE to CSCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3569 | 11027 | Mi interface (CSCF to BGCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3570 | 11028 | Mj interface (BGCF to MGCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3571 | 11029 | Mk interface (BGCF to BGCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3572 | 1310 | Support of VHE/OSA by entities and protocols of the IMS (e.g. CSCF) | IMS-ONOSA | 2 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998
3573 | 12000 | CAMEL control of IMS services | IMS-CAMEL | 2 | Rel-5 | N2 | 2001-04-16 08:00 | 2002-09-06 17:00 | 100% | NP-020305 | - | Lucent | Angelica Remoquillo | - | -
3574 | 12001 | Stage2 work 'general' | - | 3 | Rel-5 | N2 | 2001-04-16 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | -
3575 | 12002 | Stage3 work 'CAP' | - | 3 | Rel-5 | N2 | 2002-01-07 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | -
3576 | 12003 | Stage2 work 'Si interface' | - | 3 | Rel-5 | N2 | 2002-01-07 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | -
3577 | 12004 | Stage3 work 'Si interface' | - | 3 | Rel-5 | N4 | 2002-02-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | [DAB 08-03-02] - UID 12004 is MASTER of UID 14998... | -
3578 | 14004 | Deleted - SDM issues for CAMEL control of IMS | - | 3 | Rel-5 | N4 | 2002-02-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3579 | 31002 | Pre-pay/real-time charging in IMS | - | 2 | Rel-5 | S1 | 2001-06-15 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | -
3580 | 35005 | IMS Charging | OAM-CH | 2 | Rel-5 | S2,S5 | 2001-08-06 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.225
3581 | 32006 | Charging Implications of IMS architecture | - | 3 | Rel-5 | S2 | 2001-08-06 08:00 | 2001-11-16 17:00 | 100% | SP-010519 | - | - | - | - | -
3582 | 35006 | Charging management for IMS (off-line & on-line) | - | 3 | Rel-5 | S5 | 2001-11-19 08:00 | 2002-09-12 17:00 | 100% | - | - | - | - | - | 32.225
3583 | 34012 | Billing, accounting and call detail record aspects | - | 3 | Rel-5 | S5 | 2001-09-27 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | T-Mobile | Karl-Heinz.Nenner@T-MOBILE.DE | - | 32.225
3584 | 10002 | Other IETF dependencies | - | 2 | Rel-5 | NP | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Was introduced at SP#13 by Ileana Leuca (exact position in the WP and related WG have to be defined) | -
3585 | 11011 | IETF: draft-ietf-aaa-diameter - should be CN4 | - | 3 | Rel-5 | NP | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | -
3586 | 11999 | IETF: draft-johansson-aaa-diameter-mm-app - should be CN4 | - | 3 | Rel-5 | NP | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | -
3587 | 1844 | Conformance Test Aspects - Provisioning of IMS | IMS-TEST | 2 | Rel-5 | T1 | 2002-03-18 08:00 | 2002-12-27 17:00 | 100% | - | - | - | - | The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008 | -
3588 | 41004 | Testing of support for IMS - prose | - | 2 | Rel-5 | T1 | 2002-09-18 08:00 | 2003-09-30 17:00 | 100% | TP-030052 | - | Anritsu | dan.fox@eu.anritsu.com | Marked as stopped 12/2008 | 34.108, 34.123
3589 | 41005 | Testing of support for IMS - TTCN | - | 2 | Rel-5 | T1 | 2002-09-18 08:00 | 2004-03-03 17:00 | 100% | TP-030052 | - | Anritsu | dan.fox@eu.anritsu.com | Marked as stopped 12/2008 | 34.108, 34.123
3590 | 34001 | Extended Transparent End-to-End PS Streaming Service | PSS-E | 1 | Rel-5 | S4 | 2002-01-03 08:00 | 2003-03-17 17:00 | 100% | SP-010392 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.233, 26.234
3591 | 34002 | Stage 1 for Extended Transparent End-to-End PS Streaming Service | - | 2 | Rel-5 | S1 | 2002-11-18 08:00 | 2003-03-17 17:00 | 100% | SP-010392 | - | Vodafone | stephen.wolak@vodafone.com | 2nd resp SA4 | 22.233
3592 | 31032 | Interaction with other services | - | 3 | Rel-5 | S1 | 2002-11-18 08:00 | 2003-03-17 17:00 | 100% | - | - | Vodafone | stephen.wolak@vodafone.com | 2nd resp SA4. Marked as closed 12/2008 (was marked 65% complete) | 22.233
3593 | 34003 | Stage 2 (version Rel-5 of TS 26.234) | - | 2 | Rel-5 | S4 | 2002-01-03 08:00 | 2002-03-14 17:00 | 100% | SP-010392 | - | - | - | 2nd resp SA2 | 26.234
3594 | 34019 | RTP usage model | - | 2 | Rel-5 | S4 | 2002-01-03 08:00 | 2002-12-06 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | 26.937
3595 | 501637 | Rel-5 Open Service Access (OSA) enhancements | OSA1 | 1 | Rel-5 | S1,S3 | 1999-04-27 08:00 | 2002-12-20 17:00 | 100% | SP-000216 | - | Siemens | joerg.swetina@neclab.eu | - | 22.127, 23.127, 29.198-x, 29.998-x
3596 | 32010 | General Stage 2 for Rel-5 | - | 2 | Rel-5 | S2 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 47% complete) | -
3597 | 1429 | OSA APIs for Multimedia Call Control | OSA1-CSCF | 2 | Rel-5 | S2 | 2000-07-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | For Rel5 even if completed by March | -
3598 | 1430 | Stage 1 for OSA APIs for Multimedia Call Control | - | 3 | Rel-5 | S1 | 2000-07-11 08:00 | 2002-03-14 17:00 | 100% | - | - | Siemens | Manfred.leitgeb@siemens.at | - | 22.127
3599 | 15002 | Stages 2 and 3 for Multimedia Call Control | - | 3 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-04
3600 | 15003 | Generic user interaction - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-05
3601 | 15004 | OSA Charging - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-12
3602 | 15007 | Call Control Service Mapping; Multiparty Call Control SIP - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.998-04-4
3603 | 15999 | WSDL APIs for SOAP/HTTP - Stage 3 | - | 2 | Rel-5 | N5 | 2000-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198, 29.998
3604 | 1419 | OSA Security | OSA1-SEC | 2 | Rel-5 | S3 | 2000-07-11 08:00 | 2002-12-20 17:00 | 100% | SP-000302 | - | Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102
3605 | 2121 | Stage 1 for OSA Security | - | 3 | Rel-5 | S1 | 2000-07-11 08:00 | 2001-11-09 17:00 | 100% | - | - | Siemens | Manfred.leitgeb@siemens.at | - | 22.127
3606 | 1421 | OSA Stage 3 | - | 3 | Rel-5 | S3 | 2000-10-23 08:00 | 2002-06-14 17:00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102
3607 | 1422 | security related SCF(s) definition | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998
3608 | 1423 | OSA changes required from supporting platforms, e.g. gsmSCF, HLR | - | 3 | Rel-5 | S3 | 2000-09-11 08:00 | 2000-12-14 17:00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102
3609 | 15017 | OSA Security (moved from Rel-6) | - | 3 | Rel-5 | S3 | 2002-03-14 08:00 | 2002-12-20 17:00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102
3610 | 401424 | Interactions OSA - e-commerce | OSA1-ECOM | 2 | Rel-5 | S2 | 1999-04-27 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3611 | 1425 | Stage 1 for Interactions OSA - e-commerce | - | 3 | Rel-5 | S1 | 1999-04-27 08:00 | 2000-12-28 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | Marked as closed 12/2008 (was marked 95% complete) | 22.127
3612 | 1529 | Stages 2 and 3 for Interactions OSA - e-commerce | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998
3613 | 15005 | Policy Management - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-13
3614 | 15006 | Presence and Availability Management (PAM) - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-14
3615 | 1786 | LCS - OSA interfaces | OSA1-LCSI | 2 | Rel-5 | S1 | 2000-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | az: CN#13 - changed to Rel5 | -
3616 | 1787 | Stage 1 for LCS - OSA interfaces | - | 3 | Rel-5 | S1 | 2000-09-11 08:00 | 2000-12-08 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | - | 22.127
3617 | 2124 | Stage 2 for LCS - OSA interfaces | - | 3 | Rel-5 | S2 | 2000-12-11 08:00 | 2000-12-11 17:00 | 100% | - | - | Ericsson | Christophe GOURRAUD | az 24/05/01: Rel4 completion 90->100%. | 23.127
3618 | 1788 | Stage 3 for LCS - OSA interfaces | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998
3619 | 2540 | Access to User Profile | OSA2-UP | 2 | Rel-5 | S1 | 2001-06-01 08:00 | 2001-12-20 17:00 | 100% | - | - | - | - | - | -
3620 | 1433 | Retrieval of Terminal capabilities | OSA2-TC | 2 | Rel-5 | S2 | 2000-07-11 08:00 | 2002-12-13 17:00 | 100% | - | - | - | - | - | -
3621 | 1434 | Stage 1 for Retrieval of Terminal capabilities | - | 3 | Rel-5 | S1 | 2000-07-11 08:00 | 2001-01-10 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | - | 22.127
3622 | 1436 | Stages 2 and 3 for Retrieval of Terminal capabilities | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-12-13 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998
3623 | 2122 | Provisioning of the terminal capabilities | - | 3 | Rel-5 | T2 | 2001-04-02 08:00 | 2002-12-13 17:00 | 100% | - | - | - | - | According to T2 SWG1 M. Cataldo this is automatically supported by the MExE support of UAProf therefore 100% complete | 23.057
3624 | 1638 | CAMEL phase 4 | CAMEL4 | 1 | Rel-5 | S1 | 2000-04-17 08:00 | 2002-09-06 17:00 | 100% | NP-020486 | - | Nokia | keijo.palviainen@nokia.com | - | -
3625 | 1461 | Service requirements | - | 2 | Rel-5 | S1 | 2000-04-17 08:00 | 2002-06-14 17:00 | 100% | - | - | - | - | - | -
3626 | 2012 | Call Party Handling | CAMEL4-CPH | 2 | Rel-5 | N2 | 2000-07-10 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3627 | 2013 | Mid call procedure for MO and MT calls | CAMEL4-MCP | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3628 | 2014 | Interactions with Optimal Routing | CAMEL4-IOR | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | -
3629 | 2015 | Inclusion of flexible tone injection | CAMEL4-IFTI | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | -
3630 | 2016 | CSE control over MT SMS | CAMEL4-CCSMS | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | -
3631 | 2460 | Notification of GPRS mobility management to CSE | CAMEL4-NMM | 2 | Rel-5 | N2 | 2001-03-02 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3632 | 2458 | Provision of location information of called subscriber | CAMEL4-LOCB | 2 | Rel-5 | N2 | 2001-03-02 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | -
3633 | 2514 | Inclusion of ODB data in the CSE_HLR interface | CAMEL4-ODB | 2 | Rel-5 | N2 | 2001-07-09 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | Added on May 29, 2001 | -
3634 | 2515 | Location information during an ongoing call (Handover DP) | CAMEL4-HODP | 2 | Rel-5 | N2 | 2001-05-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3635 | 2516 | GPRS Any Time Interrogation | CAMEL4-ATI | 2 | Rel-5 | N2 | 2001-07-09 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3636 | 2599 | Transfer of IMEI (with SW version) to CSE (CAMEL4-ATI) | - | 2 | Rel-5 | N2 | 2001-07-09 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3637 | 12005 | Handling of partial implementations of CAMEL4 | CAMEL4-SUB | 2 | Rel-5 | N2 | 2002-03-08 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | stage2 and stage3 CRs for approval at CN#17 | -
3638 | 2464 | Rel-5 MExE enhancements | MEXE5 | 1 | Rel-5 | T2 | 2001-03-26 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | -
3639 | 2466 | MExE Rel-5 Improvements and Investigations | MEXE5-ENHANC | 2 | Rel-5 | T2 | 2001-03-26 08:00 | 2002-03-08 17:00 | 100% | TP-010071 | - | Motorola | Mark Cataldo | - | 22.057, 23.057
3640 | 1625 | Wideband Telephony Service - AMR | AMRWB | 1 | Rel-5 | S4 | 2000-01-01 08:00 | 2003-12-19 17:00 | 100% | SP-99354 | - | Siemens | Imre.Varga@mch.siemens.de | - | -
3641 | 62 | Specification | - | 2 | Rel-5 | S4 | 2000-01-01 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3642 | 31005 | Stage 1 for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S1 | 2001-10-01 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | - | -
3643 | 32007 | Stage 2 for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S4 | 2000-01-03 08:00 | 2000-04-17 17:00 | 100% | - | - | - | - | - | -
3644 | 1459 | Design Constraints for Wideband Telephony Service - AMR | - | 4 | Rel-5 | S4 | 2000-01-03 08:00 | 2000-02-07 17:00 | 100% | - | - | - | - | - | -
3645 | 1460 | General Description for Wideband Telephony Service - AMR | - | 4 | Rel-5 | S4 | 2000-02-07 08:00 | 2000-04-17 17:00 | 100% | - | - | - | - | - | -
3646 | 1626 | Feasibility Study for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S4 | 2000-04-28 08:00 | 2000-06-02 17:00 | 100% | SP-000024 | - | - | - | S4,TD SP-000024: TR 26.901 v.4.0.0 | 26.901
3647 | 1656 | N1 Aspects for Wideband Telephony Service - AMR | - | 3 | Rel-5 | N1 | 2001-09-21 08:00 | 2001-12-21 17:00 | 100% | - | - | - | - | Some of N1 tasks: Indication of supported codecs by the MS, Bearer cap negociation, codec indication to MS...... | -
3648 | 14005 | N4 work for Wideband Telephony Service - AMR | - | 3 | Rel-5 | N4 | 2002-02-13 08:00 | 2002-06-07 17:00 | 100% | N4-010538 | - | - | - | CN4#11 30/11/01: No inputs to CN4 at this meeting... | -
3649 | 67 | Codec issues | - | 3 | Rel-5 | S4 | 2000-01-03 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | -
3650 | 1627 | Codec qualification | - | 4 | Rel-5 | S4 | 2000-02-02 08:00 | 2000-05-31 17:00 | 100% | - | - | - | - | - | -
3651 | 74 | Codec selection tests | - | 4 | Rel-5 | S4 | 2000-06-01 08:00 | 2000-10-20 17:00 | 100% | - | - | - | - | - | -
3652 | 891 | Codec selection | - | 4 | Rel-5 | S4 | 2000-10-23 08:00 | 2000-10-27 17:00 | 100% | - | - | - | - | - | -
3653 | 34007 | TFO AMR-WB | AMRWB-TFO | 4 | Rel-5 | S4 | 2001-12-18 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | -
3654 | 890 | Other codec issues (verif., characterization) | - | 4 | Rel-5 | S4 | 2000-09-29 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | ANSI C-Code , Test Sequences, Speech Transcoding Functions, Error Concealment of lost frames, Source Controlled Bit-Rate Operation, Voice Activity Detector, Frame Structure | 26.976
3655 | 34008 | AMR-WB and narrrowband interworking | AMRWB-IWG | 4 | Rel-5 | S4 | 2001-09-27 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | -
3656 | 34009 | Interworking with fixed broadband networks | - | 4 | Rel-5 | S4 | 2001-09-27 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | -
3657 | 34010 | Tones and announcements | - | 4 | Rel-5 | S4 | 2001-09-27 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | -
3658 | 34011 | Deleted - WB Conferencing and WB Voice Group calls | - | 4 | Rel-5 | S1 | 2000-01-03 08:00 | 2000-01-03 17:00 | 100% | - | - | - | - | - | -
3659 | 1855 | Conformance tests (CRs to 34 series) | - | 3 | Rel-5 | T1 | 2000-01-01 08:00 | 2000-04-12 17:00 | 100% | - | - | - | - | - | -
3660 | 76 | Terminal Acoustic Characteristics | - | 4 | Rel-5 | S4 | 2000-01-01 08:00 | 2000-04-12 17:00 | 100% | - | - | - | - | - | -
3661 | 1628 | Definition for Terminal Acoustic Characteristics | - | 5 | Rel-5 | S4 | 2000-01-01 08:00 | 2000-01-31 17:00 | 100% | - | - | - | - | - | 26.131
3662 | 1629 | Test specification for Terminal Acoustic Characteristics | - | 5 | Rel-5 | S4 | 2000-02-01 08:00 | 2000-04-12 17:00 | 100% | - | - | - | - | - | 26.132
3663 | 34004 | Floating-point ANSI-C code for the AMR-WB speech codec | AMRWB-FP | 2 | Rel-5 | S4 | 2001-09-25 08:00 | 2002-03-14 17:00 | 100% | SP-010459 | - | Nokia | janne.m.vainio@nokia.com | - | 26.204
3664 | 80 | Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR | GAMRWB | 2 | Rel-5 | GP | 2000-01-03 08:00 | 2002-06-28 17:00 | 100% | GP-000453 | - | - | - | - | -
3665 | 50298 | Channel coding in 45.003 for Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2002-04-05 17:00 | 100% | - | - | - | - | 50098 -> 50298 | -
3666 | 2266 | Signalling for the A interface | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2001-06-29 17:00 | 100% | - | - | - | - | - | -
3667 | 2267 | Signalling for Iu | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3668 | 2268 | Receiver performance in TS 45.005 | - | 3 | Rel-5 | GP | 2001-04-02 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3669 | 50000 | Link Adaptation in 45.009 | - | 3 | Rel-5 | GP | 2001-03-26 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3670 | 2269 | Deleted - GERAN MS conformance test for AMR-WB | - | 2 | Rel-5 | GP | 2000-01-03 08:00 | 2003-12-19 17:00 | 100% | GP-000454 | - | - | - | Not started 02/2003. Marked as stopped 12/2008 | -
3671 | 2270 | Deleted - MS test for AMR-WB | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3672 | 2271 | GERAN BTS conformance test for AMR-WB | - | 2 | Rel-5 | GP | 2000-01-03 08:00 | 2002-12-02 17:00 | 100% | GP-000455 | - | - | - | - | -
3673 | 1826 | Rel-5 Terminal interfaces | TI, TLM5 | 1 | Rel-5 | T2 | 2001-05-14 08:00 | 2002-03-20 17:00 | 100% | - | - | - | - | - | -
3674 | 2573 | Terminal local model enhancements | TLM5 | 2 | Rel-5 | T2 | 2001-05-14 08:00 | 2002-03-20 17:00 | 100% | TP-010224 | - | - | - | - | 23.227
3675 | 1536 | Rel-5 Location Services enhancements | LCS1, Rel-5 | 1 | Rel-5 | S2,S1,S3,S5,N4,R2,R3,GP | 2000-04-03 08:00 | 2003-06-27 17:00 | 100% | SP-010518 | - | Nokia | Jan Kall | - | -
3676 | 1600 | UE positioning for Rel-5 Location Services enhancements | LCS1-Uepos, Rel-5 | 2 | Rel-5 | R2 | 2001-01-15 08:00 | 2002-03-29 17:00 | 100% | - | - | - | - | - | -
3677 | 2474 | UE positioning enhancements for 1.28 Mcps TDD | LCS-128Pos | 3 | Rel-5 | R2 | 2001-04-09 08:00 | 2002-03-29 17:00 | 100% | RP-010215 | - | CATT | Xiaohua Mei | - | 25.123, 25.224, 25.225, 25.302, 25.303, 25.304, 25.305, 25.331, 25.420, 25.423, 25.430, 25.433, New TR 25.859
3678 | 2125 | Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning | LCS-INTF | 3 | Rel-5 | R2 | 2001-01-15 08:00 | 2001-10-12 17:00 | 100% | RP-010414 | - | Qualcomm | Kirk Burroughs | RP#13 completed | -
3679 | 1171 | Event Based and Periodic LCS | LCS1-EBP | 2 | Rel-5 | S1,S2,N4 | 2000-05-22 | 2002-06-07 17:00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | - | -
3680 | 1641 | Stage 1 for Event based and Periodic LCS | - | 3 | Rel-5 | S1 | 2000-05-22 | 2000-11-17 17:00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | Evaluate Event based and Periodic LCS to be included in R00, corresponding Stage 1 description | 22.071
3681 | 1538 | Stage 2 for Event based and Periodic LCS | - | 3 | Rel-5 | S2 | 2000-11-06 08:00 | 2001-01-26 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 51% complete) | -
3682 | 1179 | Impact on MAP | - | 3 | Rel-5 | N4 | 2002-03-15 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Possible impact on UTRAN of LCS quality level request... | -
3683 | 2436 | Location Services for GERAN in A/Gb Mode | LCS-GERAN | 2 | Rel-5 | GP | 2000-04-03 08:00 | 2002-02-08 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | -
3684 | 2437 | GERAN LCS Stage 2 (first release) | - | 3 | Rel-5 | GP,S2,G1,G2 | 2000-04-03 08:00 | 2002-02-08 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | -
3685 | 2438 | Gb interface support for LCS | - | 3 | Rel-5 | GP | 2000-04-03 08:00 | 2001-08-31 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | -
3686 | 2440 | L3 protocol support for LCS | - | 3 | Rel-5 | GP | 2000-04-03 08:00 | 2001-06-01 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | -
3687 | 2441 | Stage 3 for Location Services for GERAN in A/Gb Mode | - | 3 | Rel-5 | GP | 2000-04-03 08:00 | 2001-06-01 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | -
3688 | 2442 | Location Services for GERAN in Iu Mode | - | 2 | Rel-5 | S2,G1,G2,R2,R3 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3689 | 2443 | GERAN LCS Stage 2 | - | 3 | Rel-5 | S2,G1,G2 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3690 | 2444 | Iu-ps interface support for LCS | - | 3 | Rel-5 | R2,R3 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3691 | 2445 | Iu-cs interface support for LCS | - | 3 | Rel-5 | R2,R3 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3692 | 2446 | Iur-g interface support for LCS | - | 3 | Rel-5 | G1,G2 | 2002-01-23 13:00 | 2002-04-19 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | FFS | -
3693 | 2447 | RRC protocol support for LCS | - | 3 | Rel-5 | G1,G2,R2,R3 | 2001-08-20 08:00 | 2001-11-30 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3694 | 2448 | Additional impacts on Broadcast of LCS data on packet channels | - | 3 | Rel-5 | G1,G2,R2,R3 | 2001-08-20 08:00 | 2001-12-05 12:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3695 | 2449 | Stage 3 for Location Services for GERAN in Iu Mode | - | 3 | Rel-5 | G1,G2,R2,R3 | 2002-03-25 13:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | -
3696 | 50068 | GERAN MS Conformance test for LCS | LCS-GERAN-MSconf | 2 | Rel-5 | GP | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000458 | - | - | - | - | -
3697 | 55069 | LCS MS test case work plan (Release 98/99/4) | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000458 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | -
3698 | 55070 | LCS MS test cases | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000458 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | -
3699 | 50069 | Deleted - GERAN BTS Conformance test for LCS | LCS-GERAN-BTSconf | 2 | Rel-5 | GP | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000459 | - | - | - | Not started 02/3003. Marked as stopped 12/2008 | -
3700 | 55071 | Deleted - LCS BTS test case work plan (Release 98/99/4) | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3701 | 55072 | Deleted - LCS BTS test cases | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3702 | 544 | LCS interoperation stage 2 aspects | - | 2 | Rel-5 | S2 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 17% complete) | -
3703 | 2434 | LCS interoperability aspects to GERAN (LCS-GERAN) | - | 2 | Rel-5 | GP,S5 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | GP-000456 | - | - | - | - | -
3704 | 2435 | Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN | - | 3 | Rel-5 | GP,S2,S5,R2,R3,G2,G1 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | GP-000456 | - | - | - | - | -
3705 | 1183 | FS on LCS support in the IMS | - | 2 | Rel-5 | S1 | 2001-02-12 08:00 | 2002-01-18 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 75% complete) | -
3706 | 35008 | Charging and OAM&P for LCS enhancements | LCS1-OAM | 2 | Rel-5 | S5 | 2001-09-21 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | - | - | - | 32.200-series
3707 | 521 | New security aspects of LCS | LCS1-SEC | 2 | Rel-5 | S3,S2 | 2000-04-14 08:00 | 2001-12-28 17:00 | 100% | SP-000421 | - | Nokia | valtteri.niemi@nokia.com | SP#9 updated WID S3-000609 (Location services security) | 23.271, 43.059
3708 | 32011 | Specification for the Le interface | LCS1-Le | 2 | Rel-5 | S2 | 2002-01-14 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | - | -
3709 | 32022 | Deleted - CHECK STATUS - Inter-GMLC interface | - | 2 | Rel-5 | S2 | 2002-05-30 08:00 | 2002-12-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3710 | 501571 | Rel-5 Security enhancements (SEC1) | - | 1 | Rel-5 | S3 | 2000-02-21 08:00 | 2002-06-28 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | Added BB UE authentication and rapporteur added. TO BE DELETED | -
3711 | 1576 | Rel-5 Network Domain Security (SEC1-NDS) | - | 2 | Rel-5 | S3 | 2000-02-21 08:00 | 2002-06-28 17:00 | 100% | SP-000420 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#9 approved WID SP-000420 (S3-000606 Network domain security). S3#17: All due in Rel5. (WI Update at S3#18). Replaced by NDS-IP and NDS-MAP. TO BE DELETED OR MOVED TO HISTORY FILE | New 33.200 (exists also for Rel-4)
3712 | 2576 | Rel-5 IP network layer security (NDS/IP) (SEC1-NDS-IP) | - | 3 | Rel-5 | S3 | 2000-06-15 08:00 | 2002-03-15 17:00 | 100% | SP-010326 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#12 WID updated SP-000420 (S3-000606) =>SP-010326 (S3-010286) | New 33.210
3713 | 1577 | Deleted - Control plane protection in core network (e.g., GTP, CAP, MAP/IP, provided by IPsec) | - | 3 | Rel-5 | S3 | 2000-05-12 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3714 | 1578 | Deleted - Main aspects of User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | S3 | 2000-05-12 08:00 | 2001-06-21 17:00 | 100% | - | - | - | - | TO BE DELETED. Marked as stopped 12/2008 | -
3715 | 1579 | Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | N4 | 2001-09-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Waiting for input from SA3!.... Marked as stopped 12/2008 | -
3716 | 1580 | Deleted - User plane protection in core network (e.g., provided by IPsec) | - | 3 | Rel-5 | S3 | 2000-02-21 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | TO BE DELETED. Marked as stopped 12/2008 | -
3717 | 1581 | Deleted -Main aspects of User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | S3 | 2000-02-21 08:00 | 2001-06-21 17:00 | 100% | - | - | - | - | - | -
3718 | 1582 | Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | N4 | 2001-09-14 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | 14/02/2002 requirements are not clear/not received...Marked as closed 12/2008 (was marked 95 complete) | -
3719 | 2243 | Intra Domain Connection of RAN Nodes to Multiple CN Nodes | IUFLEX | 1 | Rel-5 | S2,N1,N4,R3,GP | 2000-10-02 08:00 | 2002-06-28 17:00 | 100% | SP-000619 | - | Ericsson | stephen.terrill@ericsson.com | No clear indication on the end date. Put to Rel5 by AS. | 23.236
3720 | 2244 | Overall System Architecture for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | S2 | 2001-01-03 08:00 | 2001-09-21 17:00 | 100% | - | - | - | - | - | -
3721 | 20000 | Stage 3: RAN node selecting CN node | - | 2 | Rel-5 | R3 | 2001-09-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | Not identified | -
3722 | 2248 | N1 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | N1 | 2001-09-17 08:00 | 2002-06-28 17:00 | 100% | NP-010693 | - | - | - | - | 24.008 and check 29.018
3723 | 2249 | N4 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | N4 | 2000-10-02 08:00 | 2002-03-08 17:00 | 100% | NP-000737 | - | - | - | DAB 12.12.01 - % complete to 66%... | -
3724 | 50067 | GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | IDCRAN-GERAN | 2 | Rel-5 | GP | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | GP-020492 | - | Ericsson | ingemar.backlund@era.ericsson.se | Accept changes Gb over IP | -
3725 | 51068 | Stage 2 (changes to ) | - | 3 | Rel-5 | G1 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3726 | 51069 | 43.051 Introduction of support for IDNNS in GERAN Iu mode | - | 3 | Rel-5 | G1 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3727 | 52070 | Stage 3 (changes to ) | - | 3 | Rel-5 | G2 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3728 | 52077 | 48.016 Use of Gb interface concepts when a network applies IDNNS | - | 3 | Rel-5 | G2 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | Closed, accept changes for Gb over IP | -
3729 | 52078 | 48.018 Include MSC/VLR identity in CS IMSI paging | - | 3 | Rel-5 | G2 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3730 | 2320 | Deleted - GERAN improvements 3 (new transport layer on interface A) | GEIMP3 | 1 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | GP-010909 | - | - | - | Terminated - not standardized. Marked as stopped 12/2008 | -
3731 | 2321 | Deleted - Evolution of the transport for A | GEIMP3-EtA | 2 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | GP-010910 | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3732 | 2322 | Deleted - Definition of a new A/Ater interface Transport Layer option based on the Iu Interface Transport Layer | - | 3 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3733 | 2323 | Deleted - Adaptation of the Layer 3 BSSMAP procedures as required | - | 3 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3734 | 501142 | Rel-5 Charging Management & Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM5 | 1 | Rel-5 | S5 | 2001-09-10 08:00 | 2002-09-12 17:00 | 100% | SP-010461 | - | - | - | - | -
3735 | 35002 | Rel-5 Principles, high level Requirements and Architecture | - | 2 | Rel-5 | S5 | 2001-09-17 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | Motorola | - | - | 32.101, 32.102
3736 | 35003 | Rel-5 Performance Management | - | 2 | Rel-5 | S5 | 2001-09-17 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | Nortel | - | - | 32.4xy, 52.402
3737 | 35004 | Rel-5 Charging Management | - | 2 | Rel-5 | S5 | 2001-09-10 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | T-Mobile | Karl-Heinz.Nenner@T-MOBILE.DE | - | 32.200, 32.205, 32.215, 32.225, 32.235
3738 | 35001 | Rel-5 Network Infrastructure Management | - | 2 | Rel-5 | S5 | 2001-09-21 08:00 | 2002-09-12 17:00 | 100% | SP-010461 | - | Ericsson | thomas.tovinger@ericsson.com | - | 32.6xy, 32.3xy
3739 | 2392 | GERAN enhancements for streaming services 1 (RLC enhancements) | - | 1 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010429 | - | - | - | - | -
3740 | 2394 | Concept for GERAN enhancements for streaming services 1 (RLC enhancements) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2001-10-31 17:00 | 100% | - | - | - | - | - | -
3741 | 2395 | RLC protocol enhancement (SDU Discard) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3742 | 2396 | GERAN enhancements for streaming services 2 (usage of ECSD) | - | 1 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010430 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola, Vodafone | -
3743 | 2398 | Usage of ECSD Concept | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3744 | 2399 | Stage 2 for GERAN enhancements for streaming services 2 (usage of ECSD) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3745 | 2400 | Stage 3 for GERAN enhancements for streaming services 2 (usage of ECSD) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3746 | 2401 | RLC PDU formats | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3747 | 2402 | MAC header | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3748 | 2412 | GERAN/UTRAN interface evolution 1 (evolution of Iu PS) | GERUEV1 | 1 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2002-06-28 17:00 | 100% | GP-010481 | - | SBC | Marc Grant | SBC, Motorola, Nokia, Ericsson, Nortel | -
3749 | 2413 | Evolution of Iu ps | GERUEV1-IuPS | 2 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3750 | 2414 | Identification of GERAN requirements on Iu ps | - | 3 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3751 | 2415 | Update of Evolution of Iu ps specifications | - | 3 | Rel-5 | GP,R3 | 2001-12-03 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3752 | 2416 | GERAN/UTRAN interface evolution 2 (evolution of Iu CS) | GERUEV2 | 1 | Rel-5 | GP,R3 | 2000-06-29 08:00 | 2002-06-28 17:00 | 100% | GP-010417 | - | - | - | - | -
3753 | 2417 | Evolution of Iu cs | GERUEV2-IuCS | 2 | Rel-5 | GP,R3 | 2000-06-29 08:00 | 2002-06-28 17:00 | 100% | GP-000430 | - | Lucent | Krishna Balachandran | Lucent, Ericsson, AWS, Nortel | -
3754 | 2418 | Identification of GERAN requirements on Iu cs | - | 3 | Rel-5 | GP,R3 | 2000-06-29 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3755 | 2419 | Update of Evolution of Iu cs specifications | - | 3 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3756 | 2556 | End to End QoS for PS Domain including IMS | E2EQoS, Rel-5 | 1 | Rel-5 | S2,S5,N3 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | SP-010343 | - | Ericsson | Johnson.oyama@era.ericcson.se | - | -
3757 | 2557 | E2E QoSConcept and Architecture | - | 2 | Rel-5 | S2 | 2001-01-03 08:00 | 2001-09-07 17:00 | 100% | - | - | - | - | - | 23.207
3758 | 2558 | E2E QoS interworking | E2EQoS-IW | 2 | Rel-5 | N3 | 2000-08-28 08:00 | 2002-06-07 17:00 | 100% | NP-010528 | - | Lucent | Daisuke Yokota (yokota@lucent.com) | [DAB - 30/07/02] - % complete to 95% (if we exclude Diffserv). Marked as closed 12/2008 (was marked 95% complete) | 29.208, 29.207, 27.060, 29.061, 24.008, 24.228, , 24.229, 29.060, 29.163
3759 | 2559 | QoS Management (Provisioning and Monitoring) | E2EQoS-OAM | 2 | Rel-5 | S5 | 2001-09-21 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | - | - | - | 32-series
3760 | 2569 | Rel-5 Messaging enhancements | MESS5 | 1 | Rel-5 | T2 | 2001-06-15 08:00 | 2003-03-31 17:00 | 100% | - | - | - | - | support of UAProf, so this in my opinion is 100% complete | -
3761 | 2571 | Rel-5 Multimedia Messaging (MMS) enhancements | MESS5-MMS | 2 | Rel-5 | T2 | 2001-06-15 08:00 | 2003-03-31 17:00 | 100% | TP-010130 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | -
3762 | 31000 | Definition of service requirements for MESS5-MMS | MESS5-SR | 3 | Rel-5 | S1 | 2001-06-15 08:00 | 2002-03-15 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140
3763 | 42000 | Technical realization of MESS5-MMS | - | 3 | Rel-5 | T2 | 2001-06-15 08:00 | 2002-06-07 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | stage 3 MM7 is missing | 23.140
3764 | 42008 | WAP Forum dependency: MM1 stage 3 | - | 3 | Rel-5 | T2 | 2001-06-15 08:00 | 2003-03-31 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 80% complete) | -
3765 | 34018 | MMS formats and codecs for MESS5-MMS | - | 3 | Rel-5 | S4 | 2001-12-03 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | - | 26.140
3766 | 2572 | Enhanced Messaging Service (EMS) enhancements | MESS5-EMS | 2 | Rel-5 | T2 | 2001-06-15 08:00 | 2002-03-08 17:00 | 100% | TP-010153 | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | 23.040
3767 | 31001 | Definition of service requirements for Enhanced Messaging Service (EMS) enhancements | - | 3 | Rel-5 | S1 | 2001-06-15 08:00 | 2001-09-14 17:00 | 100% | - | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | -
3768 | 42001 | Technical realization of Enhanced Messaging Service (EMS) enhancements | - | 3 | Rel-5 | T2 | 2001-06-15 08:00 | 2002-03-08 17:00 | 100% | - | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | 23.040
3769 | 50001 | GERAN Inter BSC NACC improvements over the Gb Interface | GERNACC | 1 | Rel-5 | GP | 2001-09-03 08:00 | 2002-06-28 17:00 | 100% | GP-012313 | - | - | - | - | -
3770 | 14501 | Modification of core network protocols for GERAN Inter BSC NACC over Gb Interface | GERNACC-Cnmod | 2 | Rel-5 | N4,S2 | 2001-09-03 08:00 | 2002-04-19 17:00 | 100% | GP-011877 | - | - | - | - | -
3771 | 32502 | Stage 2 - Concept | - | 3 | Rel-5 | N4,S2 | 2001-09-03 08:00 | 2001-10-31 17:00 | 100% | - | - | - | - | - | -
3772 | 14502 | Stage 2 - 23.060 change - Definition of Inter BSC NACC | - | 3 | Rel-5 | N4,S2 | 2001-09-03 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3773 | 14503 | Stage 3 (changes to TS 29.060) | - | 3 | Rel-5 | N4 | 2001-09-03 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | IP 30/11/01: Input awaited from GERAN2 to CN4... | -
3774 | 50002 | Modification of Gb protocols for GERAN Inter BSC NACC over Gb Interface | GERNACC-Gbmod | 2 | Rel-5 | GP | 2001-11-30 08:00 | 2002-06-28 17:00 | 100% | GP-012314 | - | - | - | - | -
3775 | 50003 | Stage 3 (changes to TS 48.018) | - | 3 | Rel-5 | GP | 2001-11-30 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3776 | 50033 | Enhanced Power Control | EPC | 1 | Rel-5 | GP | 2001-11-26 08:00 | 2003-12-19 17:00 | 100% | GP-012748 | - | - | - | - | -
3777 | 50034 | Realization of Enhanced power control and signalling support | - | 2 | Rel-5 | GP | 2001-11-26 08:00 | 2001-11-30 17:00 | 100% | GP-012749 | - | - | - | Completed 11/2001 | -
3778 | 50035 | Deleted - GERAN MS Conformance test for Enhanced Power Control | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012750 | - | - | - | Not started. Marked as stopped 12/2008 | -
3779 | 50036 | Deleted - GERAN BTS Conformance test for Enhanced Power Control | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012751 | - | - | - | Not started. Marked as stopped 12/2008 | -
3780 | 50037 | 8PSK AMR HR | 8PSK-AH | 1 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012752 | - | - | - | Completed for Rel-5 | -
3781 | 50038 | Definition of channel coding, performance requirements and signalling support | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | GP-012753 | - | - | - | - | -
3782 | 50061 | Concept | - | 3 | Rel-5 | GP | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3783 | 52004 | Changes to 44.018 | - | 3 | Rel-5 | G2 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3784 | 51025 | Changes to 45.001 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3785 | 51026 | Changes to 45.002 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3786 | 51027 | Changes to 45.003 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3787 | 51028 | Changes to 45.005 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3788 | 52005 | Changes to 24.008 | - | 3 | Rel-5 | G2 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3789 | 52006 | Changes to 48.058 | - | 3 | Rel-5 | G2 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3790 | 50039 | Deleted - GERAN MS Conformance test for 8PSK HR | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012754 | - | - | - | Marked as stopped 12/2008 | -
3791 | 50040 | GERAN BTS Conformance test for 8PSK HR | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2002-12-20 17:00 | 100% | GP-012755 | - | - | - | - | -
3792 | 13000 | Service Change and UDI Fallback | SCUDIF | 1 | Rel-5 | N3 | 2001-10-08 08:00 | 2002-06-07 17:00 | 100% | NP-020164 | - | Ericsson | Rune.Werner.Wiik@ericsson.no | - | 29.007, 27.001, 24.008
3793 | 501800 | Rel-5 USIM toolkit enhancements | USAT1, USAT1-Interpr, USAT1LocLnk | 1 | Rel-5 | T3,S1 | 2000-06-05 08:00 | 2003-09-26 17:00 | 100% | - | - | G & D | Michael Meyer | - | 22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)
3794 | 43002 | Deleted - Test specification for USIM toolkit security mechanisms | - | 2 | Rel-5 | T3 | 2002-05-28 08:00 | 2003-09-26 17:00 | 100% | TP-020028 | - | Gemplus | Sophie Viallet | Marked as stopped 12/2008 | -
3795 | 1801 | Protocol Standardisation of a SIM Toolkit Interpreter | - | 2 | Rel-5 | T3,T2 | 2000-06-05 08:00 | 2003-01-22 17:00 | 100% | TP-000116 | - | G & D | Michael Meyer | 28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13. | T2 27.103
3796 | 2497 | Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter | - | 3 | Rel-5 | T3 | 2000-06-05 08:00 | 2001-03-16 17:00 | 100% | - | - | - | - | 5/10/2001: Stage one comepeted at TP-12. | 31.112, 31.113, 31.114
3797 | 2496 | Stage 2 and 3 | - | 3 | Rel-5 | T3 | 2001-01-03 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | 5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14. | 31.112, 31.113, 31.114
3798 | 2518 | Test specification for Protocol Standardisation of a SIM Toolkit Interpreter | - | 3 | Rel-5 | T3 | 2001-09-03 08:00 | 2003-01-22 17:00 | 100% | TP-010111 | - | Gemplus | Gérald MAUNIER | 5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete) | -
3799 | 501802 | (U)SIM API | USAT1-API, TEI4 | 2 | Rel-5 | T3 | 2002-03-20 08:00 | 2002-09-20 17:00 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | 8/3/2001: test spec is based on R99 core spec, so deleted from Workplan | -
3800 | 504301 | Rel-5 Java API Test specification | - | 3 | Rel-5 | T3 | 2002-03-20 08:00 | 2002-09-20 17:00 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | - | 51.013
3801 | 30001 | (Small) Technical Enhancements and Improvements for Rel-5 | TEI5 | 1 | Rel-5 | SP,CP,RP,GP | 2000-01-03 08:00 | 2000-01-03 08:00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system | -
3802 | 25018 | Test - (Small) Technical Enhancements and Improvements for Rel-5 | TEI5_Test | 1 | Rel-5 | R5,T1 | 2000-01-03 08:00 | 2008-12-31 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP. | 34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3
3803 | 31013 | Technical Report on UE Functionality Split | UESPLIT | 1 | Rel-5 | S1 | 2000-01-03 08:00 | 2000-05-01 17:00 | 100% | SP-010484 | - | Motorola | jian.j.wu@motorola.com | - | New TR 22.944
3804 | 2520 | User Equipment Management | UEM | 1 | Rel-5 | S5 | 2001-06-21 08:00 | 2002-06-28 17:00 | 100% | SP-010286 | - | Vodafone | john.mudge@vf.vodafone.co.uk | - | 32.802
3805 | 35000 | FS on User Equipment (UE) Management | OAM-UEM | 2 | Rel-5 | S5 | 2001-06-21 08:00 | 2002-06-28 17:00 | 100% | SP-010286 | - | Vodafone | john.mudge@vf.vodafone.co.uk | - | 32.802
3806 | 50201 | Flow control supporting an MS with multiple data flows with different QoS over the Gb interface | FlowCon | 1 | Rel-5 | GP | 2002-06-24 08:00 | 2002-08-30 17:00 | 100% | GP-021767 | - | Ericsson | ingemar.backlund@era.ericsson.se | 50101 -> 50201 | -
3807 | 50202 | Update of stage 2 specifications | - | 2 | Rel-5 | GP | 2002-06-24 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | 50102 -> 50202 | -
3808 | 32097 | Concept document 23.060 (changes to) | - | 3 | Rel-5 | S2 | 2002-06-28 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | -
3809 | 50203 | Flow Control | - | 3 | Rel-5 | GP | 2002-06-24 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | 50103 -> 50203 | -
3810 | 50204 | Modification of BSSGP protocol | - | 2 | Rel-5 | GP | 2002-06-24 08:00 | 2002-06-28 17:00 | 100% | GP-021508 | - | Ericsson | ingemar.backlund@era.ericsson.se | 50104 -> 50204 | -
3811 | 52095 | Stage 3 (changes to 48.018) | - | 3 | Rel-5 | G2 | 2002-06-24 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3812 | 50058 | Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF) | - | 1 | Rel-5 | GP | 2002-04-19 08:00 | 2003-11-28 17:00 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5) | -
3813 | 50059 | Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode) | - | 2 | Rel-5 | GP | 2002-04-19 08:00 | 2003-08-22 17:00 | 100% | GP-021263 | - | - | - | Marked as closed 12/2008 (was marked 26% complete) | -
3814 | 50060 | Deleted - Multiple TBF Concept paper | - | 3 | Rel-5 | GP | 2002-04-19 08:00 | 2003-08-22 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | -
3815 | 51001 | Deleted - Multiple TBF Stage 2 (43.064) CRs | - | 3 | Rel-5 | G1 | 2002-04-19 08:00 | 2002-11-22 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3816 | 50062 | Deleted - Multiple TBF Stage 3 (44.060) CRs | - | 3 | Rel-5 | G2 | 2002-04-19 08:00 | 2002-11-22 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3817 | 50206 | Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing | - | 2 | Rel-5 | GP | 2002-06-24 08:00 | 2003-11-28 17:00 | 100% | GP-022098 | - | Ericsson | ingemar.backlund@era.ericsson.se | 08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008 | -
3818 | 54101 | Deleted - MS conformance tests for Multiple TBF in A/Gb mode | - | 3 | Rel-5 | G4 | 2002-06-24 08:00 | 2003-11-28 17:00 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | -
3819 | 2345 | Alignment of 3G functional split and Iu | GER3GAL | 1 | Rel-5 | GP | 2000-06-08 08:00 | 2003-12-19 17:00 | 100% | GP-021256 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | -
3820 | 2346 | GERAN user / control plane | GER3GAL-GUCOPL | 2 | Rel-5 | GP | 2000-08-07 08:00 | 2002-08-30 17:00 | 100% | GP-021255 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | -
3821 | 2347 | Alignment with UMTS bearer concept | - | 3 | Rel-5 | GP | 2000-08-07 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | -
3822 | 50300 | Enhanced power control - for Alignment with UMTS bearer concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2001-08-31 17:00 | 100% | - | - | - | - | - | -
3823 | 2423 | Stage 2 - for Alignment with UMTS bearer concept | - | 4 | Rel-5 | GP | 2000-08-07 08:00 | 2001-06-29 17:00 | 100% | - | - | - | - | - | -
3824 | 2348 | Adoption of the UTRAN PDCP | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-12-21 17:00 | 100% | - | - | - | - | Responsible is GERAN; RAN WG2 help may be needed. | -
3825 | 50043 | Development of RLC / MAC | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | -
3826 | 50044 | Development of GERAN RRC | - | 4 | Rel-5 | GP | 2001-06-22 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3827 | 50045 | Ciphering and integrity protection concept paper | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3828 | 50046 | Multiple TBF or equivalent Concept paper | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | -
3829 | 50047 | Paging concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3830 | 50048 | Dedicated Physical subchannels, includes traffic and control channels | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3831 | 50049 | Iu support and broadcast concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3832 | 50050 | Impact of using RLC instead of LAPDm concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | -
3833 | 50051 | Contention resolution, mobile station identity, and access concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3834 | 50052 | PDCP concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | -
3835 | 50053 | Downlink delayed TBF release | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | -
3836 | 50054 | Add transparent RLC Concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | -
3837 | 50055 | Handover concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | -
3838 | 2424 | Physical layer alignment with UMTS bearer concept | - | 3 | Rel-5 | GP | 2000-11-06 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3839 | 2356 | PDTCH/TCH in 45.003 | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3840 | 2357 | Control channels in 45.003 | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3841 | 2358 | Receiver performance in 45.005 for PDTCH/TCH and control channels | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3842 | 2359 | Iu rg interface | GER3GAL-Iurg | 2 | Rel-5 | GP,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010428 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | -
3843 | 2425 | Inter BSS interface | - | 3 | Rel-5 | GP,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3844 | 2360 | Identification of requirements for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3845 | 2361 | Stage 2 for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3846 | 2362 | Adoption of relevant parts from Iur - for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3847 | 2363 | Complementation with GERAN specifics - for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3848 | 2364 | Stage 3 for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3849 | 2426 | Inter BSS-RNS interface | - | 3 | Rel-5 | GP,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3850 | 2365 | Identification of requirements for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3851 | 2366 | Stage 2 for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3852 | 2367 | Adoption of relevant parts from Iur - for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3853 | 2368 | Complementation with GERAN specifics - for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2002-01-30 13:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3854 | 2369 | Stage 3 for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2002-01-30 13:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3855 | 2370 | Voice over GERAN PS and CS concept | - | 2 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-011252 | - | - | - | - | -
3856 | 2371 | Architecture for A, Iu cs and Iu ps | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3857 | 2372 | Transcoder position/operation | - | 3 | Rel-5 | GP | 2000-11-06 08:00 | 2001-04-13 17:00 | 100% | - | - | - | - | - | -
3858 | 2373 | Handover for Voice over GERAN PS and CS | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3859 | 2374 | RTP payload | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | -
3860 | 2375 | Codec renegotiation concept | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-03-29 17:00 | 100% | - | - | - | - | - | -
3861 | 2376 | LA | - | 3 | Rel-5 | GP | 2000-11-06 08:00 | 2001-04-13 17:00 | 100% | - | - | - | - | - | -
3862 | 2388 | Deleted - GERAN MS Conformance test for GERAN interface evolution | - | 2 | Rel-5 | GP | 2001-06-11 08:00 | 2003-12-19 17:00 | 100% | GP-021253 | - | - | - | Not started. Marked as stopped 12/2008 | -
3863 | 2389 | Deleted - MS test for GERAN interface evolution | - | 3 | Rel-5 | GP | 2001-06-11 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | -
3864 | 2390 | GERAN BSS Conformance test for GERAN interface evolution | - | 2 | Rel-5 | GP | 2000-06-08 08:00 | 2003-12-19 17:00 | 100% | GP-021254 | - | - | - | Not started. Marked as stopped 12/2008 | -
3865 | 2391 | Deleted - BSS test | - | 3 | Rel-5 | GP | 2000-06-08 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | -
3866 | 2330 | GERAN support for IMS | GERIMS | 1 | Rel-5 | GP | 2000-05-01 08:00 | 2002-12-20 17:00 | 100% | GP-010420 | - | Nokia | Shkumbin Hamiti | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola | -
3867 | 2331 | GERAN Header adaptation | GERIMS-HEADAPT | 2 | Rel-5 | GP,S2,RP | 2000-05-01 08:00 | 2002-12-20 17:00 | 100% | GP-010421 | - | Nokia | Shkumbin Hamiti | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola | -
3868 | 2332 | Definition of compression and removal modes for PDCP protocol | - | 3 | Rel-5 | GP,S2,RP | 2000-07-24 15:48 | 2000-09-01 17:00 | 100% | - | - | - | - | - | -
3869 | 2333 | Conceptual description in stage 2 | - | 3 | Rel-5 | GP,S2,RP | 2000-05-01 08:00 | 2001-10-31 17:00 | 100% | - | - | - | - | - | -
3870 | 2334 | Necessary changes on stage 3 regarding header removal | - | 3 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | - | -
3871 | 2335 | Deleted - GERAN Radio access bearer design for IMS | GERIMS-RABDES | 2 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010422 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3872 | 2422 | Deleted - MuM control signalling for conversational multimedia services | - | 3 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3873 | 2431 | Deleted - Identification of requirements for MuM control signalling for conversational multimedia services | - | 4 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED | -
3874 | 2337 | Deleted - Necessary modifications due to SIP | - | 4 | Rel-5 | GP,S2,RP | 2002-05-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED | -
3875 | 2341 | Deleted - GERAN MS Conformance test for support of IMS | GERIMS-MSconf | 2 | Rel-5 | GP | 2001-06-11 08:00 | 2002-12-20 17:00 | 100% | GP-010424 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3876 | 2342 | Deleted - MS test for support of IMS | - | 3 | Rel-5 | G4 | 2001-06-11 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3877 | 2343 | Deleted - GERAN BTS Conformance test for support of IMS | GERIMS-BTSconf | 2 | Rel-5 | GP | 2001-06-11 08:00 | 2002-12-20 17:00 | 100% | GP-010425 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | -
3878 | 54001 | MS Conformance Testing of Dual Transfer Mode | MSCTDTM | 1 | Rel-5 | G4,G5 | 2002-11-11 08:00 | 2003-02-07 17:00 | 100% | GP-023236 | - | Vodafone | Dave Fox | Needed to complete DTM (R99) | -
3879 | 32033 | Handling of early Ues | LATE_UE | 1 | Rel-5 | S2 | 2000-01-03 08:00 | 2003-06-27 17:00 | 100% | SP-030125 | - | - | - | - | -
3880 | 32031 | Feasibility Study on Handling of early Ues | - | 2 | Rel-5 | S2 | 2002-10-07 08:00 | 2002-12-13 17:00 | 100% | - | - | - | - | - | -
3881 | 32032 | Stage 2 for Handling of early Ues | - | 2 | Rel-5 | S2 | 2003-01-06 08:00 | 2003-06-27 17:00 | 100% | - | - | - | - | - | -
3882 | 22001 | FS for the Early Mobile Handling in UTRAN | FSEarlyUE | 2 | Rel-5 | R2 | 2002-09-09 08:00 | 2003-06-06 17:00 | 100% | - | - | Vodafone | alan.law@vodafone.com | - | -
3883 | 96 | Note: Stage 3 RAN part not shown | - | 2 | Rel-5 | RP | 2000-01-03 08:00 | 2000-01-03 17:00 | 100% | - | - | - | - | - | -
3884 | 0 | Release 4 Features | - | 1 | Rel-4 | NP,GP,RP,SP,TP | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | -
3885 | 1861 | Miscellaneous UE Conformance Testing Activities | MISTST1 | 1 | Rel-4 | T1 | 2001-04-02 08:00 | 2004-12-01 17:00 | 100% | - | - | - | - | - | -
3886 | 1862 | Optimization of Test Time, RF Aspects (FDD) | MISTST1-OpFDD | 2 | Rel-4 | T1 | 2001-09-24 08:00 | 2003-09-03 17:00 | 100% | TP-030052 | - | - | - | It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete) | 34.121
3887 | 1863 | Optimization of Test Time, RF Aspects (TDD) | MISTST1-OpTDD | 2 | Rel-4 | T1 | 2001-09-24 08:00 | 2003-09-03 17:00 | 100% | TP-030052 | - | - | - | It is believed that the current R99 test spec. can be optimised for faster overall test times | 34.122
3888 | 1907 | Extensions to R99 Test cases | MISTST1-Ext | 2 | Rel-4 | T1 | 2001-04-02 08:00 | 2003-12-02 17:00 | 100% | TP-030052 | - | - | - | Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete) | 34.123 p 1,2
3889 | 2564 | Extension to R99 Test cases - TTCN | - | 2 | Rel-4 | T1 | 2002-06-28 08:00 | 2004-03-03 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | -
3890 | 2565 | Creation of R99 TCs for TDD - prose | MISTST1-TDD | 2 | Rel-4 | T1 | 2001-10-01 08:00 | 2004-07-01 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | 34.123-1
3891 | 2566 | Deleted - Creation of R99 TCs for TDD - TTCN | - | 2 | Rel-4 | T1 | 2002-09-03 08:00 | 2004-12-01 17:00 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | -
3892 | 1908 | Deleted - Review all other work items for impact on new or exiting 34 series specs. | - | 2 | Rel-4 | T1 | 2002-07-02 08:00 | 2002-12-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.121,122,123,125
3893 | 1340 | Real Time Facsimile | FAX-RT | 1 | Rel-4 | S1 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | - | -
3894 | 1341 | Real Time Fax | - | 2 | Rel-4 | S2 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | postponed from R99 to R00, SP-000169 | -
3895 | 1808 | Terminal capabilities, AT commands | - | 3 | Rel-4 | T2 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | 21.904, 27.007
3896 | 1343 | Signalling aspects (e.g. ICM) | - | 3 | Rel-4 | N1 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | -
3897 | 1648 | Service provision | - | 3 | Rel-4 | N3 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | 23.146
3898 | 1345 | Review whether service/stage 1 aspects need to be aligned | - | 3 | Rel-4 | S1 | 2000-04-14 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | - | -
3899 | 1346 | Review whether architecture/stage 2 aspects need to be aligned | - | 3 | Rel-4 | S2 | 2000-04-14 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | - | -
3900 | 1539 | Transparent End-to-End PS mobile streaming application | PSTREAM | 1 | Rel-4 | S4 | 2000-04-03 08:00 | 2001-03-21 17:00 | 100% | SP-000345 | - | - | - | - | 26.233, 26.234
3901 | 1818 | Multimedia Messaging | MMS, Rel-4 | 1 | Rel-4 | T2,S1 | 2000-02-22 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140
3902 | 136 | Definition of service requirements for Multimedia Messaging | - | 2 | Rel-4 | S1 | 2000-02-22 08:00 | 2000-05-31 17:00 | 100% | - | - | - | - | - | -
3903 | 1819 | Review of definition of service requirements | - | 2 | Rel-4 | T2 | 2000-06-01 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | - | - | 22.140, 23.140
3904 | 1820 | Technical Realisation | - | 2 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140
3905 | 1821 | Review of definition of reference Achitecture model | - | 3 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140
3906 | 1822 | Fulfill Requirements of Stage 1 | - | 3 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | e.g. minimum set of media formats, media format conversion, personalization of MMS. | 22.140, 23.140
3907 | 1823 | Definition of MMS primitives in Stage 2 | - | 3 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140
3908 | 1541 | Transcoder-Free Operation | TrFO | 1 | Rel-4 | N4,S2,N1 | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | Lead given to CN4 from CN... | -
3909 | 112 | Out-of-Band Transcoder Control solution | TrFO-OoBTC | 2 | Rel-4 | N4 | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | N4-000531 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | - | -
3910 | 1512 | implementation in UTRAN | TrFO-OoBTC-UTRAN | 3 | Rel-4 | R3 | 2000-09-11 08:00 | 2001-03-30 17:00 | 100% | - | - | Siemens | Alexander Vesely | moved according to NP-000575 | 25.401, 25.410, 25.413, 25.415, 23.153
3911 | 896 | Impact on architecture, Principles and Terminology | - | 3 | Rel-4 | S2 | 2000-01-03 08:00 | 2000-10-20 17:00 | 100% | - | - | - | - | e.g. study cascading TrFO/TFO/TrFO | -
3912 | 1657 | Codec Negotiation between UE and MSC | - | 3 | Rel-4 | N1 | 2000-08-14 08:00 | 2001-02-02 17:00 | 100% | - | - | Motorola | Andrew Howell | the link to NP-000085has been deleted because refering to a R99 status sheet... | 24.008, 23.009, 23.108, (29.002)
3913 | 115 | Codec Negotiation inter MSC | - | 3 | Rel-4 | N4 | 2000-07-03 08:00 | 2000-12-22 17:00 | 100% | - | - | - | - | Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues | -
3914 | 894 | Bearer establishment inter MSC | - | 3 | Rel-4 | N4 | 2000-07-03 08:00 | 2000-12-22 17:00 | 100% | NP-000127 | - | - | - | Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.... | 23.153
3915 | 905 | Speech Transcoder: Location and Control at the UMTS Core Network Border | TrFO-STLC | 2 | Rel-4 | S2 | 2000-04-10 08:00 | 2000-09-29 17:00 | 100% | - | - | - | - | WI description and Tdoc S2-99352... | -
3916 | 124 | Transcoder at Edge | - | 3 | Rel-4 | NP | 2000-04-10 08:00 | 2000-09-29 17:00 | 100% | - | - | - | - | WI description and Tdoc S2-99352... | -
3917 | 2310 | GERAN improvements 1 (Gb over IP) | GEIMP1 | 1 | Rel-4 | GP | 2000-05-09 08:00 | 2001-03-19 17:00 | 100% | GP-000433 | - | - | - | - | -
3918 | 2311 | Gb over IP (Ip-fication of Gb) | GbIP | 2 | Rel-4 | GP | 2000-05-09 08:00 | 2001-03-19 17:00 | 100% | GP-000434 | - | - | - | - | -
3919 | 2312 | Concept of Gb over IP (Ip-fication of Gb) | - | 3 | Rel-4 | GP | 2000-05-09 08:00 | 2000-11-10 17:00 | 100% | - | - | - | - | - | -
3920 | 2313 | Changes to 08.16, 08.18 | - | 3 | Rel-4 | GP | 2000-05-09 08:00 | 2001-03-19 17:00 | 100% | - | - | - | - | - | -
3921 | 2314 | GERAN improvements 2 (NACC) | GEIMP2 | 1 | Rel-4 | GP | 2000-11-06 08:00 | 2003-06-10 17:00 | 100% | GP-012812 | - | - | - | - | -
3922 | 2315 | Gb enhancements | Gben | 2 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | GP-000436 | - | - | - | - | -
3923 | 2316 | Intra BSC NACC (Network Assisted Cell Change) | - | 3 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3924 | 2420 | Concept | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3925 | 2317 | Changes in 03.64 | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3926 | 2318 | Changes in 04.60 | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3927 | 2319 | Changes in 44.008 | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3928 | 50030 | MS conformance test for Intra BSC NACC | GEIMP2-Msconf | 2 | Rel-4 | GP | 2001-11-30 08:00 | 2003-06-10 17:00 | 100% | GP-012811 | - | - | - | - | -
3929 | 50299 | Changes in 51.010 | - | 3 | Rel-4 | G5,G4 | 2001-11-30 08:00 | 2003-06-10 17:00 | 100% | - | - | - | - | az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete) | -
3930 | 2324 | GERAN improvements 4 (Delayed TBF) | GEIMP4 | 1 | Rel-4 | GP | 2001-01-15 08:00 | 2001-06-08 17:00 | 100% | GP-010363 | - | - | - | - | -
3931 | 2325 | Gb enhancements 2 | GEIMP4-Gben2 | 2 | Rel-4 | GP | 2001-01-15 08:00 | 2001-06-08 17:00 | 100% | GP-010363 | - | - | - | - | -
3932 | 2429 | Stage 2 for Gb enhancements 2 | - | 3 | Rel-4 | GP | 2001-01-15 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | -
3933 | 2421 | Stage 3 (changes in 44.060) | - | 3 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | -
3934 | 2327 | Definition of enhanced countdown procedure | - | 4 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | -
3935 | 2328 | Definition of enhanced TBF release procedure | - | 4 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | -
3936 | 2329 | Definition of USF=FREE type polling mechanism on PDCH | - | 4 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | -
3937 | 1222 | Low Chip Rate TDD option | LCRTDD | 1 | Rel-4 | R1 | 2000-07-19 08:00 | 2003-12-02 17:00 | 100% | - | - | CWTS | G. Yang | - | -
3938 | 1223 | Physical layer for Low Chip Rate TDD option | LCRTDD-Phys | 2 | Rel-4 | R1 | 2000-07-19 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | G. Yang | - | -
3939 | 1224 | Layer 2 and layer 3 protocol aspects | LCRTDD-L23 | 2 | Rel-4 | R2 | 2000-07-19 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | Y. Liu | - | -
3940 | 1225 | RF radio transmission/reception, system performance requirements and conformance testing | LCRTDD-RF | 2 | Rel-4 | R4 | 2000-08-14 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | D. Zhang | - | -
3941 | 1227 | UE radio access capability | LCRTDD-UErac | 2 | Rel-4 | R2 | 2000-08-14 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | Y. Liu | - | -
3942 | 1228 | Iub/Iur protocol aspects - for Low Chip Rate TDD option | LCRTDD-IubIur | 2 | Rel-4 | R3 | 2000-08-14 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | Y. Liu | - | -
3943 | 2262 | Low chiprate TDD interworking with GERAN | - | 2 | Rel-4 | GP | 2000-09-01 08:00 | 2001-01-19 17:00 | 100% | GP-000432 | - | - | - | - | -
3944 | 2263 | Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD | - | 3 | Rel-4 | GP | 2000-09-01 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | -
3945 | 2103 | Conformance Test Aspects - Low Chip Rate TDD | - | 2 | Rel-4 | T1 | 2001-09-17 08:00 | 2003-12-02 17:00 | 100% | - | - | - | - | - | -
3946 | 2217 | Testing Layer 2 and layer 3 protocol aspects | - | 3 | Rel-4 | T1 | 2001-09-17 08:00 | 2003-07-02 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | 34.123-1, 34.123-2
3947 | 2562 | Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN | - | 3 | Rel-4 | T1 | 2002-12-03 08:00 | 2003-12-02 17:00 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | 34.123-3
3948 | 2218 | Testing RF Radio Transmission and Reception | - | 3 | Rel-4 | T1 | 2001-09-17 08:00 | 2002-06-28 17:00 | 100% | TP-030052 | - | - | - | duration set to 6 months (was 0), finish date set | -
3949 | 1322 | Enable bearer independent CS architecture | CSSPLIT | 1 | Rel-4 | S2,N3,N4 | 2000-01-03 08:00 | 2002-03-01 17:00 | 100% | SP-000288 | - | Siemens | Alexander Milinski | - | -
3950 | 1323 | Enable bearer-independent call control | - | 2 | Rel-4 | N4 | 2000-01-03 08:00 | 2001-08-16 17:00 | 100% | N4-000512 | - | Ericsson | Heinz-Peter.Keutmann@eed.ericsson.se | DAB 12.12.01 should be 100% hence closed | -
3951 | 1516 | Architecture and Stage 2 description | - | 3 | Rel-4 | S2 | 2000-01-03 08:00 | 2000-09-08 17:00 | 100% | - | - | - | - | R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000 | 23.002
3952 | 1325 | Standardisation of protocols (control & user planes) over Nb interface | - | 3 | Rel-4 | N3 | 2001-01-02 08:00 | 2001-03-30 17:00 | 100% | N4-000512 | - | - | - | - | -
3953 | 1326 | Standardisation of protocols over reference points between MSC server and Gateway MSC server | - | 3 | Rel-4 | N4 | 2000-09-25 08:00 | 2001-03-23 17:00 | 100% | N4-000512 | - | - | - | - | -
3954 | 1616 | Standardisation of detailed stage 2 description | - | 3 | Rel-4 | N4 | 2000-07-17 08:00 | 2001-03-23 17:00 | 100% | N4-000512 | - | - | - | - | -
3955 | 1327 | Bearer control between MSC server and MGW | - | 3 | Rel-4 | N4 | 2000-09-01 08:00 | 2001-08-16 17:00 | 100% | N4-000512 | - | - | - | - | -
3956 | 1328 | stage 3 - protocol issues | - | 4 | Rel-4 | N4 | 2000-09-01 08:00 | 2001-08-16 17:00 | 100% | - | - | - | - | - | -
3957 | 1329 | stage 3 - parameter value issues | - | 4 | Rel-4 | N3 | 2001-01-02 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | -
3958 | 2052 | Deleted - Conformance Test Aspects - Enable bearer independent CS architecture | CSSPLIT-TEST | 2 | Rel-4 | T1 | 2001-03-05 08:00 | 2002-03-01 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3959 | 1445 | MExE enhancements Rel-4 | MEXE | 1 | Rel-4 | T2,S3 | 2000-01-03 08:00 | 2001-12-14 17:00 | 100% | TP-030052 | - | - | - | - | -
3960 | 1447 | MExE Security Analysis Activity | MEXE-SEC | 2 | Rel-4 | S3,T2 | 2000-02-22 08:00 | 2001-12-14 17:00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | SP#12 updated WID | -
3961 | 2045 | Stage 3 for MExE Security | - | 3 | Rel-4 | S3 | 2000-07-17 08:00 | 2001-12-14 17:00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | - | 21.133, 33.102
3962 | 1448 | Terminal aspects for MExE Security | - | 3 | Rel-4 | T2 | 2000-02-22 08:00 | 2000-12-15 17:00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | - | 23.057
3963 | 1810 | MExE Rel-4 Improvements and Investigations | MEXE-ENHANC | 2 | Rel-4 | T2 | 2000-01-03 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057
3964 | 1812 | 3rd MExE classmark | - | 3 | Rel-4 | T2 | 2000-01-03 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | Additional features for MExE R2000 | 22.057, 23.057
3965 | 1814 | FS on Secure download mechanism and capabilities to support SDR concepts | - | 3 | Rel-4 | T2 | 2000-02-07 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057
3966 | 1815 | FS on Support of MP3/MPEG4 content | - | 3 | Rel-4 | T2 | 2000-02-07 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057
3967 | 1631 | Tandem Free aspects for 3G and between 2G and 3G systems | TFO | 1 | Rel-4 | S4 | 2000-02-22 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | RAN and CN to verify no problems for GSM terminals roaming in 3G R99 | -
3968 | 1632 | Tandem Free AMR | TFO-AMR | 2 | Rel-4 | S4 | 2000-02-22 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | RAN and CN to verify UMTS_AMR_2 support | -
3969 | 130 | Specification of Tandem Free AMR | - | 3 | Rel-4 | S4 | 2000-02-22 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | 28.062
3970 | 907 | Impact of Tandem Free AMR on: | - | 3 | Rel-4 | NP | 2001-01-08 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | "Implementation" changed to "Impact on:" by A. Sultan (for better wording) | -
3971 | 131 | CN | - | 4 | Rel-4 | NP | 2001-03-26 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | RAN and CN to verify UMTS_AMR_2 support | -
3972 | 132 | GERAN | - | 4 | Rel-4 | GP | 2001-01-08 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | End date Modified from June to March to have it in Rel4 | -
3973 | 2230 | Advanced Speech Call Items enhancements_Rel-4 | ASCI, Rel-4 | 1 | Rel-4 | N1 | 2000-12-03 08:00 | 2002-03-14 17:00 | 100% | NP-000730 | - | Nortel | sonia.garapaty@nortelnetworks.com | Approved at CN#10 | -
3974 | 2232 | Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI) | - | 2 | Rel-4 | N4 | 2000-12-03 08:00 | 2002-03-14 17:00 | 100% | - | - | Sagem | Vivien Perlic | CN4#11 30/11/02: no inputs received in CN4 | 23.067, 24.067
3975 | 2231 | Stages 2 and 3 on A interface | - | 2 | Rel-4 | N1 | 2000-12-03 08:00 | 2001-03-23 17:00 | 100% | - | - | Nortel | sonia.garapaty@nortelnetworks.com | - | 44.068, 44.069, 24.008
3976 | 2403 | 700 MHz spectrum support | 700SS | 1 | Rel-4 | GP | 2000-01-03 08:00 | 2002-12-20 17:00 | 100% | GP-000449 | - | - | - | - | -
3977 | 2404 | GERAN support for the 700 MHz band | - | 2 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | -
3978 | 2405 | Signalling support | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | -
3979 | 2406 | Physical layer definitions - for GERAN support for the 700 MHz band | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | -
3980 | 2407 | Receiver performance and RF budget | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | -
3981 | 2408 | GERAN MS Conformance test for 700 MHz band | - | 2 | Rel-4 | GP | 2001-04-02 08:00 | 2001-11-30 17:00 | 100% | GP-000451 | - | - | - | - | -
3982 | 2410 | GERAN BTS Conformance test for 700 MHz band | - | 2 | Rel-4 | GP | 2001-04-02 08:00 | 2002-12-20 17:00 | 100% | GP-000452 | - | - | - | - | -
3983 | 2463 | Operator Determined Barring for Packet Oriented Services | ODB | 1 | Rel-4 | NP | 2000-06-01 08:00 | 2001-03-19 17:00 | 100% | NP-010089 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | Completed WI missing from the P-plan Added for tracking | -
3984 | 2546 | UMTS QoS Architecture for PS Domain | QoSPS | 1 | Rel-4 | S2,S5,R3,GP | 2000-01-03 08:00 | 2002-11-27 17:00 | 100% | SP-010342 | - | Ericsson | Ina.widegren@era.ericsson.se | - | -
3985 | 2548 | Architecture | - | 2 | Rel-4 | S2 | 2000-06-05 08:00 | 2001-01-03 17:00 | 100% | - | - | - | - | - | 23.107
3986 | 2550 | Charging and OAM&P for QoS Management | QoSPS-OAM | 2 | Rel-4 | S5 | 2001-09-21 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | - | - | - | 32-series
3987 | 1681 | RAB Quality of Service (re)Negotiation over Iu | QoSPS-MAPEND-RABQoS | 2 | Rel-4 | R3 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Ericsson | anders.molander@ericsson.com | - | 25.413
3988 | 1991 | RAB Quality of Service Negotiation over Iu | QoSPS-MAPEND-RABQoS-Negot | 3 | Rel-4 | R3 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Ericsson | anders.molander@ericsson.com | - | -
3989 | 2456 | RAB Quality of Service Negotiation over Iu during relocation | QoSPS-MAPEND-RABQoS-NegotReloc | 3 | Rel-4 | R3 | 2001-03-02 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
3990 | 1992 | RAB Quality of Service Re-Negotiation over Iu | QoSPS-MAPEND-RABQoS-ReNegot | 3 | Rel-4 | R3 | 2000-09-25 08:00 | 2001-03-23 17:00 | 100% | - | - | Motorola | S. Irwin | - | -
3991 | 1553 | GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms | GERQoS | 2 | Rel-4 | GP | 2000-01-03 08:00 | 2001-11-30 17:00 | 100% | GP-010431 | - | - | - | - | -
3992 | 2306 | Handover Concept for the PS domain | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3993 | 2309 | Stable RT handover report 25.936 including header removal | - | 4 | Rel-4 | GP | 2000-01-03 08:00 | 2000-01-19 17:00 | 100% | - | - | - | - | - | -
3994 | 2307 | Update of stage 2 | - | 4 | Rel-4 | GP | 2000-01-03 08:00 | 2001-02-13 17:00 | 100% | - | - | - | - | - | -
3995 | 2308 | Update of relevant stage 3 specs -> RRC | - | 4 | Rel-4 | G2 | 2000-01-03 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | -
3996 | 50010 | Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover | GERQoS-Mstest | 2 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | GP-012287 | - | - | - | Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008 | -
3997 | 50011 | Deleted - Handover for the PS domain | - | 3 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3998 | 50012 | Deleted - Stable RT handover report 25.936 including header removal | - | 4 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
3999 | 50013 | Deleted - Update of stage 2 | - | 4 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4000 | 50014 | Deleted - Update of relevant stage 3 specs | - | 4 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4001 | 1685 | PS-domain handover for real-time services | QoSPS-PSdoRTS | 2 | Rel-4 | R3 | 2000-08-28 08:00 | 2001-03-30 17:00 | 100% | - | - | Nokia | atte.lansisalmi@nokia.com | - | -
4002 | 2554 | Deleted - RAB QoS Renegotiation at Relocation | - | 2 | Rel-4 | R3 | 2001-01-03 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 25.851, 25.946
4003 | 1993 | (Small) Technical Enhancements and Improvements for Rel-4 | TEI4 | 1 | Rel-4 | SP,CP,RP,GP | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system | -
4004 | 25017 | Test - (Small) Technical Enhancements and Improvements for Rel-4 | TEI4_Test | 1 | Rel-4 | R5,T1 | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP | -
4005 | 400002 | Rel-4 Evolutions of the transport in the UTRAN | ETRAN | 1 | Rel-4 | RP | 2000-08-21 08:00 | 2002-08-23 17:00 | 100% | - | - | Alcatel | Francois Courau | - | -
4006 | 12 | QoS optimization for AAL2 connections over Iub and Iur interfaces | ETRAN-QoSAAL2 | 2 | Rel-4 | R3 | 2000-08-21 08:00 | 2001-03-30 17:00 | 100% | - | - | Japan Telecom | T. Yoshimura | - | -
4007 | 1995 | Transport bearer modification procedure on Iub, Iur, and Iu | ETRAN-MigrMod | 2 | Rel-4 | R3 | 2000-10-02 08:00 | 2001-03-30 17:00 | 100% | - | - | Japan Telecom | T. Yoshimura | - | -
4008 | 401834 | Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN | - | 2 | Rel-4 | T1 | 2002-02-25 08:00 | 2002-08-23 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4009 | 2208 | Deleted - Testing RAB support enhancements | CT-RABS? | 3 | Rel-4 | T1 | 2002-02-25 08:00 | 2002-08-23 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3
4010 | 400004 | Rel-4 Evolutions of the transport in the CN | CNTRSP | 1 | Rel-4 | N4,N1,N2,S2 | 2000-05-29 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
4011 | 859 | IP Transport of CN protocols (e.g. CAP, MAP) | SS7IP | 2 | Rel-4 | N4 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
4012 | 1679 | Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP) | - | 3 | Rel-4 | N4 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
4013 | 2018 | CAP | - | 4 | Rel-4 | N2 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
4014 | 2019 | MAP | - | 4 | Rel-4 | N4 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | 29.202
4015 | 2253 | BSSAP+ | SS7IP-BSSAP+ | 4 | Rel-4 | N1 | 2001-01-15 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | - | -
4016 | 1513 | FS on Transport and control separation in the PS CN domain | - | 2 | Rel-4 | S2 | 2000-05-29 08:00 | 2001-03-23 17:00 | 100% | SP-000293 | - | Ericsson | Juan-Antonio.Ibanez@eed.ericsson.se | - | -
4017 | 1615 | Architectural impacts | - | 3 | Rel-4 | S2 | 2000-05-29 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
4018 | 401216 | Rel-4 Improvements of Radio Interface | - | 1 | Rel-4 | RP | 2000-07-10 08:00 | 2003-03-14 17:00 | 100% | - | - | - | - | - | -
4019 | 1509 | UTRA repeater specification (master) | RInImp-REP | 2 | Rel-4 | R4 | 2000-07-10 08:00 | 2001-03-21 17:00 | 100% | - | - | Mikom, Allgon | T. Kummetz, Mikom; Alf Ahlström, Allgon | - | -
4020 | 1994 | DSCH power control improvement in soft handover | RInImp-DSCHsho | 2 | Rel-4 | R1 | 2000-09-11 08:00 | 2001-03-23 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | -
4021 | 1996 | UMTS 1800 | RInImp-UMTS18 | 2 | Rel-4 | R4 | 2000-09-25 08:00 | 2001-12-14 17:00 | 100% | - | - | Motorola | Howard Benn | - | -
4022 | 2467 | UMTS 1900 | RInImp-UMTS19 | 2 | Rel-4 | R4 | 2001-03-19 08:00 | 2001-12-14 17:00 | 100% | - | - | Motorola | Howard Benn | - | 25.101
4023 | 1219 | FS on High Speed downlink packet access | RInImp-HSDPA | 2 | Rel-4 | R2 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Motorola | Amitabha Ghosh (qa0047@email.mot.com) | - | -
4024 | 1510 | Deleted - FS on improved common DL channel for Cell-FACH state | RInImp-DLCFACH | 2 | Rel-4 | R2 | 2000-09-11 08:00 | 2001-12-28 17:00 | 100% | - | - | GBT | J. Kwak | Stopped at RP#14 | -
4025 | 401839 | Conformance Test Spec. Rel-4 improvements in Radio Interface | - | 2 | Rel-4 | T1 | 2001-10-08 08:00 | 2003-03-14 17:00 | 100% | - | - | - | - | - | -
4026 | 2212 | Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type | - | 3 | Rel-4 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4027 | 2213 | Deleted - Testing Terminal Power saving features | - | 3 | Rel-4 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4028 | 2214 | Deleted - Testing DSCH power control improvement in soft handover | - | 3 | Rel-4 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4029 | 2215 | Testing UMTS 1800 | - | 3 | Rel-4 | T1 | 2001-10-08 08:00 | 2002-06-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.108, 34,121, 34.122, 34.123-1
4030 | 41000 | Testing UMTS 1900 | - | 3 | Rel-4 | T1 | 2001-10-08 08:00 | 2002-06-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.108, 34,121, 34.122, 34.123-1
4031 | 2561 | Testing UMTS 1800 - TTCN | - | 3 | Rel-4 | T1 | 2002-06-17 08:00 | 2003-03-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-3
4032 | 41001 | Testing UMTS 1900 - TTCN | - | 3 | Rel-4 | T1 | 2002-06-17 08:00 | 2003-03-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-3
4033 | 400009 | Rel-4 RAN improvements | - | 1 | Rel-4 | RP | 2000-08-14 08:00 | 2004-03-17 17:00 | 100% | - | - | - | - | - | -
4034 | 655 | Node B synchronization for TDD | RANimp-NBsync | 2 | Rel-4 | R1 | 2000-08-14 08:00 | 2001-03-23 17:00 | 100% | - | - | Siemens | S. Oestreich | - | -
4035 | 2206 | RAB support enhancement for Rel-4 | RANimp-RABSE | 2 | Rel-4 | R2 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Ericsson | M. Israelsson, A. Krishnarajah | 29 Nov 2000: split into ROHC and non-ROHC part; 5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2 | -
4036 | 402102 | Deleted - Conformance Test Aspects - Rel-4 RAN Improvements | - | 2 | Rel-4 | T1 | 2002-01-01 08:00 | 2004-03-17 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4037 | 402222 | Deleted - Testing Radio access bearer support enhancments | - | 3 | Rel-4 | T1 | 2002-01-01 08:00 | 2002-09-02 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | -
4038 | 402461 | Deleted - Testing RAB support enhancements-Robust Header Compression | RABimp-RoCH | 3 | Rel-4 | T1 | 2002-05-28 08:00 | 2003-09-03 17:00 | 100% | TP-030052 | - | - | - | UID changed. Marked as stopped 12/2008 | 34.123-1, -2
4039 | 41006 | Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN | - | 3 | Rel-4 | T1 | 2002-05-28 08:00 | 2004-03-17 17:00 | 100% | TP-030052 | - | - | - | UID changed. Marked as stopped 12/2008 | 34.123-3
4040 | 41007 | Testing of Extended Robut Header Compression | Ext-RoHC | 3 | Rel-4 | T1 | 2002-09-18 08:00 | 2003-09-30 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 15% complete) | 34.123-1, -2
4041 | 41008 | Deleted - Testing of Extended Robut Header Compression - TTCN | - | 3 | Rel-4 | T1 | 2002-09-18 08:00 | 2003-12-16 17:00 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | 34.123-3
4042 | 41009 | Deleted - General changes to TS34.121 corresponding to release 4 | RANimp-test, TEI4 | 3 | Rel-4 | T1 | 2003-03-03 08:00 | 2004-03-03 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34.121
4043 | 401652 | Rel-4 Emergency call enhancements | EMC1, EMC1-CS | 1 | Rel-4 | N1,S1,T1 | 2000-01-03 08:00 | 2002-05-28 17:00 | 100% | - | - | Ericsson | - | - | - | Public Safety (I-A)
4044 | 1654 | For CS based calls | EMC1-CS | 2 | Rel-4 | N1 | 2000-01-03 08:00 | 2002-05-28 17:00 | 100% | NP-010136 | - | Ericsson | - | WI approved in TSG_10 | - | Public Safety (I-A)
4045 | 1320 | Distinction in CS domain of emergency call types to different emergency services | - | 3 | Rel-4 | S1 | 2000-05-01 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | - | Public Safety (I-A)
4046 | 1999 | Distinction in CS domain of emergency calls to different emergency types | - | 3 | Rel-4 | N1 | 2000-08-24 08:00 | 2000-09-22 17:00 | 100% | NP-010136 | - | - | - | Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.... | 24.008 | Public Safety (I-A)
4047 | 402224 | Deleted - Conformance Test Aspects - Emergency call enhancements | - | 3 | Rel-4 | T1 | 2000-01-03 08:00 | 2000-07-28 17:00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - | Public Safety (I-A)
4048 | 2226 | Testing CS based emergency calls | - | 3 | Rel-4 | T1 | 2002-02-25 08:00 | 2002-05-28 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-1 | Public Safety (I-A)
4049 | 2563 | Testing CS based emergency calls - TTCN | - | 3 | Rel-4 | T1 | 2001-11-22 08:00 | 2002-05-28 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-3 | Public Safety (I-A)
4050 | 401826 | Rel-4 Terminal interfaces | TI | 1 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-15 17:00 | 100% | - | - | - | - | - | -
4051 | 1827 | AT commands enhancements | TI-ATC | 2 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | - | 27.007
4052 | 1828 | Specification of AT commands for new services | - | 3 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | goal not completely achieved because of missing input | 27.007
4053 | 1829 | Wide Area Data Synchronization | TI-WADS | 2 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added | -
4054 | 1830 | Continues evolution of Synchronization protocol | TI-SYNC-EVOL | 3 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | - | 27.903, 27.103
4055 | 1832 | Terminal local model | TLM | 2 | Rel-4 | T2 | 2000-05-16 08:00 | 2001-03-15 17:00 | 100% | TP-000080 | - | Ericsson | Olga.Tome@ECS.ERICSSON.SE | - | 23.227
4056 | 401536 | Rel-4 Location Services enhancements | LCS1 | 1 | Rel-4 | S2,S1,T2,N1,N4,R3,R2 | 2000-04-03 08:00 | 2001-12-28 17:00 | 100% | SP-010518 | - | Nokia | Jan Kall | - | -
4057 | 2229 | CBS interactions | LCS1-CBS | 2 | Rel-4 | T2 | 2000-04-03 08:00 | 2001-12-28 17:00 | 100% | - | - | - | - | - | 23.041
4058 | 523 | LCS support in the CS domain | LCS1-CS | 2 | Rel-4 | S2 | 2000-05-15 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | Only MAP impact foreseen so far. To be further split if needed. | -
4059 | 525 | LCS support in the PS domain | LCS1-PS | 2 | Rel-4 | S2,S1,N1,N4 | 2000-05-01 08:00 | 2001-12-28 17:00 | 100% | - | - | - | - | - | -
4060 | 1642 | Stage 1 for LCS support in the PS domain | - | 3 | Rel-4 | S1 | 2000-07-03 08:00 | 2000-08-25 17:00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established | 22.071
4061 | 1181 | Stage 2 for LCS support in the PS domain | - | 3 | Rel-4 | S2,R2,G1 | 2000-05-01 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | SP#10 completed | 25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)
4062 | 1180 | Stage 3 for LCS support in the PS domain | - | 3 | Rel-4 | N1,N4 | 2000-08-21 08:00 | 2001-12-28 17:00 | 100% | - | - | - | - | - | -
4063 | 526 | Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS) | - | 4 | Rel-4 | N1 | 2000-08-21 08:00 | 2001-12-28 17:00 | 100% | - | - | Nokia | Janne Muhonen | - | -
4064 | 2462 | MAP impacts of LCS | - | 4 | Rel-4 | N4 | 2000-08-21 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | -
4065 | 527 | GTP signalling for LCS | - | 4 | Rel-4 | N4 | 2000-08-21 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | -
4066 | 401600 | UE positioning Rel-4 | LCS1-UEpos | 2 | Rel-4 | R3,R2 | 2000-04-03 08:00 | 2001-03-30 17:00 | 100% | RP-000509 | RP-010045 | - | - | - | -
4067 | 1601 | Iub/Iur interfaces for methods Rel 99 | LCS1-UEpos-IubIur | 3 | Rel-4 | R3 | 2000-04-03 08:00 | 2001-03-30 17:00 | 100% | RP-000509 | RP-010045 | Ericsson | Yun-Chao Hu | - | 25.401, 25.420, 25.423, 25.430, 25.433, new TR 25.850
4068 | 1602 | UE positioning enhancements - IPDL for TDD | LCS1-UEpos-enh | 3 | Rel-4 | R2 | 2000-08-28 08:00 | 2001-03-23 17:00 | 100% | RP-000509 | RP-010045 | Siemens | Armin Sitte | 5 Mar 2001: split of IPDL for TDD agreed by R2 | new TR 25.847
4069 | 401560 | Rel-4 UICC/(U)SIM enhancements and interworking | UICC1, Rel-4 | 1 | Rel-4 | T3 | 2000-07-24 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | -
4070 | 1799 | Common PCN Handset Specification (CPHS) | UICC1-CPHS | 2 | Rel-4 | T3 | 2000-07-24 08:00 | 2001-03-23 17:00 | 100% | TP-000116 | - | One2One | - | 28/5/2001: CRs approved at TP-11. WI complete. | 27.103
4071 | 401800 | Rel-4 (U)SIM toolkit enhancements | USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM | 1 | Rel-4 | T3,S1 | 2000-06-05 08:00 | 2001-03-23 17:00 | 100% | - | - | Gemplus | Jean-Francois Rubon | - | 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)
4072 | 2034 | USAT local link | USAT1-LocLnk | 2 | Rel-4 | T3,S1 | 2000-06-05 08:00 | 2001-03-23 17:00 | 100% | TP-000116 | - | Gemplus | Jean-Francois Rubon | 25/5/2001:CR was approved at TP-11. WI is complete | 22.038, 31.111
4073 | 401571 | Rel-4 Security enhancements | SEC1 | 1 | Rel-4 | S3,N4,N1 | 2000-01-03 08:00 | 2002-03-15 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | - | -
4074 | 1331 | Rel-4 Lawful Interception | SEC1-LI | 2 | Rel-4 | S3 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above. | 33.107
4075 | 1587 | Evolution of GSM CS algorithms (e.g. A5/3 development and deployment) | SEC1-CSALGO1 | 2 | Rel-4 | S3 | 2000-01-03 08:00 | 2001-01-15 17:00 | 100% | SP-000306 | - | DTI, BIS | cbrookson@iee.org | SP#8 approved WID | 33.102, 33.103, 33.105
4076 | 1588 | Evolution of GSM PS algorithms (e.g. GEA 2 deployment) | SEC1-PSALGO1 | 2 | Rel-4 | S3,N4,N1 | 2000-02-22 08:00 | 2000-12-22 17:00 | 100% | SP-000307 | - | DTI, BIS | cbrookson@iee.org | SP#8 approved WID | 33.102, 33.103, 33.105
4077 | 1589 | Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment) | - | 3 | Rel-4 | S3 | 2000-02-22 08:00 | 2000-11-24 17:00 | 100% | - | - | DTI, BIS | cbrookson@iee.org | Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED | -
4078 | 1618 | Impact on GTP | - | 3 | Rel-4 | N4 | 2000-03-20 08:00 | 2000-12-22 17:00 | 100% | - | - | DTI, BIS | cbrookson@iee.org | - | -
4079 | 1661 | GEA capability indication in MS CM | SEC1-PSALGO1-GEACAP | 3 | Rel-4 | N1 | 2000-06-19 08:00 | 2000-12-22 17:00 | 100% | - | - | Vodafone Airtouch | Duncan Mills | - | -
4080 | 401583 | Deleted - MAP application layer security | SEC1-MAPAL | 2 | Rel-4 | S3 | 2000-01-03 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008 | -
4081 | 401584 | Deleted - Main aspects of MAP application layer security | - | 3 | Rel-4 | S3 | 2000-02-21 08:00 | 2001-03-29 17:00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | -
4082 | 402025 | Deleted - Other stage 3 aspects | - | 3 | Rel-4 | N4 | 2000-02-22 08:00 | 2000-11-24 17:00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | -
4083 | 401594 | Deleted - Visibility and Configurability of security | SEC1-VCS | 3 | Rel-4 | S3 | 2000-01-03 08:00 | 2002-03-15 17:00 | 100% | SP-000305 | - | France Telecom | Sebastien.nguyenngoc@rd.francetelecom.com | CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008 | -
4084 | 401142 | Rel-4 Charging and OAM&P | OAM4 | 1 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-10-05 17:00 | 100% | SP-010461 | - | - | - | SP#13 approved WID | -
4085 | 2089 | Rel-4 Principles, high level Requirements and Architecture | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-06-21 17:00 | 100% | SP-010461 | - | Motorola, Telia | Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE | - | 32.101, 32.102
4086 | 2088 | Rel-4 Performance Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-09-28 17:00 | 100% | SP-010238 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.4xy, 52.402
4087 | 2081 | Fault Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-10-05 17:00 | 100% | SP-000524 | - | Lucent | - | - | 32.111-1/4
4088 | 2082 | Configuration Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-06-21 17:00 | 100% | SP-000524 | - | Ericsson | thomas.tovinger@ericsson.com | - | 32.106-1/8
4089 | 2083 | Rel-4 Charging Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-09-28 17:00 | 100% | SP-000524 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.200, 32.205, 32.215, 32.235
4090 | 2071 | UTRAN Operations and Maintenance procedures | UOAM | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-06-21 17:00 | 100% | SP-000524 | - | Mannesmann Mobilfunk | bert.boden@d2mannesmann.de | - | 32.800
4091 | 1517 | Global Text Telephony | GTT | 1 | Rel-4 | S1,S2,S4,T1,R5 | 2000-01-03 08:00 | 2009-09-18 17:00 | 100% | SP-010340 | - | Ericsson | gunnar.hellstrom@omnitor.se | SP#12 updated WID SP-000162=>SP-010340 | -
4092 | 1634 | Stage 1 for Global Text Telephony | - | 2 | Rel-4 | S1 | 2000-04-05 08:00 | 2000-12-22 17:00 | 100% | SP-010340 | - | - | - | - | 22.226
4093 | 1519 | Stage 2 for Global Text Telephony | - | 2 | Rel-4 | S2 | 2000-01-03 08:00 | 2000-10-13 17:00 | 100% | SP-010340 | - | - | - | - | 23.226
4094 | 2234 | Specification of Cellular Text telephone Modem | GTT-CTM | 2 | Rel-4 | S4 | 2000-09-11 08:00 | 2001-03-19 17:00 | 100% | SP-010340 | - | - | - | - | -
4095 | 2238 | General description and C-code | - | 3 | Rel-4 | S4 | 2000-09-11 08:00 | 2000-12-11 17:00 | 100% | - | - | - | - | - | 26.226, 26.230
4096 | 2237 | Minimum Performance requirements | - | 3 | Rel-4 | S4 | 2000-09-11 08:00 | 2001-03-19 17:00 | 100% | - | - | - | - | - | 26.231
4097 | 1852 | Deleted - Conformance Test Aspects - Global Text Telephony | GTT_Test | 2 | Rel-4 | R5,T1 | 2000-09-21 08:00 | 2009-09-18 17:00 | 100% | - | - | - | - | RP#45 work item abandoned/closed (it was never really started) | -
4098 | 0 | Release 1999 Features | - | 1 | R99 | NP,SP,TP,SMG | 2000-01-03 08:00 | 2000-12-29 17:00 | 100% | - | - | - | - | - | -
4099 | 60150 | UMTS Features | - | 1 | R99 | S1,S2,S4,SMG,N3,N4,RP | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4100 | 60102 | UMTS_SERVICES | UMTS_SERVICES | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.101
4101 | 60103 | UMTS phase 1 | UMTS1 | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.100
4102 | 60119 | UMTS Capabilities | UMTS_Capabil | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Requirement for high quality speech in UMTS Phase 1 but not in R99 | 22.105
4103 | 60164 | Architecture of the GSM-UMTS platform | - | 2 | R99 | S2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface” | 23.002, 23.008, 23.060, 23.101, 23.110
4104 | 60165 | UMTS Terrestrial Radio Access Network | UTRAN | 2 | R99 | RP | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,
4105 | 60083 | UMTS 1800, UMTS 1900 | Rlnlmp19, Rlnlmp18 | 2 | R99 | R2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 25.307 CR#0002, 0003 Inclusion of release independent RF related information
4106 | 60149 | Mandatory speech codec for narrowband telephony service | Mandatory_Speech_Codec, AMR-NB, AMR | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99060 | - | - | - | Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec. | 04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975
4107 | 60055 | Codec for low bitrate multimedia telephony service | Low_bit_rate_codec_for_MM_Tel., H.324M | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99060 | - | - | - | - | 26.104, 26.110, 26.111, 26.911, 26.912, 26.915
4108 | 60109 | 3G Audio-Visual Terminal characteristics | WI5TAC, 3G-AVT, Terminal_Acoustic_Characteristics | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99129 | - | - | - | - | 26.131, 26.132
4109 | 60104 | Updates_for_UMTS | Updates_for_UMTS | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 24.022, 27.001, 29.007
4110 | 60124 | UMTS | UMTS | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.060, 29.061
4111 | 60151 | UMTS and GSM Features | - | 1 | R99 | S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4112 | 60147 | Multimedia Messaging Service | MMS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols. | 22.140, 23.040, 23.140
4113 | 60121 | Location Services | LCS | 2 | R99 | S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99327 | - | - | - | LCS provide ability to localize a terminal | 02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010
4114 | 60118 | Customised Application for Mobile network Enhanced Logic Phase 3 | CAMEL3 | 2 | R99 | S1,S2,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99368 | - | - | - | CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN. | 22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078
4115 | 60218 | Global view | - | 3 | R99 | S1,S2,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.078, 23.078, 29.078
4116 | 60318 | Multiple Subscriber Profile (MSP) based on CAMEL phase 3 | - | 3 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls. | 22.097 (Advanced Addressing)
4117 | 60038 | Short Message Service enhancements / Enhanced Messaging Service (EMS) | EMS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS. | 23.038, 23.039, 23.040, 23.042
4118 | 60122 | Mobile Station Execution Environment | MExE | 2 | R99 | S1,SMG1,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based. | 02.57, 22.057, 22.101, 23.057
4119 | 60123 | MS_Classmark | MS_Classmark | 2 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. | 24.008
4120 | 60057 | MultiCall | Multicall | 2 | R99 | S1,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-000348 | - | - | - | Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time. | 22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010
4121 | 60058 | Stage 1 for Multicall | - | 3 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.030, 22.083, 22.087
4122 | 60105 | Virtual Home Environment | VHE | 2 | R99 | S1,SMG1,S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. | 02.01, 22.105, 22.121,23.127
4123 | 60067 | Open Service Access | OSA | 2 | R99 | S1,S2,N5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community. | 22.121, 23.127, 29.198, 29.998
4124 | 60091 | Super Charger mechanism for signalling traffic associated with mobility | Super_Charger | 2 | R99 | N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and … | 21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002
4125 | 60039 | Follow_Me service | Follow_Me | 2 | R99 | S1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD | 21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002
4126 | 60093 | Wide area network Synchronization and object exchange | SYNC | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. | 27.103, 27.903
4127 | 60145 | R99 Terminal Interfaces | - | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | - | -
4128 | 60166 | AT commands for 3GPP | - | 3 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services. | 27.005, 27.007
4129 | 60167 | Physical interfaces | - | 3 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements | 27.901
4130 | 60168 | Multiplexer | MUX MS-TE | 3 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal; used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it. | 27.010
4131 | 60169 | Bearer Services | - | 2 | R99 | S1,T2,N1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4132 | 60012 | Circuit Switched Bearer Services | Circuit_switched_Bearer_Services | 3 | R99 | S1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported | 22.002, 23.910, 27.001, 29.007
4133 | 60021 | Stage 1 for Circuit Switched Bearer Services | CS_Bearerss_in_UMTS | 4 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported | 22.002
4134 | 60019 | CS_Bearers | CS_Bearers | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.007
4135 | 60020 | CS_Bearerss | CS_Bearerss | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.21, 23.910, 27.001, 29.007
4136 | 60022 | CS_Data | CS_Data | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.001, 27.002, 27.003, 29.007
4137 | 60023 | CS_Data_Bearers | CS_Data_Bearers | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.910, 27.001, 29.007
4138 | 60024 | Deleted - CN3 poart of Circuit Switched Bearer Services | CSBS | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 23.910, 27.001, 29.007
4139 | 60040 | Frame Tunnelling Mode | FTM | 3 | R99 | T2,N1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side. | 22.002, 27.001, 27.007, 29.007
4140 | 60171 | Access to ISPs and Intranets – Wireless/Remote access to LANs | Interworking with PDN (DHCP) | 3 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | N3-99069 | - | - | - | Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. | 29.061
4141 | 60070 | PHS Internet Access Forum Specification | PIAFS | 3 | R99 | S1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter). | 22.002, 27.001, 27.007, 29.007
4142 | 60170 | Personal Handyphone System Internet Access Forum Standard (PIAFS) | - | 4 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf | 22.002
4143 | 60092 | Support_of_PIAFS_in_UMTS | Support_of_PIAFS_in_UMTS | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.001, 27.007, 29.007
4144 | 60172 | Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM) | UICC, USIM | 2 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102) | -
4145 | 60173 | UICC / Terminal interface; Physical and logical characteristics | UICC | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator. | 31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface TS 102 221)
4146 | 60142 | UICC/(U)SIM enhancements and interworking | UICC1 | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 31.102, 31.900
4147 | 60174 | Characteristics of the USIM application | USIM | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist | 31.102
4148 | 60114 | UICC Application Identifiers | AID, Application_Identifiers | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5). | 21.111, 31.110
4149 | 60139 | SIM Application Toolkit | SAT | 3 | R99 | S1,T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 11.14, 22.030, 22.100, 22.101
4150 | 60141 | USIM Application Toolkit | USAT | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101. | 31.111
4151 | 60175 | Bearer Independent Protocol for SAT applications to exchange data over the GSM network | BIP | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD) | 03.48, 11.10, 11.14
4152 | 60176 | Administrative commands and functions for IC cards | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000. | ETSI TS 102 222
4153 | 60177 | USIM and UICC requirements | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services | 21.111
4154 | 60140 | SIM_API | SIM_API | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.19
4155 | 60086 | SIM_toolkit_API | SIM_toolkit | 3 | R99 | SMG9,T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.48, 11.11, 11.14
4156 | 60087 | Deleted - 1.8 Volt SIM ME interface | SMIME_1.8V | 3 | R99 | SMG9 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 11.18
4157 | 60178 | USIM/UICC Testing | - | 2 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4158 | 60179 | Terminal tests for the UICC Interface | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121 | 31.120
4159 | 60180 | USIM application test specification | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface. | 31.121
4160 | 60181 | USIM conformance test specification | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102. | 31.122
4161 | 60182 | SIM toolkit test specification | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests. | 11.10-4
4162 | 60137 | Security for UMTS and GSM Features | Security | 2 | R99 | S3,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)
4163 | 60183 | Fraud Information Gathering Service (for connection-orientated services) | FIGS | 3 | R99 | S3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure | New 22.031, 23.031
4164 | 60085 | Immediate Service Termination / SECurity Immediate Service Termination | IST, SECIST | 3 | R99 | S3,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress. | 03.35, 22.032, 23.008, 23.016, 23.035, 29.002
4165 | 60018 | Core_Network_Security | Core_Network_Security | 3 | R99 | N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.002
4166 | 60152 | GSM Features | - | 1 | R99 | S1,S2,SMG,T2,N1,N2,N3,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4167 | 60184 | Dual Transfer Mode within GSM and GPRS | DTM | 2 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | 2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)” | 03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008
4168 | 60013 | Class A Dual Transfer Mode | Class_A_Dual_Transfer_Mode_(DTM) | 3 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.10
4169 | 60027 | Dual Transfer Mode | - | 3 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008
4170 | 60185 | General Packet Radio Service enahancements | GPRS enhancements | 2 | R99 | S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. | 05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060
4171 | 60132 | General Packet Radio Service | GPRS | 3 | R99 | S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061
4172 | 60133 | GPRS2 | GPRS2 | 3 | R99 | SMG1,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2) | 02.60, 23.003
4173 | 60134 | GPRS Tunnelling Protocol enhancement | GTP_enhancement | 3 | R99 | N4,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.003, 23.008, 29.060
4174 | 60186 | Enhanced Data rates for GSM Evolution - Phase 1 | EDGE - Phase 1 | 2 | R99 | SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation. | 10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26
4175 | 60030 | Enhanced Data rates for GSM Evolution | EDGE | 3 | R99 | SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID in SMG2 331/97, SMG 1147/97, SMG 1148/97 | 02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,
4176 | 60034 | EDGE-Layer1 | EDGE-Layer1 | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID in SMG2 331/97, SMG 1147/97, SMG 1148/97 | 05.05, 05.10, 05.50
4177 | 60135 | High Speed Circuit Switched Data | HSCSD | 3 | R99 | SMG1,SMG2,SMG7 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No additional features for R99. | 02.34, 04.18, 11.10-1
4178 | 60029 | Enhanced Circuit Switched Data - Phase 1 | ECSD | 3 | R99 | S1,SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info | 05.02, 08.58, 22.034
4179 | 60032 | EDGE-Enhanced Circuit Switched Data | EDGE-ECSD | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.03
4180 | 60035 | Enhanced GPRS - Phase 1 | EGPRS | 3 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008
4181 | 60033 | EDGE-EGPRS | EDGE-EGPRS | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.03, 05.05, 05.08
4182 | 60069 | Packet Flow Context (PFC) | PFC | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.18
4183 | 60031 | Support for EGPRS in ANSI-136 networks and EDGE COMPACT | EDGE-Compact | 3 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of services in spectrum below 1 MHz | 03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10
4184 | 60036 | EGPRS COMPACT | EGPRS-Compact | 3 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | COMPACT = Deployment of services in spectrum below 1 MHz | 04.18, 05.02
4185 | 60136 | COMPACT | COMPACT | 3 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | COMPACT = Deployment of services in spectrum below 1 MHz | 03.22, 04.18, 04.60, 05.08, 23.122, 24.008
4186 | 60047 | GSM_400 | GSM_400 | 2 | R99 | SMG2,SMG7,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info. | 02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007
4187 | 60048 | GSM_450 | GSM_450 | 2 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.22, 03.30, 05.01, 05.05, 05.08
4188 | 60131 | GSM_700 | GSM_700 | 2 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.05
4189 | 60041 | Deleted - GERAN | GERAN | 2 | R99 | SMG2,S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | G2: 04.18 CR#A248 , 04.60 CR#B090
4190 | 60153 | GSM Features transposed to UMTS | - | 1 | R99 | S1,S3,T2,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4191 | 60187 | Cell Broadcast Service | CBS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks | 23.041
4192 | 60188 | GSM mobile number portability euro MNP / North American MNP | MNP | 2 | R99 | S1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability. | 22.066
4193 | 60144 | Mobile Number Portability | - | 3 | R99 | N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.018, 23.066, 29.002
4194 | 60189 | Automatic establishment of roaming relations | - | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | Telecom Italia | enrico.scarrone@telecomitalia.it | framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other. | 22.101, 22.971
4195 | 60190 | Advanced addressing | - | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.101, 22.75U, 22.975
4196 | 60191 | UMTS numbering, addressing and identities | - | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity. | 22.101
4197 | 60192 | Lawful Interception for GSM Features transposed to UMTS | LI | 2 | R99 | S3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported. | New 33.106, 33.107
4198 | 60154 | Charging | - | 1 | R99 | S1,S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4199 | 60011 | R99 Charging | Charging | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.115, 23.121
4200 | 60215 | R99 OAM Charging Management | OAMCH, CH | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99271 | - | - | - | - | 32.005, 32.015
4201 | 60155 | Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM1999 | 1 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99581 | - | - | - | - | -
4202 | 60073 | OAM Principles and High-level Requirements | PR, Princs_&_Reqs_(PR) | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99581 | - | - | - | - | 32.101
4203 | 60062 | OAM Architecture | OAMAR, AR, Telecom_Management_Arch_(AR) | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99581 | - | - | - | - | 32.101, 32.102
4204 | 60014 | OAM Configuration Management | OAMCM, CM | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99273 | - | - | - | - | 32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8
4205 | 60063 | OAM Fault Management | OAMFM | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99272 | - | - | - | - | 32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4
4206 | 60064 | OAM Performance Management | OAMPM, PM | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99274 | - | - | - | - | 12.04, 32.104
4207 | 60106 | Vocabulary | Vocabulary | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 21.905
4208 | 60037 | Emergency | Emergency | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.101
4209 | 60049 | GSM General Bearer Services (GBS) and interworking scenarios support in UMTS | GSM_to_UMTS_Evol | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02 | 22.105
4210 | 60043 | GPRS_Mobile_IP_interworking | GPRS_Mobile_IP_interworking | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.061
4211 | 60046 | GSM/UMTS interworking | 2G3Ginterworking | 1 | R99 | N1,N2,N4,R3,S1,SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108
4212 | 60050 | Handover | Handover | 1 | R99 | S1,SMG2,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010
4213 | 60120 | 2G3Ghandover | 2G3Ghandover | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010
4214 | 60088 | Service Provider Name Indication | SPANME | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99 | 22.101
4215 | 60026 | Data & Data_CleanUp | Data, Data_CleanUp | 1 | R99 | SMG1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.01, 02.02, 02.04, 02.34
4216 | 60125 | Unstructured Supplementary Service Data (USSD) | USSD | 1 | R99 | SMG1,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No additional features for R99. | 02.04, 02.90, 23.090, 29.002
4217 | 60126 | Man-Machine Interface (MMI) of the User Equipment (UE) | MMI | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Data services streamlining + Support for Anonymous Call Rejection | 22.030
4218 | 60127 | Network Identity and Timezone (NITZ) | NITZ | 1 | R99 | SMG1,SMG3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.42, 04.08
4219 | 60128 | Deleted - Operator Determined Barring for Packet Oriented Services | ODB_Enh. | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Remove ODB for Packet Oriented Services from R99 | 22.041
4220 | 60068 | Packet Flow Management | Packet_Flow_Management | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 08.18
4221 | 60044 | GPRS_Point-To-Multipoint Group call | GPRS_PTMG | 1 | R99 | SMG1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.60
4222 | 60156 | Call Forwarding | - | 1 | R99 | SMG1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4223 | 60010 | Call Forwarding enhancements | CF_enhancements | 2 | R99 | N4,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No additional features for R99. | 23.078, 23.079, 23.082, 29.002, 29.078
4224 | 60116 | Call_Forwarding | Call_Forwarding | 2 | R99 | SMG1,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.82, 29.002
4225 | 60117 | Call_Forwarding_Enhancements | Call_Forwarding_Enhancements | 2 | R99 | N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.082
4226 | 60157 | Quality of Service | - | 1 | R99 | S2,T2,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID SMG 98-0781 End To End UMTS QoS Management | -
4227 | 60076 | End-to-end UMTS Quality of Service management | QoS | 2 | R99 | S2,T2,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID SMG 98-0781 End To End UMTS QoS Management | 23.107, 23.907, 24.008
4228 | 60130 | End-to-end QoS for PS Domain including IMS | E2EQoS | 2 | R99 | S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.060, 23.170
4229 | 60045 | GPRS-enhanced_QoS | GPRS-enhanced_QoS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | AT-commands for Enhanced QoS Support management | 27.007
4230 | 60077 | QoS_enhancements | QoS_enhancements | 2 | R99 | N2,N1,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.008, 23.016, 24.008, 29.002, 29.060
4231 | 60129 | Support of Localised Service Area | SoLSA | 1 | R99 | SMG2,SMG3,SMG7,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99. | 04.08, 04.18, 08.08, 11.10-1, 29.002
4232 | 60100 | Transcoder_location | Transcoder_location | 1 | R99 | S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum. | 23.110
4233 | 60113 | Antenna_test_methods | Antenna_test_methods | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.30
4234 | 60107 | WBAMR / high quality speech in UMTS Phase 1 but not in R99 | WBAMR | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Add requirement for high quality speech in UMTS Phase 1 but not in R99 | 22.105
4235 | 60138 | Codec | - | 1 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4236 | 60015 | Codecs for Multimedia Telephony Service | Codec_for_Multimedia_Telephony | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4237 | 60415 | Codecs for Multimedia Telephony Service | Multimedia_Codec | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111
4238 | 60515 | Codecs for Multimedia Telephony Service | CSM | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111
4239 | 60615 | Codecs for Multimedia Telephony Service | WI2MMC | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111
4240 | 60715 | Codecs for Multimedia Telephony Service | Codec(s)_for_CS_MM_Tel._Serv | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111
4241 | 60815 | Codecs for Multimedia Telephony Service | Codec(s)_for_MM_Tel_Service | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111
4242 | 60915 | Codecs for Multimedia Telephony Service | - | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111
4243 | 60078 | QoS for Speech and Multimedia Codec | QoS_for_Speech_&_MM_Codecs_/_AMR | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99060 | - | - | - | - | 26.102, 26.912
4244 | 60099 | Tandem Free Operation - Adaptive Multi-Rate codec types | TFOAMR | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | UMTS_AMR2 is default Codec Type in R99 dual_mode terminals | 26.103
4245 | 60112 | Noise Suppression for AMR | AMRNS | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078. | 06.77, 06.78
4246 | 60065 | Out-of-Band Transcoder | OoBT | 2 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR | 23.009, 24.008
4247 | 60066 | Out-of-Band Transcoder Control | OoBTC | 2 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | 24.008 CR#0572 in NP-020220 was approved under this WI | 24.008 CR#0572 in NP-020220
4248 | 60143 | Advanced Speech Call Items enhancements | ASCI | 1 | R99 | SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002
4249 | 60009 | Call Control improvements | CC_Related_items | 1 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441). | 24.007, 24.008
4250 | 60059 | Multimedia | Multimedia | 1 | R99 | N1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 24.008, 27.001, 29.007
4251 | 60089 | Sub-System Number allocation for RANAP, RNSAP | SSN_allocation | 1 | R99 | N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part | 23.003
4252 | 60053 | Intranet / ISP access with DHCP end-to-end | ISPaccess | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Access to an Intranet/ISP with DHCP end to end | 29.061
4253 | 60072 | Point_to_Multipoint_Services | Point_to_Multipoint_Services | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Support for the IP-Multicast protocol | 29.061
4254 | 60146 | Facsimile | FAX | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.003, 22.100
4255 | 60081 | Realtime_NT_FAX_in_UMTS | Realtime_NT_FAX_in_UMTS | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX | 27.001, 27.003
4256 | 60042 | Gateway Location Register (GLR) - Mobile Application Part (MAP) specification | GLR | 1 | R99 | N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.120
4257 | 60056 | Multiple Subscriber Profile phase 2 | MSP2 | 1 | R99 | S1,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097
4258 | 60074 | Prepaging | Prepaging | 1 | R99 | N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.018, 23.082, 29.002
4259 | 60148 | Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS | - | 1 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Re-definition of channel quality measure used for AMR link adaptation for DARP MS | 05.09
4260 | 60051 | Harmonized Standard | HS | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 13.21
4261 | 60090 | Streamlining of specifications | Streamlining | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.060, 29.061
4262 | 60079 | R99_Service_Clean_up | R99_Service_Clean_up | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061
4263 | 60094 | (Small) Technical Enhancements and Improvements for R99 | TEI | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4264 | 60095 | TEI_[CS_Data] | TEI_[CS_Data] | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4265 | 60096 | TEI_[GPRS] | TEI_[GPRS] | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4266 | 25016 | R99 UE Conformance Testing | TEI_Test | 1 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard. | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3
4267 | 60084 | Deleted - RTEI | RTEI | 2 | R99 | T1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150
4268 | 60193 | Common test environments for User Equipment (UE); Conformance testing | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | - | 34.108
4269 | 60194 | Terminal conformance specification, Radio transmission and reception (FDD) | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode. | 34.121
4270 | 60195 | Terminal conformance specification, Radio transmission and reception (TDD) | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode. | 34.122
4271 | 60196 | UE conformance specification; Part 1: Protocol conformance specification | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure. | 34.123-1
4272 | 60197 | UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. | 34.123-2
4273 | 60198 | UE conformance specification; Part 3: Abstract test suites (ATSs) | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. | 34.123-3
4274 | 60028 | Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system | DTMF | 1 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 23.014 CR#0004
4275 | 60052 | Deleted - Intersystem_Change | Intersystem_Change | 1 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 04.18 CR#A243
4276 | 60054 | Deleted - Long_Forwardedto_Numbers | Long_Forwardedto_Numbers | 1 | R99 | N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.002
4277 | 60080 | Deleted - RANimp-FSEarlyUE | RANimp-FSEarlyUE | 1 | R99 | R3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547
4278 | 0 | Release 1999 Studies | - | 1 | R99 | S1,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | -
4279 | 60061 | Advanced Addressing/Numbering | Numbering | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | Vodafone | mona.mustapha@vodafone.com | Study on requirements for numbering and addressing for UMTS | 22.975
4280 | 60161 | Combined GSM and Mobile IP mobility handling in UMTS IP CN | - | 1 | R99 | S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.923
4281 | 60101 | UE Capabilities Requirements | UCR | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure | 21.904
4282 | 60158 | Electrical safety requirements and regulations | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions. | 34.907
4283 | 60159 | Specific Absorbtion Rate (SAR) requirements and regulations in different regions | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to RAN4 at TSG-T closure. | 34.925
4284 | 60160 | Multi-mode UE issues | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs | 21.810, 21.910
4285 | 60162 | Provision of fax service in GSM and UMTS | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | Ericsson | peter.bleckert@ericsson.com | CP#27: Moved to C1 on closure of T2; see TP-050062. CP#28: C1->C3 | 22.945
4286 | 60163 | Separating Radio Resources and Mobility Management specific parts of the MS Classmark | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | CP#27: change of WG as a result of closure of CN and T. | 23.814
4287
4288
4289
4290
4291
4292
4293
4294
4295
4296
4297
4298
4299
4300
4301
4302
4303
4304
4305
4306
4307
4308
4309
4310
4311
4312
4313
4314
4315
4316
4317
4318
4319
4320
4321
4322
4323
4324
4325
4326
4327
4328
4329
4330
4331
4332
4333
4334
4335
4336
4337
4338
4339
4340
4341
4342
4343
4344
4345
4346
4347
4348
4349
4350
4351
4352
4353
4354
4355
4356
4357
4358
4359
4360
4361
4362
4363
4364
4365
4366
4367
4368
4369
4370
4371
4372
4373
4374
4375
4376
4377
4378
4379
4380
4381
4382
4383
4384
4385
4386
4387
4388
4389
4390
4391
4392
4393
4394
4395
4396
4397
4398
4399
4400
4401
4402
4403
4404
4405
4406
4407
4408
4409
4410
4411
4412
4413
4414
4415
4416
4417
4418
4419
4420
4421
4422
4423
4424
4425
4426
4427
4428
4429
4430
4431
4432
4433
4434
4435
4436
4437
4438
4439
4440
4441
4442
4443
4444
4445
4446
4447
4448
4449
4450
4451
4452
4453
4454
4455
4456
4457
4458
4459
4460
4461
4462
4463
4464
4465
4466
4467
4468
4469
4470
4471
4472
4473
4474
4475
4476
4477
4478
4479
4480
4481
4482
4483
4484
4485
4486
4487
4488
4489
4490
4491
4492
4493
4494
4495
4496
4497
4498
4499
4500
4501
4502
4503
4504
4505
4506
4507
4508
4509
4510
4511
4512
4513
4514
4515
4516
4517
4518
4519
4520
4521
4522