#### 3GPP Work Plan – Cover page

Version 2000, September 26th

# Introduction

This paragraph contains recurrent information provided to the reader not familiar with the 3GPP Work Plan. The usual reader can skip it and go to the section “Content of this version”.

The Work Plan is a living document, aiming at providing co-operations between all the 3GPP TSGs and WGs to help them reaching common targets.

These targets are called “Features”, and are new or substantially enhanced functionality which represents added value to the existing system. A feature should normally embody an improved service to the customer and / or increased revenue generation potential to the supplier. The features are divided into “Building Blocks”, a BB being a set of technical functionality which would generally be expected to reside in a single system element, i.e. a single physical or logical entity or a single protocol. The Building Blocks are divided into “Work Tasks”, a WT being by definition handled by a single Working Group. The output of a work task is the creation of one or more new Technical Specifications (or Reports) and / or Change Requests to existing TSs / TRs.

These definitions are extracted from SP-000109.

This tree structure is established to ease the monitoring of the 3GPP work progress for R00, and to make explicit the purpose of the work assigned to one WG in the global system.

A Work item is a generic term to refer to a feature, building block or work task, i.e. all the lines of the Work Plan are work items. A full description of the a work item can be found in the 3GPP Working Procedures, available at http://www.3gpp.org/About_3GPP/3gpp_wp.zip .

## General description

The Work Plan is provided in the form of a Gantt chart: the left part contains the names and attributes of the Work Items, the right part contains a calendar view reflecting the work progress (blue and grey lines apply to foreseen tasks, black lines for completed tasks).

The indentation of WI names reflects the hierarchical level in the tree structure (Features, Building Blocks, and Work Tasks).

## Attributes applicable to a WI

From the Work Plan perspective, a WI is fully characterised by the following set of attributes:

Name, Splitable (defining if the WI has to be considered as a single block or if it can be realised onto different releases), Acronym, Resource name (defining the responsible WG or TSG), Modified (see next section), Modified since last TSG (see next section), IGC (defining the responsible IGC), Start, Finish,  % completed, Impacted TS and TR, WG/TSG Approved (clarifying if the WI coversheet has been approved at WG/TSG level or if it’s just a proposal), hyperlink (to the proposed/approved WI coversheet), WI rapporteur name, WI rapporteur e-mail, Unique ID, Notes (free field).

These attributes are fully defined in a separate document.

For better readability, only some of these attributes are shown in the PDF views.

## How is the Work Plan updated?

The Work Plan is updated according to the proposals of the IGCs, Working Groups and the decisions of the TSGs.

When a proposal is rejected by the TSG, then the WI has to be deleted from the Work Plan.

The rules for modifications of WIs are the following:

- A WG can only modify the WIs under its responsibility, as well as the WIs below it: e.g. if the WG is responsible of a BB, it can modify the BB and all the corresponding WTs, even it does not have the main responsibility for these WTs. These WI modifications have to be later officially approved by the corresponding TSGs. This rule applies also to the creation and the deletion of WI(s). A TSG can act on behalf of all his WGs.

- All the editing of the Work Plan (WGs’ proposals, track of the work progress, TSG’s decisions) is performed by MCC: each member of the MCC support team includes the changes proposed or decided by his/her group. Comments on the inaccuracy of the Work Plan on a given WI shall then be addressed directly to the responsible MCC support team member.

- A modification proposed by a WG on a WI that impacts other WG(s) has to be pointed out to all the impacted WGs and, if possible, the impacted WGs’ chairmen have to be consulted before the modification is proposed (as to minimise the risk of disagreement between WGs).

# Content of this version

The modifications compared to the previous version are the following:

For the version of September 14th:

- The field “splitable” has been introduced. For a given WI, it identifies whether its children WIs can be split on different Releases (splitable= “yes”) or if the WI has to be considered as a single block (splitable= “no”).

- Milestones are now appearing in the Gantt Chart

- The inputs considered for the elaboration of this version are:

  - Key results of the SA ad-hoc of Helsinki

  - Verbal inputs from the IGCs (one meeting in Bristol)

  - MCC updates (based on WG’s review or discussion with chairmen):

    - N3 meeting #12 (David Boswarthick)

    - GERAN GP-00480 (Paolo Usai)

    - N1 meeting #13 (Ban Al Bakri)

    - T2 meeting #10 (Friedhelm Rodermund)

    - Peter George and Lidia Salmeron for T1

    - Michael Sanders for T3

    - Hans van der Veen for TSG RAN

    - Carolyn Taylor for R3

  - Also, Vodafone’s proposal on completion date was considered each time it was not conflicting with the previous inputs.

- “R4” and “R5” have been deleted from the name of the features. They will be reintroduced as soon as the R4 content will be officially approved.

For the version of September 26th:

The major modifications are:

By T groups:

- Testing dispatched to other features

- Incorporation of T approved WIs

- Advanced Cell Broadcast deleted (no active work on this feature since the beginning)

By RAN groups:

- “Evolution of transport” split into “Evolution of transport for CN” and “Evolution of transport for UTRAN”: this split was decided by TSG RAN and TSG CN chairmen but does not fit with the spirit of features being transversal items through all the system.

- “RAN technical small enhancements and improvements” added

- lot of work in updating all the RAN WIs

By CN groups:

Updates by all CN WGs, but:

- N3 updates not incorporated because incomprehensible (seems to make only one change, and this change is meaningless!).

- N5 update to add “Support of VHE/OSA by R4 network entities and protocols of the IM subsystem (e.g. CSCF)” not incorporated: not clear: IM subsystem is Rel 5, not R4.

The following BBs are deleted by CN (part of “Evolutions of the transport in the CN”):

User/signalling data transport on TCP/RTP/UDP/IP based bearers (Nb/Nc)

User/signalling data transport on ATM/AAL2 bearers (Nb/Nc)

“CAMEL phase 5” deleted because the only stage 3 WT composing it (“CAMEL applicability to media streams like VoIP”) has been moved to CAMEL phase 4.

N2 updates: the following items have been added: "Charging notification to the CSE", "Call Party Handling", "Mid call procedure for MO and MT calls" and "Inclusion of flexible tone injection"

The last version of the Work Plan and of all the related documents (cover page, WI attributes, PDF view, etc) will be available at:

ftp://ftp.3gpp.org/information/work_plan