## Slide 1: FS_NG_RTC_Ph2 SI Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2
Total 11.5 TUs
  6 TUs for Study Phase and 5.5 TUs for Normative Work
  5.5 TUs have been used after #162, 0.5 TUs are left for study phase
FS_NG_RTC_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #159 | Oct. 2023 | 1 | 1 | TR skeleton, scope and achitectural assumptions were agreed; 5 Key Issues were agreed.
SA2 #160 | Nov. 2023 | 1.5 | 1.5 | All 8 KIs were agreed; Started discussions on solutions.
SA2 #160AH-e | Jan. 2024 | 1 | 1 | Discussions on solutions
SA2 #161 | Feb 2024 | 1 | 1 | Discussions on solutions;
SA2 #162 | Apr 2024 | 1 | 1 | Discussions on solutions; Last meeting for new solution proposals; Start discussion on evaluation and conclusion;
SA2 #163 | May 2024 | 0.5 | 0.5 | Complete conclusions; Send TR for approval or for information.
 |  | 5.5 | 5.5 | TBD
 | Total | 11.5 | 11.5 | 

## Slide 3: FS_NG_RTC_ph2 status after SA2#163
General
  44 contributions were submitted to #162 and 8 contributions were handled
  Achievements:
    5 KIs (1, 2, 4, 5, 7) has been concluded
    3 KI is under discussion and revision
  TR will be sent for approval, cover sheet will be updated based on the result from this meeting
  WID will be modified based on the result from this meeting and agreed
  Controversial issues
    None
  RAN impacts and dependencies:
  None
Next steps:
  start normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC_Ph2 | Study on system architecture for next generation real time communication services phase 2 | 45%->100% | June, 2024 | 1010030