3GPP TSG-SA4 Meeting # 128 	S4-241242

Jeju, KR, 20th - 24th May 2024

Agenda item: 	8.10

Source: 	Orange

Title: 	[FS_MediaEnergyGREEN] Work Plan v0.2

Document for	Agreement

# Introduction

The FS_MediaEnergyGREEN study aims to identify sustainable media metrics, architectural impacts (APIs), functional extensions required for SA4 service enablers and evaluate the feasibility of an evaluation framework to facilitate efficient energy use and energy saving for media services.

The main objectives of this study include:

- Refine relevant SA1 use cases (5.5, 5.8, 5.9, 5.10 and 5.14) in TR 22.882 in the SA4 context.

- Document existing APIs, metrics, and mechanisms inside or outside 3GPP that could be used for energy measurement, reporting and exposure of media services. This includes whether and what information is exposed, how it is exposed, and at what granularity (QoE measurement and reporting, QoS measurement and reporting, audience measurement and reporting, event exposure, CMCD reporting, etc.).

- Study the feasibility of having implementation-independent metrics and a framework to evaluate the energy usage/savings of multimedia standards features and proposals.

NOTE 1: The study will consider the work done by SA WG2 and WG5 regarding energy consumption measurement, information collection and energy saving, and reuse it as much as possible.

NOTE 2: Exchanges with other 3GPP WGs, CTA WAVE and DVB may be needed, e.g., via formal Liaison Statements.

# Time Plan

The following time plan for the execution of the FS_MediaEnergyGREEN study item objectives is proposed in the following table.

| Meeting | Study on Media enerGy consumption exposuRE and EvaluatioN framework |
| --- | --- |
| SA4#127 (29 January - 2 February 2024, Sophia-Antipolis, FR) | - Agree New Study Item FS_MediaGREEN in S4-240438. |
| SA#103 (19 - 22 March 2024, FR) | - Approve New Study Item FS_MediaEnergyGREEN in in SP-240491. |
| SA4#127-bis-e (08 - 12 April 2024, online) | - Define and agree initial workplan. - Agree Specification skeleton for TR 26.942. - Initiate work on key issues. - Communicate with other 3GPP working groups and external organizations, if necessary. |
| 3GPP SA4 MBS SWG Telco (May 7, 2024, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on key issues. |
| SA4#128 (20 - 24 May 2024, Jeju) | - Progress work on the above. - Initiate work on potential solutions addressing KI#1 and #2. - Communicate with other 3GPP working groups and external organizations, if necessary. |
| 3GPP SA4 MBS SWG Telco (June 6, 2024, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the description of the related work - Progress work on potential additional use cases - Progress work on Key issues description |
| 3GPP SA4 MBS SWG Telco (June 27, 2024, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the description of the related work - Progress work on potential additional use cases - Progress work on Key issues description |
| 3GPP SA4 MBS SWG Telco (July 11, 2024, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the description of the related work - Progress work on potential additional use cases - Progress work on Key issues description |
| 3GPP SA4 MBS SWG Telco (July 25, 2024, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the description of the related work - Progress work on potential additional use cases - Progress work on Key issues description |
| SA4#129-e (19 - 23 August 2024, online) | - Progress work on the above. - Initiate work on potential solutions addressing others Key Issues. - Communicate with other 3GPP working groups and external organizations, if necessary. |
| Post SA4#129 AHG calls | - Progress work on the above. |
| SA4#130 (18 - 22 November 2024, Orlando) | - Progress work on the above. - Initiate work on Conclusions and proposed next steps. - Communicate with other 3GPP working groups and external organizations, if necessary. - Agree on TR 26.942 v1.0.0 to be sent to SA plenary for information. |
| SA#106 (10 - 13 December 2024, Madrid) | - Present TR 26.942 v1.0.0 to SA for information. |
| SA4#131 (17 - 21 February 2025, Geneva) | - Complete all remaining open issues. - Communicate with other 3GPP working groups and external organizations, if necessary. - Agree on TR 26.942 to be sent to SA plenary for approval |
| SA#107 (11 - 14 March 2025, Korea) | - Send TR 26.942 v2.0.0 to SA for Approval |

# Proposal

We propose the above Work Plan for the SA4 team's consideration.