## Slide 1: Exec Report SA5#156 Charging Management (CH)
Gerald Görmer, SA5 Charging Chair, MATRIXX Software

## Slide 2: Administrative aspects
Charging Work progress on Rel-19 (see S5-244481)
SA5 SWG statistics:
  participation to this meeting
  • 15 delegates participated to Charging session
  • 4 delegatefrom remote
  documents to this meeting
    122 total input and 90 output contributions
    5 Rel-19 WID (1 new) and 4 Rel-19 SID
    2 liaisons treated (1 in, 1 out)
    14 agreed CRs for Rel-19, 44 pCRs for Rel-19, 27 CRs for Maintenance
Forge process
  Yaml and ASN.1 code moderators are expected to work on Forge

## Slide 3: Incoming LSs
Tdoc | Title | Source | Decision | Reply In
S5-243816 | LS response to 3GPP_Reservation of Edge Resources and Correlation information for API volume-based charging | GSMA OPG Operator Platform API Group | postponed | -

## Slide 4: Outgoing LSs
Tdoc | Title | To | Cc | Reply To
S5-244491 | LS on Usage Information Reporting for Ranging and Sidelink Positioning Charging | SA2 | - | -

## Slide 5: Charging (CH) WIs/SIs

## Slide 6
New or Revised Charging SIDs/WIDs
Number | Title | Source
S5-244485 | New WID on Charging Aspects for 5G ProSe Phase 3 | China Telecom

## Slide 7: SA5 progress – Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
 | Rel-19 Work Items | ------ | ----- | ------ | ---- | ---- | 
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 | 5 % | SP-241001 | 25 % | 
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 20 % | SP-241002 | 50 % | 
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 13/06/2025 | 0 % | SP-241003 | 45 % | 
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 0 % | 
xxx | New WID on Charging for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | SP-241004 | 0 % | New WID
 | Rel-19 Studies | ------ | ----- | ------ | ----- | ---- | 
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 1212/2024 | 10 % | SP-240980 | 40 % | 
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_CH | 12/12/2024 | 15 % | SP-240981 | 35 % | 
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 10 % | SP-240982 | 45 % | 
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_CH | 12/12/2024 | 0 % | SP-240983 | 40 % | 
 | Rel-20 Studies | ------ | ----- | ------ | ----- | ----- | 
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan

## Slide 8
Charging Exception requests
Number | Title

## Slide 9: Rel-19 WID on CHF Segmentation
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 | 5 % | SP-241001 | 25 % | 
Progress since SA#104
  3 CRs agreed covering:
    Addition of NRF discovery reference for SMF (32.255) and AMF (32.256)
    Clarify the query attributes for NRF based CHF discovery (32.290)
RAN impacts and dependencies:
  None identified
Next steps:
  Use of CHF Group Id for CHF selection and procedures/message flow, PCF interaction when N107 is used

## Slide 10: Rel-19 WID on Charging Aspects of Ranging and Sidelink Positioning
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 20 % | SP-241002 | 50 % | 
Progress since SA#104
  7 CRs agreed covering:
    Introduction of Ranging and Sidelink Positioning Charging (TS 32.271)
    Add converged charging architecture for Ranging and Sidelink Positioning, principles for Ranging and Sidelink Positioning Charging (TS 32.271)
    Add message flows of converged charging for UE positioning assisted by Sidelink Positioning and involving 5GC (TS 32.271)
    Add CDR generation and handling for converged charging of Ranging and Sidelink Positioning (TS 32.271)
    Introduction of Data Type and Binding for Ranging and Sidelink Positioning Charging (TS 32.291)
RAN impacts and dependencies:
  None identified
Next steps:
  Introduce OpenAPI extension and charging information to CDR

## Slide 11: Rel-19 WID on charging aspects for energy efficiency of 5G
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 13/06/2025 | 0 % | SP-241003 | 45 % | 
Progress since SA#104
  3 CRs agreed covering:
    Support the energy related information per network slice (32.240, 28.201 and 28.202)
RAN impacts and dependencies:
  None identified
Next steps:
  Message flow and parameter definition

## Slide 12: Rel-19 WID on charging enhancement for indirect network sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 0 % | 
Progress since SA#104
  No contribution at this meeting
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID

## Slide 13: Rel-19 New WID on Charging Aspects for 5G ProSe Ph3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
xxx | New WID on Charging Aspects for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | tbd | 0 % | New WID
Progress since SA#104
  New WID for approval
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID

## Slide 14: Rel-19 Study (FS_5GSAT_CH_Ph3)
Progress since SA#104
  14 pCRs for TR 28.846 were approved covering
    Add the skeleton, scope and reference, background and the business roles for satellite charging
    Introduce the use cases for the roaming charging of satellite access
    Add business scenarios for roaming from terrestrial operator network to satellite operator network
    Add business scenarios for satellite resource rental between satellite network operator and terrestrial network operator
    Charging for satellite resource rental between satellite network operator and terrestrial network operator
    Charging between satellite operator and satellite MVNO
    Add business scenarios, charging scenarios, charging requirements and key issues for store and forward satellite operation
  Draft TR 28.846(email approval S5-244557)
RAN impacts and dependencies:
  None identified
Next steps:
  Drafting of requirements, key issues and solutions for the study
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 12/12/2024 | 10 % | SP-240980 | 40 % | 

## Slide 15: Rel-19 Study (FS_CAPIF_CH)
Progress since SA#104
  11 pCRs for TR 28.849 were approved covering
    The initial skeleton, update skeleton and document structure
    The scope, references and background
    Introduce the background of CAPIF charging
    Add Topic for CAPIF Charging Scenarios and KI and on API invocation charging
    Addition of use cases for the CAPIF Converged Charging of multiple API Providers, API Invokers, API Usage and API operation and management
    Introduce the solution for API invocation charging
  Draft TR 28.849 (email approval S5-244558)
RAN impacts and dependencies:
  None identified
Next steps:
  Additional CAPIF use cases, solutions for the existing use cases
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_CH | 12/12/2024 | 15 % | SP-240981 | 35 % | 

## Slide 16: Rel-19 Study (FS_NG_RTC_Ph2_CH)
Progress since SA#104
  10 pCRs for TR 28.851 were approved covering
    The initial skeleton and update skeleton
    The scope, references and background
    Support of standalone IMS Data Channel sessions
    Introduce the use case of charging for DC application download and usage
    New KI on support IMS network capabilities exposure
    New KI on support IMS Data Channel PS Data Off
  Draft TR 28.851 (email approval S5-244559)
RAN impacts and dependencies:
  None identified
Next steps:
  Add more use cases, key issues and corresponding solutions.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 10 % | SP-240982 | 45 % | 

## Slide 17: Rel-19 Study (FS_UAS_CH)
Progress since SA#104
  10 pCRs for TR 28.853 were approved covering
    Add initial skeleton and update skeleton for TR 28.853.
    Add scope, background, references and abbreviations.
    Add use cases and key issues related to UAV identifier and C2 communication.
    Add use cases, key issues and solutions on charging for Services Exposure to the USS
  Draft TR 28.853 (email approval S5-244560)
RAN impacts and dependencies:
  None identified
Next steps:
  Add more use cases, key issues and corresponding solutions.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_CH | 12/12/2024 | 0 % | SP-240983 | 40 % | 

## Slide 18
Charging TSs & TRs to be sent to SA#105
Number | Title | For

## Slide 19: Charging CRs
Maintenance
TEI16
TEI17
TEI17_NIESGU
CHRACHF
TEI18
Release 19
CHFSeg
Ranging_SL_CH
EnergySys_CH

## Slide 20: Thank you!