Source:	Ericsson LM

Title:	Proposed update of IVAS project plan (IVAS-2)

Document for:	Agreement

Agenda Item:	7.6

Introduction

In this contribution an update of the IVAS project plan [1] is proposed, for a few different reasons.

First of all, the major operating points of the IVAS fixed-point code (targeting TS 26.251) were expected to be ready by the May meeting, to allow the IVAS characterization tests to start. As reported in [2] by Ittiam, this is not the case, and a further work item exception has also been requested in [3]. Further, some expected events for the IVAS specifications were missing (e.g. submission of TS 26.250 for approval). The proposed time plan considers this WI exception in the planning and includes expected CRs to IVAS specifications.

As for the current project plan, the characterization testing would be done after the completion of the fixed-point code, and may, given the end of the release, be split into a separate study/work item. The current proposal does therefore not include the details on the characterization testing.

Finally, it is noted that there were two different versions v.0.8.0 of IVAS-2, which should at least be captured in the revision history.

Proposal

It is proposed to revise the IVAS project plan [1] based on the proposal in Annex A and amend the revision history to include the missing v.0.8.0 from SA4#124.

References

[1] Tdoc S4-240369: IVAS Project Plan v.0.8.0. : Codec for Immersive Voice and Audio Services; Test sequences, v1.0.0

[2] https://list.etsi.org/scripts/wa.exe?A2=3GPP_TSG_SA4_IVAS_BASOP;eeee3f77.2405A&S=

[3] Tdoc 24-240961, Rel-18 Work Item Exception for IVAS_Codec, Huawei

## Annex A – Proposed updates to IVAS-2

| April-2024 | SA4#127bis (8-12 April) | Progress IVAS characterization permanent documents, including: - IVAS-7b Processing Plan for Characterization Phase - IVAS-8b Test Plan for Characterization Phase Drafting of IVAS Technical Report. Agreement on CRs to TS 26.117, 26.143, and 26.511. |
| --- | --- | --- |
| May-2024 | SA4#128 (20-24 May) | Progress IVAS characterization permanent documents, including: - IVAS-7b Processing Plan for Characterization Phase - IVAS-8b Test Plan for Characterization Phase Agreement on CR to TS 26.258. Agreement on TS 26.250 to be submitted for approval. Agreement on TS 26.251 to be submitted for information. Agreement on CR to TS 26.114. |
| June-2024 | TSG-SA | TS 26.250 is submitted for approval. CR on TS 26.258 is submitted for approval. CRs on TS 26.114, TS 26.117, TS 26.143, and TS 26.511 are submitted for approval. |
| Aug-2024 | SA4#129 (14-23 August) | Finalization of IVAS characterization permanent documents, including: - IVAS-7b Processing Plan for Characterization Phase - IVAS-8b Test Plan for Characterization Phase Proponents deliver justification in terms of functionality and quality of major operating points to submit the fixed-point code for approval. Agreement on IVAS FX specification TS 26.251 to be submitted for approval. Agreement on potential CRs to other IVAS specifications (e.g. TS 26.258) Agreement on IVAS TR 26.997. |
| Sep-2024 | TSG-SA | IVAS FX specification TS 26.251 is submitted for approval. Potential CRs to other IVAS specifications (e.g. TS 26.258) is submitted for approval. IVAS TR 26.997 submitted for approval. |