## Slide 1: SA WG Rel-19 capacity consolidated information

## Slide 2: SA2 Rel-19 capacity summary
SA2 capacity (see SWS-230052 / SWS-230053):
  Max TUs: 134
    Additional buffer TUs: 48 (for TEI-19, Rel-18 alignment, 5G deployment issues, …)
  Max number of SIs/WIs: 10 – 14
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 14
Assumptions
  Start: Sept 2023, End: Dec 2024 (15 months)
  Number of meetings: 8
  Expected total TUs per meeting (for all releases): 36
  Total TUs (for all releases): 288
  TUs for maintenance of past releases: 106

## Slide 3: SA3 Rel-19 capacity summary
SA3 capacity (based on SWS-230074):
  Max TUs: 98
    Additional buffer TUs: not defined
  Max number of SIs/WIs: 14
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 9
Assumptions
  Start: Sept 2023 (for early security topics), End: March 2025 (18 months)
  Number of meetings: 7
  Expected total TUs per meeting (for all releases): 17
  Total TUs (for all releases): 119
  TUs for maintenance of past releases: 21

## Slide 4: SA4 Rel-19 capacity summary
SA4 capacity (based on SWS-230076):
  Max TUs: 152
    Additional buffer TUs: 32 (for Rel-19 alignment with other WGs, …)
  Max number of SIs/WIs: 16 - 25
    Note: one feature might result in up to 3 WI/SI: study, stage 2, stage 3, and counted separately
  Max TUs per Feature: not defined
Assumptions
  Start: March 2024, End: Sept 2025 (18 months)
  Number of meetings: 8
  Expected total TUs per meeting (for all releases): 27
  Total TUs (for all releases): 216
  TUs for maintenance of past releases: 32

## Slide 5: SA5 Rel-19 capacity summary
SA5 capacity (based on SWS-230071):
  Max TUs: 120 (OAM) / 60 (Charging)
    Additional buffer TUs: not defined
  Max number of SIs/WIs: 20 (OAM) / 12 (Charging)
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: not defined
Assumptions
  Start: Jan 2024, End: Sept 2025 (21 months)
  Number of meetings: 10
  Expected total TUs per meeting (for all releases): 18 (OAM) / 8 (Charging)
  Total TUs (for all releases): 180 (OAM) / 80 (Charging)
  TUs for maintenance of past releases: 60 (OAM) / 20 (Charging)

## Slide 6: SA6 Rel-19 capacity summary
SA6 Capacity (see SWS-230085):
  Max TUs: 160
    Additional buffer TUs: not defined
  Max number of SIs/WIs: 16
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 20
Assumptions
  Start: Sept 2023, End: Dec 2024 (15 months)
  Number of meetings: 9
  Expected total TUs per meeting (for all releases): 20
  Total TUs (for all releases): 180
  TUs for maintenance of past releases: 20