Source:	MCC

Title:	Status Report for 2008

Agenda item:	3.1

| Decision |  |
| --- | --- |
| Discussion |  |
| Information | X |

Document for:

This report provides detailed information on 3GPP income and expenditure for 2008 and is based on figures available on 12 February 2009.

Table of Contents

1	Year 2008 MCC Expenditure	3

1.1	MCC Staff Expenditure (Officers and Assistants)	3

1.1.1	Additional Staff - Testing	3

1.1.2	Additional on site IT support during 3GPP meetings	3

1.2	MCC Contracted Support Experts Expenditure	3

1.2.1	MCC Contracted Support Experts Expenditure including non remunerated experts	3

1.2.2	MCC Contracted Support Experts Expenditure excluding non remunerated experts	3

1.2.3	MCC Contracted Experts Expenditure Detailed Breakdown by Activity	3

1.3	MCC Travel and Subsistence	3

1.4	MCC Marketing and Communications Expenditure	3

2	Year 2008 Expenditure for 3GPP Task Forces	3

2.1	MCC Task Force 160 - 3GPP ATSs and PIXIT	3

3	Contingency	3

4	Year 2008 Partner Contributions	3

4.1	ARIB (24 Members)	3

4.2	CCSA (11 Members)	3

4.3	ETSI (243 Members)	3

4.4	ATIS (24 Members)	3

4.5	TTA (9 Members)	3

4.6	TTC (7 Members)	3

4.7	Total income expected from Partners	3

5	Invoices issued 2008	3

6	Payments received in year 2008 from 3GPP Partners	3

# 1	Year 2008 MCC Expenditure

## MCC Staff Expenditure (Officers and Assistants)

This budget line is for those permanently employed ETSI Secretariat Staff within the Mobile Competence Centre.  There have been a number of changes in the staff complement which currently comprises 10 Support Officers, 2,5 Assistants, and 0,5 Manager as follows:

John MEREDITH, Maurice POPE, Adrian ZOICAS, Xavier PIEDNOIR, Joern KRAUSE, Frédéric FIRMIN, Ingbert SIGOVICH, Paulo USAI, Dionisio ZUMERLE, Kevin FLYNN (joined in April 2008 as Marketing and Promotion officer),  Susanna KOOISTRA, Anna RIONDET, Emmanuelle WURFFEL (50%), and Adrian SCRASE (50%).

The budget line has been modified since it now comprises of the former allocation for staff (888kEur) and the allocation for Marketing and Communication staff (150 kEUR), which gives 1038 kEUR.

A number of Contractors departing in 2008 have been replaced with Staff (as a policy decision) and this raises the expenditure above the budget set.  However, this increase is more than compensated for by the corresponding reduction in Contractor expenditure over the same period . At the year end, 1297 kEUR had been spent against a budget of 1038 kEUR.

### 1.1.1	Additional Staff - Testing

The additional budget line is included to cover the full time employment of Shicheng Hu for the management of TTCN development within MCC.  (Shicheng Hu is part of another ETSI Secretariat Team but currently works full time on MCC matters).  A budget of 150kEUR had been set for this item. An additional 50 k€ had been set for succession planning but wasn’t spent in 2008 since Shicheng will continue to work beyond normal retirement age. At the year end 150kEUR had been spent against a budget of 200kEUR.

### 1.1.2	Additional on site IT support during 3GPP meetings

The table given below shows the total cost of the additional IT support provided during 3GPP “super meetings”.  The budget (30 kEUR) for this expenditure had been taken from the 2008 Contingency. This only includes labour charges, the cost of the related travels being included in the 3GPP Travel expenses.

| IT Support | man/days | total days | total k€ |
| --- | --- | --- | --- |
| 3GPPRAN1#52-bis | 8 |  |  |
| 3GPPRAN4#47 | 9 |  |  |
| 3GPPRAN1#54 | 6 |  |  |
| 3GPPRAN4#48-bis | 6 |  |  |
| 3GPPRAN 1,2,3,4,5 | 6 |  |  |
|  |  | 35 | 21 |

At the year end 21kEUR had been spent against a budget of 30kEUR.

## 1.2	MCC Contracted Support Experts Expenditure (3GPP and ETSI)

### MCC Contracted Support Experts Expenditure including non remunerated experts

The table and chart given below show the expenditure incurred for MCC Support Experts, including the value of the expert which is provided on a non-remunerated basis by TTA.  In each case, the number of days worked by each expert can be seen and the total value of that work given. At the year end, 992,10 kEUR had been spent against a budget of 1430 kEUR. The underspend is due to the conversion of contractor posts to staff posts.

The following experts left MCC during year 2008 and have since been replaced with staff:

Claude Arzelier (March)
Stoyan Baev (April)
Andrijana Brekalo (July)
Juergen Caldenhoven (December).

In many cases, the replacement of the leaving expert has not occurred immediately after his contract expired which resulted in the decrease of the Experts expenditure.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 16,00 | 1,00 |  |  |  |  |  |  |  |  |  |  | 17,00 |  |
| S. Baev | 20,00 | 25,00 | 18,00 |  |  |  |  |  |  |  |  |  | 63,00 |  |
| A. Brekalo | 20,00 | 23,00 | 13,00 | 19,00 | 20,00 | 17,50 |  |  |  |  |  |  | 112,50 |  |
| J. Caldenhoven | 18,00 | 22,50 | 23,00 | 15,00 | 24,00 | 18,50 | 2,00 | 23,00 | 24,00 | 12,00 | 22,00 | 16,00 | 220,00 |  |
| G. Chun | 24,00 | 18,00 | 25,00 | 18,00 | 25,00 | 22,00 | 22,00 | 22,00 | 19,00 | 27,00 | 22,00 | 0,00 | 244,00 |  |
| K. Kymalainen | 21,00 | 16,00 | 20,00 | 26,00 | 24,00 | 0,00 | 18,00 | 21,00 | 22,00 | 23,00 | 23,00 | 17,00 | 231,00 |  |
| P. Merias | 20,00 | 18,00 | 21,00 | 23,00 | 22,00 | 21,00 | 12,00 | 18,00 | 20,00 | 18,00 | 19,00 | 10,00 | 222,00 |  |
| S. Sesia | 18,50 | 19,00 | 23,00 | 18,00 | 24,00 | 20,50 | 10,00 | 12,00 | 9,00 | 24,00 | 21,00 | 15,00 | 214,00 |  |
| A. Sultan | 12,50 | 9,50 | 17,00 | 3,00 | 13,00 | 7,00 | 14,00 | 0,00 | 10,00 | 14,00 | 10,00 | 0,00 | 110,00 |  |
| G. Thomasen | 20,00 | 24,00 | 21,00 | 22,00 | 21,00 | 24,00 | 11,00 | 13,00 | 22,00 | 21,00 | 21,00 | 0,00 | 220,00 |  |
| Total | 190,00 | 176,00 | 181,00 | 144,00 | 173,00 | 130,50 | 89,00 | 109,00 | 126,00 | 139,00 | 138,00 | 58,00 | 1653,50 | 992,10 |

This chart includes the equivalent monetary value of the expert provided by TTA

### MCC Contracted Support Experts Expenditure excluding non remunerated experts (3GPP and ETSI)

The table and chart given below show the expenditure incurred for MCC Support Experts, excluding the value of the expert which is provided on a non-remunerated basis.  In each case, the number of days worked by each expert can be seen.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 16,00 | 1,00 |  |  |  |  |  |  |  |  |  |  | 17,00 |  |
| S. Baev | 20,00 | 25,00 | 18,00 |  |  |  |  |  |  |  |  |  | 63,00 |  |
| A. Brekalo | 20,00 | 23,00 | 13,00 | 19,00 | 20,00 | 17,50 |  |  |  |  |  |  | 112,50 |  |
| J. Caldenhoven | 18,00 | 22,50 | 23,00 | 15,00 | 24,00 | 18,50 | 2,00 | 23,00 | 24,00 | 12,00 | 22,00 | 16,00 | 220,00 |  |
| K. Kymalainen | 21,00 | 16,00 | 20,00 | 26,00 | 24,00 | 0,00 | 18,00 | 21,00 | 22,00 | 23,00 | 23,00 | 17,00 | 231,00 |  |
| P. Merias | 20,00 | 18,00 | 21,00 | 23,00 | 22,00 | 21,00 | 12,00 | 18,00 | 20,00 | 18,00 | 19,00 | 10,00 | 222,00 |  |
| S. Sesia | 18,50 | 19,00 | 23,00 | 18,00 | 24,00 | 20,50 | 10,00 | 12,00 | 9,00 | 24,00 | 21,00 | 15,00 | 214,00 |  |
| A. Sultan | 12,50 | 9,50 | 17,00 | 3,00 | 13,00 | 7,00 | 14,00 | 0,00 | 10,00 | 14,00 | 10,00 | 0,00 | 110,00 |  |
| G. Thomasen | 20,00 | 24,00 | 21,00 | 22,00 | 21,00 | 24,00 | 11,00 | 13,00 | 22,00 | 21,00 | 21,00 | 0,00 | 220,00 |  |
| Total | 166,00 | 158,00 | 156,00 | 126,00 | 148,00 | 108,50 | 67,00 | 87,00 | 107,00 | 112,00 | 116,00 | 58,00 | 1409,50 | 845,70 |

At the year end, 845,70 kEUR had been spent against a budget of 1294 kEUR.

This chart excludes the equivalent monetary value of the experts provided by TTA

### 1.2.3	MCC Contracted Experts Expenditure Detailed Breakdown by Activity

#### 1.2.3.1	3GPP Including Non Remunerated Experts

This budget line shows the expenditure incurred by MCC experts in support of 3GPP TSGs, including the non remunerated expert provided by TTA.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 16,00 | 1,00 |  |  |  |  |  |  |  |  |  |  | 17,00 |  |
| S. Baev | 20,00 | 25,00 | 18,00 |  |  |  |  |  |  |  |  |  | 63,00 |  |
| A. Brekalo | 18,00 | 23,00 | 13,00 | 19,00 | 20,00 | 17,50 |  |  |  |  |  |  | 110,50 |  |
| J. Caldenhoven | 18,00 | 22,50 | 23,00 | 15,00 | 24,00 | 18,50 | 2,00 | 23,00 | 24,00 | 12,00 | 22,00 | 16,00 | 220,00 |  |
| G. Chun | 24,00 | 18,00 | 25,00 | 18,00 | 25,00 | 22,00 | 22,00 | 22,00 | 19,00 | 27,00 | 22,00 | 0,00 | 244,00 |  |
| K. Kymalainen | 21,00 | 16,00 | 20,00 | 26,00 | 24,00 | 0,00 | 18,00 | 21,00 | 22,00 | 23,00 | 23,00 | 17,00 | 231,00 |  |
| P. Merias | 20,00 | 18,00 | 21,00 | 23,00 | 22,00 | 21,00 | 12,00 | 18,00 | 20,00 | 18,00 | 19,00 | 10,00 | 222,00 |  |
| S. Sesia | 18,50 | 19,00 | 23,00 | 18,00 | 24,00 | 20,50 | 10,00 | 12,00 | 9,00 | 24,00 | 21,00 | 15,00 | 214,00 |  |
| A. Sultan | 12,50 | 9,50 | 17,00 | 3,00 | 13,00 | 7,00 | 14,00 | 0,00 | 10,00 | 14,00 | 10,00 | 0,00 | 110,00 |  |
| G. Thomasen | 13,00 | 18,00 | 15,00 | 12,00 | 19,00 | 18,00 | 6,00 | 11,00 | 18,00 | 12,00 | 14,00 | 0,00 | 156,00 |  |
| Total | 181,00 | 170,00 | 175,00 | 134,00 | 171,00 | 124,50 | 84,00 | 107,00 | 122,00 | 130,00 | 131,00 | 58,00 | 1587,50 | 952,50 |

At the year end, 952,50 kEUR had been spent against a budget of 1390 kEUR.

This chart shows the use of Contractor resources for the support of 3GPP TSGs and includes the non remunerated expert provided by TTA

#### 3GPP Excluding Non Remunerated Experts

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C. Arzelier | 16,00 | 1,00 |  |  |  |  |  |  |  |  |  |  | 17,00 |  |
| S. Baev | 20,00 | 25,00 | 18,00 |  |  |  |  |  |  |  |  |  | 63,00 |  |
| A. Brekalo | 18,00 | 23,00 | 13,00 | 19,00 | 20,00 | 17,50 |  |  |  |  |  |  | 110,50 |  |
| J. Caldenhoven | 18,00 | 22,50 | 23,00 | 15,00 | 24,00 | 18,50 | 2,00 | 23,00 | 24,00 | 12,00 | 22,00 | 16,00 | 220,00 |  |
| K. Kymalainen | 21,00 | 16,00 | 20,00 | 26,00 | 24,00 | 0,00 | 18,00 | 21,00 | 22,00 | 23,00 | 23,00 | 17,00 | 231,00 |  |
| P. Merias | 20,00 | 18,00 | 21,00 | 23,00 | 22,00 | 21,00 | 12,00 | 18,00 | 20,00 | 18,00 | 19,00 | 10,00 | 222,00 |  |
| S. Sesia | 18,50 | 19,00 | 23,00 | 18,00 | 24,00 | 20,50 | 10,00 | 12,00 | 9,00 | 24,00 | 21,00 | 15,00 | 214,00 |  |
| A. Sultan | 12,50 | 9,50 | 17,00 | 3,00 | 13,00 | 7,00 | 14,00 | 0,00 | 10,00 | 14,00 | 10,00 | 0,00 | 110,00 |  |
| G. Thomasen | 13,00 | 18,00 | 15,00 | 12,00 | 19,00 | 18,00 | 6,00 | 11,00 | 18,00 | 12,00 | 14,00 | 0,00 | 156,00 |  |
| Total | 157,00 | 152,00 | 150,00 | 116,00 | 146,00 | 102,50 | 62,00 | 85,00 | 103,00 | 103,00 | 109,00 | 58,00 | 1343,50 | 806,10 |

This budget line shows the expenditure incurred by MCC experts in support of 3GPP TSGs, excluding the non remunerated expert provided by TTA.

At the year end, 806,10 kEUR had been spent against a budget of 1254 kEUR.

This chart shows the use of Contractor resources for the support of 3GPP TSGs and excludes the non remunerated expert provided by TTA

1.2.3.3	ETSI TC MSG

This budget line shows the expenditure incurred in support of the ETSI Mobile Standards Group activity which is closely aligned with the work of 3GPP.  The activity is 100% funded by ETSI so it is necessary to accurately track the true cost such that it may be deducted from the 3GPP accounts.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| G. Thomasen | 5,00 | 4,00 | 4,00 | 5,00 | 1,00 | 5,00 | 0,00 | 1,00 | 4,00 | 8,00 | 6,00 | 0,00 | 43,00 |  |
| Total | 5,00 | 4,00 | 4,00 | 5,00 | 1,00 | 5,00 | 0,00 | 1,00 | 4,00 | 8,00 | 6,00 | 0,00 | 43,00 | 25,80 |

At the year end, 25,80 kEUR had been spent against a budget of 25 kEUR.

#### 1.2.3.4	ETSI RT

This budget line shows the expenditure incurred in support of the ETSI Railway Telecommunications activity which performs the adaptation of 3GPP’s work for deployment in high speed trains.  The activity is 100% funded by ETSI so it is necessary to accurately track the true cost such that it may be deducted from the 3GPP accounts.

| MCC | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. Brekalo | 2,00 |  |  |  |  |  |  |  |  |  |  |  | 2,00 |  |
| G. Thomasen | 2,00 | 2,00 | 2,00 | 5,00 | 1,00 | 1,00 | 5,00 | 1,00 | 0,00 | 1,00 | 1,00 | 0,00 | 21,00 |  |
| Total | 4,00 | 2,00 | 2,00 | 5,00 | 1,00 | 1,00 | 5,00 | 1,00 | 0,00 | 1,00 | 1,00 | 0,00 | 23,00 | 13,80 |

At year end, 13,80 kEUR had been spent against a budget of 15 kEUR.

## MCC Travel and Subsistence (3GPP only)

The cost of travel and subsistence incurred by MCC is given in the chart below.  MSG, SCP and RT- related travels are not included in the total of MCC travels therefore the amount of 20kEUR has been deducted. The additional travel incurred for IT support of 3GPP “super meetings” (approx. 17 kEUR) is included, ther efore the budget had been slightly overspent. At the year end, 608 kEUR had been spent against a budget of 600 kEUR.

## MCC Marketing and Communications Expenditure

A budget of 75 kEUR has been set for Marketing and Communications in 2008. Expenditure shown in the table below excludes staff cost (150 kEUR for MarCom Officer have been included in the general Staff budget).

At year end 2008, 67 kEUR had been spent against a budget of 75 kEUR.

# 2	Year 2008 Expenditure for 3GPP Task Forces

## MCC Task Force 160 - 3GPP ATSs and PIXIT

This Task is the ongoing activity for the development of TTCN for 3G terminals.

The budget for this activity in 2008 is comprised of the following elements:

754 kEUR – 2008 3GPP funding allocation

Total 2008 budget is therefore = 754 kEUR.

The table given below shows the expenditure incurred during 2008 which shows a total of 734,40 against a budget of 754 kEUR.

PAID EXPERTS

| STF 160 | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| V. Bardaux | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 8,00 | 7,00 | 12,00 | 18,00 | 18,00 | 15,00 | 10,00 | 88,00 |  |
| O. Bergengruen | 0,00 | 0,00 | 10,00 | 5,00 | 0,00 | 5,00 | 5,00 | 5,00 | 0,00 | 0,00 | 5,00 | 0,00 | 35,00 |  |
| X. Chen | 0,00 | 0,00 | 11,00 | 14,00 | 0,00 | 0,00 | 0,00 | 0,00 | 22,00 | 3,00 | 0,00 | 4,00 | 54,00 |  |
| H. Griffiths | 15,00 | 13,00 | 14,00 | 14,50 | 14,50 | 9,50 | 15,00 | 13,00 | 19,00 | 11,00 | 11,00 | 10,50 | 160,00 |  |
| B. Martin | 0,00 | 9,00 | 12,00 | 13,00 | 7,00 | 13,00 | 0,00 | 0,00 | 5,00 | 0,00 | 0,00 | 0,00 | 59,00 |  |
| A. Rasheed | 0,00 | 19,00 | 19,00 | 7,00 | 16,00 | 18,00 | 23,00 | 14,50 | 21,00 | 19,00 | 8,00 | 5,50 | 170,00 |  |
| Thiruvathirai | 0,00 | 0,00 | 3,00 | 5,00 | 5,00 | 5,00 | 5,00 | 4,00 | 4,00 | 4,00 | 4,00 | 4,00 | 43,00 |  |
| L. Salmeron | 6,00 | 5,00 | 6,00 | 4,00 | 4,00 | 4,00 | 2,00 | 2,00 | 4,00 | 4,00 | 6,00 | 2,00 | 49,00 |  |
| T. Wacker | 2,00 | 4,50 | 1,50 | 4,50 | 8,50 | 3,00 | 1,50 | 4,00 | 9,50 | 2,00 | 5,00 | 9,00 | 55,00 |  |
| N. Wang | 0,00 | 2,00 | 3,00 | 4,00 | 1,00 | 5,00 | 24,00 | 16,00 | 13,00 | 11,00 | 4,00 | 3,00 | 86,00 |  |
| E. Weber | 2,00 | 10,00 | 2,00 | 9,50 | 10,50 | 1,50 | 4,50 | 6,50 | 14,00 | 2,00 | 1,50 | 1,00 | 65,00 |  |
| W. Seka | 14,00 | 17,00 | 16,00 | 22,00 | 20,00 | 14,00 | 21,00 | 18,00 | 19,00 | 19,00 | 0,00 | 0,00 | 180,00 |  |
| H. Zhang | 0,00 | 0,00 | 11,00 | 14,00 | 0,00 | 0,00 | 0,00 | 0,00 | 22,00 | 3,00 | 0,00 | 4,00 | 54,00 |  |
| H. Zischler | 12,00 | 12,00 | 12,00 | 12,00 | 12,00 | 9,00 | 4,00 | 9,00 | 12,00 | 10,00 | 10,00 | 6,00 | 120,00 |  |
| H. Kumar |  |  |  |  |  |  |  |  |  |  | 5,00 | 1,00 | 6,00 |  |
| Total | 51,00 | 91,50 | 120,50 | 128,50 | 98,50 | 95,00 | 112,00 | 104,00 | 182,50 | 106,00 | 74,50 | 60,00 | 1224,00 | 734,40 |

In addition, the following voluntary resources have been pledged for this task (man/month = 21.6days):

5 man months – TDIA contribution

3 man months – R&S contribution

4 man months – Qualcomm contribution

5,1 man months – Anritsu contribution

3 man months – Nokia contribution

4 man months – Ericsson contribution

1 man months – Motorola contribution

The total 2008 voluntary resources therefore = 25,1 man months.

The table given below shows the total value of the voluntary resources used for the development of TTCN:

VOLUNTARY EXPERTS

| STF 160 V | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Total days | Total kEUR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| V. Bardaux | 15,00 | 12,00 | 13,00 | 19,00 | 12,00 | 9,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 80,00 |  |
| O. Bergengruen | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 5,00 | 0,00 | 0,00 | 0,00 | 5,00 |  |
| X. Chen | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 11,00 | 0,00 | 0,00 | 0,00 | 19,00 | 14,00 | 10,00 | 54,00 |  |
| H. Eideberg | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 14,00 | 20,00 | 21,25 | 10,00 | 65,25 |  |
| H. Kumar |  |  |  |  |  |  |  |  |  | 5,00 | 0,00 | 0,00 | 5,00 |  |
| M. Abdul | 0,00 | 0,00 | 0,00 | 13,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 9,50 | 0,00 | 22,50 |  |
| M. Puumala |  |  |  |  |  |  |  |  |  | 13,00 | 10,00 | 8,00 | 31,00 |  |
| Thiruvathirai | 0,00 | 3,00 | 3,00 | 3,00 | 3,00 | 3,00 | 3,00 | 3,00 | 0,00 | 0,00 | 0,00 | 0,00 | 21,00 |  |
| L. Salmeron | 7,00 | 9,00 | 10,00 | 11,00 | 9,00 | 12,00 | 1,00 | 1,00 | 6,00 | 7,00 | 7,00 | 6,00 | 86,00 |  |
| W. Seka | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 14,50 | 5,50 | 20,00 |  |
| K. Tetzlaff |  |  |  |  |  |  |  |  |  | 5,00 | 7,00 | 8,00 | 20,00 |  |
| E. Weber | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 6,50 | 6,00 | 8,50 | 21,00 |  |
| H. Zhang | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 11,00 | 0,00 | 0,00 | 0,00 | 19,00 | 14,00 | 10,00 | 54,00 |  |
| Total | 22,00 | 24,00 | 26,00 | 46,00 | 24,00 | 46,00 | 4,00 | 4,00 | 25,00 | 94,50 | 103,25 | 66,00 | 484,75 | 290,85 |

# 3	Contingency

| Contingency | 200kEUR |
| --- | --- |
| Allocated | 15 kEUR for Gala Dinner |
| Spent | 16,26 kEUR |
| Allocated | 30 kEUR Additional IT support |
| Spent | 21kEUR |
| TOTAL ALLOCATED | 45 kEUR |
| TOTAL SPENT | 37,26 kEUR |
| Contingency remaining at year end | 162,74 kEUR |

# 4	Year 2008 Partner Contributions

The following tables give the contributions expected from the Organizational Partners in year 2008.

## 4.1	ARIB (24 Members)

| Budget category | Amount (k€) |
| --- | --- |
| Equal division of Support budget | 191 |
| Proportional division of Support budget | 346 |
| Amount due | 538 |

## 4.2	CCSA (11 Members)

| Budget category | Amount (k€) |
| --- | --- |
| Equal division of Support budget | 191 |
| Proportional division of Support budget | 159 |
| Amount due | 350 |

## 4.3	ETSI (243 Members)

| Budget category | Amount (k€) |
| --- | --- |
| Equal division of Support budget | 191 |
| Proportional division of Support budget | 3507 |
| Amount due | 3698 |

## 4.4	ATIS (24 Members)

| Budget category | Amount (k€) |
| --- | --- |
| Equal division of Support budget | 191 |
| Proportional division of Support budget | 346 |
| Amount due | 538 |

## 4.5	TTA (9 Members)

| Budget category | Amount (k€) |
| --- | --- |
| Equal division of Support budget | 191 |
| Proportional division of Support budget | 130 |
| Total | 321 |
| Deduction for provision of human resources | 136,2 |
| Amount due | 184,80 |

## 4.6	TTC (7 Members)

| Budget category | Amount (k€) |
| --- | --- |
| Equal division of Support budget | 191 |
| Proportional division of Support budget | 101 |
| Amount due | 292 |

## 4.7	Total income expected from Partners

Total Financial Payment from Partners = 		5600,8 kEUR

Value of voluntary resources from Partners = 	   	136,2 kEUR

Total = 				  5737  kEUR

# 5	Invoices issued 2008

The following invoices were addressed to 3GPP Partners for 2008.

ARIB (Japan)

| 2008 INVOICE | dated 04/04/2008 | 464 020 EUR |
| --- | --- | --- |
| AMOUNT DUE |  | 464 020 EUR |

CCSA (China)

| 2008 INVOICE | dated 04/04/2008 | 308 570 EUR |
| --- | --- | --- |
| AMOUNT DUE |  | 308 570 EUR |

ETSI (France)

| 2008 INVOICE | dated 04/04/2008 | 3 250 000 EUR |
| --- | --- | --- |
| AMOUNT DUE |  | 3 250 000 EUR |

ATIS (United States)

| 2008 INVOICE | dated 04/04/2008 | 473 920 EUR |
| --- | --- | --- |
| AMOUNT DUE |  | 473 920 EUR |

TTA (Korea)

| 2008 INVOICE | dated 04/04/2008 | 140 380 EUR |
| --- | --- | --- |
| AMOUNT DUE |  | 140 380 EUR |

TTC (Japan)

| 2008 INVOICE | dated 04/04/2008 | 254 520 EUR |
| --- | --- | --- |
| AMOUNT DUE |  | 254 520 EUR |

TOTAL PAYMENTS DUE = 4 891 410 EUR

# 6	Payments received in year 2008 from 3GPP Partners

The following payments have been received from 3GPP Organizational Partners during year 2008.

ARIB (Japan)

Amount due	464 020 EUR

Amount Paid	464 020 EUR		30/06/2008

ATIS (USA)

Amount due	473 920 EUR

Amount Paid	473 920 EUR		01/08/2008

CCSA (China)

Amount due	308 570 EUR

Amount Paid	308 570                          09/07/2008

ETSI (Europe)

Amount due	3 250 000 EUR

Amount Paid	3 250 000 EUR		04/06/2007

TTA (Korea)

Amount due	140 380 EUR

Amount Paid	140 380 EUR		23/06/2008

TTC (Japan)

Amount due	254 520 EUR

Amount Paid	120 000 EUR		30/06/2008

Amount due	134 520 EUR		05/09/2008

TOTAL PAYMENTS RECEIVED FROM ORGANIZATIONAL PARTNERS = 4 891 410 EUR

# Text boxes

MCC Contracted Experts

3GPP Expenditure 2008

Including Non Remunerated Experts

(Budget = 1390 kEUR)

952,50

1390

0

200

400

600

800

1000

1200

1400

1600

Jan.

Feb.

March

April

May

June

July

Aug.

Sept.

Oct.

Nov.

Dec.

Months

k

E

U

R

Cumulative Spend

Monthly Spend

Actual

Linear Spend to Budget

MCC Contracted Experts

3GPP Expenditure 2008

Excluding Non Remunerated Experts

(Budget = 1254 kEUR)

806,10

1254

0

200

400

600

800

1000

1200

1400

Jan.

Feb.

March

April

May

June

July

Aug.

Sept.

Oct.

Nov.

Dec.

Months

k

E

U

R

Cumulative Spend

Monthly Spend

Actual

Linear Spend to Budget

3GPP Contracted Experts

RT Expenditure 2008

(Budget = 15 kEUR)

13,80

15

-1

1

3

5

7

9

11

13

15

Jan.

Feb.

March

April

May

June

July

Aug.

Sept.

Oct.

Nov.

Dec.

Months

k

E

U

R

Cumulative Spend

Monthly Spend

Actual

Linear Spend to Budget

MCC Travels Expenditure 2008

(3GPP only)

(Budget = 600 kEUR)

608

600

0

100

200

300

400

500

600

700

Jan.

Feb.

March

April

May

June

July

Aug.

Sept.

Oct.

Nov.

Dec.

Months

k

E

U

R

Cumulative Spend

Monthly Spend

Actual

Linear Spend to Budget