## Slide 1
3GPP F2F return
Overall plan from 4Q/2022 onwards Outcome from DM#4
16th August 2022
OPf220041

## Slide 2: Proposed planning for November/2022 WGs
Agreements from DM#3bis
  November WGs confirmed as F2F, and to be hosted in Canada
  TSG chairs to work on best practices for 2-way remote access
  If pandemic-related travel hardship does not fundamentally and substantially degrade, OPs will not veto the November meeting to go ahead F2F
  Strongly encourage F2F participation, 2-way remote access primarily meant for folks under severe pandemic-related hardship
Decision from DM#4
  Re-locate November WG meetings to Europe
    EF3 to seek suitable location(s), and provide information by 29th August
    Goal is for EF3 to have signed contract(s) and provide meeting invitations by end of August
    Note that NAF3 will stop efforts and negotiations on hosting the November WGs

## Slide 3: Overall Planning for 2023
Proposed 2023 plan – overall considerations
  Goal is for 4 F2F WG meetings and 2 F2F TSGs. All other meetings planned as Electronic.
  CCSA to provide feedback on the most workable F2F meeting spacing (and location) from the perspective of pandemic-related hardship
    Option A: Feb, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q2 and Q4. Option B: April, May, Oct, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q3. Option C: April, May, Aug, Nov as F2F WG meetings. 1 Electronic WG meeting each in Q1 and Q4.
    F2F TSGs: March, September. Other TSGs planned as Electronic.
  It is decided to pursue Option A
  In case travel hardship eases, then 1 additional WG meeting (October) and 1 additional TSG meeting (December) in 2H/2023 can potentially be converted to F2F

## Slide 4: Detailed Planning for 2023
Proposed 2023 meeting plan (confirmed, pending)
  February WGs: F2F in Europe – Athens (RAN), TBD (SA/CT)
  March TSGs: F2F in Europe (Rotterdam)
  April WGs: Electronic
  May WGs: F2F in Asia (RAN in Korea, SA/CT in [Europe?])
  June TSGs: Electronic
  August WGs: F2F in Europe
  September TSGs: F2F in [Europe?]
  October WGs: Electronic
  November WGs: F2F in [NA?]
  December TSGs: [Electronic?]
TSDSI indicated willingness to host a TSG or SA/CT WG meeting in 2023
  How to utilize this offer is TBD

## Slide 5: Next steps for F2F_DM
Follow up F2F_DM#4bis on 29/August 12:30-15:30h UTC
  Confirm November/2022 details
  Confirm pending issues in 2023 plan
  Initial distribution of hosts for 2024 meeting calendar

## Slide 6
Thank You!