## Slide 1: 3GPP TSG SA Management Report
Georg Mayer, 3GPP SA Chairman
PCG44_06
Agenda item: 4.3

## Slide 2: Executive Summary
COVID-19 Crisis has tremendous impact on the work of 3GPP as a whole and on 3GPP SA and its WGs.
Thanks to quick and efficient coordination amongst TSG chairs, a number of hurtful but necessary steps were possible to be approved, mainly
  Cancellation of all 3GPP face-to-face meetings in Q1 and Q2 2020 and complete change to e-meetings
  Shifting of Rel-16 stage 3 freeze from March to June plenaries 2020
  Shifting of Rel-17 timeline (which was agreed in December 2019) by 3 months
Rel-17 Planning (December 2019) was concluded
  Prioritization of Work Items and Work Tasks led to a stable set of 3GPP SA2 work items, which are well-coordinated with other WGs and other TSGs wherever necessary
  Rel-17 agreed to be a “15-month Release”
Focus in the upcoming months will be the completion of all still open Rel-16 items to ensure freezing in June 2020 and to meet the IMT-2020 submission deadline.
Work on Rel-17 items is starting up in Q2 in e.g. SA2 and SA6. Nevertheless, the reduced amount of work that can be achieved during e-meetings limits the output.

## Slide 3: 3GPP SA Leadership

## Slide 4: TSG SA Officials (December 2019)
Georg Mayer
TSG SA Chairman
ETSI
georg.mayer@huawei.com
김래영 Laeyoung Kim
TSG SA Vicechair
TTA
laeyoung.kim@lge.com
Gregory (Greg) Schumacher
TSG SA Vicechair
ATIS
gregory.schumacher@sprint.com
中野 裕介 Yusuke Nakano
TSG SA Vicechair
ARIB
you-nakano@kddi.com
Maurice Pope
Secretary
MCC
maurice.pope@etsi.org

## Slide 5: SA1 Officials (December 2019)
José Luis Almodovar Chico
SA1 Chairman
ETSI jose.almodovarchico@tno.nl
Gregory (Greg) Schumacher
TSG SA1 Vicechair
ETSI
gregory.schumacher@sprint.com
Alain Sultan
Secretary
MCC
alain.sultan@etsi.org
夏 旭 Xu Xia
SA1 Vicechair
CCSA
xiaxu@chinatelecom.cn

## Slide 6: SA2 Officials (December 2019)
Puneet Jain
SA2 Chairman
ATIS
puneet.jain@intel.com
Andy Bennett
SA2 Vicechair
ETSI
a.bennett@samsung.com
孙滔 Tao Sun
SA2 Vicechair
CCSA
suntao@chinamobile.com
Maurice Pope
Secretary
MCC
maurice.pope@etsi.org

## Slide 7: SA3 Officials (December 2019)
Noamen Ben Henda
SA3 Chairman
ETSI
noamen.ben.henda@ericsson.com
齐旻鹏 Minpen Qi
SA3 Vicechair
CCSA
qiminpeng@chinamobile.com
Rajavelsamy Rajadurai SA3 Vicechair
TTA
rajvel@samsung.com
Mirko Cano Soveri
Secretary
MCC
mirko.cano@etsi.org

## Slide 8: SA3-LI Officials (December 2019)
Alex Leadbeater
SA3-LI Chairman
ETSI
alex.leadbeater@bt.com
Maurizio Iovieno
SA3-LI Vice-Chairman
ETSI
maurizio.iovieno@ericsson.com
Carmine Rizzo
Secretary
MCC
carmine.rizzo@etsi.org

## Slide 9: SA4 Officials (December 2019)
Frédéric Gabin
SA4 Chairman
ETSI
frederic.gabin@ericsson.com
Nikolai Leung
SA4 Vicechair
ATIS
nleung@qti.qualcomm.com
Gilles Teniou
SA4 Vicechair
ETSI
gilles.teniou@orange.com
Paolino Usai
Secretary
MCC
paolo.usai@etsi.org

## Slide 10: SA5 Officials (December 2019)
Thomas Tovinger
SA5 Chairman
ETSI
thomas.tovinger@ericsson.com
邹兰 Zou Lan SA5 Vicechair
CCSA zoulan@huawei.com
Maryse Gardella
SA5 Vicechair
ETSI
maryse.gardella@nokia.com
Mirko Cano Soveri
Secretary
MCC
mirko.cano@etsi.org

## Slide 11: SA6 Officials (December 2019)
సురేష్ చిట్టూరి Suresh Chitturi
SA6 Chairman
TTA
s.chitturi@samsung.com
Alan Soloway
SA6 Vicechair
ATIS
asoloway@qti.qualcomm.com
Jukka Vialen
SA6 Vicechair
ETSI
jukka.vialen@airbus.com
Bernt Mattsson
Secretary
MCC
bernt.mattsson@etsi.org

## Slide 12: General

## Slide 13: TSG SA Dates
Meetings since PCG 43
  TSG SA 86 – Sitges, Spain, 10-13 December 2019
  TSG SA 87-e – e-meeting, 17-20 March 2020
Meetings before PCG 45
  TSG SA 88-e – e-meeting, 30 June – 3 July 2020 (shifted by 2 weeks)
  TSG SA 87 – Madeira, Portugal, 16-19 September 2020

## Slide 14: Self-Evident 3GPP Organization Issues
The following items are seen as self-evident for the organization, (cross-TSG) coordination and general work of 3GPP. From the SA Chairs point of view they are especially necessary to be followed during the current crisis, as they give delegates a reliable base on which 3GPP conducts its work.
  The 3GPP Working Procedures give the basic guidelines on how 3GPP work is conducted and is organized. They need to be followed.
  Article 30 gives clear guidance to the TSGs to take care that plenary meetings are held in the same week. TSG chairs therefore need to undertake well coordinated efforts to make this possible.
  TSG SA has an overall coordination function amongst the TSGs. This doesn’t mean TSG SA (or any other TSG) can take decisions on its own which affect the planning of other TSGs. But it needs to be guaranteed that overall issues, such as e.g. freezing of a 3GPP Release, will be coordinated with and concluded by SA.
These principles can only be changed by a wider discussion within 3GPP, e.g. as it was held when plenaries were moved to a single week.

## Slide 15: For PCG Action: June Plenary
After the COVID-19 crisis started impacting also 3GPP by making face-to-face meetings impossible for an unforeseeable time, it was agreed amongst the TSG chairs that Rel-16 completion needs to be in the main focus for all WGs.
It was also said that SA & CT give RAN more freedom in overall planning, in order to guarantee the IMT-2020 submission deadline to be met by RAN (and 3GPP).
The shifting of RAN plenary from the originally planned week 25 (15-19 June) to week 27 (29 June – 3 July) was one of these steps, where RAN took the related decision and informed the other TSG chairs afterwards.
Due to that SA decided to also shift its meeting to week 27.
Currently TSG RAN still plans to use the full Friday (July 3) for RAN meeting.
Normally Plenaries are conducted in a way that RAN closes on Thursday evening, RAN reports to SA on Friday and SA closes on Friday. This is necessary to guarantee a well-coordinated and stable outcome of 3GPP as a whole.
As no conclusion could be reached amongst TSG chairs on this issue, the SA Chairman kindly asks PCG to make sure that on Friday July 3rd 2020 RAN closes latest by 09:00 UTC, so that normal procedures for 3GPP internal coordination and release freeze can be applied.

## Slide 16: For PCG Action: PCG/OP Dates
Critical issues for overall discussion often come up during plenaries and lead to discussions in the subsequent weeks.
PCG/OP meetings are usually held one or two weeks after March/September plenaries.
This puts the TSG chairs reporting to PCG under pressure and makes it impossible to e.g. bring well-worked out and discussed proposals by the PCG submission deadline for documents for decision.
For example, this report could not be finished before the related discussions on Q2 meetings were finished, which were a direct outcome of March TSGs.
This was already highlighted in the last SA Chairs report to PCG. For this PCG meeting now, the short time between Plenaries and PCG became an even bigger factor.
The SA Chair suggests that PCG/OP meetings are held earliest 4 weeks after 3GPP Plenaries, i.e. PCG/OP meetings should be held in May and November.

## Slide 17: Improvements
The improvements as reported at the last PCG meeting were further implemented during Q4/2019.
Several “Newcomer Sessions” were held during the weeks of November WG meetings and December plenaries. These sessions had good participation and after the initial presentation of general material there were also lively discussions on various topics.
Further improvement plans were planned for March plenary (e.g. further detailing of 3GPP Mentoring, possibly new liaison persons, etc). Due to the COVID-19 crisis those had to be postponed.
For the upcoming months TSG chairs discuss to use webinars for newcomer introduction. This is still in very early discussion and will be worked out over the next weeks.

## Slide 18: 3GPP Release Planning

## Slide 19
Rel-17 RAN Content Def.
100%
Rel-16 Completion
Current Ongoing Releases timelines
83
84
85
86
87
88
89
90
Release 16
2019
2020
Rel-16 Stage 2
Rel-16 Stage 3
09/21
Release 17
Rel-16 Coding
Rel-17 Stage 1 80%
91
92
93
94
2021
TSG#
Release 18
RAN4
Rel-18 RAN Content Def (TBC)
95
2022
Coding
Rel-17 Completion
Rel-17 Stage 3
Rel-17 Stage 2 (SA2)
03/20
12/20
06/20

## Slide 20: Rel-16 and earlier
Rel-16
  SA1 finished (not shown any longer in upcoming slides)
  With few exceptions Studies are not listed, only WIDs are shown
  All WGs are in good shape regarding R16
  Some items might need shifting to R17
  Freeze Date: June 2020 Plenary (Stage 3 and Coding)
  Exception sheets were endorsed on R16 issues by all impacted SA/CT groups
Rel-15: All Work Items are 100 %, besides some IETF drafts.

## Slide 21: Rel-16 SA2 WIDs
Stage 2 of 5G_URLLC | 5G_URLLC | S2 | 100% | SP-181233
Stage 2 of Vertical_LAN | Vertical_LAN | S2 | 100% | SP-181120
Stage 2 of 5G_CIoT | 5G_CIoT | S2 | 98% | SP-181118
Stage 2 of eV2XARC | eV2XARC | S2 | 100% | SP-181121
Stage 2 of 5G_eLCS | 5G_eLCS | S2 | 100% | SP-181119
Stage 2 of RACS | RACS | S2 | 100% | SP-190180
Stage 2 of eNA | eNA | S2 | 100% | SP-181123
Stage 2 of 5WWC | 5WWC | S2 | 100% | SP-181117
Stage 2 of eNS | eNS | S2 | 100% | SP-181232
Stage 2 of PARLOS | PARLOS | S2 | 100% | SP-180738
Stage 2 of ETSUN | ETSUN | S2 | 100% | SP-181116
Stage 2 of ATSSS | ATSSS | S2 | 100% | SP-181124
Single radio voice continuity from 5GS to 3G | 5G_SRVCC | S2 | 100% | SP-180897
Stage 2 of 5G_eSBA | 5G_eSBA | S2 | 100% | SP-181125
Stage 2 of eIMS5G_SBA | eIMS5G_SBA | S2 | 100% | SP-190181
Stage 2 of UDICOM | UDICOM | S2 | 100% | SP-190182
Stage 2 of IABARC | IABARC | S2 | 100% | SP-190627
Stage 2 of xBDT | xBDT | S2 | 100% | SP-180509
Reliable Data Service Serialization Indication | RDSSI | S2 | 100% | SP-190446
S6b Optional for ePDG connected to 5GS | 5GS_S6b_Optional | S2 | 100% | SP-190447
Study on system architecture for next generation real time communication services | FS_NG_RTC | S2 | 0% | SP-180508
Study on Application Awareness Interworking between LTE and NR | FS_AAI_LTE_NR | S2 | 30% | SP-180122
Stopped - Study on supporting Flexible Local Area Data Network | FS_FLADN | S2 | 100% | SP-180506
Study on encrypted traffic detection | FS_ENTRADE | S2 | 70% | SP-181111

## Slide 22: Rel-16 SA3 WIDs
Security of URLLC for 5GS | 5G_URLLC_SEC | S3 | 80%
Security for Vertical_LAN | Vertical_LAN_SEC | S3 | 95%
Security aspects of SEAL | SEAL | S3 | 65%
Security of 5G_CIoT | 5G_CIoT | S3 | 90%
Security Aspects of eV2XARC | eV2XARC | S3 | 70%
Security of 5G_eLCS | 5G_eLCS | S3 | 75%
Security of 5WWC | 5WWC | S3 | 95%
Mission Critical Services Security Enhancements | MCXSec | S3 | 75%
Security aspects of Enhanced Network Slicing | eNS | S3 | 30%
Security Aspects of PARLOS | PARLOS | S3 | 100%
Security aspects of single radio voice continuity from 5GS to UTRAN | 5GS_UTRAN_SEC | S3 | 100%
Security for 5G_eSBA | 5G_eSBA | S3 | 70%
Security aspects of eCAPIF | eCAPIF | S3 | 100%
Security for IAB | IAB | S3 | 65%
User Plane Gateway Function for Inter-PLMN Security | UPGF | S3 | 100%
Security Assurance Specification for 5G | SCAS_5G | S3 | 100%
Lawful Interception Rel-16 | LI16 | S3LI | 60%
Lawful Interception Report Rel-16 | LIR16 | S3LI | 0%
Study on authentication and key management for applications based on 3GPP credential in 5G | FS_AKMA | S3 | 95%
Authentication and key management for applications based on 3GPP credential in 5G | AKMA | S3 | 60%
3GPP profiles for cryptographic algorithms and security protocols | CryptPr | S3 | 100%
(IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446) | TEI16 | S3-IETF | 100%
Study on security aspects of single radio voice continuity from 5G to UTRAN | FS_5G_UTRAN_SEC | S3 | 100%
Study on supporting 256-bit algorithms for 5G | FS_256_Algo | S3 | 100%
Study on storage and transport of 5GC security parameters for ARPF authentication | FS_5GC_SEC_ARPF | S3 | 30%

## Slide 23: Rel-16 SA4 WIDs
Stage 2 of MC_XMB | MC_XMB | S4 | 100% | SP-180665
Enhancements to Framework for Live Uplink Streaming | E_FLUS | S4 | 90% | SP-180285
Coverage and Handoff Enhancements for Multimedia | CHEM | S4 | 100% | SP-180664
Media streaming architecture | 5GMSA | S4 | 100% | SP-180984
Media Handling Extensions for 5G Conversational Services | 5G_MEDIA_MTSI_ext | S4 | 100% | SP-190640
EVS Floating-point Conformance for Non Bit-Exact | EVS_FCNBE | S4 | 100% | SP-180983
Addition of HLG HDR to TV Video Profiles | HLG_HDR | S4 | 100% | SP-180287
Stage 2 of E2E_DELAY | E2E_DELAY | S4 | 100% | SP-180662
Service Interactivity | SerInter | S4 | 100% | SP-170796
Alternative EVS implementation using updated fixed-point basic operators | Alt_FX_EVS | S4 | 100% | SP-180286
Usage of CAPIF for xMB API | CAPIF4xMB | S4 | 100% | SP-180031
RTCP Verification for Real-Time Services | RTCPVer | S4 | 100% | SP-190639
Support of Hybrid DASH/HLS over eMBMS | DAHOE | S4 | 100% | SP-190988
Handsets Featuring Non-Traditional Earpieces | HaNTE | S4 | 5% | SP-190989
Ambient noise test methodology for evaluation of acoustic UE performance | ANTeM | S4 | 0% | SP-200051

## Slide 24: Rel-16 SA5 WIDs
Charging Aspect for 5WWC | 5WWC | S5 | 35% | SP-191188
Overall aspects of 5G_SLICE_ePA | 5G_SLICE_ePA | S5 | 97% | SP-190247
KPI reporting | 5G_SLICE_ePA-KPI | S5 | 100% | SP-190881
Charging aspects of ETSUN | ETSUN | S5 | 100% | SP-190880
Charging Access of ATSSS | ATSSS | S5 | 15% | SP-191187
Volume Based Charging Aspects for VoLTE | VBCLTE | S5 | 73% | SP-180813
Energy efficiency of 5G | EE_5G | S5 | 95% | SP-191193
Management of QoE measurement collection | QOED | S5 | 80% | SP-181069
Network policy management for mobile networks based on NFV scenarios | NETPOL | S5 | 100% | SP-191194
OAM aspects of LTE and WLAN integration | OAM_LTE_WLAN | S5 | 100% | SP-180820
Methodology for 5G management specifications | METHOGY | S5 | 100% | SP-180822
Nchf Online and Offline charging services | OFSBI_CH | S5 | 100% | SP-181066
Charging Enhancement of 5GC interworking with EPC | 5GIEPC_CH | S5 | 100% | SP-181067
NRM enhancements | eNRM | S5 | 92% | SP-190778
Network Exposure Charging in 5G System Architecture | 5GS_Ph1_NEFCH | S5 | 100% | SP-181070
Charging AMF in 5G System Architecture Phase 1 | 5GS_Ph1_AMFCH | S5 | 100% | SP-181071
Discovery of management services in 5G | 5GDMS | S5 | 80% | SP-181072
Trace Management in the context of Services Based Management Architecture | TM_SBMA | S5 | 50% | SP-181073
Network Slice Performance and Analytics Charging in 5G System | 5GS_NSPACH | S5 | 30% | SP-190780
Closed loop SLS Assurance | COSLA | S5 | 55% | SP-190781
Streaming trace reporting | OAM_RTT | S5 | 25% | SP-190782
Self-Organizing Networks (SON) for 5G networks | SON_5G | S5 | 80% | SP-190785
Enhancement of 3GPP management system for multiple tenant environment support | MEMTANE | S5 | 35% | SP-190786
Network Slice Management Charging in 5G System | 5GS_NSMCH | S5 | 5% | SP-190788
Management Aspects of 5G Service-Level Agreement | MA5SLA | S5 | 100% | SP-200185
Integration of ONAP and 3GPP 5G management framework | ONAP3GPP | S5 | 100% | SP-190139
CHF-controlled quota management | CHFCQM | S5 | 50% | SP-191189
Management of MDT in 5G | 5GMDT | S5 | 100% | SP-191190
5G management capabilities | 5GMNC | S5 | 100% | SP-191195
Network policy managementfor 5G mobile networks | NPM | S5 | 0% | SP-191211

## Slide 25: Rel-16

## Slide 26: Rel-16
Stage 2 of SEAL | SEAL | S6 | 100% | SP-181141
Stage 2 of V2XAPP | V2XAPP | S6 | 100% | SP-180898
Stage 2 of enh2MCPTT | enh2MCPTT | S6 | 0% | SP-190068
Stage 2 of eMCData2 | eMCData2 | S6 | 100% | SP-180378
Stage 2 of MBMS APIs for MC Services | MBMSAPI_MCS | S6 | 100% | SP-180380
Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI | S6 | 100% | SP-180680
Application Architecture for MONASTERY2 | MONASTERY2 | S6 | 100% | SP-190064
Stage 2 for eCAPIF | eCAPIF | S6 | 100% | SP-181137

## Slide 27: Rel-17
SA1 finished work as foreseen on stage 1 in Q4/19
SA2 prioritization & timeplan
  Long and controversial discussions over nearly 6 months
  Content and timeplan (“15 month release”) were finally approved in December 2019 SA Plenary
  Coordination with RAN groups on details of content ongoing
General Planning Problem: Old Release eats too much time
Due to COVID-19 crisis R17 timeline was shifted by 3 months

## Slide 28: Rel-17 SA1 WIDs
Stage 1 of ATRAC | ATRAC | S1 | 100% | SP-190931
Stage 1 of CMED | CMED | S1 | 100% | SP-190306
Stage 1 of eCAV | eCAV | S1 | 95% | SP-191043
Complete Gap Analysis for Railways Mobile Communication System | MONASTERYEND | S1 | 100% | SP-190312
Study on Future Railway Mobile Communication System3 | FS_FRMCS3 | S1 | 100% | SP-190321
Stage 1 of AVPROD | AVPROD | S1 | 100% | SP-191041
Stage 1 of EAV | EAV | S1 | 100% | SP-190308
Broadcast / Multicast requirements supporting Mission Critical Services in 5G | 5MBS_eMC | S1 | 100% | SP-190942
Stage 1 of REFEC | REFEC | S1 | 100% | SP-190307
Stage 1 of NCIS | NCIS | S1 | 100% | SP-191039
Stage 1 of MUSIM | MUSIM | S1 | 100% | SP-190309
Multi-Device and multi-identity Enhancements | MuDE | S1 | 100% | SP-190823
Stage 1 of MPS2 | MPS2 | S1 | 100% | SP-190561
Verification-modified Calling Name Display | VMOD_DISPLAY | S1 | 100% | SP-190085
Enhanced Calling Name Service Analytics Interworking | eCNAM_An | S1 | 100% | SP-190940
Enhancement for the 5G Control Plane Steering of Roaming for UE in CONNECTED mode | eCPSOR_CON | S1 | 100% | SP-190941
Study on MINT | FS_MINT | S1 | 100% | SP-190090
Stage 1 of MINT | MINT | S1 | 100% | SP-190938
IMS emergency support for SNPN | IESNPN | S1 | 100% | SP-191038

## Slide 29: Rel-17 SA2 WIDs
Study on enhancement of support for 5G LAN-type service | FS_5GLAN_enh | S2 | 0% | SP-190626
Enhancement to the 5GC LoCation Services-Phase 2 | 5G_eLCS_ph2 | S2 | 0% | SP-200082
Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | FS_ID_UAS_SA2 | S2 | 25% | SP-200097
Study on architecture aspects for using satellite access in 5G | FS_5GSAT_ARCH | S2 | 85% | SP-181253
Integration of satellite components in the 5G architecture | 5GSAT_ARCH | S2 | 0% | SP-191335
Study on enhanced support of Industrial IoT | FS_IIoT | S2 | 40% | SP-200298
Study on V2X services – Phase 2 | FS_eV2XARC_Ph2 | S2 | 0% | SP-190631
Study on Architectural enhancements for 5G multicast-broadcast services | FS_5MBS | S2 | 35% | SP-200092
Study on Stage 2 (System Enablers) for MUSIM | FS_MUSIM | S2 | 45% | SP-200297
Stage 2 of Multimedia Priority Service (MPS) Phase 2 | MPS2 | S2 | 0% | SP-200083
5G System Enhancement for Advanced Interactive Services | 5G_AIS | S2 | 0% | SP-190564
Supporting Flexible Local Area Data Network | FLADN | S2 | 0% | SP-190563
Study on Enhancement of Network Slicing Phase 2 | FS_eNS_Ph2 | S2 | 35% | SP-190931
Study on System enhancement for Proximity based Services in 5GS | FS_5G_ProSe | S2 | 55% | SP-190443
Study on enhancement of support for 5WWC | FS_5WWC_Ph2 | S2 | 0% | SP-190562
Study on enhanced support of Non-Public Networks | FS_eNPN | S2 | 35% | SP-200094
Study on Enablers for Network Automation for 5G - phase 2 | FS_eNA_Ph2 | S2 | 32% | SP-200098
Study on enhancement of 5G UE Policy | FS_eUEPO | S2 | 0% | SP-190449
Study on the Usage of User Identifiers in the 5G System | FS_UUI5 | S2 | 0% | SP-190450
Study on service-based support for SMS in 5GC | FS_SB_SMS | S2 | 0% | SP-190184
Study on enhancement of support for Edge Computing in 5GC | FS_enh_EC | S2 | 40% | SP-200093
Study on UPF enhancement for control and SBA | FS_UPCAS | S2 | 0% | SP-190187
Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | FS_ATSSS_Ph2 | S2 | 15% | SP-200095
Study on Multimedia Priority Service (MPS) Phase 2, Stage 2 | FS_MPS2_St2 | S2 | 0% | SP-190629

## Slide 30: Rel-17 SA3
Integration of GBA into 5GC | GBA_5G | S3 | 0% | SP-190714
Assurance Specification for IMS | SCAS_IMS | S3 | 0% | SP-191128
Security Assurance Specification for 5G | eSCAS_5G | S3 | 0% | SP-200149
Security Assurance Specification for Non-3GPP InterWorking Function (N3IWF) | SCAS_5G_N3IWF | S3 | 0% | SP-200146
Security Assurance Specification for 5G NWDAF | SCAS_5G_NWDAF | S3 | 0% | SP-200147
Security Assurance Specification for Service Communication Proxy (SECOP) | SCAS_5G_SECOP | S3 | 0% | SP-200148
Lawful Interception Rel-17 | LI17 | S3 | 0% | SP-190983
Study on 5G security enhancement against false base stations | FS_5GFBS | S3 | 75% | SP-180690
Study on SECAM and SCAS for 3GPP virtualized network products | FS_VNP_SECAM_SCAS | S3 | 35% | SP-180696
Study on User Plane Integrity Protection | FS_UP_IP_Sec | S3 | 65% | SP-181035
Study on Security Impacts of Virtualisation | FS_SIV | S3 | 45% | SP-181236
Study on Long Term Key Update Process (LTKUP) Detailed solutions | FS_LTKUP_Detail | S3 | 60% | SP-181038
Study on authentication enhancements in 5GS | FS_AUTH_ENH | S3 | 40% | SP-190713

## Slide 31: Rel-17 SA4
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | S4 | 0% | SP-200238
5G Media Streaming stage 3 | 5GMS3 | S4 | 70% | SP-190464
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | S4 | 35% | SP-180985
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | S4 | 15% | SP-190040
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | S4 | 27% | SP-170611
VR QoE metrics | VRQoE | S4 | 100% | SP-190331
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | S4 | 10% | SP-190642
Study on 5G Video Codec Characteristics | FS_5GVideo | S4 | 0% | SP-200052
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | S4 | 0% | SP-200053
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | S4 | 0% | SP-200056

## Slide 32: Rel-17 SA5
Enhancements on EE for 5G networks | EE5GPLUS | S5 | 0% | SP-200188
Management of non-public networks | OAM_NPN | S5 | 0% | SP-200189
Enhancement on Management Aspects of 5G Service-Level Agreement | EMA5SLA | S5 | 0% | SP-200190
Management of MDT enhancement in 5G | e_5GMDT | S5 | 0% | SP-200191
Additional NRM features | adNRM | S5 | 0% | SP-200192
Enhancement of QoE Measurement Collection | eQoE | S5 | 0% | SP-200193
Enhancements of Self-Organizing Networks (SON) for 5G networks | eSON_5G | S5 | 0% | SP-200194
Closed loop SLS Assurance | eCOSLA | S5 | 0% | SP-200196
IMS Charging in 5G System Architecture | 5GSIMSCH | S5 | 30% | SP-190367
Intent driven management service for mobile network | IDMS_MN | S5 | 55% | SP-180899
Study on network slice management enhancement | FS_NSMEN | S5 | 0% | SP-191192
Study on enhancement of Management Data Analytics Service | FS_eMDAS | S5 | 30% | SP-190930
Study on new aspects of EE for 5G networks | FS_EE5G | S5 | 0% | SP-200187
Study on enhancements of edge computing management | FS_eECM | S5 | 0% | SP-200195

## Slide 33: Rel-17 SA6
Study on application layer support for Factories of the Future in 5G network | FS_FFAPP | S6 | 50% | SP-190724
Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 | eMONASTERY2 | S6 | 60% | SP-191104
Study on application layer support for Unmanned Aerial System (UAS) | FS_UASAPP | S6 | 35% | SP-200111
Study on enhancements to application layer support for V2X services | FS_eV2XAPP | S6 | 50% | SP-200110
Study on Mission Critical services support over 5G System | FS_MCOver5GS | S6 | 45% | SP-181136
Mission Critical Data | eMCData3 | S6 | 15% | SP-191106
Study on Mission Critical services over 5G multicast-broadcast system | FS_MC5MBS | S6 | 100% | SP-190929
Study on Application Architecture for enabling Edge Applications | FS_EDGEAPP | S6 | 100% | SP-190065
Architecture for enabling Edge Applications | EDGEAPP | S6 | 20% | SP-200109
MC services support on IOPS mode of operation | MCIOPS | S6 | 50% | SP-190944
Enhanced Mission Critical Push-to-talk architecture phase 3 | enh3MCPTT | S6 | 0% | SP-200108
Study on support of the 5GMSG Service | FS_5GMARCH | S6 | 40% | SP-190559

## Slide 34: Rel-18 (so far only SA1 SIDs)
Study on evolution of IMS multimedia telephony service | FS_MMTELin5G | S1 | 10% | SP-190836
Study on sharing administrative configuration between interconnected MCX Service systems | FS_SACI_MCS | S1 | 5% | SP-190837
Study on Supporting of Railway Smart Station Services | FS_RAILSS | S1 | 5% | SP-190838
Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS | FS_AMMT | S1 | 0% | SP-191040
Guidelines for Extra-territorial 5G Systems | FS_5GET | S1 | 0% | SP-191042

## Slide 35: Acknowledgements
The SA Chair wants to thank the SA Plenary and SA WGs leadership for their excellent work, perfect cooperation, coordination and support.
The TSG CT and TSG RAN chairs for finding common ways forward especially at the start and during the crisis.
The hosts of all SA Plenary and WG meetings either held or cancelled. All hosts of all cancelled meetings helped greatly in managing the new situation.
MCC, especially Maurice Pope, for support and guidance.
All delegates in 3GPP SA and the SA WGs for patience, support, hard work as well as great and stable output.

## Slide 36: Thank You!
Georg Mayer
3GPP SA Chairman
mail: georg.mayer@huawei.com
phone: +43 699 1900 5758