## Slide 1: 3GPP TSG SA Report
Puneet Jain
SA Chair
PCG52_06
Agenda item: 4.1

## Slide 2: TSG SA Dates
Meetings Since PCG#51
    TSG SA#102: FTF meeting, 11-15 Dec 2023, Edinburgh, UK
    TSG SA#103: FTF meeting, 19-22 Mar 2024, Maastricht, Netherlands
Meetings before PCG#53
    3GPP Stage-1 Workshop on IMT2030 Use-cases : FTF adhoc Meeting, 08-10 May 2024, Rotterdam, Netherlands
    TSG SA#104: FTF meeting, 18-21 Jun 2024, Shanghai, China
    TSG SA#105: FTF meeting, 10-13 Sep 2024, Melbourne, Australia

## Slide 3: TSG SA Officials
Mona Mustapha
TSG SA Vicechair
ETSI
mona_mustapha@apple.com
永田 聡 Satoshi Nagata
TSG SA Vicechair
ARIB nagatas@nttdocomo.com
Mark Younge
TSG SA Vicechair
ATIS
Mark.Younge@T-Mobile.com
Maurice Pope
Secretary
MCC
maurice.pope@etsi.org
Puneet Jain
TSG SA Chair
ATIS
puneet.jain@intel.com

## Slide 4
Rel-18 Timeline
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)

## Slide 5: Release 18 Status
Stage 2 has been successfully finalized in all SA Working Groups.
  SA2 and SA6 Stage-2 functional freeze happened in June 2023.
  SA3, SA4, SA5 Stage-2 were frozen in Sep 2023.
Stage 3 has been successfully finalized in all SA Working Groups (some exception) -
  SA5 Stage-3 frozen in Mar 2024.
  SA4 Stage-3 frozen in Mar 2024, except for following exception. Only IVAS_Codec has CT impacts, and it will not impact ASN.1/OpenAPI freeze deadline.
We remain on track to deliver the implementable Rel-18 specifications by June 2024.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 3/3/2024 -> 6/6/2024 | 60% | SP-230977 | 75% | Exception request in SP-240058
960042 | IMS-based AR Conversational Services | IBACS | 3/3/2024 -> 6/6/2024 | 50% | SP-230165 | 70% | Exception request in SP-240057
960045 | Split Rendering Media Service Enabler | SR_MSE | 3/3/2024 -> 6/6/2024 | 60% | SP-220685 | 85% | Exception request in SP-240053
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 3/3/2024 -> 6/6/2024 | 60% | SP-190040 | 70% | Exception request in SP-240054
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 3/3/2024 -> 6/6/2024 | 78% | SP-220608 | 80% | Exception request in SP-240055
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 3/3/2024 -> 6/6/2024 | 25% | SP-231291 | 35% | Exception request in SP-240056
1000018 | 5G Media Streaming Protocols Phase 2 | 5GMS_Pro_Ph2 | 3/3/2024 -> 6/6/2024 | 55% | SP-230976 | 75% | Exception request in SP-240059

## Slide 6
Rel-19 Timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Release 19

## Slide 7: Release 19 Progress
SA1 has achieved 100% completion for the Rel-19 stage-1 normative work.
SA#102 approved 15 SA2 Rel-19 study items. SA#102 also approved 14 normative TEI19 miniWIDs.
SA3 has 18 study items and 9 work items (one already complete) for Rel-19
SA4 has 10 study items and 2 work items approved for Rel-19
SA5 has 17 study items and 4 work items approved for Rel-19
SA6 has 7 study items and 8 work items approved for Rel-19

## Slide 8: SA Rel-19 Content definition Process

## Slide 9: SA Rel-19 Content Planning (Step 1 @ SA#101)

## Slide 10
SA Rel-19 Content Planning (Step 2 @ SA#102)
Tdoc# | Rel-19 study title | Rapporteur(s) / comment
SP-231805 | Study on Architecture enhancement for XRM Ph2 | Nokia, Meta
SP-231391 | Study on 5GS Enhancement for Energy Efficiency and Energy Saving as Service Criteria | Samsung, Lenovo
SP-231196 | Study on system architecture for next generation real time communication services Ph 2 | China Mobile
SP-231199 | Study on Integration of satellite components in the 5G architecture Phase III | THALES, CATT
SP-231672 | Study on MPS for IMS Messaging and SMS services* | Peraton Labs
SP-231795 | Study on UPF enhancement for Exposure and SBA Phase 2 | ZTE, Vodafone
SP-231796 | Study on Enhancement of support for Edge Computing in 5G Core network phase 3 | Intel
SP-231797 | Study on architecture aspects of 5G Femto | NTT DOCOMO
SP-231798 | Study on System Enhancement for Proximity-based Services in 5GS - Phase 3 | AT&T, KPN
SP-231799 | Study on Architecture Enhancements for Vehicle Mounted Relays (VMR) Phase 2 | Qualcomm, Sony
SP-231800 | Study on Core Network Enhanced Support for AI/ML | vivo, MediaTek
SP-231801 | Study on Phase 3 for UAS, UAV and UAM | LG Electronics, Ericsson
SP-231802 | Study on Multi-Access (Dual 3GPP access + ATSSS Enhancements) | Apple, China Telecom
SP-231803 | Study on Architecture support of Ambient power-enabled Internet of Things | Huawei, OPPO Only Study. Check in Dec 2024
SP-231804 | Study on the Enhancement of Usage of User Identifiers in the 5G System | InterDigital, Inc.
SP-231754 | Study on Architecture Enhancement to support Integrated Sensing and Communication | No study. Check in Sep 2024
SP-231052 | Network Sharing Enhancements SA WG2 Status | Possible TEI19
SP-231503 | New WID on Architecture support of Roaming Value Added Services | Possible TEI19
SP-231674 | Study on Improvements of network controlled Network Slicing Selection | Possible TEI19
SP-231757 | Study on enhancement of Timing Resiliency, TSC&URLLC and LAN | Noted
SP-231701 | Study on Enhanced Traffic Management | Noted
SP-231682 | New WID on Study on Sidelink time synchronisation | Noted
After lengthy online and offline discussions, the SA Chair prepared a proposal (in SP-231760) on Rel-19 content, reflecting a balance of Rel-19 priority from the Operators and Vendors side, which was endorsed.
Based on SP-231760, SA#102 approved a package of 15 study items (green in the table)
  AI/ML study: whether SA2 can start work on Work Tasks 1.1, 1.2, and 1.3 will be discussed at SA#105 (Sep. 2024) based on the outcome of the related work in the involved RAN WGs
  Ambient IoT: check in TSG#106 (Dec’24) for further Ambient IoT work taking into account RAN Ambient IoT progress
The Sensing study (cyan in the table) was only endorsed. The work on this study is postponed until Sep 2024 when it will be determined if/when to start the study
Three study item proposals (yellow in the table) will be considered as a small technical enhancement (TEI19)
The remaining items (red in the table) were not considered as part of Rel-19 content.

## Slide 11: SA1 Release 19 SIDs/WIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on Energy Efficiency as service criteria | FS_EnergyServ | 100% | SP-230235 | 22.882
Stage 1 of Energy Efficiency as Service Criteria | EnergyServ | 100% | SP-230520 | 22.261
Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 100% | SP-220439 | 22.875; 22.876
AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | 100% | SP-230514 | 22.261
Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 100% | SP-220085 | 22.84
Stage 1 of Ambient power-enabled Internet of Things | AmbientIoT | 95% | SP-231403 | 22.261
Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 100% | SP-220679 | 
Stage 1 of Satellite access Phase 3 | 5GSAT_Ph3 | 100% | SP-230516 | 22.261
Study on Localized Mobile Metaverse Services | FS_Metaverse | 100% | SP-220353 | 22.856
Stage 1 of Localized Mobile Metaverse Services | Metaverse | 100% | SP-230509 | new 22.156, 22.261 ; 22.156
Supporting UE Mobility for XR Services | XRMobility | 100% | SP-230233 | 22.261
Study on Integrated Sensing and Communication | FS_Sensing | 100% | SP-220717 | 22.837
Stage 1 of Integrated Sensing and Communication | Sensing | 100% | SP-230750 | 22.137
Study on (Stage 1 of) UAV Phase 3 | FS_UAV_Ph3 | 100% | SP-220954 | 
Stage 1 of Uncrewed Aerial System Phase 3 | UAS_Ph3 | 100% | SP-230518 | 
Study on Network Sharing Aspects | FS_NetShare | 100% | SP-220087 | 22.851
Indirect Network Sharing | NetShare | 100% | SP-230511 | 22.261
Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 100% | SP-220445 | 22.841
Upper layer traffic steering and switching over dual 3GPP access | DualSteer | 95% | SP-231412 | 22.261
Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds | 100% | SP-231037 | 22.261
Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 100% | SP-220437 | 22.989
FRMCS Phase 5 | FRMCS_Ph5 | 100% | SP-230512 | 22.280; 22.179; 22.289; 22.261
Study on Supporting of Railway Smart Station Services | FS_RAILSS | 100% | SP-190838 | New ; 22.890
Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 100% | SP-220447 | 22.916
Study on roaming value added services | FS_RVAS | 100% | SP-220442 | 22.877
Roaming Value-Added Services | RVAS | 100% | SP-230231 | 22.261
Study on Interconnect of SNPN | FS_ISN | 65% | SP-230236 | 22.848
Interconnect of SNPN | ISN | 100% | SP-240194 | 
Edge Computing for Industrial Scenarios | EDGINDUS | 100% | SP-230229 | 22.104
PS Data Off for IMS Data Channel Service | IMSDCDataOff | 100% | SP-230227 | 22.011
Multi-path relay | MultiRelay | 100% | SP-220943 | 22.261
UE-to-UE multi-hop relay | UEMHopRelay | 100% | SP-230521 | 22.261; 22.280
Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | 100% | SP-220941 | 22.261
MPS for Messaging services | MPS4msg | 100% | SP-220939 | 22.153
Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 100% | SP-220992 | 22.261
Measurement Data Collection | MeasureData | 100% | SP-221263 | 22.261
Local traffic routing for multi-access UE | LTR_MA | 100% | SP-231035 | 22.261
Non-Public Network (NPN) security considerations | SecNPN | 100% | SP-230523 | 22.261

## Slide 12: SA2 Release 19 SIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on Energy Efficiency and Energy Saving | FS_EnergySys | 55% | SP-231391 | 23.700-66
Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 25% | SP-231800 | 23.700-84
Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | 25% | SP-231803 | 23.700-13
Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 55% | SP-231199 | 23.700-29
Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2 | 45% | SP-231671 | 23.700-70
Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 50% | SP-231801 | 23.700-59
Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 30% | SP-231802 | 23.700-54
Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 50% | SP-231796 | 23.700-49
Study on System aspects of 5G NR Femto | FS_5G_Femto | 40% | SP-231797 | 23.700-45
Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | 45% | SP-231798 | 23.700-03
Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 40% | SP-231799 | 23.700-06
Study on User Identities and Authentication Architecture | FS_UIA_ARC | 35% | SP-231804 | 23.700-32
Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 45% | SP-231795 | 23.700-54
Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 45% | SP-231196 | 23.700-77
Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 70% | SP-231197 | 23.700-75

## Slide 13: SA2 Release 19 normative TEI19 miniWIDs
Name | Acronym | %Complete | Hyperlink
(Stage 2 of) Indirect Network Sharing | TEI19_NetShare | 0% | SP-240117
Architecture support of roaming value-added services | TEI19_RVAS | 0% | SP-240119
ProSe support in NPN | TEI19_ProSe_NPN | 0% | SP-240122
5GS enhancement on On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 0% | SP-240116
Minimize the Number of Policy Associations | TEI19_MINPA | 0% | SP-240118
Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 0% | SP-240120
Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 0% | SP-240121
Multiple Location Procedure for Emergency LCS Routing | TEI19_MLR4RTR | 0% | SP-240123
Roaming traffic offloading via session breakout in HPLMN | TEI19_HSBO | 0% | SP-240124
Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 0% | SP-240125
5GS enhancement on QoS monitoring enhancement | TEI19_QME | 0% | SP-240126
Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 0% | SP-240127
Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 0% | SP-240128
NF discovery and selection by target PLMN | TEI19_TPlmnNfSel | 0% | SP-240129

## Slide 14: SA3 Release 19 SIDs/WIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on security aspects of energy saving in 5G | FS_Energy_Sec | 0% | SP-240512 | 33.766
Study on security aspects of Core Network Enhanced Support for AIML | FS_AIML_CN_SEC | 0% | SP-240509 | 33.784
Study on Security Aspect of Ambient IoT Services in 5G | FS_Ambient_IoT_Sec | 0% | SP-240506 | 33.713
Study on Security Aspects of 5G Satellite Access Phase 3 | FS_5GSAT_Ph3_SEC | 10% | SP-240232 | 33.700-29
Study on security aspects of 5G Mobile Metaverse services | FS_Metaverse_Sec | 0% | SP-240508 | 33.721
Study on security for PLMN hosting a NPN | PLMNNPN_SEC | 25% | SP-231786 | 33.757
UAS security enhancements | FS_UAS_Ph3_Sec | 0% | SP-240504 | 33.759
Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) | FS_MASSS_Sec | 0% | SP-240511 | 33.754
Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | FS_EDGE_Ph3 | 0% | SP-240510 | 33.749
Study on security aspects of 5G NR Femto Document for: Approval | FS_5G_Femto_Sec | 0% | SP-240505 | 33.745
Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3_SEC | 0% | SP-240513 | 33.743
Study on security aspects of User Identities and Authentication | FS_UIA_Sec | 0% | SP-240507 | 33.700-32
Security aspects for MSGin5G Service Phase 3 | 5GMARCH_SEC_Ph3 | 0% | SP-240516 | 33.501
Security Assurance Specification for maintenance of 5G features | SCAS_5G_Maint | 0% | SP-240515 | 
5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) | SCAS_5G_UDR | 10% | SP-230864 | 33.926 ; 33.530
5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) | SCAS_5G_SMSF | 40% | SP-231158 | 33.529
Addition of 256-bit security Algorithms | 256_Algo | 100% | SP-240476 | 35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240
Addition of Milenage-256 algorithm | Milenage_256 | 5% | SP-231792 | 35.237; 35.236; 35.235; 35.234
Study on enabling a cryptographic algorithm transition to 256-bits | FS_CAT256 | 10% | SP-231788 | 33.700-41
Study on enablers for Zero Trust Security | FS_eZTS | 20% | SP-231784 | 33.794
Mission critical security enhancements for release 19 | MCXSec4 | 10% | SP-231783 | 33.18
Study on the security support for the Next Generation Real Time Communication services phase 2 | FS_NG_RTC_SEC_Ph2 | 17% | SP-240233 | 33.79
Study of ACME for Automated Certificate Management in SBA | FS_ACME_SBA | 15% | SP-231787 | 33.776
3GPP profiles for cryptographic algorithms and security protocols | CryptoSP | 20% | SP-231793 | 33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501
Study on mitigations against bidding down attacks | FS_MiBiDA | 20% | SP-231789 | 33.701
Security for mobility over non-3GPP access to avoid full primary authentication | FS_Non3GPPMob_Sec | 25% | SP-231791 | 33.702

## Slide 15: SA4 Release 19 SIDs/WIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 0% | SP-240481 | 
Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 0% | SP-240060 | 
Split rendering over IMS | SR_IMS | 0% | SP-240492 | 26.264
Study on Media Messaging | FS_MeMe | 0% | SP-240477 | 
Study on Advanced Media Delivery | FS_AMD | 0% | SP-240478 | 26.802; 26.804
Study of 5G Real-time Transport Protocol Configurations, Phase 2 | FS_5G_RTP_Ph2 | 0% | SP-240482 | 
Study on Beyond 2D Video | FS_Beyond2D | 0% | SP-240479 | 
Study on Audio Codec APIs | FS_ACAPI | 0% |  | 
Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 70% | SP-221330 | 26.933
Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 60% | SP-220328 | 26.927; 26.847
Study on Film Grain Synthesis | FS_FGS | 30% | SP-230539 | 26.955
Study of Avatars in Real-Time Communication Services | FS_AVATAR | 30% | SP-230544 | 26.813

## Slide 16: SA5 Release 19 SIDs/WIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on energy efficiency and energy saving aspects of 5G networks and services | FS_Energy_OAM_Ph3 | 10% | SP-231723 | 28.866
Study on AI/ML management - phase 2 | FS_AIML_MGT_Ph2 | 0% | SP-231780 | 
Study on intent driven management services for mobile network phase 3 | FS_IDMS_MN_Ph3 | 0% | SP-231737 | 
Study on closed control loop management | FS_CCLM | 0% | SP-231735 | 
Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 0% | SP-231781 | 
Study on Service Based Management Architecture enhancement phase 3 | FS_SBMA_Ph3 | 0% | SP-231725 | 
Study on data management regarding subscriptions and reporting | FS_Data_SREP | 0% | SP-231732 | 
Study on Management Aspects of NTN Phase 2 | FS_NTN_OAM_Ph2 | 0% | SP-231733 | 
Study on management of IAB nodes | FS_NR_mobile_IAB_OAM | 0% | SP-231729 | 
Study on Management of Network Sharing Phase3 | FS_NetShare_OAM_Ph3 | 0% | SP-231731 | 
Study on Enablers for Security Monitoring | FS_SECM | 0% | SP-231736 | 28.87
Study on management aspects of RedCap feature | FS_NR_RedCap_OAM | 0% | SP-231734 | 
Study on management aspects of Network Digital Twin | FS_NDT | 0% | SP-231428 | 28.915
Study on Management Data Analytics (MDA) Phase 3 | FS_eMDAS_Ph3 | 0% | SP-231726 | 
Study on Enhancement of Management Aspects related to NWDAF Phase 2 | FS_NWDAF_OAM_Ph2 | 0% | SP-231724 | 
Study on Management of planned configurations | FS_PlanM | 0% | SP-231721 | 28.872
Study on Enhanced OAM for management exposure to external consumers | FS_MExpo | 0% | SP-231728 | 
Data management phase 2 | MADCOL_Ph2 | 0% | SP-231746 | 28.622; 28.623
5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 0% | SP-231747 | 28.552; 32.425; 28.554; 28.532; 28.550; 28.abc
5G Advanced NRM features phase 3 | AdNRM_Ph3 | 0% | SP-231745 | 28.540; 28.541; 28.622; 28.623
Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 0% | SP-231748 | 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623

## Slide 17: SA6 Release 19 SIDs/WIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on application layer support for AI/ML services | FS_AIMLAPP | 55% | SP-231182 | 23.700-82
Study on application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | 25% | SP-240296 | 23.700-01
Study on application enablement for Localized Mobile Metaverse Services | FS_Metaverse_App | 30% | SP-231806 | 23.700-21
Study on Application enabler for XR Services | FS_XRApp | 20% | SP-2315739 | 23.700-23
Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | 40% | SP-230991 | 23.255; 23.434
Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP | 35% | SP-230779 | 23.222 ; 23.700-92
Study on enhanced application layer support for location services | FS_eLSAPP | 40% | SP-240295 | 23.434 ; 23.700-72
Sharing of administrative configuration between interconnected MC service systems | MCShAC | 90% | SP-230692 | 23.280; 23.379; 23.281; 23.282
5GMSG Service phase 3 | 5GMARCH_Ph3 | 35% | SP-230781 | 
Railways specific Enhancements to Mission Critical Services | enh4FRMCS | 40% | SP-230780 | 23.280; 23.281; 23.282; 23.379; 23.283; 23.289
Enhanced Mission Critical Architecture | enhMC | 40% | SP-230988 | 23.280; 23.379; 23.281; 23.282; 23.283; 23.289
SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | 35% | SP-230989 | 
Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | 35% | SP-231160 | 23.558
Guidelines for CAPIF Usage | CAPIF_EXT | 55% | SP-231161 | 23.946
Study on CAPIF Phase 3 | FS_CAPIF_Ph3 | 20% | SP-231741 | 23.700-22

## Slide 18
Rel-20 Timeline (5G-Advanced)
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
Rel-20 - 5GA part
2025
2026
2027
5GA ASN.1 & Open APIs
St.2 SID def. TBD
St.3 SID def. TBD
Note: All starting dates are indicative

## Slide 19
Release 20 SA1 work planning
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
TSG#100
June
2023
Now
SA1#102
SA1#103
SA1#104
SA1#105
SA1#106
SA1#107
SA1#108
SA1#109
SA1#110
SA1#111
SA1#112
Rel-20 part 1 (≈50%)
SIDs presentation
SIDs agreement
Rel -20 SA1 Stage 1
Rel-20 part 2 (≈50%)
presentations
SID(s) agreement
Grey boxes = SA 1 Content definition process
Release 20
Stage-1
100%
80%
Rel-20: SA1 work is split in two parts:
  Rel-20 part 1: 5G-Advanced
    24 new ideas presented by the companies
    3 SIDs agreed
    FS_FRMCS_Ph6
    FS_EnergyServ_Ph2
    FS_5GSAT_Ph4
  Rel-20 part 2: 6G
    Discussions will start in the next quarter
IMT2030 usecases Workshop

## Slide 20: SA1 Release 20 SIDs
Name | Acronym | %Complete | Hyperlink | Impacted TSs and TRs
Study on satellite access - Phase 4 | FS_5GSAT_Ph4 | 0% | SP-240495 | 
Study on FRMCS Phase 6 | FS_FRMCS_Ph6 | 0% | SP-240199 | 22.989
Study on Energy Efficiency as Service Criteria Phase 2 | FS_EnergyServ_Ph2 | 0% | SP-240494 | 

## Slide 21: 6G Workplan & Timeline – Summary
Background
ITU-R has agreed on the timeline for IMT-2030
In Dec '23, 3GPP agreed on some first key aspects of the 6G timeline (SP-231693).
3GPP is expected to discuss further details of the 6G timeline in future meetings
Key agreements from SA #102/#103
May '24 – 3GPP Stage-1 workshop on IMT-2030 use cases
March ‘25 – 3GPP wide workshop to kick off Rel-20 technical studies in SA and RAN
June '25 - Approval of SA2 studies on 6G
6G Studies in Release 20 and 6G normative work in Release 21
Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
In Mar ‘24, 3GPP agreed on some additional consideration for 6G timeline (SP-240458).

## Slide 22
Stage-1 workshop on IMT2030 use cases: May 8th – 10th(Wednesday – Friday), 2024
First 3GPP TSG-wide 6G workshop: March 10th – 11th(Monday – Tuesday), 2025
Details TBD (e.g., whether to have a joint or separate workshop across TSGs, how to handle contributions, etc.)
TSG#107 plenary meetings are to be scheduled subsequently in the same week
Studies for 6G in 3GPP: from Release 20
See Next Slide for more details
Normative work for 6G in 3GPP: from Release 21
Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
Rel-21 timeline is to be decided no later than June 2026. However, ASN.1/OpenAPI freeze date is no earlier than March 2029
6G timeline – Planning (1/2)

## Slide 23
Rel-20 (5G-Advanced)
  For 5G-Advanced: 18-month. Assuming no delay of Rel-19
    Stage-1 freeze : Jun 2025
    Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
    Stage-3 freeze : Mar 2027
    ASN.1/OpenAPI freeze: June 2027
Rel-20 (6G Study Item)
  6G SI Approval
    SA1 SI approval: TSG#105 (Sept 2024)
    SA2 SI approval: TSG#108 (Jun 2025)
    Other SA WG (SA3, SA4, SA5, SA6) SI approval: TBD at future TSG meeting
    SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates for 5G-Advanced
  6G SI completion (this may use time from Rel-21)
    SA1 6G SI completion: Mar 2026
    SA2 6G SI completion: Dec 2026 or Mar 2027 (To be confirmed at future TSG meeting)
6G timeline – Planning (2/2)

## Slide 24
Illustration of 3GPP SA Rel-20 Timeline
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
Workshop 6G TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA SI+ WI 80%
Stage 3 5GA SI + WI
Stage 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Stage-1 Workshop IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
SA2 6G Study(ies)
Stage 3 6G Study(ies)
5G-Advanced
6G Study
2025
2026
2027
SA2 6G SID def.
SA3/4/5/6 SID def. TBD
ASN.1 & Open APIs
or
TBD
Stage 3 SID def.
Stage 2 SID def.

## Slide 25: 3GPP Stage 1 Workshop on IMT 2030 use cases
3GPP Stage 1 Workshop on IMT 2030 use cases
(8 - 10 May; Rotterdam, Netherlands)
(For details see - SP-240456)
The objective of the workshop is to bring 3GPP closer to the ongoing initiatives of various global/regional research organizations and MRPs regarding 6G use cases.
This collaborative effort is particularly crucial as SA1 embarks on defining the requirements and use cases for 6G in Rel-20.
Presentations from 3GPP MRPs (e.g. GSMA, 5GAA, …), regional research alliances (Next G Alliance, China IMT 2030 Promotion Group, Japan B5GPC, Kora 6G Forum, Bharat 6G Alliance), and global organizations/institutions (e.g. NGMN, ITU-R).
Conference-style event with a restricted agenda

## Slide 26: Draft Agenda: 3GPP Stage 1 Workshop on IMT 2030 use cases
Note: the order of presentations within the Verticals and within the Research Alliances is subject to change
Time | Wednesday May 8th Opening, Operators, Verticals | Thursday May 9th Research Alliances | Friday May 10th ITU, 3GPP, Closing
1st session | 08.45-09.15: Registration 09.15-09.30: Opening ---------------------------------------------- Operators 09.30-10.00: GSMA 10.00-10.30: NGMN | 09:00-09.45: Japan (B5GPC) 09.45-10.30: South Korea (6G Forum) | 09.00-09.30: ITU-R 09.30-10.00: 3GPP 10.00-10.30: Panel#4: “ITU & 3GPP synergies for 6G”
Morning break | Morning break (10.30-11.00) | Morning break (10.30-11.00) | Morning break (10.30-11.00)
2nd session | 11.00-11.40: Panel#1: “6G Drivers for Operators” ---------------------------------------------- Verticals 11.45-12.10: Automotive (5GAA) 12.10-12.35: Industry (5G-ACIA) | 11.00-11.45: China (IMT2030 Promotion Group) 11.45-12.30: India (Bharat 6G Alliance) | 11.00-11.40: Summary read-out of the Workshop 11.40-12.00: Next steps 12.00-12.30: Closing
Lunch break | Complimentary lunch (12.35-14.00) | Complimentary lunch (12.30-14.00) | Workshop ends 12.30 latest
3rd session | 14.00-14.25: Multimedia (5GMAG) 14.25-14.50: Satellite (GSOA) 14.50-15.15: Public Safety (TCCA) 15.15-15.40: WBA | 14.00-14.45: America (ATIS Next G Alliance) 14.45-15.30: Europe (6G-SNS) | 
Afternoon break | Afternoon break (15.40-16.10) | Afternoon break (15.30-16.00) | 
4th session | 16.10-17.00: Panel#2 : “6G Drivers for Verticals” | 16.00-17.00: Panel#3: “Building a Global 6G View” | 

## Slide 27: Cross TSG and SA Internal Coordination
A joint SA, RAN and CT session was held during TSGs#102 and TSG#103 on the consideration for 6G workplan and timeline.
TSG Chairs have regular co-ordination calls and at least one coordination call before every TSG meeting.
SA Officials (SA Chair, SA Vice Chairs, SA MCC, SA WG Chairs) had continuous coordination, mostly by mail.

## Slide 28: For PCG Information
Besides the issues already mentioned in earlier slides there are no other issues for PCG information

## Slide 29: For PCG Action
Clarification on SWG (See PCG52_22)

## Slide 30: Acknowledgements
The 3GPP SA Chair wants to thank
The SA Plenary and SA WGs officials for their exceptional work, flawless cooperation, precise coordination, and unwavering support.
The TSG CT and TSG RAN chairs for their outstanding coordination and cooperation.
MCC for their provision of highly reliable e-meeting facilities, as well as their valuable support and guidance.
The organizations responsible for hosting the meetings for their remarkable flexibility and excellent communication.
All delegates in 3GPP SA and the SA WGs for their support, dedicated efforts, and the consistently high-quality results they have delivered.

## Slide 31: Thank You!
Puneet Jain
3GPP TSG SA Chair
puneet.jain@intel.com
www.3gpp.org