## Slide 1: Additional Considerations for 6G Timeline
Source: TSG Chairs
3GPP TSG#103 Joint Session
March 20th, 2024
RP-240823
AI 6.1

## Slide 2: Background: As Endorsed in TSG#102
First TSG-wide 6G workshop is expected to be in March 2025
  Right before the planned Rel-19 RAN1 functional freeze (June 2025). Detailed information for the workshop is TBD
Organization of a 3GPP Stage 1 workshop on IMT-2030 use cases is being discussed separately
  Refer to SP-231619
Studies for 6G in 3GPP are expected to start from Release 20
  Requirements studies:
    SA1 SID is expected to be approved in Sept’2024.
    RAN plenary SID (e.g., radio requirements and KPIs) is expected to be approved TBD (to be decided at RAN#103)
  Technology studies:
    SA2 SID is expected to be approved in June’2025. Other SA-WG SIDs (e.g., Security, etc.) are expected to be approved TBD
    RAN-WG SIDs are expected to be approved in June’2025
    CT-WG SIDs are expected to be approved in March’2026 (depends on SA2 SI work)
IMT-2030 submission and normative work for 6G in 3GPP are expected to start from Release 21
  Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
  Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
Target TSG#103 (March’2024) for the remaining detailed 6G timeline decisions
High-Level Considerations for 6G Timeline

## Slide 3: Proposal: Additional Details for TSG-Wide 6G Workshop
Note: TSG#102 endorsed the TSG-wide 6G workshop to be in March’2025
Proposal:
  TSG-Wide 6G Workshop (WS): Monday – Tuesday of the TSG#107 meeting week
    Details TBD (e.g., whether to have a joint or separate workshop across TSGs, how to handle contributions, etc.)
  TSG#107 plenary meetings are to be scheduled subsequently in the same week
    RAN/SA: Wed (0900) – Friday (1800)
    CT: Wed (0900) – Thursday (1200)

## Slide 4: Proposal: Additional Details for 3GPP RAN Plenary Study for 6G
RAN
  RAN plenary work is split into an ITU focused SI (study item) and General RAN SI
    IMT-2030 discussion is expected in RAN from 09/24 to 12/24
    RP SI Rel-20 focusing on ITU– IMT-2030: approval 12/24 until 06/25
    RP SI Rel-20 focusing on 6G General: approval 03/25 (after WS), until 06/26

## Slide 5: Proposal: Additional Details for Rel-20 1/2
Proposal: in Rel-20
  For 5G-Advanced: 18-month. Assuming no delay of Rel-19
    Stage-1 freeze : Jun 2025
    Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
    Stage-3 freeze : Mar 2027
    ASN.1/OpenAPI freeze: June 2027

## Slide 6: Proposal: Additional Details for Rel-20 2/2
Proposal (Cont’d): in Rel-20
  For 6G SI
    SA WGs:
      SA1 SI approval: TSG#105(Sept2024) – endorsed at TSG#102
      SA2 SI approval: TSG#108(Jun2025) – endorsed at TSG#102
      Other SA WG (SA3, SA4, SA5, SA6) SI approval: TBD at future TSG meeting
      SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates for 5G-Advanced
      6G SI (this may use time from Rel-21)
        SA1 6G SI completion: Mar 2026
        SA2 6G SI completion: Dec. 2026 or Mar 2027 (To be confirmed at future TSG meeting)
    RAN WGs: 21 months
      RAN1 starts in 3Q/25 until 1Q/27; RAN2/3/4 start in 4Q/25 until 2Q/27
    CT WGs: at least 9 months
      CT WG 6G SI will start 9 months after approval of SA2 SI.

## Slide 7: Proposal: Additional Details for Rel-21
Proposal:
  Rel-21 timeline is to be decided no later than June 2026
    However, ASN.1/OpenAPI freeze date is no earlier than March 2029