## Intro
Legend
Study item phase
Stage 1 drafting
Stage 2 drafting
Stage 3 drafting
Intent is to maintain this document in its current form until TSGs #35, when the content should be included in the 3GPP Workplan maintained by MCC.
The format is based on and includes the TSG RAN LTE Workplan.
History
PA1 | 2006-09-25 | Draft version for review by SAE Rapporteur
PA2 | 2006-09-27 | Presented to SA#33
PA3 | 2006-09-28 | Revised after SA#33 drafting session, noted at SA#33 for review by WGs.
PA4 | 2006-09-28 | Revised after SA#33, to align colour coding with RAN LTE workplan
Contact person: jan.ellsberger@ericsson.com

## SA1
SA1 Workplan
| Timeline | 2006 |  |  | 2007
|  | 2006-09-25 | 2006-10-23 | 2006-12-04 | 2006-02-05 | 2006-03-12 | 2007-04-23 | 2007-06-04 | 2007-06-25 | 2006-09-17
| SA | #33 |  | #34 |  | #35 |  | #36 |  | #37
| SA1 |  | #34 |  | #35 |  | #36 |  | #37
| Location | US | Paris | Budapest | Asia | EU | EU | Korea | US | Riga
| SA milestones |  |  | Stage 1 complete
SA1 Mainly | Finalize SAE Stage 1
Service requirements for "Single Radio VCC"

## SA2
SA2 Workplan
|  | Timeline | 2006 |  |  |  | 2007
|  |  | 2006-09-25 | 2006-10-23 | 2006-11-14 | 2006-12-04 | 2007-01-15 | 2006-02-12 | 2006-03-12 | 2007-03-26 | 2007-04-27 | 2007-06-04 | 2007-06-25 | 2006-08-27 | 2006-09-17
|  | SA | #33 |  |  | #34 |  |  | #35 |  |  | #36 |  |  | #37
|  | SA2 |  | #55 | SAE ad-hoc |  | #56 | Ad-hoc |  | Ad-hoc | #57 |  | #58 | #59
|  | Location | US | Busan | Montreal | Budapest | EU | TBD | EU | TBD | TBD | Korea | TBD | TBD | Riga
|  | SA milestones |  |  |  | WI created for LTE related parts, TR 23.882 closed, agreements on 'open' Rel-8 interfaces. |  |  | WI created for non-3GPP access related parts |  |  | Stage 2 specifications for LTE related parts approved. |  |  | Stage 2 specifications for non-3GPP access related parts approved.
SA2 mainly |  | Single Radio Voice Call Continuity
Mobility between 3GPP and non-3GPP accesses (architecture and protocols)
Define required reference points to connect non-3GPP accesses to EPC.
Mobility, detailed architecture
IP connectivity with multiple PDNs
Optimal routeing
Local breakout
Complete design of roaming scenarios
Ensure that system design is efficient for mix of devices and usage patterns (eg to include machines that send/receive data very infrequently, as well as high end devices)
Migration from pre-Release 8 systems to SAE.
Architectural impacts of Evolved HSPA
Identify IMS impacts (if any)
Document in annex in TR 23.882 any known requirements that are not addressed by SAE (may be addressed by other Wis) or only partially met SAE.
| SA2 | Overall architecture
| SA2 | High level architecture (identification of open reference points and functions over open reference points)
| R2, R3 | Detailed functional allocation MME/UPE
| SA2 | Detailed architecture including functional allocation to remaining elements.
Supported by other working groups | R2, R3 | Addressing/Identification requirements and solutions
E-UTRAN Identities
| R2, R3 | Intra E-UTRAN mobility in LTE_IDLE
| R2, R3 | Intra E-UTRAN mobility in LTE_Active
MME/UPE relocation
| R2,R3 | QoS concept and architecture
Parameters on S1
One or multiple PCRFs
Definition of non-operator controlled services
Specific LTE QoS issues
| S4, R2, R3, GERAN | Inter 3GPP mobility
Signalling free mobility etc
Active mode mobility, roaming & non-roaming architecture, seamless service performance
Means to minimize data loss at EUTRA - UTRA/GSM HO (bicasting or not)
| R2, R3 | MBMS Architecture
| R2, R3 | Roaming restrictions
| S3, R3, CT1 | Authentication and authorization
| R2, R3, CT1, CT4 | Location services
Location for emergency calls
|  | Drafting Stage 2 specifications |  |  | Draft WIDs | Approve WIDs
Note on C8: eraells: LTE related?
Note on C18: eraells: R2, R3
Note on C21: eraells: LTE related
Note on C22: eraells: R2, R3, CTx
Note on C23: eraells: R2, R3
Note on C26: eraells: SA2 assumption is that RAN will handle this.
Note on C28: eraells: Completed
Note on C35: eraells: SA2 status unclear.

## SA3
SA3 Workplan
| Timeline | 2006 |  |  |  | 2007
|  | 2006-09-25 | 2006-10-17 | 2006-10-31 | 2006-12-04 | 2007-02-06 | 2006-02-13 | 2006-03-12 | 2007-04-25 | 2007-05-15 | 2007-06-04 | 2006-09-17
| SA | #33 |  |  | #34 |  |  | #35 |  |  | #36 | #37
| SA3 |  | #23-LI | #45 |  | #24-LI | #46 |  | #25-LI | #47
| Location | US | Vienna | Dulles | Budapest | US | Beijing | EU | Riga | TBD | Korea | Riga
SA milestones
Mainly SA3 | Security and integrity mechanisms
Authentication mechanisms
Impacts on Network Domain Security
Legal Intercept
UICC requirements
Interworking with legacy UICC

## SA4
SA4 Workplan
| Timeline | 2006 |  |  | 2007
|  | 2006-09-25 | 2006-11-06 | 2006-12-04 | 2007-01-29 | 2006-03-12 | 2007-04-23 | 2007-06-04 | 2007-06-25 | 2006-09-03 | 2006-09-17
| SA | #33 |  | #34 |  | #35 |  | #36 |  |  | #37
| SA4 |  | #41 |  | #42 |  | #43 |  | #44 | #45
| Location | US | Athens | Budapest | TBD | EU | TBD | Korea | TBD | TBD | Riga
SA milestones
Mainly SA4 | Deriving QoS attributes for applications
Mainly SA4 | Performance characterization of applications over SAE/LTE bearers.

## SA5
SA5 Workplan
| Timeline | 2006 |  |  | 2007
|  | 2006-09-25 | 2006-10-30 | 2006-12-04 | 2007-01-22 | 2006-03-12 | 2007-04-02 | 2007-05-07 | 2007-06-04 | 2006-06-25 | 2006-08-27 | 2006-09-17
| SA | #33 |  | #34 |  | #35 |  |  | #36 |  |  | #37
| SA5 |  | #50 |  | #51 |  | #52 | #53 |  | #54 | #55
| Location | US | Fairfax | Budapest | EU | EU | Xian | TBD | Korea | TBD | TBD | Riga
SA milestones
SA5 mainly | O&M Specifications for LTE/SAE
Charging and inter-operator accounting aspects

## RAN1
RAN1 Workplan
|  | Timeline | 2006 |  |  |  |  | 2007
|  |  | 2006-08-28 | 2006-09-19 | 9-Oct | 2006-11-06 | 2006-11-28 | Jan | 2006-02-12 | 6-Mar | Apr | 7-May | 29-May | Jun | 2006-08-20 | 2006-09-11
|  | RAN |  | #33 |  |  | #34 |  |  | #35 |  |  | #36 |  |  | #37
|  | WG1 | #46 |  | #46bis | #47 |  | #47bis | #48 |  | #48bis | #49 |  | #49bis | #50
|  | WG2 | #54 |  | #55 | #56 |  | #56bis | #57 |  | #57bis | #58 |  | #58bis | #59
|  | WG3 | #53 |  | #53bis | #54 |  |  | #55 |  | #55bis | #56 |  |  | #57
|  | WG4 | #40 |  |  | #41 |  | #41bis | #42 |  |  | #43 |  |  | #44
|  | Location | Tallinn | US | Seoul | Riga | Budapest |  | US | Europe |  | Japan | Korea |  | Europe | Riga
|  | RAN milestones |  | WI created | [5 empty] | Stage 2 complete | [5 empty] | Stage 3 complete
RAN1 mainly |  | Numerology The basic parameters such as sub-frame length, TTI length, sub-carrier space, number of sub-carriers etc.
Channel encoder principle Bacis channel coding scheme such as turbo code, LDPC etc.
Channel coding detail Interleaving, rate matching, etc
DL/UL refence signal Reference signal mapping, sequence etc. for unicast in UL/DL and muticast in DL
Modulation Modulation scheme for UL/DL and scramble code for cell or eNB
Physical layer model Physical channels definition, Transport channel mapping onto physical channel
UL Timing Control
UL/DL power control
DL MIMO
UL MIMO
DL/UL control signalling
MIMO related DL/UL control signalling
RACH preamble
Supported by other WG(s) | R2 | RACH L1 procedure L1 procedure of overall RACH procedure to be discussed with RAN2 such as timing, etc
| R2 | Scheduling Dynamic and persistent scheduling
| R2 | BCH,PCH
| R4 | Cell Search SCH structure, cell search algorithm
| R2 | Link Adaptation
| R4 | DL PAPR reduction
| R2, R3 | MBMS aspects related to the physical layer Requirements for network synchronisation, etc
| R2, R4 | UE and eNode B measurement definition
| R2, R4 | UE Capabilities Minimum UE capability and UE category, Layer1 aspects
Supported by RAN2 and RAN3 particualrly for delay, handover interruption requirements |  | Initial performance verification to ensure that system performance is inline with that expected on study item closure.
Performance evaluation to capture final system performance.
Drafting RAN1 responsible parts of the Stage 2 specification
|  | Drafting RAN1 stage 3 Specifications | Fix RAN1 Spec. structure

## RAN2
RAN2 Workplan
|  | Timeline | 2006 |  |  |  |  | 2007
|  |  | 2006-08-28 | 2006-09-19 | 9-Oct | 2006-11-06 | 2006-11-28 | Jan | 2006-02-12 | 6-Mar | Apr | 7-May | 29-May | Jun | 2006-08-20 | 2006-09-11
|  | RAN |  | #33 |  |  | #34 |  |  | #35 |  |  | #36 |  |  | #37
|  | WG1 | #46 |  | #46bis | #47 |  | #47bis | #48 |  | #48bis | #49 |  | #49bis | #50
|  | WG2 | #54 |  | #55 | #56 |  | #56bis | #57 |  | #57bis | #58 |  | #58bis | #59
|  | WG3 | #53 |  | #53bis | #54 |  |  | #55 |  | #55bis | #56 |  |  | #57
|  | WG4 | #40 |  |  | #41 |  | #41bis | #42 |  |  | #43 |  |  | #44
|  | Location | Tallinn | US | Seoul | Riga | Budapest |  | US | Europe |  | Japan | Korea |  | Europe | Riga
|  | RAN milestones |  | WI created | [5 empty] | Stage 2 complete | [5 empty] | Stage 3 complete
RAN2 mainly |  | Logical Channels
Protocol Architecture
Overview of the Services and Functions
Transport of NAS messages
RLC/MAC Functions Segmentation, etc
HARQ - ARQ and their interaction
RRC Functions Mobility, BCCH scheduling, connection, etc
Supported by other WG(s) | R1 | Number of TrCH and transport blocks
| R1 | RACH procedure
| R1 | HARQ Sync/async, etc
| R1 | DRX
| R1, R4 | UE Capabilities L2 aspects
| R1 | Measurements for mobility
| R1 | Scheduling Scheduler operation, signalling of scheduling decisions, measurements to support scheduler operation
| R1 | MIMO Layer 2 aspects
| R3, S2 | E-UTRAN Identities
| R3, S2 | Intra E-UTRAN mobility in LTE_IDLE Radio protocol aspects
| R3, S2 | Intra E-UTRAN mobility in LTE_Active Radio protocol aspects
| R3, S2 | QoS concept & architecture Including logical channe and Radio bearer
| R3, S2 | Inter 3GPP mobility Radio protocol aspects
| R3 | NW Self Configuration Radio protocol aspects
| R3, S2 | MBMS concept & protocol
| R3, S2 | Roaming Restrictions Radio protocol aspects
| CT1 | PDCP Functions ROHC, reordering, etc
| R3, S3 | Security Radio protocol aspects
Drafting RAN2 responsible parts of the Stage 2 specification
|  | Drafting RAN2 stage 3 Specifications |  |  |  | Fix RAN2 Spec. structure

## RAN3
RAN3 Workplan
|  | Timeline | 2006 |  |  |  |  | 2007
|  |  | 2006-08-28 | 2006-09-19 | 9-Oct | 2006-11-06 | 2006-11-28 | Jan | 2006-02-12 | 6-Mar | Apr | 7-May | 29-May | Jun | 2006-08-20 | 2006-09-11
|  | RAN |  | #33 |  |  | #34 |  |  | #35 |  |  | #36 |  |  | #37
|  | WG1 | #46 |  | #46bis | #47 |  | #47bis | #48 |  | #48bis | #49 |  | #49bis | #50
|  | WG2 | #54 |  | #55 | #56 |  | #56bis | #57 |  | #57bis | #58 |  | #58bis | #59
|  | WG3 | #53 |  | #53bis | #54 |  |  | #55 |  | #55bis | #56 |  |  | #57
|  | WG4 | #40 |  |  | #41 |  | #41bis | #42 |  |  | #43 |  |  | #44
|  | Location | Tallinn | US | Seoul | Riga | Budapest |  | US | Europe |  | Japan | Korea |  | Europe | Riga
|  | RAN milestones |  | WI created | [5 empty] | Stage 2 complete | [5 empty] | Stage 3 complete
RAN3 mainly |  | C/U-plane of S1/X2
RRM Functions
eNodeB logical model
NW Sharing
RRM Architecture
NW Synchronisation
eNB Logical O&M
Supported by other WG(s) | R2, S2 | MBMS eUTRAN architecture MBMS Functional allocation
| R2, S2 | QoS concept S1 interface aspects
| R2, S2 | Intra E-UTRAN mobility in LTE_IDLE S1 and X2 interface aspects
| R2, S2 | Intra E-UTRAN mobility in LTE_Active S1 and X2 interface aspects
| R2, S2 | Inter 3GPP mobility S1 interface aspects
| R2, S3 | Security S1 and X2 interface aspects
| R2 | NW Self Configuration S1 & X2 interface and O&M aspects
| R2, S2 | Roaming Restrictions S1 interface aspects
Drafting RAN3 responsible parts of the Stage 2 specification
|  | Drafting RAN3 stage 3 Specifications |  |  |  | Fix RAN3 spec. structure

## RAN4
RAN4 Workplan
|  | Timeline | 2006 |  |  |  |  | 2007
|  |  | 2006-08-28 | 2006-09-19 | 9-Oct | 2006-11-06 | 2006-11-28 | Jan | 2006-02-12 | 6-Mar | Apr | 7-May | 29-May | Jun | 2006-08-20 | 2006-09-11
|  | RAN |  | #33 |  |  | #34 |  |  | #35 |  |  | #36 |  |  | #37
|  | WG1 | #46 |  | #46bis | #47 |  | #47bis | #48 |  | #48bis | #49 |  | #49bis | #50
|  | WG2 | #54 |  | #55 | #56 |  | #56bis | #57 |  | #57bis | #58 |  | #58bis | #59
|  | WG3 | #53 |  | #53bis | #54 |  |  | #55 |  | #55bis | #56 |  |  | #57
|  | WG4 | #40 |  |  | #41 |  | #41bis | #42 |  |  | #43 |  |  | #44
|  | Location | Tallinn | US | Seoul | Riga | Budapest |  | US | Europe |  | Japan | Korea |  | Europe | Riga
|  | RAN milestones |  | WI created | [5 empty] | Stage 2 complete | [5 empty] | Stage 3 complete
RAN4 mainly |  | UL co-existence
Deployment Scenarios
UE and BS RF requirements concepts
Framework for UE and BS performance requirements
Supported by other WG(s) | R1 | SI numerology verification
| R1 | RRM requirement concepts
Drafting RAN4 responsible parts of the Stage 2 specification
|  | Drafting RAN4 stage 3 Specifications | Fix RAN4 spec. structure

## CT1
CT1 Workplan
|  | Timeline | 2006 |  |  |  | 2007
|  |  | 2006-09-20 | 2006-10-30 | 2006-10-31 | 2006-11-29 | 2006-02-05 | 2006-02-13 | 2006-03-07 | 2007-03-26 | 2006-05-07 | 2006-05-08 | 2007-06-04 | 2007-08-20 | 2006-09-17
|  | CT | #33 |  |  | #34 |  |  | #35 |  |  |  | #36 |  | #37
|  | CT1 |  | #44 | - |  | #45 | - |  | #46 | #47 | - |  | #48
|  | CT3 |  | #42 | - |  | #43 | - |  | - | #44 | - |  | #45
|  | CT4 |  | #33 | - |  | #34 | - |  | - | #35 | - |  | #36
|  | CT6 |  | - | #41 |  | - | #42 |  | - | - | #43 |  | -
|  | Location | US | Virginia | Virginia | Budapest | EU | Sophia Antipolis | EU | TBD | Beijing |  | Korea | Vienna | Riga
CT milestones
CT1 Mainly |  | UE to EPC signalling specification for both 3GPP and non-3GPP accesses
NAS functions in Idle mode
DM Objects for LTE UEs
Equivalent to 24.007?
| CT1, R2, R3, GERAN | MME - SGSN "signalling free protocol"
| R2 | PDCP specification

## CT3
CT3 Workplan
| Timeline | 2006 |  |  |  | 2007
|  | 2006-09-20 | 2006-10-30 | 2006-10-31 | 2006-11-29 | 2006-02-05 | 2006-02-13 | 2006-03-07 | 2007-03-26 | 2006-05-07 | 2006-05-08 | 2007-06-04 | 2007-08-20 | 2006-09-17
| CT | #33 |  |  | #34 |  |  | #35 |  |  |  | #36 |  | #37
| CT1 |  | #44 | - |  | #45 | - |  | #46 | #47 | - |  | #48
| CT3 |  | #42 | - |  | #43 | - |  | - | #44 | - |  | #45
| CT4 |  | #33 | - |  | #34 | - |  | - | #35 | - |  | #36
| CT6 |  | - | #41 |  | - | #42 |  | - | - | #43 |  | -
| Location | US | Virginia | Virginia | Budapest | EU | Sophia Antipolis | EU | TBD | Beijing |  | Korea | Vienna | Riga
CT milestones
Mainly CT3 | Upgrades to QoS mechanisms
PCC impacts
Multiple PDN impacts (interworking)
Interfaces to "E-PDG"

## CT4
CT4 Workplan
|  | Timeline | 2006 |  |  |  | 2007
|  |  | 2006-09-20 | 2006-10-30 | 2006-10-31 | 2006-11-29 | 2006-02-05 | 2006-02-13 | 2006-03-07 | 2007-03-26 | 2006-05-07 | 2006-05-08 | 2007-06-04 | 2007-08-20 | 2006-09-17
|  | CT | #33 |  |  | #34 |  |  | #35 |  |  |  | #36 |  | #37
|  | CT1 |  | #44 | - |  | #45 | - |  | #46 | #47 | - |  | #48
|  | CT3 |  | #42 | - |  | #43 | - |  | - | #44 | - |  | #45
|  | CT4 |  | #33 | - |  | #34 | - |  | - | #35 | - |  | #36
|  | CT6 |  | - | #41 |  | - | #42 |  | - | - | #43 |  | -
|  | Location | US | Virginia | Virginia | Budapest | EU | Sophia Antipolis | EU | TBD | Beijing |  | Korea | Vienna | Riga
CT milestones
CT4 mainly |  | EPC - HSS interface
User and Control plane protocols
EPC
EPC - GPRS
Identities
| CT1, R2, R3, GERAN | MME - SGSN "signalling free protocol"

## CT6
CT6 Workplan
| Timeline | 2006 |  |  |  | 2007
|  | 2006-09-20 | 2006-10-30 | 2006-10-31 | 2006-11-29 | 2006-02-05 | 2006-02-13 | 2006-03-07 | 2007-03-26 | 2006-05-07 | 2006-05-08 | 2007-06-04 | 2007-08-20 | 2006-09-17
| CT | #33 |  |  | #34 |  |  | #35 |  |  |  | #36 |  | #37
| CT1 |  | #44 | - |  | #45 | - |  | #46 | #47 | - |  | #48
| CT3 |  | #42 | - |  | #43 | - |  | - | #44 | - |  | #45
| CT4 |  | #33 | - |  | #34 | - |  | - | #35 | - |  | #36
| CT6 |  | - | #41 |  | - | #42 |  | - | - | #43 |  | -
| Location | US | Virginia | Virginia | Budapest | EU | Sophia Antipolis | EU | TBD | Beijing |  | Korea | Vienna | Riga
CT milestones
CT6 mainly | USIM impacts

## GERAN
GERAN Workplan
|  | Timeline | 2006 |  | 2007
|  |  | 2006-10-16 | 2006-11-13 | 2006-02-12 | 2006-05-14 | 2007-08-27 | 2007-11-12
|  | GERAN | - | #32 | #33 | #34 | #35 | #36
|  | G1 | - | #32 | #33 | #34 | #35 | #36
|  | G2 | #31bis | #32 | #33 | #34 | #35 | #36
|  | G3 | - | #32 | #33 | #34 | #35 | #36
|  | Location | Torino | Sophia Antipolis | Seoul | Shenzen | Dublin | US
GERAN milestones
Joint with other working groups | R2, R3 | GERAN to LTE cell reselection
| R2, R3 | Signalling specifications for handover to/from LTE and cell change
| R5 | Test specifications for GERAN-LTE interworking