## Summary
3GPP TSG-CT WG3 Meeting #109e C3-202021 E-Meeting, 20th – 24th April 2020 Source: Qualcomm Incorporated Title: 5G CIoT work and contribution plan for CT3 Agenda item: 16.14 - Cellular IoT support and evolution for the 5G System [5G_CIoT] Document for: Information
Summary: This document updates C3-194028 - the previous work plan document - that was submitted in CT3#106. The agreements from the last meeting, if any, have been listed for each key issue (tab). The updates are reflected in red fonts and have been made in the following tabs: a) Support NB-API for EPC-5GC IWK: cells D3/E3/F3 b) Monitoring: see rows 3, 4, 5 c) Supp. for Expected UE Behaviour: cell E3 Moving forward: 1) comments/questions on this document is kindly requested 2) if possible, it will be much appreciated if the CR cover sheets can indicate which Key Issue the CR is related to, and which row/aspect (as identified in the tabs) the CR is trying to address. This will make tracking of work progress much easier

## CP CIoT Optimization (NIDD)
WORK PLAN (Key Issue 1)
Expected changes |  |  | Impacted Specifications | Status | Notes
Procedures for Non-IP data delivery: 1) The NEF triggers NIDD configuration towards the AF (NEF ID, AF ID, GPSI as UE ID) 2) The AF triggers NIDD configuration towards the NEF (GPSI or External Group Identifier, AF ID, NIDD Duration, T8 Destination Address, MTC Provider Information) |  |  | 29.522 | Completed | See 4.25.3 of TS 23.502 For 2), the CR references TS 29.122 as follows: "the procedures for NIDD configuration triggered by the AF and NIDD delivery are described in subclause 4.4.5 of 3GPP TS 29.122" |  | C3-192427, CR0051
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
103 | C3-192427, CR0051 (replaces C3-191384 from C3#102) | NIDD configuration and delivery in 5G | Ericsson, Huawei | 29.522 | 1) Editor's note: New TS number is not ready yet [Qualcomm, September 27, 2019: resolved in C3-193381]
105 | C3-193381, CR0063 | Resolving EN in NIDD | Ericsson | 29.522 | None | Resolves the existing Editor's note "New TS number is not ready yet" that was introduced by C3-192427
108-e | C3-201204 | Correct TS number for NEF southbound NIDD service | Ericsson | 29.522
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes
Correct TS number for NEF southbound NIDD service 29522 |  |  | Ericsson | 29.522 | For MO NIDD, the interaction between the SMF and the NEF shall use Nnef_SMContext service as specified in 3GPP TS 29.541; and for MT NIDD, the interaction between the SMF and the NEF shall use Nsmf_NIDD service as specified in 3GPP TS 29.542.

## Overload Control for Small Data
WORK PLAN (Key Issue 7)
Expected changes |  |  | Impacted Specifications | Status | Notes
Description of support for: 1) Serving PLMN rate control (applies to data over CP) a) The UE shall limit the rate at which it generates uplink NAS Data PDUs to comply with the Serving PLMN policy b) The UPF/NEF shall limit the rate at which it generates downlink Data PDUs. In the UPF/NEF the indicated rate control applies only on the PDU Session where it was received, and therefore the UPF/NEF shall limit the rate of its downlink Data PDUs to comply with the rate that is indicated for the PDU Session c) The (V-)SMF may enforce these limits per PDU Session by discarding or delaying packets that exceed these limits. The (V-)SMF starts the Serving PLMN Rate Control when the first NAS Data PDU is received 2) Small data rate control (applies to both data over CP and over UP): the (H-)SMF can send a Small Data Uplink Rate Control command to the UE using the PCO information element. The (H-)SMF informs the UPF or NEF of any Small Data Rate Control that shall be enforced |  |  | 29.561 (5G System; Interworking between 5G Network and external Data Networks) | Complete | For 1), see 5.31.14.2 (Serving PLMN Rate Control) in TS 23.501 For 2) see 5.31.14.3 (Small Data Rate Control) in TS 23.501 |  | S2-1906050 | S2-1906051
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
102 | C3-191186, CR0005 | Rate control for 5G CIoT | Ericsson | 29.561 (5G System; Interworking between 5G Network and external Data Networks) | 1) Editor’s Note: Above procedure needs to confirm with CT4.
105 | C3-193380, CR0017 | Correct small data rate control status | Ericsson | 29.561 | None
108-e | C3-201207 | Resolve editor note for PLMN rate control | Ericsson | 29.561
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes

## Management of Enhanced Coverage
WORK PLAN (Key Issue 6)
Expected changes |  |  | Impacted Specifications | Status | Notes
Enhanced Coverage Restriction Control via NEF (to query, enable/disable): 1) Query The AF may may query the status of Enhanced Coverage Restriction by sending Nnef_ECRestriction_Get Request. The NEF sends the Nnef_ECRestriction_Get Response. 2) Enable/disable The AF may enable or disable Enhanced Coverage Restriction by sending the Nnef_ECRestriction_Update Request. The NEF sends the Nnef_ECRestriction_Update Response Both the service operations from the AF require GPSI and AF Identifier as required input |  |  | 29.522 | Completed | See 4.27 Procedures for Enhanced Coverage Restriction Control via NEF in TS 23.502 (The service is new in 5GS but exists in EPS)
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
105 | C3-193323, CR0079 | Nnef_ECRestriction service | Huawei | 29.522 | None
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes

## Reliable Data Service
WORK PLAN (Key Issue 8)
Expected changes |  |  | Impacted Specifications | Status | Notes
During the NIDD configuration procedure: The AF sends a Nnef_NIDDConfiguration_Create Request message (GPSI or External Group Identifier, AF ID, NIDD Duration, T8 Destination Address, MTC Provider Information) to the NEF. If Reliable Data Service Configuration is present, the Reliable Data Service Configuration may include the mobile terminated and mobile originated serialization format(s) that are supported by the AF for each port number. |  |  | 29.522 | Completed | See 4.25.3 NIDD Configuration in TS 23.502 THIS IS COVERED AS PART OF NIDD procedures in the CP CIoT Optimization tab
During NIDD procedure 1) for MO data delivery, when the NEF receives the unstructured data and finds an NEF PDU Session context and the related T8 Destination Address, then it sends the unstructured data to the AF that is identified by the T8 Destination address in a Nnef_NIDD_DeliveryNotify Request (GPSI, unstructured data, Reliable Data Service Configuration). 2) for MT data delivery, if AF has already activated the NIDD service for a given UE, and has downlink unstructured data to send to the UE, the AF sends a Nnef_NIDD_Delivery Request (GPSI, TLTRI, unstructured data, Reliable Data Service Configuration) message to the NEF. |  |  | 29.522 | Completed | See 4.25.4 (NEF Anchored Mobile Originated Data Transport procedure) and 4.25.5 (NEF Anchored Mobile Terminated Data Transport procedure) in TS 23.502 THIS IS COVERED AS PART OF NIDD procedures in the CP CIoT Optimization tab
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
NO AGREED CONTRIBUTIONS SO FAR
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes

## Supp. Param. Conf. API via NEF
WORK PLAN (Key Issue 10)
Expected changes |  |  | Impacted Specifications | Status | Notes
Enhancement to the Nnef_ParameterProvision service to contain contain at least one of the Network configuration parameters, and Validity Time. (Network configuration parameters include: Maximum Response Time, Maximum Latency, Suggested Number of Downlink Packets.) |  |  | 29.522, 29.122 | Complete
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
NO AGREED CONTRIBUTIONS SO FAR
102 | C3-191377, CR0050 | Network parameter provisioning support | Ericsson | 29.522 | 1) Editor's note: It is FFS whether the two existing 4G APIs (CP provisioning and network parameter Provisioning) can be enhanced to satisfy 5G provisioning service without introducing new 5G provisioning API. | Resolved
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes

## Support NB-API for EPC-5GC IWK
WORK PLAN (Key Issue 9)
Expected changes |  |  | Impacted Specifications | Status | Notes
Subscription and Notification of availability or expected level of support of a service API (Nnef_APISupportCapability service to support awareness on availability or expected level of a service) 1) Subscription: the AF subscribes to Nnef_APISupportCapability service for a UE or a group of UEs by sending Nnef_APISupportCapability_Subscribe Request (UE ID or External Group ID, Report Type, callback URI, Duration of Reporting) message. 2) Notification: According to the CN type received and local detected, the SCEF+NEF node determines the availability or expected level of support of common north-bound APIs for the indicated UE or the indicated group of UEs. SCEF+NEF inform AF of such API information by sending Nnef_APISupportCapability_Notify (API Indication) message. 3) Unsubscribing: The AF unsubscribes to Nnef_APISupportCapability service for a UE or a group of UEs by sending APISupportCapability_Unsubscribe Request (UE ID or External Group ID) message |  |  | 29.522, 29.122 | Complete (see C4-194338 & C4-194339) | See 4.11.6 (Interworking for common network exposure) and 5.2.6.12 (Nnef_APISupportCapability service) in TS 23.502. This is a new API compared to EPS. In the last discussion of the work plan, it was not clear whether this will be a new API or an existing monitoring API in EPS can be used. Any views on this? (this question was from the previous work plan C3-193019)
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
106 | C3-194338, CR0202 | Nnef_APISupportCapability Service | Huawei | 29.122 | None
106 | C3-194339, CR0086 | Nnef_APISupportCapability Service | Huawei | 29.522 | None
107 | C3-195275, CR0216 | Support API capability change based on API filter | Ericsson | 29.122 | None
108-e | C3-201203 | Clarify empty array for API capability change | Ericsson | 29.122
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes

## c-Monitoring
WORK PLAN (Key Issue 11)
Expected changes |  |  | Impacted Specifications | Status | Notes
To support Availability after DDN Failure for cases of multiple AFs: 1) Enhancement of Nnef_EventExposure service to include identifying the source of the downlink IP or Ethernet traffic 2) Configuring the event at the SMF: UDM sends the Nsmf_EventExposure_Subscribe Request message with the event type "Availability after DDN Failure" to each SMF. See notes for futher description. 3) Reporting an event by the SMF: the SMF sends the event report, by means of Nsmf_EventExposure_Notify message (including NEF reference ID), to the AMF indicated as notification endpoint. See notes for further description 4) NEF notifies the AF: the NEF sends Nnef_EventExposure_Notify message with the "Availability after DDN Failure" event to AF. See notes for further description |  |  | 29.522, 29.122, 29.508 (5G System; Session Management Event Exposure Service) | Complete | See agreed CRs S2-1910636 in incoming LS response S2-1910641. For 2): "If the UDM is able to derive the applicable DNN/S-NSSAI from the traffic descriptor via configured information, the UDM may send Nsmf_EventExposure_Subscribe Request messages only to SMFs with PDU sessions with that DNN/S-NSSAI for such UEs. The UDM includes the traffic descriptor if it was received. As the UDM itself is not the Event Receiving NF, the UDM shall provide the AMF's notification endpoint information, i.e., Notification Target Address (+ Notification Correlation Id) reveived in step 4. A separate subscription is used for each UE. Each notification endpoint is associated with the event type "Availability after DDN Failure". In case of home-routed PDU session or PDU session with I-SMF, the UDM sends the Nsmf_EventExposure_Subscribe Request message(s) to (H-)SMF(s) identified as described above, and the (H-)SMF(s) further send Nsmf_EventExposure_Subscribe Request message(s) to the related V-SMF(s) or I-SMF(s)" For 3): "The SMF is informed that the UE is unreachable via a Namf_Communication_N1N2MessageTransfer service operation. The SMF then decides to discard downlink packets received from the UPF. By comparing those discarded downlink packets received from the UPF with the Traffic Descriptor(s) received in the event subscription(s), the SMF determines whether any traffic from an AF having a event subscription occurred and if so, the SMF sends the event report, by means of Nsmf_EventExposure_Notify message (including NEF reference ID), to the AMF indicated as notification endpoint.If the UE is not reachable after the AMF received the notification from the SMF, the AMF shall set a Notify-on-available-after-DDN-failure flag corresponding to the NEF Reference ID" For 4): occurs after the AMF notifies the NEF as described in S2-1910636 "[Conditional] The AMF detects the UE is reachable and sends the event report(s) based on the Notify-on-available-after-DDN-failure flag, by means of Namf_EventExposure_Notify message(s), only to the NEF(s) indicated as notification endpoint(s) identified via the corresponding subscription in step 3. In this way, only the AF(s) for which DL traffic transmission failed are notified." |  | S2-1910636 | S2-1910641
To support Downlink Data Delivery Status event: 1) The AF sends Nnef_EventExposure_Subscribe Request to NEF requesting notification for event “Downlink data delivery status” with traffic descriptor (e.g. the source of the downlink IP or Ethernet traffic) for a UE or group of UEs. See notes for further description of the Downlink Data Delivery Status event. 2) UDM sends the Nsmf_EventExposure_Subscribe Request message to each SMF. See notes for further description. 3) The SMF sends the Nsmf_EventExposure_Subscribe Response message to the UDM 4) The NEF sends the Nsmf_EventExposure_Subscribe response to the AF 5) The SMF sends the Nsmf_EventExposure_Notify with Downlink Delivery Status event message to NEF. See notes for further description. 6) The NEF sends Nnef_EventExposure_Notify with Downlink Delivery Status event message to AF |  |  | 29.522, 29.122, 29.508 (5G System; Session Management Event Exposure Service) | Complete | See agreed CR S2-1910637 in the incomding LS S2-1910641 For 1: The details of the Downlink Data Delivery Status event is as follows: a) First DL Packet(s) in extended buffering event: This event is triggered when the first new downlink data packet is buffered with extended buffering matching the traffic descriptor. in notifications about this Downlink data delivery status, the SMF provides the Extended Buffering time as determined in clause 4.2.3.3 of TS 23.502 b) First DL Packet discarded: This event occurs when the first packet matching the traffic descriptor is discarded because the Extended Buffering time, as determined by the SMF, expires or the amount of downlink data to be buffered is exceeded c) First DL Packet transmitted: This event occurs when the first packet matching the traffic descriptor is transmitted after previous buffering or discarding of corresponding packet(s) because the UE of the PDU Session becomes ACTIVE, and buffered data can be delivered to UE according to clause 4.2.3.3 of TS 23.502 For 2: "The UDM sends the Nsmf_EventExposure_Subscribe Request message to each SMF where at least one UE identified in step 2 has a PDU session established; if the UDM is able to derive the applicable DNN and S-NSSAI from the traffic descriptor via configured information, the UDM may send Nsmf_EventExposure_Subscribe Request messages only to SMFs with PDU sessions with that DNN and S-NSSAI for such UEs and includes Identifier of the UE or Internal-Group-Id, traffic descriptor, monitoring event and the notification endpoint of NEF received in step 2 are included in the message. If the UDM becomes aware that such a UE has a PDU session established with the DNN and S-NSSAI corresponding to the traffic descriptor at a later time than when receiving step 2, the UDM then executes step 3. In case of home-routed PDU session or PDU session with I-SMF, the UDM sends the Nsmf_EventExposure_Subscribe Request message to each H-SMF or SMF, and the H-SMF or SMF further sends Nsmf_EventExposure_Subscribe Request message to each related V-SMF or I-SMF. Steps 7-8 are performed by V-SMF or I-SMF" For 5: This occurs after the following step as described in S2-1910637 "SMF detects a change in Downlink Data Delivery Status event as described in clause 4.2.3. The SMF becomes aware that Downlink Packet(s) require extended buffering via a Namf_Communication_N1N2MessageTransfer service operation with the AMF. If the the SMF decides to discard packets, the "Downlink Packet(s) discarded event" is detected. The SMF detects that previously buffered packets can be transmitted by the fact that the related PDU session becomes ACTIVE" |  | S2-1910637 | S2-1910641
NEF Event Exposure functionality in roaming cases (I-NEF) Note: this (TS 29.591) is not applicable to roaming cases only. Please see actual spec for scope. |  |  | TS 29.591 (5G System (5GS); Network exposure function southbound services; Stage 3) | Incomplete | See related LS out in C3-194445 The TS skeletion was agreed in C3-194392 in meeting CT3#106 under A/I "16.5 - CT aspects on Enablers for Network Automation for 5G"
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
102 | C3-191399, CR0156 | Notification of Downlink data delivery status and availability after DDN failure notification for multiple Afs | Huawei | 29.122 | 1) Editor´s note: Stage 2 clarifications are required whether multiple traffic filters and ethernet traffic descriptors are permissable. The Encoding of the DddTrafficDescriptor is also FFS (reuse of TS 29.523 data types EthernetFlowInfo, IpFlowInfo?).
102 | C3-191400, CR0044 | Application function notification of downlink data delivery status | Huawei | 29.522 | 1) Editor's note: It is FFS whether the update of the subscription is supported. 2) Editor's note: references of TS 29.523 need to be updated later. 3) Editor´s note: If multiple traffic filters are permissable in the subscription, Flow IDs may be required. | At least the following would require an update as the agreement in S2-1908551 now has the NEF subscribe via the UDM: "the NEF shall subscribe the events to the appropriate PCF(s) within the network by invoking the Npcf_EventExposure_Subscribe service operation as defined in subclause 4.2.2.2 of 3GPP TS 29.523 [x]" Also, references to TS 29.523 should be replaced accordinlgy (with TS 29.503) (Qualcomm, September 27, 2019: this has been corrected by document C3-193383) | S2-1908551
102 | C3-191401, CR0045 | Availability after DDN failure notification for multiple Afs | Huawei | 29.522 | 1) Editor´s note: If multiple traffic filters are permissable in the subscription, Flow IDs may be required.
102 | C3-191406, CR0039 | Downlink data delivery status event | Nokia, Nokia Shanghai-Bell | 29.508 | 1) Editor´s note: Implicit subscription of the PCF for the "downlink data delivery status" event is ffs to solve issues related to the interactions with traffic descriptors for that event with traffic descriptors supplied by PCC. 2) Editor´s note: Stage 2 clarifications are required whether traffic descriptors are also applicable for other delivery stati and if so how the SMF then handles the traffic descriptors and interacts with the UPF. If traffic filters need to be installed in the UPF, stage 2 clarifications on interactions with traffic filters derived from PCC rules are required. 3) Editor´s note: If multiple traffic filters are permissible in the subscription, Flow IDs may be required. 4) Editor´s note: Stage 2 clarifications are required whether multiple traffic filters and ethernet traffic descriptors are permissible. The Encoding of the dddTraDes" attribute is also ffs (reuse of TS 29.523 data types EthernetFlowInfo, IpFlowInfo?). [Qualcomm, September 27, 2019: EN #4 partly resolved in C3-193588] 5) Editor´s note: This data type is ffs. Reuse of TS 29.523 data types EthernetFlowInfo, IpFlowInfo could be an alternative. [Qualcomm, September 27, 2019: EN #5 resolved in C3-193588]
102 | C3-191407 | LS on Nsmf_EventExposure and Nnef_EventExposure service handling of the "Downlink data delivery status" and " Availability after DDN Failure" events | CT3 | N/A (sent to SA2)
105 | C3-193588, CR0050 | Notification of downlink data delivery status | Huawei | 29.508 | None | 1) Partly resolves an Editor's note by deleting "The Encoding of the dddTraDes" attribute is also ffs (reuse of TS 29.523 data types EthernetFlowInfo, IpFlowInfo?)" (see EN #4 in C3-191406 above) 2) Deletes the existing Editor's note "This data type is ffs. Reuse of TS 29.523 data types EthernetFlowInfo, IpFlowInfo could be an alternative" (see EN # 5 in C3-191406)
105 | C3-193383, CR0075 | Notification of downlink data delivery status | Huawei | 29.522 | None newly added but fixes the referenced spec in an existing EN which now reads: "references of TS 29.523 503 need to be updated later"
105 | C3-193324, CR0080 | Differences between EPC and 5GC for MonitoringEvent API | Huawei | 29.522 | None
105 | C3-193574 | LS on I-NEF service | CT3/Huawei | N/A: this is an LS out | None | Email from the CT3 Chairperson on the CT3 email reflector titled "C3-193574 LS on I-NEF services" "As you may know, LS on C3-193574 was approved in CT3#105 meeting to ask CT4 whether they can confirm that the I-NEF service can be defined by CT3. CT4 chairman has informed me that the LS was discussed in Wroclaw and that CT4 agrees to the proposal. Mind that there will be no reply to the LS"
106 | C3-194445 | LS on Service on I-NEF Event Exposure | CT3/Huawei | N/A: this is an LS out | None | CT3 has started the work on 5G_CIoT and is specifying the I-NEF Event Exposure (i.e. Ninef_EventExposure) service as defined in TS 23.502. CT3 is also specifying the NEF Event Exposure (i.e. Nnef_EventExposure) service which is used by the NF service consumer(s) (e.g. NWDAF) to (un)subscribe to notification of observed events in the NEF. From CT3 point of view, the NEF acts as I-NEF in roaming scenario, the Nnef_EventExposure service works well in both non-roaming and roaming scenarios for different NF service consumers. It’s unnecessary to define a dedicated service for the I-NEF Event Exposure functionality. CT3 has already decided to implement the functionality of I-NEF Event Exposure by the Nnef_EventExposure service.
107 | C3-195274 | Pseudo-CR on Clarify NEF southbound services | Ericsson | 29.591 | None | This is a pCR
108-e | C3-201210 | V-SMF applicable event | Ericsson | 29.508
| C3-201208 | Support PDU session status | Ericsson | 29.122
| C3-201209 | Support PDU session status | Ericsson | 29.522
| C3-201206 | Remove DDN failure event | Ericsson | 29.508 |  | Cat F, merged
| C3-201205 | Support PDU session establishment event | Ericsson | 29.508
| C3-201464 | Update of the Availability after DDN Failure event | Huawei | 29.522
| C3-201404 | Update of the Availability after DDN Failure event | Huawei, Ericsson | 29.508
| C3-201405 | Update of the DDD status event | Huawei | 29.522
| C3-201406 | Update of the DDD status event | Huawei, Ericsson | 29.508
| C3-201402 | Update of the DDD status event and availability of DDN failure event | Huawei | 29.122
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes
V-SMF applicable event |  |  | Ericsson | 29.508 | to clarify that "DDD status" is the only event applicable for V-SMF
support PDU session status |  |  | Ericsson | 29.122 | to add support for monitoring event "PDU session status" in 5G.
support PDU session status |  |  | Ericsson | 29.522 | to add support for monitoring event "PDU session status" in 5G.
PDU session establishment event |  |  | Ericsson | 29.508 | add support for PDU session establishement event
remove DDN failure event |  |  | Ericsson | 29.508 | remove DDN failure from SMF event exposure
TBD |  |  | Huawei | 29.591 | Add support for the following events: Loss of connectivity, UE reachability, Location Reporting, Communication failure, Availability after Downlink Data Notification failure; and Downlink data delivery status.
Update of the Availability after DDN Failure event |  |  | Huawei | 29.522 | to add support for the availability after DNN Failure event
Update of the Availability after DDN Failure event |  |  | Huawei | 29.508 | to remove the availability after DNN Failure event
Update of the DDD status event |  |  | Huawei | 29.522 | to add support for the DDD status event
Update of the DDD status event |  |  | Huawei | 29.508 | to add support for the DDD status event
Update of the DDD status event and availability of DDN failure event |  |  | Huawei | 29.122 | to add support for the availability after DNN Failure event and DDD status event

## Supp. for Expected UE Behaviour
WORK PLAN (Key Issue 13)
Expected changes |  |  | Impacted Specifications | Status | Notes
Enhancement for existing Nnef_ParameterProvision service to support more expected UE Behaviour for 5G CIoT |  |  | 29.522, 29.122 | Complete (see C3-194340, C3-194389) | The Expected UE Behaviour to include more parameters. Note 1: the existing “Expected UE Moving Trajectory” parameter is supported in the communication pattern parameter provisioning API (CpProvisioning API). Note 2: some of the extended parameters are also supported in EPS: Stationary Indication, Communication Duration Time, Periodic Time, Scheduled Communication Time Note 3: also supported in EPS - Battery indication, Traffic profile (The above was supported in stage 2 for EPS but not in stage 3 EPS, in TS 23.682) The Scheduled Communication Type parameter is this is the only one that is new for 5GS
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
106 | C3-194340, CR0203 | Scheduled communication type | Huawei | 29.122 | None
106 | C3-194389, CR0088 | Scheduled communication type | Huawei | 29.522 | None
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes

## MSISDN-less SMS
WORK PLAN (Key Issue 17)
Expected changes |  |  | Impacted Specifications | Status | Notes
Support new NEF MSISDN-less MO SMS service API |  |  | 29.522 | Completed | This will reuse the existing service API in EPS. It will just be listed as a new service for the NEF but will reference 29.122
Meeting # | Tdoc, CR | Title | Source | Target Specification | Editor's Notes | Comments
102 | C3-191376, CR0043 | Nnef_MSISDN-less_MO_SMS service | Huawei | 29.522
Please list your contribution plan below for meeting C3#TBD
Title |  |  | Source | Target Specifiation | Notes