## CT3
NBI17 WI (CP-213262) - CT3 Work Plan - 01/2022
Impact Description |  | Specification | Contributing company | Tdoc Numbers | Targeted CT3 meeting | Status
1. Common aspects fully align with 5GC APIs, following TS 29.500/29.501, when relevant/possible
Missed descriptrion field update in OpenAPI file and/or Unbreakable spaces | Missing description fields need to be added and unbreakable spaces (or any other unauthorized character, e.g. tabulations) should be corrected. | 29.122 | Huawei | C3-212414-C3-212428 | CT3#115-e | Agreed
|  | 29.522 | Huawei | C3-212458-C3-212468 | CT3#115-e | Agreed
|  | 29.222 | Huawei | C3-212078/2080/2081/2429/2430/2552 | CT3#115-e | Agreed
|  |  | Ericsson, Huawei | C3-212435-C3-212445 | CT3#115-e | Agreed
|  | 29.486 | Huawei | C3-211480 under SBIProtoc17 (before NBI17 WI start) | CT3#114-e | Agreed
|  | 29.549 | Huawei | C3-211485 under SBIProtoc17 (before NBI17 WI start) | CT3#114-e | Agreed
Respecting 3GPP Forge executing rules | Cf. TS 21.801. | 29.122 | Huawei | C3-213538 | CT3#116-e | Agreed
2. Common aspects (different from the common aspects for 5GC APIs)
Redirection handling | Support 307/308 status codes for 3GPP Northbound APIs (except NEF Northbound APIs which already supports from Rel-16) | 29.122 | Huawei | CRs C3-211425 to 1448 (starting from Rel-16) | CT3#114-e | Agreed
|  |  |  | C3-212121 (only from Rel-17, for pure SCEF northbound APIs) | CT3#115-e | Agreed
|  | 29.522 | n/a | Already supported from Rel-16 | _ | _
|  | 29.222 | Huawei | C3-213388 | CT3#116-e | Agreed
|  | 29.549 | Huawei | C3-213438 | CT3#116-e | Agreed
|  | 29.486 | Huawei | C3-211499 under TEI17 (when NBI17 not exist) | CT3#114-e | Agreed
More custom headers | General support of custom headers for northbound and application layer APIs Support of new Nb-Api-Sender-Timestamp, Nb-Api-Max-Rsp-Time, Nb-Api-Lci, Nb-Api-Oci headers | 29.122 | Huawei | C3-211490 under SBIProtoc17 (before NBI17 WI start) | CT3#114-e | Agreed
|  |  |  | C3-214603 (under NBI17) | CT3#117-e | Agreed
|  | 29.522 | n/a |  | _ | _
|  | 29.222 | Huawei | C3-211491 under SBIProtoc17 (before NBI17 WI start) | CT3#114-e | Agreed
|  | 29.486 | Huawei | C3-211201 under SBIProtoc17 (before NBI17 WI start) | CT3#114-e | Agreed
|  |  | Huawei | C3-212469 | CT3#115-e | Agreed
|  | 29.549 | Huawei | C3-211492 under SBIProtoc17 (before NBI17 WI start) | CT3#114-e | Agreed
3. Multiple events per subscription
MonitoringEvent API |  | 29.122 | Huawei | C3-216527 | CT3#119-e | Agreed
AsSessionWithQoS API | Already fully covered by C3-214459 and C3-215493. | 29.122 | Huawei | C3-214459, C3-215493. | CT3#119-e | Agreed
ChargeableParty API | Already fully covered by C3-214459 and C3-215494. | 29.122 | Huawei | C3-214459, C3-215494. | CT3#119-e | Agreed
4. 204 No Content for resource modification (PUT and/or PATCH if defined)
MonitoringEvent API |  | 29.122 | Huawei, Ericsson | C3-213387 | CT3#116-e | Agreed
NIDD API |  | 29.122 | Ericsson | C3-213395 | CT3#116-e | Agreed
ResourceManagementOfBdt API |  | 29.122 | KDDI, Huawei | C3-215483 | CT3#118-e | Agreed
ChargeableParty API |  | 29.122 | Huawei | C3-213179 | CT3#116-e | Agreed
DeviceTriggering API |  | 29.122 | China Telecom | C3-214543 | CT3#117-e | Agreed
GMD via MBMS related APIs |  | 29.122 | Ericsson | C3-214323 & C3-214324 | CT3#117-e | Agreed
ReportingNetworkStatus API |  | 29.122 | China Telecom | C3-214460 | CT3#117-e | Agreed
CpProvisioning API |  | 29.122 | HAVELSAN, Huawei | C3-216541 | CT3#119-e | Agreed
PfdManagement API |  | 29.122 | ZTE | C3-213384 | CT3#116-e | Agreed
NpConfiguration API |  | 29.122 | China Telecom, Ericsson | C3-213386 | CT3#116-e | Agreed
AsSessionWithQoS API |  | 29.122 | Huawei | C3-213178 | CT3#116-e | Agreed
RacsParameterProvisioning API |  | 29.122 | Ericsson | C3-213394 | CT3#116-e | Agreed
CAPIF_Publish_Service_API |  | 29.222 | ZTE | C3-213385 | CT3#116-e | Agreed
CAPIF_API_Invoker_Management_API |  | 29.222 | Ericsson | C3-214327 | CT3#117-e | Agreed
CAPIF_API_Provider_Management_API |  | 29.222 | Huawei | C3-214237 | CT3#117-e | Agreed
SS_LocationReporting API |  | 29.549 | China Mobile | C3-213287 | CT3#116-e | Agreed
SS_GroupManagement API |  | 29.549 | Huawei | C3-213437 | CT3#116-e | Agreed
5. Update of notification destination via HTTP PATCH operation (if defined)
ResourceManagementOfBdt API |  | 29.122 | Huawei | C3-213389 | CT3#116-e | Agreed
NIDD API |  | 29.122 | Ericsson | C3-213399 | CT3#116-e | Agreed
AsSessionWithQoS API |  | 29.122 | Huawei | C3-213185 | CT3#116-e | Agreed
ChargeableParty API |  | 29.122 | Huawei | C3-213184 | CT3#116-e | Agreed
GMD via MBMS related APIs |  | 29.122 | Ericsson | C3-214325 & C3-214326 | CT3#117-e | Agreed
NpConfiguration API |  | 29.122 | China Telecom | C3-213134 | CT3#116-e | Agreed
TrafficInfluence API |  | 29.522 | Huawei | C3-213186 | CT3#116-e | Agreed
6. Support of PUT or PATCH operation for resource modification (if needed and not already defined)
NIDD API | Add the support of HTTP PATCH. | 29.122 | Huawei |  | CT3#119-bis-e | Planned
DeviceTriggering API | Add the support of HTTP PATCH. | 29.122 | Huawei |  | CT3#119-bis-e | Planned
ReportingNetworkStatus API | Add the support of HTTP PATCH. | 29.122 | Huawei |  | CT3#120-e | Planned
CpProvisioning API | Add the support of HTTP PATCH. | 29.122 | Huawei |  | CT3#120-e | Planned
PfdManagement API | Add the support of HTTP PATCH. | 29.122 | Huawei |  | CT3#120-e | Planned
CAPIF_Publish_Service_API |  | 29.222 |  |  | CT3#120-e | Planned
CAPIF_Events_API |  | 29.222 |  |  | CT3#120-e | Planned
CAPIF_API_Invoker_Management_API |  | 29.222 |  |  | CT3#120-e | Planned
CAPIF_API_Provider_Management_API |  | 29.222 |  |  | CT3#120-e | Planned
SS_LocationReporting API |  | 29.549 |  |  | CT3#120-e | Planned
SS_GroupManagement API |  | 29.549 |  |  | CT3#120-e | Planned
SS_NetworkResourceAdaptation API |  | 29.549 |  |  | CT3#120-e | Planned
SS_Events API |  | 29.549 |  |  | CT3#120-e | Planned
7. Mandatory HTTP error status codes
All the CAPIF APIs |  | 29.222 | Huawei | C3-213388 | CT3#116-e | Agreed
8. Reception report for UL/DL message delivery
Reception report for DL message delivery |  | 29.486 | Huawei | C3-213150 | CT3#116-e | Agreed
Reception report for UL message delivery |  | 29.486 | Huawei | C3-213150 | CT3#116-e | Agreed
9. Behaviour of the VAE server for VAE services
VAE_ApplicationRequirement service |  | 29.486 | Huawei | C3-213435 | CT3#116-e | Agreed
VAE_DynamicGroup service |  | 29.486 | Huawei | C3-213436 | CT3#116-e | Agreed
VAE_ServiceContinuity service |  | 29.486 | Huawei | C3-213436 | CT3#116-e | Agreed
10. Corrections to the API URI, path after API URI and resource URIs (e.g. remove trailing slash)
MonitoringEvent API |  | 29.122 | Huawei, KDDI | C3-214228 | CT3#117-e | Agreed
ResourceManagementOfBdt API |  | 29.122 | KDDI, Huawei | C3-214101 | CT3#117-e | Agreed
ChargeableParty API |  | 29.122 | Huawei | C3-214230 | CT3#117-e | Agreed
NIDD API |  | 29.122 | Ericsson | C3-214450 | CT3#117-e | Agreed
DeviceTriggering API |  | 29.122 | China Telecom | C3-214239 | CT3#117-e | Agreed
GMD via MBMS related APIs |  | 29.122 | Huawei | C3-214449 | CT3#117-e | Agreed
ReportingNetworkStatus API |  | 29.122 | China Telecom | C3-214240 | CT3#117-e | Agreed
CpProvisioning API |  | 29.122 | HAVELSAN, Huawei | C3-216024 | CT3#119-e | Agreed
PfdManagement API |  | 29.122 | Nokia | C3-214447 | CT3#117-e | Agreed
NpConfiguration API |  | 29.122 | Nokia | C3-214447 | CT3#117-e | Agreed
AsSessionWithQoS API |  | 29.122 | Huawei | C3-214448 | CT3#117-e | Agreed
RacsParameterProvisioning API |  | 29.122 | Ericsson | C3-214451 | CT3#117-e | Agreed
NEF specific APIs |  | 29.522 | Huawei | C3-214231 | CT3#117-e | Agreed
CAPIF APIs |  | 29.222 | Huawei | C3-214232 | CT3#117-e | Agreed
SEAL APIs |  | 29.549 | Huawei | C3-214234 | CT3#117-e | Agreed
VAE APIs |  | 29.486 | Huawei | C3-213436 | CT3#117-e | Agreed
11. Explicit subscription to events
ChargeableParty API |  | 29.122 | Ericsson, Huawei | C3-214459 | CT3#117-e | Agreed
|  | 29.122 | Huawei | C3-215494 | CT3#118-e | Agreed
AsSessionWithQoS API |  | 29.122 | Huawei | C3-215493 | CT3#118-e | Agreed
12. Updates to the subcriptions retrieval GET request to allow the retrieval of a subset of subscriptions
ChargeableParty API |  | 29.122 | Ericsson, Huawei | C3-215429 | CT3#118-e | Agreed
AsSessionWithQoS API |  | 29.122 | Ericsson, Huawei | C3-215428 | CT3#118-e | Agreed
MonitoringEvent API |  | 29.122 | Ericsson | C3-216526 | CT3#119-e | Agreed
ServiceParameter API |  | 29.522 | Ericsson | C3-216523 | CT3#119-e | Agreed
13. Other corrections (attribute cardinalities, data model clauses, etc.)
Corrections on SCEF/NEF APIs | TrafficInfluence API | 29.522 | Nokia | C3-213261 | CT3#116-e | Agreed
Corrections on CAPIF APIs | CAPIF_API_Invoker_Management_API | 29.222 | Huawei | C3-213064 | CT3#116-e | Agreed
| CAPIF_Auditing_API | 29.222 | Huawei | C3-213381 | CT3#116-e | Agreed
| CAPIF_Events_API | 29.222 | Huawei | C3-213066 | CT3#116-e | Agreed
| CAPIF_Logging_API_Invocation_API | 29.222 | Huawei | C3-213067 | CT3#116-e | Agreed
| CAPIF_Publish_Service_API | 29.222 | Huawei | C3-213068 | CT3#116-e | Agreed
| CAPIF_Security_API | 29.222 | Huawei | C3-213069 | CT3#116-e | Agreed
| AEF_Security_API | 29.222 | Huawei | C3-213382 | CT3#116-e | Agreed
| CAPIF_Discover_Service_API | 29.222 | Huawei | C3-213383 | CT3#116-e | Agreed
| CAPIF_API_Provider_Management_API | 29.222 | Huawei | C3-213072 | CT3#116-e | Agreed
| CAPIF_Routing_Info_API | 29.222 | Huawei | C3-213073 | CT3#116-e | Agreed
| CAPIF_Access_Control_Policy_API | 29.222 | Huawei | C3-213074 | CT3#116-e | Agreed
Correcting the resource URI structure figures to put the "{afId}" resource under the API URI | NEF Northbound APIs | 29.522 | Huawei | C3-215283 | CT3#118-e | Agreed
Adding the API specific data types tables | MonitoringEvent API | 29.122 | Huawei, KDDI | C3-216489 | CT3#119-e | Agreed
| ResourceManagementOfBdt API | 29.122 | KDDI, Huawei |  | CT3#119-bis-e | Planned
| ChargeableParty API | 29.122 | KDDI, Huawei |  | CT3#119-bis-e | Planned
| NIDD API | 29.122 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| DeviceTriggering API | 29.122 | Huawei | C3-216490 | CT3#119-e | Agreed
| GMD via MBMS related APIs | 29.122 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| ReportingNetworkStatus API | 29.122 | Huawei | C3-216491 | CT3#119-e | Agreed
| CpProvisioning API | 29.122 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| ECRControl API | 29.122 | Huawei | C3-216492 | CT3#119-e | Agreed
| PfdManagement API | 29.122 | KDDI, Huawei |  | CT3#119-bis-e | Planned
| NpConfiguration API | 29.122 | Huawei | C3-216493 | CT3#119-e | Agreed
| AsSessionWithQoS API | 29.122 | KDDI, Huawei |  | CT3#119-bis-e | Planned
| MsisdnLessMoSms API | 29.122 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| RacsParameterProvisioning API | 29.122 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| TrafficInfluence API | 29.522 | Huawei, KDDI | C3-216488 | CT3#119-e | Agreed
| AnalyticsExposure API | 29.522 | KDDI, Huawei | C3-216482 | CT3#119-e | Agreed
| 5GLANParameterProvision API | 29.522 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| ApplyingBdtPolicy API | 29.522 | KDDI, Huawei | C3-216484 | CT3#119-e | Agreed
| IPTVConfiguration API | 29.522 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| LpiParameterProvision API | 29.522 | Huawei, KDDI |  | CT3#119-bis-e | Planned
| ServiceParameter API | 29.522 | KDDI, Huawei | C3-216483 | CT3#119-e | Agreed
| ACSParameterProvision API | 29.522 | KDDI, Huawei | C3-216485 | CT3#119-e | Agreed
| TimeSyncExposure API | 29.522 |  |  | CT3#120-e | Planned
| EcsAddressProvision API | 29.522 |  |  | CT3#120-e | Planned
| AMPolicyAuthorization API | 29.522 |  |  | CT3#120-e | Planned
| AMInfluence API | 29.522 |  |  | CT3#120-e | Planned
Adding a list of APIs table | T8 APIs | 29.122 | Huawei | C3-216486 | CT3#119-e | Agreed
| NEF Northbound APIs | 29.522 | Huawei | C3-216487 | CT3#119-e | Agreed
Adding/correcting "summary", "operationId" and "tags" fields in OpenAPI files | MonitoringEvent API | 29.122 | Ericsson | C3-215460 | CT3#118-e | Agreed
| ResourceManagementOfBdt API | 29.122 | Ericsson | C3-215244 | CT3#118-e | Agreed
| ChargeableParty API | 29.122 | Ericsson | C3-215245 | CT3#118-e | Agreed
| NIDD API | 29.122 | Ericsson | C3-215459 | CT3#118-e | Agreed
| DeviceTriggering API | 29.122 | Ericsson | C3-215458 | CT3#118-e | Agreed
| GMD via MBMS related APIs | 29.122 | Ericsson | C3-215248, C3-215249 | CT3#118-e | Agreed
| ReportingNetworkStatus API | 29.122 | Ericsson | C3-215250 | CT3#118-e | Agreed
| CpProvisioning API | 29.122 | Ericsson | C3-215457 | CT3#118-e | Agreed
| PfdManagement API | 29.122 | Ericsson | C3-215252 | CT3#118-e | Agreed
| NpConfiguration API | 29.122 | Ericsson | C3-215253 | CT3#118-e | Agreed
| AsSessionWithQoS API | 29.122 | Ericsson | C3-215254 | CT3#118-e | Agreed
| MsisdnLessMoSms API | 29.122 | Ericsson | C3-215461 | CT3#118-e | Agreed
| RacsParameterProvisioning API | 29.122 | Ericsson | C3-215256 | CT3#118-e | Agreed
| UAE_C2OperationModeManagement API | 29.257 | Huawei | C3-216218 | CT3#119-e | Agreed
Other editorial corrections |  | 29.549 | Ericsson | C3-216438 | CT3#119-e | Agreed