## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #119Bis-e eMeeting, 17th - 21st January 2022 |  | C3-220282
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of eSEAL
Agenda item: | 17.32
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | SA6 agreed CR(s) | Responsible Company | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
29.549 | SEAL API Specification; Stage 3 (Rel-17) |  |  |  |  | Approved WID - CP-211331
| Overview |  | Samsung
| References |  | Samsung
| Definition of Terms and Abbreviation |  | Samsung
| Introduction of SEAL services |  | Samsung
Location Management APIs (Service description, API definition, OpenAPI)
| CR on clarifications for T8 interface | S6-202301 |  |  |  | Architecture requirement. No direct impacts.
| Tracking UE and obtaining dynamic UE information | S6-202195 |  |  | CT3#118e (C3-215486)
| Service identification in location management procedures | S6-210647 | Samsung |  | CT3#119bis-e (C3-220285)
| Update to LMS server APIs | S6-210677 |  |  | CT3#118e (C3-215486)
| Service identification in location management procedures | S6-210359
| Fixing the descriptions of IEs in Information flows for location information | S6-211455
| SEAL Location Deviation Service Information flows and APIs | S6-211470 | Samsung |  | CT3#119e(C3-216474), CT3#119bis-e (C3-220283)
| SEAL Location Deviation Service | S6-211469 | Samsung |  | CT3#119e(C3-216474), CT3#119bis-e (C3-220283)
| Supplementary location information to verticals | S6-210921
| Requirements for Location management service | S6-211030 |  |  |  | Architecture requirement. No direct procdure impact.
| Location report timestamp support | S6-210995 | Samsung |  | CT3#119bis-e (C3-220285)
| Utilize NEF location service for SEAL LM | S6-211838 |  |  |  | Architecture impact to fetch location information from NEF. The services and APIs can use this information when specifying in TS 29.549.
Group Management APIs (Service description, API definition, OpenAPI)
| Temporary Groups formation | S6-202362 |  |  |  | The group management server notifies the VAL server regarding the temporary group creation
| API and information flow description for Temporary groups | S6-211453
| Enhancement of information flows to add VAL service specific information | S6-210559 | Samsung |  | CT3#119bis-e (C3-220286) | Data model extension to update the group creation and update notification to VAL server with VAL service information.
| Add location criteria to group creation request | S6-210721 |  |  |  | New service or update existing one.
| Update to GMS APIs | S6-211085
| Group Management support for 5G-VN | S6-210360 | Ericsson |  | CT3#118e (C3-215489)
| SEAL enable 5G CN capabilties for SEAL groups | S6-211484 | Samsung |  | CT3#117e (C3-214573)
| Group Management Enhancements | S6-211066 | Samsung |  | CT3#117e (C3-214397) | Updates to identity list notification to VAL server.
| Resolve EN for group management | S6-211086 | Ericsson |  | CT3#118e (C3-215489)
| location based dynamic group update | S6-212152 | Samsung |  | CT3#119bis-e (C3-220284)
Configuration Management APIs (Service description, API definition, OpenAPI)
| add VAL UE Information to configuration management procedure | S6-211483 | Samsung |  | CT3#119bis-e (C3-220288) | May have impacts on UserProfileRetrieval proceedure.
Network resource Management APIs (Service description, API definition, OpenAPI)
| support local MBMS | S6-202343 |  |  | CT3#118e (C3-215485)
| Unified support for TSC/TSN services | S6-211485 | Ericsson |  | CT3#119e
| QoS Monitoring support | S6-211392 | Ericsson |  | CT3#119e | subscription/notify
| Complete resource reservation with PCC procedure | S6-211361
| SEAL Event Monitoring Service | S6-211068 | Samsung |  | CT3#118e (C3-215437), CT#94e(CP-213250)
| Improved Event Monitoring Service | S6-211840 | Ericsson |  | CT#94e(CP-213250)
| Support for TSC services procedures | S6-212151 | Ericsson |  | CT#94e(CP-213231), CT3#119e (C3-216283, C3-216430, C3-216432, C3-216433),
| Support for TSN services procedures | S6-212099 | Ericsson |  | CT3#119e
| Unicast QoS monitoring data retrieval | S6-212100 | Ericsson |  | CT3#119e | request/response
| Removal of PCP from TSC stream discovery | S6-212820 | Ericsson
Identity Management APIs (Service description, API definition, OpenAPI)
No impacts
Key Management APIs (Service description, API definition, OpenAPI)
No impacts
Events APIs (Service description, API definition, OpenAPI)
| New events from various SEAL services will be implemented under this API |  |  |  |  | New events are added as part of other CRs/Services.
Network slice capability management API (Service description, API definition, OpenAPI)
| Network slice adaptation for VAL applications | S6-202353 | NTT |  | CT#94e (CP-213254)
| Procedure for VAL UE-triggered and network-based network slice adaptation for VAL application | S6-211076
CAPIF impacts (if any)
Any additional security aspects
| Annex Updates (if needed) |  |  |  |  | None, only Open API updates, as part new/existing APIs.
Target Completion - TSG CT#95 (March 2022)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments