## Cover sheet
3GPP TSG-CT WG4 Meeting #107-e |  | C4-216289
E-Meeting, 15th – 23rd November 2021
Source: | Qualcomm Incorporated
Title: | ID_UAS CT4 Work plan
Document for: | Discussion
Agenda Item: | 6.2.9
Work Item / Release: | Rel-17

## Contribution plan
Latest update: 25/10/2021
Topic number | Description | Stage-2 Reference | TS | Contributor | CT4 meeting # Tdoc # | Status | Notes
General
| TS skeleton |  | 29.256 | Qualcomm | CT4#103e | Close
| Scope and overview | TS 23.256 | 29.256 | Qualcomm | CT4#103e | Close
| Corrections and alignement with SA2#144 | TS 23.256 | 29.256 | Qualcomm | CT4#104e | Close
| Corrections and alignement with SA2#145 | TS 23.256 | 29.256 | Qualcomm | CT4#105e | Close
| Terms and Definition | TS 23.256 | 29.256 | Qualcomm | CT4#103e | Close
| OpenAPI General Subclause |  | 29.256 | Qualcomm | CT4#103e | Close
| Correction missing references |  | 29.256 | Qualcomm | CT4#104e | Close
| List of UAS-NF services | TS 23.256 | 29.256 | Qualcomm | CT4#104e | Close
OpenAPI
Subscription
| Aerial Subscription | TS 23.256 4.2.1 | 29.503 | Huawei | CT4#104e | Close | C4-213582 CR 29.503 0658 Rel-17 Aerial UE subscription data
| SM Subscription data | TS 23.256 5.2.1 | 29.503 | Qualcomm | CT4#106e
UUAA-MM
| Authenticate Req/Resp | TS 23.256 5.2.2.2 | 29.256 | Qualcomm | CT4#105e | Close | Provided in C4-214738 to TS v0.3.0
| Add Authentication Session Correlation Id | TS 23.256 5.2.2.2 | 29.256 | Nokia | CT4#106e | Close | Added in stage-2 v2.0.0
| Further alignments |  | 29.256 | Nokia | CT4#106e | Close
| The UUAA context may be stored in the UDSF or in the UAS NF | TS 23.256 5.2.2.1, 5.2.7 | 29.256 | Nokia | CT4#106e | Close
| AMF subscribes for notification at UAS-NF to trigger re-auth | TS 23.256 5.2.7 | 29.256 | Qualcomm | CT4#105e | Close | Provided in C4-214738 to TS v0.3.0
| Further alignments |  | 29.256 | Nokia | CT4#106e | Close
| Namf_EventExposure Subscribe/Unsubscribe | TS 23.256 5.2.2 | 29.518 | Qualcomm | CT4#106e |  | Namf_EventExposure Service consumers: NEF is already a consumer
| AMF UE context update | TS 23.256 5.2.2 | 29.518 | Nokia | CT4#106e | Close
UUAA-SM
5GS
| The UUAA context may be stored in the UDSF or in the UAS NF | TS 23.256 5.2.3, 5.2.7 | 29.256 | Qualcomm | CT4#105e | Discarded | "UUAA Context" per stage-2 seems an implementation aspect, its not defined, read or written in any procedure explictly.
| Authenticate Req/Resp | TS 23.256 5.2.2.2 | 29.256 | Qualcomm | CT4#105e | Close | Provided in C4-214738 to TS v0.3.0
| Nnef_Session_Notification_Start | TS 23.256 5.2.3.2 | 29.256 | Qualcomm | CT4#105e | Discarded | The API is not clearly defined. Update 23256 v200: has been removed
| SMF identification/selection of UAS-NF/NEF based on USS address | TS 23.256 5.2.3.2 |  |  |  | Discarded | Implementation
| N1N2 auth message transfer | TS 23.256 5.2.3.2 | 29.518 | Nokia | CT4#106e | Close
| Nsmf PDU session auth message transfer | TS 23.256 5.2.3.2 | 29.502 | Qualcomm | CT4#106e | Close | 3f. Nsmf_PDUSession_UpdateSMContext (N1 SM message)
| SMF subscribes for notification at UAS-NF to trigger re-auth | TS 23.256 5.2.7 | 29.256 |  | CT4#105e | Close | Provided in C4-214738 to TS v0.3.0
EPS
| PCO to SMF+PGW-C in attach: CAA-Level UAV ID, USS address, UUAA Aviation Payload, etc. | TS 23.256 5.2.3.3 | 29.274
| PCO in Update Bearer Request including UUAA result transferred from SMF+PGW-C to UAV/UE within a UUAA Authorization Payload | TS 23.256 5.2.3.3 | 29.274
| SMF+PGW-C configuraton of ACL in UPF+PGW-U to stop traffic over default PDN Connection. | TS 23.256 5.2.3.3
UUAA Re-authentication
| UAS NF sends Nnef_Auth_Notification | TS 23.256 5.2.4 | 29.256 | Nokia | CT4#106e |  | chapter 5
C2 authorization
5GS
| PDU session mod req/resp, including CAA-level UAV ID, identification info of UAV-C, Flight Authorization information. Response includes authorization result, new CAA-level UAV ID and security information | TS 23.256 5.2.5.2 | 29.502
| Authenticate Req/Resp including UAS container, UAV IP address | TS 23.256 5.2.5.2 | 29.256
| SMF retrieves from PCF the associated policy rules based on the authorization info provided by the USS | TS 23.256 5.2.5.2 | 29.512
| SMF configures UPF based on the policy rules provided by the PCF to enable the requested C2 communication | TS 23.256 5.2.5.2 | 29.244
At PDN Connection
| PCO to SMF+PGW-C in PDN connectivity req: UAS container including UAV UAV-C pairing information, flight authorization information | TS 23.256 5.2.5.3.1 | 29.274
| PCO with RITI in Create Session Response from SMF+PGW-C | TS 23.256 5.2.5.3.1 | 29.274
| if the SMF+PGW-C determines ... the SMF+PGW-C rejects the PDN connectivity request and provides in PCO an indication that USS authorization is required | TS 23.256 5.2.5.3.1 | 29.274
UE requested bearer resource modification
| PCO to SMF+PGW-C in bearer resource mod: UAS container including UAV UAV-C pairing information, flight authorization information | TS 23.256 5.2.5.3.2 | 29.274
| PCO with RITI in bearer resource mod Create Session Response from SMF+PGW-C | TS 23.256 5.2.5.3.2 | 29.274
UAV tracking
| UAV location reporting | TS 23.256 5.3.2 |  |  |  | Close | All existing CN features are used; UAS-NF is the NEF as service consumer
| UAV presence monitoring | TS 23.256 5.3.3 |  |  |  | Close | All existing CN features are used; UAS-NF is the NEF as service consumer
| Obtaining list of Aerial UEs in a geographic area | TS 23.256 5.3.4
| Notification enhancement with additional filtering |  | 29.518 | Nokia | CT4#106e | Close | requirements are clear in SA2, Nokia will bring the CR