## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #130 Xiamen,China, 9th - 13th October, 2023 |  | C3-234422
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of System Support for AI/ML-based Services
Agenda item: | 18.31
Document for: | Information

## Contributions plan
Contribution Plan
Spec (Rel-18) | Topic | SA2 agreed CR(s) | Responsible Company | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
Approved WID - CP-230329
(New) 29.543 | 5G System; Data Transfer Policy Control Services; Stage 3
| TS Skeleton |  | Ericsson
| Enhancements of PCF Services and NEF Services | S2-2211333, S2-2211426, S2-2211427, S2-2303729, S2-2303898, S2-2305436, S2-2308208, S2-2308210, S2-2309852, S2-2309510 | Huawei, Ericsson, OPPO
| Scope, Overview |  | Ericsson |  | C3-231477
| Service description and operations of PDTQ Policy Control service, |  | Ericsson |  | C3-231477, C3-233070, C3-233533
| Specification of procedures for the Npcf_PDTQPolicyControl service operations: Create, Update and Notify |  | Ericsson |  | C3-231477, C3-231479, C3-232059
| General clauses of the Npcf_PDTQPolicyControl API |  | Ericsson |  | C3-231478
| Resource structure for the Npcf_PDTQPolicyControl API |  | Ericsson |  | C3-231478
| Npcf_PDTQPolicyControl API Notifications |  | Ericsson |  | C3-231479
| Data model for the Npcf_PDTQPolicyControl API |  | Ericsson |  | C3-231480, C3-232059, C3-233533
| OpenAPI file of the Npcf_PDTQPolicyControl API |  | Ericsson |  | C3-232435, C3-233533
| TS for Information (CT3#102 Dec 2023) |  | Ericsson |  |  | C3-231510 - v0.1.0, C3-232460 -v0.2.0
| TS for approval (CT3#103 Dec 2024) |  | Ericsson
29.122 | T8 reference point for Northbound APIs
| AIMLsys: KI#1 – 23.502 Solution for 5GC assistance to support Group-MBR Monitoring via NEF Event Exposure Extensions | S2-2211439 | Huawei, OPPO, Toyota
| Adding support for Negotiations for planned data transfer with QoS (PDTQ) with QoS requirements as agreed in TR 23.700-80 | S2-2211427 | Ericsson, OPPO, Huawei
| Parameter provisioning - Application specific Expected UE Behaviour | S2-2305434 | Ericsson |  | C3-232250 | Update to CpProvisioning API Editor's Note: The content of AppExpUeBehaviour data type is for FFS.
| AFSessionWithQoS (QoS Timing) | S2-2308212 | Nokia |  | C3-233692
| AFSessionWithQoS (List of UEs) | S2-2308206 | Samsung, Ericsson, Nokia, Huawei, Oppo |  | C3-233695 | Editor’s Note: Whether a new data structure for list of UE is needed or not is FFS.
| UE Behaviour parameters updates |  | Samsung, Ericsson, Vodafone |  | C3-233528, C3-233617
29.522 | 5G System; Network Exposure Function Northbound APIs; Stage 3
| NEF Services update | S2-2308202 | Samsung |  |  | Update with new services that are introduced for AIML
| Enhancements of PCF Services and NEF Services | S2-2211333, S2-2211426 | Huawei, OPPO
| Definition of the new API Nnef_PDTQPolicyNegotiation services | S2-2305436, S2-2308208, S2-2309852, S2-2309853 | Ericsson, ZTE |  | C3-231460, C3-232425, C3-233671, C3-233292, C3-233323 | S2-2305436,S2-2308208 to be implemented.
| 5GC assistance to support Group-MBR Monitoring via NEF Event Exposure Extensions | S2-2211439, S2-2303827, S2-2303826 | Huawei, Samsung, OPPO, Toyota
| List of FL areas for UE mobility analytics (AnalyticsExposure API) | S2-2301588 | Ericsson, CATT, Samsung |  | C3-231546
| DN Performance analytics updates (AnalyticsExposure API) | S2-2303728 | Ericsson, Huawei |  | C3-231593 | Open API alignment pending
| Network Performance analytics updates (AnalyticsExposure API) | S2-2300122, S2-2301581 | Ericsson, Huawei |  | C3-231648
| Service Experience Analytics updates for FL operations | S2-2301585 | Ericsson, ETRI
| UE Latency performance (end to end data volume) analytics | S2-2303832, S2-2304038, S2-2305452 | Nokia, Samsung, Ericsson, Huawei |  | C3-232661, C3-232662 , C3-232561 | Stage-2 EN: Editor’s Note: The inclusion of the following OAM inputs: RAN part delay and Average UL/DL packed delay between PSA UPF and UE is subject to SA5 verification. C3-232661, C3-232662 - AnalyticsExposure C3-232561 - EventExposure
| WLAN performance Analytics updates for FL operations | S2-2303739 | Ericsson, Vivo, Huawei
| Nnef_UEMemberSelectionAssistance Service and UE selection criterias | S2-2303731, S2-2303874, S2-2303736, S2-2303734, S2-2303735, S2-2303830, S2-2305440, S2-2305441, S2-2308034, S2-2305224, S2-2305440, S2-2306840, S2-2308223, S2-2308245, S2-2305446, S2-2308219, S2-2308220, S2-2305441, S2-2308259, S2-2308221, S2-2308222, S2-2307096, S2-2309447 | Samsung, Nokia, Ericsson, CMCC, Huawei, Oppo, Sony, InterDigital, LGE, NTT |  | C3-232568, C3-232567, C3-232569 | Editor’s Note: The list of Member UE filtering criteria and their corresponding procedures are FFS. Api Name changes to MemberUESelectionAssistance
| UE member assistance with QoS filtering criteria | S2-2303831, S2-2308218, S2-2309447 | Ericsson, Oppo, Nokia
| Assistance to AIML Operations | S2-2303723 | Samsung |  |  | No stage-3 impacts
| Nnef_MultiMemberAFSessionWithQoS service API | S2-2303873, S2-2303894, S2-2303826, S2-2304258, S2-2308202, S2-2308243, S2-2308206, S2-2308205, S2-2309851 | Samsung, Ericsson, Nokia, Huawei, Oppo |  | C3-233694 | SA2 decided (S2-2304258) to enhance Nnef_AFSessionWithQoS API with the requirements of Nnef_MultiMemberAFSesssionWithQoS API. Changes to AFSessionWithQoS API are captured in S2-2308206
| Nnef_AFSessionWithQoS | S2-2308212 | Nokia |  | C3-233691
| Nnef_ParameterProvisioning API updates for AIML assistance | S2-2303727, S2-2305434 | Samsung, Ericsson |  | C3-232251 | C3-232251 - Expected UE Behaviour params through CpProvisioning API based on S2-2305434
| UE Behaviour parameters updates | S2-2309447, S2-2309507 | Oppo, Nokia
29.513 | 5G System; Policy and Charging Control signalling flows and QoS parameter mapping; Stage 3
| Negotiation for planned data transfer with QoS requirements (PDTQ) policies and PDTQ warning notification |  | Ericsson, Huawei |  | C3-231649, C3-231650, C3-233538
29.514 | 5G System; Policy Authorization Service; Stage 3
| Adding timing info for AF QoS | S2-2308225 | Nokia |  | C3-233693
29.517 | 5G System; Application Function Event Exposure Service; Stage 3
| Support UL/DL in DN performance analytics data collection for AIML |  | Ericsson |  | C3-230741
| List of FL areas for UE mobility analytics | S2-2301588 | Ericsson |  | C3-230912
| E2E transfer time analytics | S2-2304038, S2-2305449 | Ericsson, NTT |  | C3-232560, C3-233571
| E2E transfer time analytics - eventID | S2-2304288 | NTT |  | C3-232560
29.519 | 5G System; Usage of the Unified Data Repository Service for Policy Data, Application Data and Structured Data for Exposure; Stage 3
| Update the Nudr_DataRepository for Policy data with the PDTQ Information |  | Ericsson, Huawei |  | C3-231039, C3-233539, C3-233291, C3-233322
29.520 | 5G System; Network Data Analytics Services; Stage 3 |  |  |  | C3-233600
| TS 23.288 Enhancement to Support AI/ML Data Transfer | S2-2211182 | NTT DOCOMO, OPPO
| Enhancements to Network Performance Analytics to support AIML data traffic policies (Nnwdaf_EventSusbcription) | S2-2211331, S2-2300122, S2-2301581 | Huawei, Ericsson |  | C3-231646, C3-233600
| NWDAF updates to assist resource monitoring of AI/ML-based services | S2-2211330 | Samsung |  |  | No stage 3 imapcts. AF is already a consumer of NWDAF
| List of FL areas for UE mobility analytics (Nnwdaf_EventSubscription, Nnwdaf_AnalyticsInfo API) | S2-2301588 | Ericsson, CATT, Samsung |  | C3-231523, C3-231471
| DN Performance analytics updates (Nnwdaf_EventsSubscription, Nnwdaf_AnalyticsInfo) | S2-2303728, S2-2305453 | Ericsson, Huawei |  | C3-231521, C3-231592, C3-233600 | Nnwdaf_AnalyticsInfo open API alignment pending
| UE Latency performance analytics (Nnwdaf_AnalyticsInfo, Nnwdaf_EventsSubscription, Nnwdaf_MLModelProvision) | S2-2303832, S2-2304038, S2-2305452, S2-2305447, S6-2305427, S2-2305451, S2-2305450 | Nokia, Samsung, Ericsson, Huauwei, China Mobile, LG, Vivo |  | C3-231687, C3-231688, C3-231689, C3-232659, C3-232658, C3-233467, C3-233600, C3-233535, C3-233536, C3-233707 | Stage-2 EN: Editor’s Note: The inclusion of the following OAM inputs: RAN part delay and Average UL/DL packed delay between PSA UPF and UE is subject to SA5 verification.
| Service Experience Analytics updates for FL operations | S2-2301585, S2-2308226 | Ericsson, ETRI
| WLAN performance Analytics updates for FL operations (Nnwdaf_EventsSubscription API, Nnwdaf_AnalyticsInfo API) | S2-2303739 | Ericsson, Vivo, Huawei |  | C3-231643, C3-231644, C3-231647, C3-233600 | Nnwdaf_AnalyticsInfo Open API alignment pending
29.552 | 5G System; Network Data Analytics signalling flows; Stage 3 |  |  |  |  | Is this Spec is impacted? Update WID
| Enhancements on service experience analytics |  | Huawei |  | C3-231429
| End to end data volume transfer time analytics | S2-2303832 | Nokia, Ericsson |  | C3-232663
29.521 | 5G System; Binding Support Management Service; Stage 3
29.591 | 5G System; Network Exposure Function Southbound Services; Stage 3
| List of FL areas for UE mobility analytics | S2-2301588 | Ericsson |  | C3-230913 | To include the SA3 agreed CRs
| Update to Data Type PerformanceDataInfo for DN Performance |  | Ericsson |  | C3-231522
| E2E transfer time analytics | S2-2305449 | NTT
29.508 | 5G System; Session Management Event Exposure Service; Stage 3
| WLAN performance Analytics updates for FL operations | S2-2303739 | Ericsson, Vivo, Huawei |  | C3-231645
| E2E transfer time analytics | S2-2303832, S2-2305449 | Nokia, NTT |  | C3-232660 | EN: Editor's Note: The exact SMF event name for "5QI_INFO" is FFS.
Security aspects (any additional)
Annex Updates (if needed)
WID Target Completion - TSG CT#103 (March 2024)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments
C3-230783 | LS out Rel-18 LS on API enhancement for GMEC services and AIMLSys services | C3-230783 | 1. Clarification on merger of Nnef_AFRequestForQoS and Nnef_MultiMemberAFSessionWithQoS APIs. Waiting for response from SA2. Also, on common and difference aspects between these APIs
C3-233618 | LS on clarification for list of UEs parameter handling |  | In case list of UE is provided, whether the flow description information(s) will be provided per UE or the flow description information(s) is common for list of UEs?