## Tdoc cover sheet
3GPP TSG CT WGX Meeting #XXX PLACE, DATE |  | CX-23XXXX
Source: | Lenovo
Title: | Work plan for the CT1 part and CT3 part of ADAES
Agenda item: | X.X.X
Document for: | Discussion

## Contributions plan CT1
Contribution Plan
Spec | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | Responsible company | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | CT3 meeting | Comments | Open issues
24.559
| Skeleton for Application Data Analytics Enablement Service | TS 23.436 | Lenovo |  | C1-230160 | CT1 #140
| Application data analytics enablement service abbreviations and refences | TS 23.436 | Lenovo |  | C1-233310 | CT1 #142
| Application data analytics enablement service functional entities | TS 23.436 | Lenovo |  | C1-234031 | CT1 #142
| Application data analytics enablement service procedures | TS 23.436 | Lenovo |  | C1-234033 | CT1 #142
| Application data analytics enablement service procedures | TS 23.436 | Lenovo |  | C1-234032 | CT1 #142
| Correction of general description | TS 23.436 | Lenovo |  | C1-237009 | CT1 #144
| ADAES configuration API | TS 23.436 | Lenovo |  | C1-237962 | CT1 #144
| Application performance analytics configuration API | TS 23.436 | Lenovo |  | C1-237963 | CT1 #144
| Procedure for application performance analytics | TS 23.436 | Lenovo |  | C1-237964 | CT1 #144
| Notification overview for ADAE services | TS 23.436 | Lenovo |  | C1-239477 | CT1 #145
| Data model for ADAE services | TS 23.436 | Lenovo |  | C1-239586 | CT1 #145
| Error handling for ADAE services | TS 23.436 | Lenovo |  | C1-239587 | CT1 #145
| Service experience for ADAE services | TS 23.436 | Lenovo |  | C1-239588 | CT1 #145
| Resource review for ADAE services | TS 23.436 | Lenovo |  | C1-239589 | CT1 #145
| Application performance event subscription for ADAE services | TS 23.436 | Lenovo |  | C1-239666 | CT1 #145
| UE-to-UE session performance for ADAE services | TS 23.436 | Lenovo |  | C1-239672 | CT1 #145
| Edge load event subscription for ADAE services | TS 23.436 | Lenovo |  | C1-239673 | CT1 #145
| Application performance event notification for ADAE services | TS 23.436 | Lenovo |  | C1-239674 | CT1 #145
| Edge load event notification for ADAE services | TS 23.436 | Lenovo |  | C1-239675 | CT1 #145
| Add references | TS 23.436 | Lenovo |  | C1-240300 | CT1#146
| Corrections and removal of some titles | TS 23.436 | Lenovo |  | C1-240301 | CT1#146
| Restructuring of resource URI for ADAES | TS 23.436 | Lenovo |  | C1-240302 | CT1#146
| Service description and operations for application performance analytics | TS 23.436 | Lenovo |  | C1-240303 | CT1#146
| Service description and operations for UE-to-UE session performance analytics | TS 23.436 | Lenovo |  | C1-240304 | CT1#146
| Service description and operations for edge load data collection | TS 23.436 | Lenovo |  | C1-240305 | CT1#146
| Service description and operations for service-experiment | TS 23.436 | Lenovo |  | C1-240306 | CT1#146
| Usage of HTTP, common API framework, and security | TS 23.436 | Lenovo |  | C1-240307 | CT1#146
| ADAE service configuration OpenAPI | TS 23.436 | Lenovo |  | C1-240308 | CT1#146
| Miscellaneous corrections | TS 23.436 | Lenovo |  | C1-241600 | CT1#147
| Miscellaneous corrections | TS 23.436 | Ericsson |  | C1-241601 | CT1#147
| OpenAPI corrections | TS 23.436 | Ericsson, Lenovo |  | C1-241602 | CT1#147
| Description of functional entities | TS 23.436 | Ericsson, Lenovo |  | C1-241603 | CT1#147
| Usage of HTTP | TS 23.436 | Ericsson |  | C1-241604 | CT1#147
| Update the configuring triggers and PUSH service experience information report procedures. | TS 23.436 | Samsung |  | C1-241605 | CT1#147
| Support of redirections | TS 23.436 | Ericsson |  | C1-242428 | CT1#148
| Definition of timeWindow | TS 23.436 | Ericsson |  | C1-242429 | CT1#148
| Supported features indication in UE-to-UE session performance analytics | TS 23.436 | Ericsson |  | C1-242517 | CT1#148
| UE-to-UE session performance analytics request | TS 23.436 | Ericsson, Lenovo |  | C1-242802 | CT1#148
| Remove API definition and OPEN API for Configuring Triggers and PUSH service experience information report. | TS 23.436 | Samsung |  | C1-243955 | CT1#149

## Contribution plan CT3
Contribution Plan
Spec | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | Responsible company | Related LS or other WG tdoc(s) # | tdoc(s) # | CT3 meeting | Comments | Open issues
29.549
| VAL application performance API | TS 23.436 | Lenovo |  | C3-235514 | CT3 #131
| Slice-specific application performance API | TS 23.436 | Lenovo |  | C3-235515 | CT3 #131
| UE-to-UE session performance API | TS 23.436 | Lenovo |  | C3-235516 | CT3 #131
| Location accuracy API | TS 23.436 | Lenovo |  | C3-235517 | CT3 #131
| Service API API | TS 23.436 | Lenovo |  | C3-235518 | CT3 #131
| Slice usage pattern API | TS 23.436 | Lenovo |  | C3-235519 | CT3 #131
| Edge load API | TS 23.436 | Lenovo |  | C3-235520 | CT3 #131
| VAL performance analytics | TS 23.436 | Lenovo, Ericsson |  | C3-240243 | CT3 #132
| VAL performance analytics data model updates | TS 23.436 | Nokia, Nokia Shanghai Bell, Lenovo |  | C3-240208 | CT3 #132
| SS_ADAE_VALPerformanceAnalytics API | TS 23.436 | Lenovo, Nokia, Nokia Shanghai Bell |  | C3-240160 | CT3 #132
| Slice-specific application performance analytics | TS 23.436 | Lenovo, Ericsson |  | C3-240247 | CT3 #132
| SS_ADAE_SlicePerformanceAnalytics API | TS 23.436 | Lenovo, Nokia, Nokia Shanghai Bell |  | C3-240162 | CT3 #132
| The procedures of the SS_ADAE_Ue2UePerformanceAnalytics API | TS 23.436 | Ericsson |  | C3-240229 | CT3 #132
| Implementation of the SS_ADAE_Ue2UePerformanceAnalytics API | TS 23.436 | Ericsson |  | C3-240230
| Location accuracy performance analytics | TS 23.436 | Lenovo, Ericsson |  | C3-240248 | CT3 #132
| SS_ADAE_LocationAccuracyAnalytic API | TS 23.436 | Lenovo, Nokia, Nokia Shanghai Bell |  | C3-240162 | CT3 #132
| Service API analyics | TS 23.436 | Lenovo, Ericsson |  | C3-240258 | CT3 #132
| SS_ADAE_ServiceApiAnalytics API | TS 23.436 | Lenovo, Nokia, Nokia Shanghai Bell |  | C3-240164 | CT3 #132
| Slice usage pattern analytics OpenAPI | TS 23.436 | Nokia, Nokia Shanghai Bell |  | C3-240207 | CT3 #132
| Slice usage pattern analytics data model completion | TS 23.436 | Lenovo, Nokia, Nokia Shanghai Bell |  | C3-240206 | CT3 #132
| Slice usage pattern analytics operations | TS 23.436 | Nokia, Nokia Shanghai Bell |  | C3-240205 | CT3 #132
| OpenAPI for SS_ADAE_EdgeLoadAnalytics API | TS 23.436 | Ericsson |  | C3-240228 | CT3 #132
| Service Operation Description for SS_ADAE_EdgeLoadAnalytics API | TS 23.436 | Ericsson |  | C3-240227 | CT3 #132
| Updates to API Definition for SS_ADAE_EdgeLoadAnalytics API and Solve ENs | TS 23.436 | Ericsson |  | C3-240226 | CT3 #132
| Define service descriptions of SS_AADRF_DataManagement API | TS 23.436 | Huawei |  | C3-240175 | CT3 #132
| Define OpenAPI of SS_AADRF_DataManagement API | TS 23.436 | Huawei |  | C3-240174 | CT3 #132
| Define API of SS_AADRF_DataManagement API | TS 23.436 | Huawei |  | C3-240173 | CT3 #132
| SS_ADAE_LocationAccuracyAnalytics API | TS 23.436 | Lenovo, Nokia, Nokia Shanghai Bell |  | C3-241038 | CT3 #133
| Implementation of the OpenAPI file for the SS_ADAE_Ue2UePerformanceAnalytics API | TS 23.436 | Ericsson |  | C3-241410 | CT3 #133
| Implementation of the SS_ADAE_Ue2UePerformanceAnalytics API | TS 23.436 | Ericsson |  | C3-241595 | CT3 #133
| API Definition for SS_ADAE_EdgeLoadAnalytics API and Solve ENs | TS 23.436 | Ericsson |  | C3-241596 | CT3 #133
| OpenAPI for SS_ADAE_EdgeLoadAnalytics API | TS 23.436 | Ericsson |  | C3-241608 | CT3 #133
| Exception sheet for ADAES WI | TS 23.436 | Lenovo |  | C3-241749 | CT3 #133
| Clarification for Exposure level requirements | TS 23.436 | Lenovo |  | C3-242458 | CT3 #134
| Add reporting requirements to SliceAppPerfSub | TS 23.436 | Lenovo |  | C3-242669 | CT3 #134
| Add reporting requirements to LocAccurSub | TS 23.436 | Lenovo |  | C3-242460 | CT3 #134
| Add new attributes to SrvApiSub | TS 23.436 | Lenovo |  | C3-242461 | CT3 #134
| Add reporting requirements to SUPSub | TS 23.436 | Lenovo |  | C3-242462 | CT3 #134
| Edge Load Analytics corrections | TS 23.436 | Nokia |  | C3-242128 | CT3 #134
| A-ADRF Data Management API corrections | TS 23.436 | Nokia |  | C3-242129 | CT3 #134
| Removal of the Editor’s Note for the analytics type in the notification | TS 23.436 | Huawei, Lenovo, Ericsson |  | C3-242596 | CT3 #134
| Resolve the Editor's Notes for the analytics and data output | TS 23.436 | Huawei, Ericsson |  | C3-242597 | CT3 #134
| Update the analytics type in the subscription | TS 23.436 | Huawei, Ericsson |  | C3-242598 | CT3 #134
| 307 and 308 responses support in ADAES APIs | TS 23.436 | Ericsson |  | C3-242228 | CT3 #134
| Alignment of the SS_ADAE_Ue2UePerformanceAnalytics API | TS 23.436 | Ericsson, Nokia, Lenovo |  | C3-242544 | CT3 #134
| Updates to the API Definition for SS_ADAE_EdgeLoadAnalytics API | TS 23.436 | Ericsson |  | C3-242545 | CT3 #134
| Updates to the OpenAPI for SS_ADAE_EdgeLoadAnalytics API | TS 23.436 | Ericsson |  | C3-242546 | CT3 #134
| UE to UE Performance Analytics API corrections | TS 23.436 | Nokia, Huawei |  | C3-243470 | CT3 #135
| Corrections on SS_ADAE_EdgeLoadAnalytics service | TS 23.436 | Huawei |  | C3-243308 | CT3 #135
| Corrections on SS_ADAE_LocationAccuracyAnalytics service | TS 23.436 | Huawei, Nokia |  | C3-243471 | CT3 #135
| Corrections on SS_ADAE_ServiceApiAnalytics service | TS 23.436 | Huawei |  | C3-243310 | CT3 #135
| Corrections on SS_ADAE_SlicePerformanceAnalytics service | TS 23.436 | Huawei, Nokia |  | C3-243469 | CT3 #135
| Corrections on SS_ADAE_SliceUsagePatternAnalytics service | TS 23.436 | Huawei, Nokia |  | C3-243472 | CT3 #135
| Corrections on SS_ADAE_VALPerformanceAnalytics service | TS 23.436 | Huawei |  | C3-243313 | CT3 #135

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; CT3 meeting # tdoc(s) # | Open issues | Comments
C3-242030 | Reply LS on A-DCCF, A-ADRF and ADAES services |  | CT3#134
C3-242031 | Reply LS on Issues related to ADAE server APIs |  | CT3#134

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; CT3 meeting # tdoc(s) # | Open issues | Comments
C3-240225 | LS on Issues related to ADAE server APIs | CT3#132
C3-240095 | LS on A-DCCF, A-ADRF and ADAES services | CT3#132