## Cover
3GPP TSG-CT3 Meeting #137 C3-245060 Hefei, China, 14 - 18 Oct, 2024
Source: CATT Title: Work Plan of eLSAPP Agenda item: 19.32 Document for: Information

## CT3
Stage 2 (SA6) Input |  |  | Stage 3 (CT3) Impacts
Meeting No. | Agreed Tdocs | Description | Specification | Contributing Company | Target Meeting No. | Agreed TDoc No. | Note
Work Task 1. Support of Geofencing
SA6#62 | S6-243704 Dynamic geofencing | 1. Enhance existing procedure (Monitoring Location Deviation procedure) | 29.549 | Ericsson | CT3#137
SA6#62 | S6-243715 Add Geofencing subscription/unsubscribe procedure | 1. Enhance existing procedure (Location area monitoring information procedure) | 29.549 | Huawei | CT3#138
SA6#62 | S6-243716 Add procedure of Geofencing UE(s) Information request/response | 1. Enhance existing procedure (Obtaining UE(s) information at a location). | 29.549 | CATT | CT3#137 |  | The existing location information already covers shape and coordinates information.
Work Task 2. Support of history tracing request or playback
SA6#62 | S6-243730 Add procedure of querying for history location | 1. New procedure (Location history querying procedure) | 29.549 | Huawei | CT3#138 |  | New API not defined by SA6
Work Task 3. Support location QoS improvement
SA6#62 | S6-243691 LMS reuse the stored UE location information | 1. Reuse existing procedures. | 29.549 | Huawei | CT3#138
SA6#62 | S6-243705 Target UE location provided by surrounding Ues | 1. Enhance existing procedures (On-demand location reporting procedure, Location information subscription procedure, Event-trigger location information notification procedure) . 2. New procedure (Surrounding UEs retrieval procedure). | 29.549 | Ericsson | CT3#137 CT3#138 |  | New API not defined by SA6
Work Task 4. Support location information exposure
SA6#62 | S6-243604 Support for adaptive location configuration and reporting | 1. Enhance existing procedure (Client-triggered or VAL server-triggered location reporting procedure) . 2. New procedure (SEAL location management server provides adaptive configuration). | 29.549 | Ericsson | CT3#137
SA6#62 | S6-243692 Exposure of value-added UE location information | 1. Enhance existing procedures (Location information subscription procedure, Event-trigger location information notification procedure) | 29.549 | CATT | CT3#137
SA6#62 | S6-243757 Support of Location-related UE Group Analytics | 1. New procedure (Procedure for Location-related UE Group Analytics) | 29.549 | Ericsson | CT3#138
Work Task 5. Support for ranging/sidelink positioning services
SA6#62 | S6-243756 Support of Collision Detection Analytics | 1. New procedure (Procedure for Collision Detection Analytics) | 29.549 | Ericsson | CT3#138
Work Task 6. Support of location services for multiple USIMs/UEs sharing the same location
Note: The progress status in SA6 is 30% after SA6#62.