## Tdoc cover sheet
3GPP TSG CT WG3 Meeting #137 Hefei, CN, 14th – 18th October, 2024 |  | C3-245170
Source: | Huawei
Title: | SEALDD_Ph2 WI CT3 Work Plan
Agenda item: | 19.33
Document for: | Agreement

## CT3
CT3 Work Plan - CT3#137 - 2024-10 - SEALDD_Ph2 WI (CP-242101)
# | Impact Description |  | Specification | Contributing company(ies) | Agreed Tdoc Numbers | Targeted CT3 meeting | Status
1. Updates to the SDD_Transmission API exposed by the SEALDD Server
1 | Support SEALDD enabled congestion monitoring for VAL applications |  | 29.548 | Huawei, Nokia |  | CT3#137 | Planned
2 | Support SEALDD client connection status monitoring for VAL applications |  | 29.548 | Ericsson |  | CT3#137 | Planned
3 | Corrections to SEALDD Flow terminology |  | 29.548 | Huawei |  | CT3#137 | Planned
2. Updates to the SDD_PolicyConfiguration API exposed by the SEALDD Server
4 | Support data transmission quality optimization policy provisioning and management |  | 29.548 | Ericsson |  | CT3#137 | Planned
5 | Support geofence policy provisioning and management |  | 29.548 | Nokia, Ericsson |  | CT3#137 | Planned
6 | Support temporal policy provisioning and management |  | 29.548 | Ericsson |  | CT3#138 | Planned
3. Updates to the SDD_DataStorage API exposed by the SEALDD Server
7 | Support the storage, retrieval and management of the same Application Data by multiple SEALDD Servers |  | 29.548 | Huawei |  | CT3#137 | Planned
4. Updates to the SDD_DDContext API exposed by the SEALDD Server
8 | Enhance the seamless SEALDD context transfer with content breakpoint information for downlink delivery |  | 29.548 | Huawei |  | CT3#137 | Planned
9 | Support ACR Event reporting (new stage 2 defined Sdd_InformACREvent to be merged into the SDD_DDContext API) |  | 29.548 | Ericsson |  | CT3#138 | Planned
5. Support Background Data Transfer (BDT) policy management
10 | New SDD_BDT Service API to support Background Data Transfer (BDT) policy management | Service and service operations description clauses | 29.548 | Ericsson |  | CT3#137 | Planned
11 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 | Ericsson |  | CT3#137 | Planned
12 |  | API resources and custom operations clauses | 29.548 | Ericsson |  | CT3#137 | Planned
13 |  | API notifications clauses | 29.548 | Ericsson |  | CT3#137 | Planned
14 |  | API data model clauses | 29.548 | Ericsson |  | CT3#137 | Planned
15 |  | OpenAPI description | 29.548 | Ericsson |  | CT3#137 | Planned
16 |  | Error handling, corrections, general clean-up and resolving ENs | 29.548 | Ericsson, Huawei, Nokia |  | CT3#138 onwards | Planned
17 | Updates to the SS_NetworkResourceAdaptation API exposed by the SEAL NRM Server to support the SEALDD Server as a new service consumer |  | 29.549 | Huawei |  | CT3#137 | Planned