## Cover sheet
RAN5#100 meeting | [8 empty] | R5-235454
Toulouse, France, August 21 - 25, 2023
Agenda Item: | 7.5.2
Source: | Vodafone
Title: | WP UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects)
Work item code: | UPIP_SEC_LTE-RAN-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
The objective of this work item is to enable UE conformance testing for Rel-17 User Plane Integrity Protection support for EPC connected architectures corresponding to the WID on UPIP_SEC_LTE-RAN-Core with Unique identifier 941111.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 62% (+37%) | 5 (+3) | 9
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE
NSA Option 3 (EN-DC) |  | 61.7% (+37.3%) | 5 (+3) | 9
FR1 |  | 61.7% (+37.3%) | 5 (+3) | 9
FR2 |  | 61.7% (+37.3%) | 5 (+3) | 9
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | [5 empty] | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 0% | [7 empty] | 0% |  |  | 0%
Common ICS | 38.508-2 | 100% | [7 empty] | 100% |  |  | 100%
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 55.6% (+33.3%) | 5 (+3) | 9 | [5 empty] | 55.6% (+33.3%) | 5 (+3) | 9 | 55.6% (+33.3%) | 5 (+3) | 9
Applicability Protocol test cases | 38.523-2 | 50% (+40%) | [7 empty] | 50% (+40%) |  |  | 50% (+40%)
Test suites (TTCN) | 38.523-3 | 100% (+100%) | [7 empty] | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-222372 | New WID on UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl.CT/SA Aspekts)
[2] RP-230070 | Revised WID on UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl.CT/SA Aspekts)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | UPIP_SEC_LTE-RAN-UEConTest
WP Scope: |  | The objective of this work item is to enable UE conformance testing for Rel-17 User Plane Integrity Protection support for EPC connected architectures corresponding to the WID on UPIP_SEC_LTE-RAN-Core with Unique identifier 941111.
WP Resp: |  | Petra Rauer |  |  | petra.rauer@vodafone.com | [5 empty] | WP item completion |  |  |  | LTE | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE | NSA Option 3 (EN-DC) |  |  | FR1 | FR2
[16 empty] | 61.7% (+37.3%) | 61.7% (+37.3%)
[15 empty] | 0 | 13 | 13
[15 empty] | 0 | 10.3 | 10.3
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | VOID | Table 4.6.1-19 RRCconnectionReconfiguration Command IE | Add default value for RRCConnectionReconfiguration Command IE (PDCP config IE for UPIP) |  |  |  | Default NAS message and information elements contents for UPIP | 0
2 |  | 36.508 | VOID | Integrity protection algorithm and key for UPIP | TS 36.331 clause 5.3.1.2: The integrity protection algorithm signalled in nr-RadioBearerConfig1/ nr-RadioBearerConfig2 for the DRBs configured to apply integrity protection of user data and keyToUse set to master as defined in TS 38.331 [82] is the same as the one signalled in securityAlgorithmConfig. | Huawei, HiSilicon |  | R5-230652 (withdrawn) | Author confirmed withdrawn, Not need to check the UPIP capability in UE network capability in every occurrence of the Attach Request and TAU Request. The check may be added to a specific EPS-UPIP L3 test case in the future. | 0
3 |  | 36.508 | VOID | UE network capability IE | Add UE network capability IE EPS-UPIP (octet4) according to TS 24.301 v17.6.0, clause 9.9.3.34 |  |  |  |  | 0
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
Layer 2
4 |  | 36.523-1 | VOID | User Plane Integrity Protection / Correct Funvctionality of User Plane Integrity Protection/Uplink | Integrity protection / Correct functionality of UP integrity protection TS.33.401, clause 7.3.3, 7.3.4 TS.36.331, clause 5.3.1.2, 6.3.3 | Huawei, HiSilicon |  | R5-230649 (withdrawn) | Author confirmed withdrawn, as 7.3.4.x could be covered by 7.1.3.2.x (PR:38.523-1) , so 7.3.4.x is not needed Check that uplink data is properly integrity protected | 0
5 |  | 36.523-1 | VOID | User Plane Integrity Protection / Correct Funvctionality of User Plane Integrity Protection/Downlink | Integrity protection / Correct functionality of UP integrity protection TS.33.401, clause 7.3.3, 7.3.4 TS.36.331, clause 5.3.1.2, 6.3.3 |  |  |  | Check that: a) Downlink data without integrity protection is discarded; b) Downlink data with incorrect integrity protection is discarded. | 0
RRC
6 |  | 36.523-1 | VOID | RRC connection establishment / Reception of SecurityModeCommand by the UE - UPIP | Test Purpose(s): <Describe test purpose(s)> Configuration of UPIP in field integrityProtectionAlgorithm in IE SecurityAlgorithmConfig in the TS 36.331 SecurityModeCommand message, and this is used to derive KUPint (and also to derive KUPEnc, as for legacy LTE UE). TS 36.331, clause 5.3.1.2, 5.3.4.3 |  |  |  |  | 0
7 |  | 36.523-1 | VOID | RRC connecton re-establishment / Reception of the RRCConnection Reestablishment by UE - UPIP | Test Purpose(s): <Describe test purpose(s)> TS 36.331, clause 5.3.1.2, 5.3.7.5 (RRCConReestabl) 2>if capable of user plane integrity protection: 3>derive the KUPint key associated with the previously configured integrity algorithm, as specified in TS 33.401 [32]; |  |  |  |  | 0
8 |  | 36.523-1 | VOID | RRC connection reconfiguration / Handover / Success / Reception of RRCConnctionReconfiguration including mobilityControlInfo by UE - UPIP | Test Purpose(s): <Describe test purpose(s)> TS 36.331, clause 5.3.1.2, 5.3.5.4 (handover): 3>if capable of user plane integrity protection: 4>derive the KUPint key associated with the integrityProtAlgorithm, as specified in TS 33.401 [32]; 3> if capable of user plane integrity protection: 4> derive the KUPint key associated with the current integrity algorithm, as specified in TS 33.401 [32]; |  |  |  | mismatch of UP IP policy (33.401, clause 7.3.3) | 0
9 |  | 36.523-1 | VOID | Inter-RAT mobility - Handover to E-UTRA - Reception of RRCConnection Reconfiguration by UE - UPIP | Test Purpose(s): <Describe test purpose(s)> TS 36.331, clause 5.3.1.2, 5.4.2.3 (RRCConReconf) 1> if capable of user plane integrity protection: 2> derive the KUPint key associated with the integrityProtAlgorithm, as specified in TS 33.401 [32]; |  |  |  | Including Handover from: a) non-UPIP to UPIP b) UPIP to UPIP c) UPIP to non-UPIP | 0
NAS
10 |  | 36.523-1 | VOID | User plane Integrity Protection / Correct functionality of User Plane Integrity Protection | Test Purpose(s): <Describe test purpose(s)> | Ericsson |  |  | Refer to 36.300; 14.1: An EN-DC capable UE supporting user plane integrity protection (see TS 24.301 [20]) when connected to E-UTRA/EPC (as specified in TS 33.401 [22]) shall support integrity protection for all DRBs (MN and SN terminated) at any data rate, up to and including the highest data rate supported by the UE for both UL and DL. When supported, user plane integrity protection with NR PDCP can be activated (on a per radio bearer basis) upon DRB addition. Refer to 36.300; 14.2: NOTE 1: User Plane Integrity Protection may be supported by UEs capable of EN-DC operation. This version of the specifications does not provide UPIP support for other UEs when using E-UTRA.
TS 36.523-2: Applicability for Protocol test cases
11 |  | 36.523-2 | VOID | Applicability for UE supporting user plane integrity protection when connected to E-UTRA/EPC (as specified in TS 33.401 | Add test case applicability statements for the new test cases introduced in 36.523-1 | Huawei, HiSilicon |  | R5-230650 (withdrawn) | Add test applicability for EPS UPIP TC Author confirmed withdrawn,as 7.3.4.x could be covered by 7.1.3.2.x, so 7.3.4.x is not needed
19 |  | 36.523-2 | VOID | Applicability for UE supporting user plane integrity protection when connected to E-UTRA/EPC (as specified in TS 33.401 | Add test case applicability statements for the new test cases introduced in 36.523-1 | Huawei, HiSilicon |  | R5-230651 (withdrawn) | Add PICS for EPS UPIP Author confirmed withdrawn, as PICS for EPS UPIP will move to 38.508-2 in the next meeting because this feature only apply for the EN-DC UE
TS 36.523-3: Protocol test suites (TTCN)
12 |  | 36.523-3 | VOID | Test model for Rel-17 EN-DC User Plane Integrity Protection | Introduction of test model for Rel-17 LTE User Plane Integrity Protection | MCC TF160 |  |  |  | 1
5GS
5GS Common
TS 38.508-1: Common test environment
TBD |  | 38.508-1 | <Clause> | UE network capability IE | Add UE network capability IE EPS-UPIP (octet4) according to TS 24.301 v17.6.0, clause 9.9.3.34 |  | RAN5#101 (Nov-23) |  | Check current spec whether test points need to be added! | 0.1 | 0% |  | 0% |  |  | 0% | 0%
TS 38.508-2: Common ICS
20 |  | 38.508-2 | A.4.3.7 | Add PICS for EPS UPIP General Capabilities Table A.4.3.7-1: UE General Capabilities | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei, HiSilicon | RAN5#101 (Nov-23) | R5-232965 |  | 0.1 | 100% |  | 100% |  |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Layer 2
13 | Y | 38.523-1 | 7.1.3.2.4 | Integrity protection / Correct functionality of UP integrity protection/Uplink | TS.33.401, clause 7.3.3, 7.3.4 TS.38.331, clause 6.3.2 (RRC information elements) TS.36.331, clause 5.3.1.2, 6.3.3 | ZTE | RAN5#101 (Nov-23) |  | Testpoints for EN-DC capable devices in LTE only environment need to be considered: 1. When EN-DC is in use: a) UPIP on DRB over NR, b) UPIP on DRB over E-UTRA (using NR PDCP). 2. When E-UTRA/EPC is in use: a) UPIP on DRB over E-UTRA (using NR PDCP). | 1 | 0% |  | 0% |  |  | 0% | 0%
14 | Y | 38.523-1 | 7.1.3.2.5 | Integrity protection / Correct functionality of UP integrity protection/Downlink | TS.33.401, clause 7.3.3, 7.3.4 TS.38.331, clause 6.3.2 (RRC information elements) TS.36.331, clause 5.3.1.2, 6.3.3 | ZTE | RAN5#101 (Nov-23) |  | Testpoints for EN-DC capable devices in LTE only environment need to be considered: 1. When EN-DC is in use: a) UPIP on DRB over NR, b) UPIP on DRB over E-UTRA (using NR PDCP). 2. When E-UTRA/EPC is in use: a) UPIP on DRB over E-UTRA (using NR PDCP). | 1 | 0% |  | 0% |  |  | 0% | 0%
25 | Y | 38.523-1 | 7.1.3.2.6 | Integrity protection / Correct functionality of UP integrity protection/multipe DRB | Refer to 36.300; 14.1: An EN-DC capable UE supporting user plane integrity protection (see TS 24.301 [20]) when connected to E-UTRA/EPC (as specified in TS 33.401 [22]) shall support integrity protection for all DRBs (MN and SN terminated) at any data rate, up to and including the highest data rate supported by the UE for both UL and DL. When supported, user plane integrity protection with NR PDCP can be activated (on a per radio bearer basis) upon DRB addition. | Ericsson | RAN5#101 (Nov-23) | R5-235380 | This test case was in NAS (36.523-1) before, proposed to move to Layer 2. | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100% | 100%
RRC
15 | Y | 38.523-1 | 8.1.2.1.7 | RRC reconfiguration / DRB / Addition of DRB / User Plane Integrity Protection | TS.38.331 5.3.5.6.5 3> else (i.e., UE connected to NR or UE connected to E-UTRA/EPC (in EN-DC or capable of EN-DC)): 4> if the PDCP entity of this DRB is not configured with cipheringDisabled: 5> configure the PDCP entity with the ciphering algorithm and KUPenc key associated with the master key (KeNB/ KgNB) or the secondary key (S-KgNB/S-KeNB), as indicated in keyToUse, i.e. the ciphering configuration shall be applied to all subsequent PDCP PDUs received and sent by the UE; 4> if the PDCP entity of this DRB is configured with integrityProtection: 5> configure the PDCP entity with the integrity protection algorithms according to securityConfig and apply the KUPint key associated with the master key (KeNB/KgNB) or the secondary key (S-KgNB) as indicated in keyToUse; | ZTE | RAN5#101 (Nov-23) |  | Refer to 38.331: PDCP config - Adding DRB | 1 | 0% |  | 0% |  |  | 0% | 0%
16 | Y | 38.523-1 | 8.2.2.1.3 | SRB3 Establishment, Reconfiguration and Release / NR addition, modification and release / EN-DC / User Plane Integrity Protection | TS.38.331 5.3.5.6.5 | ZTE | RAN5#101 (Nov-23) |  | Refer to 38.331: PDCP config - Adding DRB | 1 | 0% |  | 0% |  |  | 0% | 0%
|  | 38.523-1 | 8.2.6.4 | UPIP / RRC connection
21 | Y | 38.523-1 | 8.2.6.4.1 | UPIP / RRC connection establishment / Reception of SecurityModeCommand by the UE | Test Purpose(s): <Describe test purpose(s)> Configuration of UPIP in field integrityProtectionAlgorithm in IE SecurityAlgorithmConfig in the TS 36.331 SecurityModeCommand message, and this is used to derive KUPint (and also to derive KUPEnc, as for legacy LTE UE). TS 36.331, clause 5.3.1.2, 5.3.4.3 | Vodafone | RAN5#101 (Nov-23) | R5-235379 | Check testpoints of existing testcases in Layer 2 test cases 7.1.3.2.x Note: EPC related EN-DC test cases have been specified in TS 38.523-1 clause 10.2: | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100% | 100%
22 | Y | 38.523-1 | 8.2.6.4.2 | UPIP / RRC connecton re-establishment / Reception of the RRCConnection Reestablishment by UE | Test Purpose(s): <Describe test purpose(s)> TS 36.331, clause 5.3.1.2, 5.3.7.5 (RRCConReestabl) 2>if capable of user plane integrity protection: 3>derive the KUPint key associated with the previously configured integrity algorithm, as specified in TS 33.401 [32]; | Huawei, HiSilicon | RAN5#101 (Nov-23) | R5-233391 | Check testpoints of existing testcases. Note: EPC related EN-DC test cases have been specified in TS 38.523-1 clause 10.2: | 1 | 100% |  | 100% |  |  | 100% | 100%
23 | Y | 38.523-1 | 8.2.6.4.3 | UPIP / RRC connection reconfiguration / Handover / Success / Reception of RRCConnctionReconfiguration including mobilityControlInfo by UE | Test Purpose(s): <Describe test purpose(s)> TS 36.331, clause 5.3.1.2, 5.3.5.4 (handover): 3>if capable of user plane integrity protection: 4>derive the KUPint key associated with the integrityProtAlgorithm, as specified in TS 33.401 [32]; 3> if capable of user plane integrity protection: 4> derive the KUPint key associated with the current integrity algorithm, as specified in TS 33.401 [32]; | Huawei, HiSilicon | RAN5#101 (Nov-23) | R5-233392 R5-234474 | Check testpoints of existing testcases. Note: EPC related EN-DC test cases have been specified in TS 38.523-1 clause 10.2: mismatch of UP IP policy (33.401, clause 7.3.3) | 1 | 100% |  | 100% |  |  | 100% | 100%
24 | Y | 38.523-1 | 8.2.6.4.4 | UPIP / Inter-RAT mobility / Handover to E-UTRA / Reception of RRCConnection Reconfiguration by UE | Test Purpose(s): <Describe test purpose(s)> TS 36.331, clause 5.3.1.2, 5.4.2.3 (RRCConReconf) 1> if capable of user plane integrity protection: 2> derive the KUPint key associated with the integrityProtAlgorithm, as specified in TS 33.401 [32]; | Vodafone | RAN5#101 (Nov-23) | R5-235381 | Check testpoints of existing testcases. Note: EPC related EN-DC test cases have been specified in TS 38.523-1 clause 10.2: Including Handover from: a) non-UPIP to UPIP b) UPIP to UPIP c) UPIP to non-UPIP | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
17 |  | 38.523-2 | 4.1 | Applicability for UE supporting user plane integrity protection when connected to E-UTRA/EPC | Add test case applicability statements for the new test cases introduced in 38.523-1 | Huawei, HiSilicon | RAN5#101 (Nov-23) | R5-233393 R5-234475, R5-234806, R5-235382 |  | 0.1 | 50% (+40%) |  | 50% (+40%) |  |  | 50% | 50%
TS 38.523-3: Protocol test suites (TTCN)
18 |  | 38.523-3 | 5.1.1.1 | Test model for Rel-17 EN-DC User Plane Integrity Protection | Introduction of test model for Rel-17 EN-DC User Plane Integrity Protection | MCC TF160 | RAN5#101 (Nov-23) | R5-235451 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.