## Cover sheet
3GPP TSG-RAN WG5 Meeting #100-e | [10 empty] | R5-233937
Toulouse, France, 21st Aug 2023 - 25th Aug 2023
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP - UE Conformance - Multi-SIM devices for LTE/NR
Work item code: | LTE_NR_MUSIM_plus_CT1-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
This work item covers the protocol conformance testing for Rel-17 LTE/NR Multi-SIM devices
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+100%) | 13 (+13) | 14 (+14)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+100%) | 6 (+6) | 7 (+7)
FR1 |  | 100% (+100%) | 6 (+6) | 7 (+7)
FR2 |  | 100% (+100%) | 6 (+6) | 7 (+7)
LTE |  | 100% (+100%) | 7 (+7) | 7 (+7)
FDD |  | 100% (+100%) | 7 (+7) | 7 (+7)
TDD |  | 100% (+100%) | 7 (+7) | 7 (+7)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% (+100%) | [9 empty] | 100% (+100%) |  |  | 100% (+100%)
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 100% (+100%) | 7 (+7) | 7 (+7) | [7 empty] | 100% (+100%) | 7 (+7) | 7 (+7) | 100% (+100%) | 7 (+7) | 7 (+7)
Applicability Protocol test cases | 36.523-2 | 100% (+100%) | [9 empty] | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
UE specific test functions | 38.509 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+100%) | 6 (+6) | 7 (+7) | 100% (+100%) | 6 (+6) | 7 (+7) | 100% (+100%) | 6 (+6) | 7 (+7)
Applicability Protocol test cases | 38.523-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-230079 | Revised WID on UE Conformance - Multi-SIM devices for LTE/NR, China Telecom
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Multi-SIM devices for LTE/NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NR_MUSIM_plus_CT1-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-17 Multi-SIM devices for LTE/NR(UID=950060) | [13 empty] | vs Area
WP Resp: |  | Jing Zhao，China Telecom |  |  | zhaoj16@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | FDD | TDD
[15 empty] | 98.1% (+98.1%) | 98.1% (+98.1%) | 100% (+100%) | 100% (+100%)
[15 empty] | 13 (+13) | 13 (+13) | 11 (+11) | 11 (+11)
[15 empty] | 9.4 (+9.4) | 9.4 (+9.4) | 7.9 (+7.9) | 7.9 (+7.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
1 |  | 36.508 | 4.7 | General and Signaling Test Environment for LTE Rel-17 MUSIM testing | Add changes to default messages | China Telecom | RAN5#96 (Aug-22) | R5-225324 R5-232055 | zhaoj16@chinatelecom.cn | 0.25 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
2 |  | 36.508 |  | USIM configuration and general test procedure for registration for Rel-17 LTE Multi-SIM testing |  | Qualcomm | RAN5#96 (Aug-22) | R5-227476 R5-227477 | bcheruvu@QTI.QUALCOMM.COM | 0.25 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NAS
3 | Y | 36.523-1 | 9.2.1.1.32 | Attach / Success / MUSIM | ****TP1: [TS 24,301: 5.5.1.2.2]**** WITH : MUSIM UE is switched-off with two valid USIMs inserted WHEN: the UE is powered on. THEN: the UE transmits ATTACH REQUEST message and sets one or more MUSIM feature bits in UE network capability IE to "supported" individually with cell1 and cell2 which belong to different PLMNs (i.e. NAS signalling connection release, paging indication for voice services, reject paging request, paging restriction the paging timing collision control) | China Telecom | RAN5#96 (Aug-22) | R5-224199 R5-231520 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
4 | Y | 36.523-1 | 9.2.1.1.33 | Attach / Success / MUSIM / IMSI offset | ****TP1: [TS 24,301: 5.5.1.2.4]**** WITH: UE has sent an ATTACH REQUEST message containing the Requested IMSI offset IE WHEN: the UE receives the Negotiated IMSI offset IE in the ATTACH ACCEPT message THEN: the UE receives a paging message in a valid new paging occasion which calculated based on the Negotiated IMSI offset ****TP2: [TS 24,301: 5.5.1.2.4]**** WITH: UE has transmited ATTACH REQUEST message containing the Requested IMSI offset IE WHEN: the UE receives the ATTACH ACCEPT message without Negotiated IMSI offset IE THEN: the UE receives a paging message in a valid old paging occasion which calculated without any IMS offset. | CATT | RAN5#96 (Aug-22) | R5-230958 R5-234933 | chenxiaozhong@catt.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
5 | Y | 36.523-1 | 9.2.3.1.29 | Normal Tracking Area Update / Accepted / MUSIM | ****TP1: [TS 24,301: 5.5.3.2.2]**** WITH: UE in state EMM-REGISTERED and EMM-IDLE mode WHEN: the UE detects entering a new tracking area not included in the TAI list THEN: the UE transmits TRACKING AREA UPDATE REQUEST message and sets one or more MUSIM feature bits in UE network capability IE to "supported"(i.e. the NAS signalling connection release, the paging indication for voice services, the reject paging request, the paging restriction and the paging timing collision control) | China Telecom | RAN5#96 (Aug-22) | R5-224374 R5-231517 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
6 | Y | 36.523-1 | 9.2.3.1.30 | Normal Tracking Area Update / Accepted / MUSIM / NAS signalling connection release | ****TP1: [TS 24,301: 5.5.3.2.2]**** WITH: UE in EMM-CONNECTED state and UE has transmitted an TRACKING AREA UPDATE REQUEST with Request type is "NAS signalling connection release" in the UE request type IE and the "active" flag is 0 in the EPS update type IE WHEN: the UE receive TRACKING AREA UPDATE ACCEPT message with NAS signalling connection release bit is "NAS signalling connection release supported" in the EPS network feature support IE THEN: the UE enters the state EMM-REGISTERED | China Telecom | RAN5#97 (Nov-22) | R5-231516 R5-234940 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
7 | Y | 36.523-1 | 9.2.3.1.31 | /Normal Tracking Area Update / Accepted / MUSIM / IMSI offset | ****TP1: [TS 24,301: 5.5.3.2.4]**** WITH: The UE has transmitted TRACKING AREA UPDATE REQUEST message with the Requested IMSI offset IE and EPS update type IE not indicating "periodic updating" WHEN: The UE receives a TRACKING AREA UPDATE ACCEPT message with the Negotiated IMSI offset IE and a new GUTI THEN: The UE transmits the TRACKING AREA UPDATE COMPLETE message and receives a paging message in a valid new paging occasion which calculated based on the Negotiated IMSI offset ****TP2: [TS 24,301: 5.5.3.2.4]**** WITH: The UE has transmitted TRACKING AREA UPDATE REQUEST message with the Requested IMSI offset IE and EPS update type IE not indicating "periodic updating" WHEN: The UE receives a TRACKING AREA UPDATE ACCEPT message without the Negotiated IMSI offset IE THEN:The UE transmits the TRACKING AREA UPDATE COMPLETE message and receives a paging message in a valid old paging occasion which calculated without any IMS offset. | CATT | RAN5#96 (Aug-22) | R5-231523 R5-234953 | chenxiaozhong@catt.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
8 | Y | 36.523-1 | 9.3.1.19 | Service Request / MUSIM / NAS signalling connection release | ****TP1: [TS 24,301: 5.6.1.4.1]**** WITH : UE in EMM-CONNECTED state and has transmitted an EXTENDED SERVICE REQUEST message and set the Request type to "NAS signalling connection release" in the UE request type IE and Service type to "packet services via S1" WHEN:the UE received SERVICE ACCEPT message THEN: the UE enters the state EMM-REGISTERED | China Telecom | RAN5#97(Nov-22) | R5-231515 R5-235312 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
9 | Y | 36.523-1 | 9.3.1.20 | Service Request / MUSIM / Rejection of paging | ****TP1: [TS 24,301: 5.6.1.4.1 5.6.2.2.1.1]**** WITH : UE in EMM-IDLE state and has transmitted an EXTENDED SERVICE REQUEST message and set the Request type to "Rejection of paging" in the UE request type IE and Service type to "packet services via S1" WHEN: the UE receives SERVICE ACCEPT message THEN: the UE enters the state EMM-REGISTERED | CATT | RAN5#97(Nov-22) | R5-231522 R5-234957 | chenxiaozhong@catt.cn | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
TS 36.523-2: Applicability for Protocol test cases
10 |  | 36.523-2 | 4 | <Title> | Add Applicability Conditions for new LTE Multi-SIM test cases | China Telecom,CATT | RAN5#99(May-23) | R5-224373 R5-231518 R5-231524 | zhaoj16@chinatelecom.cn | 0.2 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
11 |  | 36.523-2 | A.4 | <Title> | Add ICS for the new test cases introduced in 36.523-1 | China Telecom,CATT | RAN5#99(May-23) | R5-224373 R5-231518 R5-231524 | zhaoj16@chinatelecom.cn | 0.2 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
12 |  | 38.508-1 | 4.7 | General and Signaling Test Environment for Rel-17 NR Multi-SIM testing | Add changes to default messages | China Telecom | RAN5#98（Feb-23） | R5-231519 R5-233142 | covered by general CR R5-225179 | 0.25 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
13 |  | 38.508-1 | 4.9/6.4 | USIM configuration and general test procedure for registration for Rel-17 NR Multi-SIM testing | Add changes to default messages | Qualcomm | RAN5#98（Feb-23） | R5-227476 R5-227477 R5-231519 | bcheruvu@QTI.QUALCOMM.COM | 0.25 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
14 |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-17 NR Multi-SIM testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | China Telecom | RAN5#98（Feb-23） | R5-224288, R5-231513 R5-233904 | zhaoj16@chinatelecom.cn | 0.5 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
RRC
15 | Y | 38.523-1 | 8.1.5.10.2 | UE Assistance Information / MUSIM | ****TP1: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information for leaving RRC_CONNECTED and timer T346g is not running THEN: The UE transmits a UEAssistanceInformation message ****TP2: [TS 38.331: 5.7.4.2]**** With UE in NR RRC_CONNECTED state When UE configured to provide MUSIM assistance information for leaving RRC_CONNECTED and timer T346g is running then { the UE Dose NOT transmit a UEAssistanceInformation message } ****TP3: [TS 38.331: 5.7.4.2]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE configured to provide MUSIM assistance information without leaving RRC_CONNECTED and the current musim-GapPreferenceList is different from the one indicated in the last transmission of the UEAssistanceInformation message including musim-GapPreferenceList THEN: The UE transmits a UEAssistanceInformation message | China Telecom | RAN5#98（Feb-23） | R5-233469 R5-233905 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
16 | Y | 38.523-1 | 8.1.5.10.3 | UE Assistance Information / MUSIM / Leaving RRC_CONNECTED / T346g expires | ****TP1: [TS 38.331: 5.7.4.3]**** WITH: UE has transmitted the UEAssistanceInformation message with ”musim-PreferredRRC-State“ in MUSIM-Assistance-r17 IE that it prefers to idle state WHEN: UE did not receive a response from the network until t346g expires THEN: UE autonomously leaves RRC_CONNECTED state and enters RRC_IDLE with release cause 'other' | CATT | RAN5#98（Feb-23） | R5-231521 R5-233470 | chenxiaozhong@catt.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
17 | Y | 38.523-1 | 8.1.2.1.6 | RRC reconfiguration/ MUSIM / MUSIM- gap / Addition / Modification / Release | ****TP1: [TS 38.331: 5.3.5.3]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE receives the RRCReconfiguration message includes the musim-GapConfig with periodic musim-GapID involved in musim-GapToAddModList and the gap configuration is active in SS1 THEN: UE stops all interworking with SS1 during the configured gaps periodically ****TP2: [TS 38.331: 5.3.5.3]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE receives the RRCReconfiguration message includes the musim-GapConfig with periodic musim-GapID involved in musim-GapToAddModList and an entry is matched with musim-GapID that exists in the musim-GapConfigLis in SS1 THEN: UE stops all interworking with SS1 during the replaced new configured gaps periodically ****TP3: [TS 38.331: 5.3.5.3]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE receives the RRCReconfiguration message includes the musim-GapConfig with periodic musim-GapID involved in musim-GapToReleaseList in SS1 THEN: UE performs normal interworking with SS1 during the released gaps periodically ****TP4: [TS 38.331: 5.3.5.3]**** WITH: UE in NR RRC_CONNECTED state WHEN: UE receives the RRCReconfiguration message includes the musim-GapConfig with musim-AperiodicGap-r17 THEN: UE stops all interworking with SS1 temporarily with configuration MUSIM-GapInfo-r17 | China Telecom | RAN5#99（May-23） | R5-231514 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
NAS
18 | Y | 38.523-1 | 9.1.5.1.16 | Initial Registration / Success / MUSIM | ****TP1: [TS 24,501: 5.5.1.2.2]**** WITH : The MUSIM UE is switched-off with two valid USIMs inserted WHEN: The UE is powered on. THEN: MUSIM UE transmits REGISTRATION REQUEST message and sets one or more MUSIM feature bits in 5GMM capability IE to "supported" individually with cell1 and cell2 which belong to different PLMNs (i.e. NAS signalling connection release, paging indication for voice services, reject paging request, paging restriction) | Qualcomm | RAN5#97(Nov-22) | R5-227478 R5-233143 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
19 | Y | 38.523-1 | 9.1.5.2.10 | Mobility registration update / MUSIM / NAS signalling connection release | ****TP1: [TS 24,501: 5.5.1.3.2 5.5.1.3.4]**** WITH: UE was configured to release the NAS connnection and transmits REGISTRATION REQUEST message with UE request type IE was set as "NAS signalling connection release" and the Follow-on request indicator to "No follow-on request pending" WHEN: UE receives REGISTRATION ACCEPT message with "N1 NAS signalling connection release supported" " in the 5GS network feature support IE THEN: the UE enters the 5GMM-REGISTERED or 5GMM-IDLE state | Qualcomm | RAN5#99（May-23） | R5-230547 R5-235070 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
20 | Y | 38.523-1 | 9.1.7.3 | Service request / MUSIM / NAS signalling connection release | ****TP1: [TS 24,501: 5.6.1.4.1]**** WITH: UE in state 5GMM-CONNECTED. The UE has transmitted an SERVICE REQUEST message and set the Request type to "NAS signalling connection release" in the UE request type IE WHEN: UE receives SERVICE ACCEPT message THEN:After the completion of the Service Request procedure, The UE enters the state 5GMM-REGISTERED | Qualcomm | RAN5#99（May-23） | R5-230548 R5-233145 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
21 | Y | 38.523-1 | 9.1.7.4 | Service request / MUSIM / Rejection of paging | ****TP1: [TS 24,501: 6.4.1.4.2]**** WITH: The UE in state5GMM-IDLE and has transmitted an SERVICE REQUEST message and set the Request type to "Rejection of paging" in the UE request type IE and service type to "mobile terminated services" WHEN: UE receives SERVICE ACCEPT message THEN:UE enters the state 5GMM-REGISTERED | Qualcomm | RAN5#97(Nov-22) | R5-227479 R5-233144 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
22 |  | 38.523-2 | 4.1 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | China Telecom,CATT,Qualcomm | RAN5#99(May-23) | R5-227312 R5-230546 R5-230991 R5-232038 | zhaoj16@chinatelecom.cn | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
23 |  | 38.523-2 | 4.2 | <Title> | Add Applicability Condition for new NR Multi-SIM test cases | China Telecom,CATT,Qualcomm | RAN5#99(May-23) | R5-227312 R5-230546 R5-230991 R5-232038 | zhaoj16@chinatelecom.cn | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.509 Test function
24 |  | 38.509 |  | Introduction for Test function for MUSIM UAI features. |  | China Telecom | RAN5#99(May-23) | R5-233380 | zhaoj16@chinatelecom.cn | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | R5-232199 |  | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.