## Cover sheet
3GPP TSG-RAN WG5 Meeting #100 | [10 empty] | R5-233939
Toulouse, France, 21st Aug 2023 - 25th Aug 2023
Agenda Item: | 7.4.2
Source: | China telecom
Title: | UE Conformance - IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS
Work item code: | ING_5GS-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
This work item covers the protocol conformance testing for IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 2 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 2 (+2)
FR1 |  | 5% (+5%) | 0 | 2 (+2)
FR2 |  | 5% (+5%) | 0 | 2 (+2)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 2 (+2) | 0% | 0 | 2 (+2) | 0% | 0 | 2 (+2)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-230873 | New WID on UE Conformance - IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | ING_5GS-UEConTest
WP Scope: |  | UE Conformance test for IMS voice service support and network usability guarantee when UE’s E-UTRA capability is disabled in 5GS | [12 empty] | vs Area
WP Resp: |  | Jing Zhao，China Telecom |  |  | zhaoj16@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 5% (+5%) | 5% (+5%)
[14 empty] | 5 (+5) | 5 (+5)
[14 empty] | 3.2 (+3.2) | 3.2 (+3.2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | General and Signaling Test Environment for No E-UTRA Disabling In 5GS | Add changes to default messages | China Telecom | RAN5#101 (Dec-23) |  |  | 0.2 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for No E-UTRA Disabling In 5GS | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | China Telecom | RAN5#101 (Dec-23) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Multi-layer
1 | Y | 38.523-1 | 11.1.10 | MO MMTEL voice call setup from NR RRC_IDLE / EPS Fallback with redirection / Single registration mode with N26 interface / No E-UTRA Disabling In 5GS/ attach attempt counter is equal to 5/Success | ****TP1: [TS 24.301: 5.5.1.2.6]**** WITH: UE supporting both S1 mode and N1 mode and is switched on without NR coverage but with very poor LTE coverage When：attach attempt counter is equal to 5 and then UE moves back to a good coverage with both NR and LTE network THEN: UE enable the E-UTRA capability and UE in NR RRC_IDLE state ****TP2: [TS 24.301: 5.5.1.2.6]**** With:UE in NR RRC_IDLE state and operating in single-registration mode and the Network having indicated "interworking without N26 interface not supported" and the UE in NR RRC_IDLE state When:UE initiates an MMTEL call Then: UE enable the E-UTRA capability and UE in NR RRC_IDLE state | Qualcomm | RAN5#101 (Dec-23) |  | yogesht@qti.qualcomm.com | 1 | 0% | 0% |  | 0% | 0%
2 | Y | 38.523-1 | 11.1.11 | MO MMTEL voice call setup from NR RRC_IDLE / EPS Fallback with redirection / Single registration mode with N26 interface / No E-UTRA Disabling In 5GS/ tracking area updating attempt counter is equal to 5/Success | ****TP1: [TS 24.301: 5.5.1.3.6,5.5.3.2.6]**** WITH: UE supporting both S1 mode and N1 mode and is switched on without NR coverage but with good LTE coverage When：UE moves to a poor LTE coverage and performs TAU, tracking area updating attempt counter is equal to 5 and then UE moves back to a good coverage with both NR and LTE network THEN: UE enable the E-UTRA capability and UE in NR RRC_IDLE state ****TP2: [TS 24.301: 5.5.1.3.6,5.5.3.2.6]**** With:UE in NR RRC_IDLE state and operating in single-registration mode and the Network having indicated "interworking without N26 interface not supported" and the UE in NR RRC_IDLE state When:UE initiates an MMTEL call Then: UE requests the establishment of an MMTEL call by transmitting an RRCSetupRequest message with establishmentCause set to 'mo-VoiceCall' and a SERVICE REQUEST message with Service type set to 'data' | China Telecom | RAN5#102 (Feb-24) |  | zhaoj16@chinatelecom.cn | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. | China Telecom，Qualcomm | RAN5#102 (Feb-24) |  | zhaoj16@chinatelecom.cn | 0.5
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | China Telecom，Qualcomm | RAN5#102 (Feb-24) |  | zhaoj16@chinatelecom.cn | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.