## Cover sheet
3GPP TSG-RAN WG5 Meeting #100 | [10 empty] | R5-234717
Toulouse, France, Aug 21st - Aug 25th, 2023
Agenda Item: | 7.5.2
Source: | CMCC
Title: | WP-UE Conformance - Enhancement of RAN slicing for NR plus CT1 aspects
Work item code: | NR_slice-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
This work item covers the protocol conformance testing for Rel-17 enhancement of RAN slicing for NR.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 98% (+10%) | #VALUE! | #VALUE!
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 97.9% (+9.6%) | #VALUE! | #VALUE!
FR1 |  | 100% (+11.7%) | 8 (+1) | 8
FR2 |  | 95.8% (+7.5%) | 4 (-3) | 8
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 97.5% (+10%) | 4 (+4) | 8 (+8) | 100% (+12.5%) | 8 (+1) | 8 | 95% (+7.5%) | 4 (-3) | 8
Applicability Protocol test cases | 38.523-2 | 100% (+55%) |  |  | 100% (+55%) |  |  | 100% (+55%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-221364 | New WID - UE Conformance - Enhancement of RAN slicing for NR
[2] RP-223067 | Revised WID - UE Conformance - Enhancement of RAN slicing for NR plus CT1 aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP-UE Conformance - Enhancement of RAN slicing for NR plus CT1 aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_slice-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-17 Enhancement of RAN slicing for NR plus CT1 aspects (UID-960078) | [12 empty] | vs Area
WP Resp: |  | Danni Song，CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 100% (+11.7%) | 95.8% (+7.5%)
[14 empty] | 12 | 12
[14 empty] | 9 | 9
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | <Title of task> | General and Signaling Test Environment for Rel-17 RAN slicing testing | CMCC | RAN5#98 (Feb-23) | R5-225356, R5-225357, R5-227542, R5-233379 | hanaitong@chinamobile.com | 0.5 | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | <Clause> | <Title> | Introduction of common implementation conformance statements for Rel-17 RAN slicing | CMCC | RAN5#97 (Nov-22) | R5-224593, R5-231270 | hanaitong@chinamobile.com | 0.3 | 100% | 100% |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
3 |  | 38.523-1 | 6.1.2 | NG-RAN Only Cell Selection | [5 empty] | TBD
4 | Y | 38.523-1 | 6.1.2.24 | Slice-based cell reselection / Reselection priorities provided by SIB16 | **** TP1: [Ref: 38.304 clause 5.2.4.11] WITH: UE supporting slice-based cell reselection and in NR RRC_IDLE state WHEN: UE detects the cell reselection criteria is met for two cells on different frequencies supporting different NAS-provided NSAG priorities THEN: UE reselects to the cell on the frequency which supports higher priority NSAG **** TP2: [Ref: 38.304 clause 5.2.4.11] WITH: UE supporting slice-based cell reselection and in NR RRC_IDLE state WHEN: UE detects the cell reselection criteria is met for two cells on different frequencies supporting same NAS-provided NSAG priority THEN: UE reselects to the cell on the frequency which supports the NSAG having higher nsag-CellReselectionPriority | CMCC | RAN5#100 (Aug-23) | R5-231555, R5-233421, R5-234721 | hanaitong@chinamobile.com Incomplete due to FR2 power level issue. | 1 | 95% (-5%) | 95% (-5%) |  | 100% | 90%
5 | Y | 38.523-1 | 6.1.2.25 | Slice-based cell reselection / Re-derive reselection priority for frequency | **** TP1: [Ref: 38.304 clause 5.2.4.5, 5.2.4.11] WITH: UE supporting slice-based cell reselection and in NR RRC_IDLE state WHEN: UE detects the cell on the highest priority frequency supporting NSAG is listed in the sliceExcludedCellListNR of this NSAG THEN: UE does not attempt to reselect to the cell listed in the sliceExcludedCellListNR **** TP2: [Ref: 38.304 clause 5.2.4.5, 5.2.4.11] WITH: UE supporting slice-based cell reselection and in NR RRC_IDLE state WHEN: UE detects the cell on the highest priority NR frequency supporting NSAG is listed in the sliceExcludedCellListNR THEN: UE re-derive a reselection priority for the frequency by considering other NSAG(s) supported by this cell | CATT | RAN5#100 (Aug-23) | R5-233420 | chenxiaozhong@catt.cn Incomplete due to FR2 power level issue. | 1 | 95% (-5%) | 95% (-5%) |  | 100% | 90%
6 |  | 38.523-1 | 6.4.2 | Cell Selection/Qrxlevmin & Cell Reselection (Intra NR in RRC_INACTIVE state) | [5 empty] | TBD
7 | Y | 38.523-1 | 6.4.2.3 | Slice-based cell reselection in RRC_INACTIVE state / Reselection priorities provided by SIB16 | **** TP1: [Ref: 38.304 clause 5.2.4.11] WITH: UE supporting slice-based cell reselection and in NR RRC_INACTIVE state WHEN: UE detects the cell reselection criteria is met for two cells on different frequencies supporting different NAS-provided NSAG priorities THEN: UE reselects to the cell on the frequency which supports higher priority NSAG and remains in RRC_INACTIVE state **** TP2: [Ref: 38.304 clause 5.2.4.11] WITH: UE supporting slice-based cell reselection and in NR RRC_INACTIVE state WHEN: UE detects the cell reselection criteria is met for two cells on different frequencies supporting same NAS-provided NSAG priority THEN: UE reselects to the cell on the frequency which supports the NSAG having higher nsag-CellReselectionPriority and remains in RRC_INACTIVE state | CMCC | RAN5#100 (Aug-23) | R5-231556, R5-233422, R5-234722 | hanaitong@chinamobile.com Incomplete due to FR2 power level issue. | 1 | 95% (-5%) | 95% (-5%) |  | 100% | 90%
Layer 2
8 |  | 38.523-1 | 7.1.1.1 | Random Access Procedures | [5 empty] | TBD
9 | Y | 38.523-1 | 7.1.1.1.11 | Random access procedure / Successful/ Slice specific RACH configuration | **** TP1: [Ref: 38.321 clause 5.1] WITH: UE in NR RRC_IDLE state and starts Random Access procedure WHEN: SS configures NSAG indicator and associated set of preambles in FeatureCombinationPreambles in SIB1 THEN: UE transmits a random access preamble using the slice specific random access resource | Lenovo/Motorola Mobility | RAN5#100 (Aug-23) | R5-231261, R5-232179 | rasheed@motorola.com<rasheed@motorola.com> | 1 | 100% | 100% |  | 100% | 100%
10 | Y | 38.523-1 | 7.1.1.1.12 | Random access procedure / Successful/ ra-PrioritizationForSlicing | **** TP1: [Ref: 38.321 clause 5.1.1a] WITH: UE in NR RRC_IDLE state and starts Random Access procedure WHEN: SS configures both ra-PrioritizationForSlicing for a NSAG identity and ra-PrioritizationForAccessIdentity in SIB1 and set enableRA-PrioritizationForSlicing to TRUE THEN: UE uses powerRampingStepHighPriority and scalingFactorBI configured in the ra-PrioritizationForSlicing for Random Access procedure **** TP2: [Ref: 38.321 clause 5.1.1a, 5.1.4] WITH: UE in RRC_Connected state after transmission of a PRACH preamble on NR SpCell WHEN: SS configures scalingFactorBI in ra-PrioritizationForSlicing for a NSAG identity in SIB1 and sends a Random Access Response including a Backoff Indicator with the Random Access Preamble identifier different from the value received from the UE THEN: UE triggers RA preamble after a random time between 0 and the indicated Backoff parameter multiplied with scalingFactorBI configured in the ra-PrioritizationForSlicing | Lenovo/Motorola Mobility | RAN5#100 (Aug-23) | R5-231262, R5-232180 | rasheed@motorola.com<rasheed@motorola.com> | 1 | 100% | 100% |  | 100% | 100%
11 | Y | 38.523-1 | 7.1.1.1.13 | Random access procedure / Successful / Slice specific RACH configuration / 2-step RACH | **** TP1: [Ref: 38.321 clause 5.1] WITH: UE in NR RRC_IDLE state and starts Random Access procedure WHEN: SS configures NSAG indicator and associated set of preambles in FeatureCombinationPreambles in RACH-ConfigCommonTwoStepRA in SIB1 THEN: UE transmits a MSGA including random access preamble using the slice specific random access resource | Lenovo/Motorola Mobility | RAN5#100 (Aug-23) | R5-231263, R5-232181 | rasheed@motorola.com<rasheed@motorola.com> | 1 | 100% | 100% |  | 100% | 100%
12 | Y | 38.523-1 | 7.1.1.1.14 | Random access procedure / Successful/ ra-PrioritizationForSlicingTwoStep / 2-step RACH | **** TP1: [Ref: 38.321 clause 5.1.1a] WITH: UE in NR RRC_IDLE state and starts Random Access procedure WHEN: SS configures both ra-PrioritizationForSlicingTwoStep for a NSAG identity and ra-PrioritizationForAccessIdentityTwoStep in SIB1 and set enableRA-PrioritizationForSlicing to TRUE THEN: UE uses powerRampingStepHighPriority and scalingFactorBI configured in the ra-PrioritizationForSlicing for Random Access procedure **** TP2: [Ref: 38.321 clause 5.1.1a, 5.1.4] WITH: UE in RRC_Connected state after transmission of a MSGA on NR SpCell WHEN: SS configures scalingFactorBI in ra-PrioritizationForSlicingTwoStep for a NSAG identity in SIB1 and sends a MSGB including a Backoff Indicator with the Random Access Preamble identifier different from the value received from the UE THEN: UE performs the Random Access Resource selection procedure for 2-step RA type Random Access after a random time between 0 and the indicated Backoff parameter multiplied with scalingFactorBI configured in the ra-PrioritizationForSlicing | Lenovo/Motorola Mobility | RAN5#100 (Aug-23) | R5-231264, R5-232182 | rasheed@motorola.com<rasheed@motorola.com> | 1 | 100% | 100% |  | 100% | 100%
RRC
13 |  | 38.523-1 | 8.1.1.3 | RRC release | <Describe required change of the existing test case> |  |  |  |  | TBD
14 | Y | 38.523-1 | 8.1.1.3.9 | RRC connection release / Success / With slice specific cell reselection information | **** TP1: [Ref: 38.304 clause 5.2.4.11, 38.331 clause 5.3.8.3] WITH: UE in RRC_IDLE state having received an RRCRelease message with slice specific cell reselection information WHEN: UE detects the cell reselection criteria is met for two cells on different frequencies supporting different NAS-provided NSAG priorities THEN: UE reselects to the cell on the frequency which supports higher priority NSAG **** TP2: [Ref: 38.304 clause 5.2.4.11, 38.331 clause 5.3.8.3] WITH: UE in RRC_IDLE state having received an RRCRelease message with slice specific cell reselection information WHEN: UE detects the cell reselection criteria is met for two cells on different frequencies supporting same NAS-provided NSAG priority THEN: UE reselects to the cell on the frequency which supports the NSAG having higher nsag-CellReselectionPriority **** TP3: [Ref: 38.304 clause 5.2.4.1, 38.331 clause 5.3.8.3] WITH: UE in RRC_CONNECTED state having received slice specific cell reselection information in SIB16 WHEN: UE receives RRCRelease including nsag-CellReselectionPriority THEN：UE shall ignore any fields with nsag-CellReselectionPriority provided in system information and stores new nsag-CellReselectionPriority in RRCRelease | CMCC | RAN5#100 (Aug-23) | R5-234723 | hanaitong@chinamobile.com Incomplete due to FR2 power level issue. | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
TS 38.523-2: Applicability for Protocol test cases
15 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add new ICS statements. | CMCC | RAN5#100 (Aug-23) | R5-230382, R5-231557, R5-233472, R5-234724 | hanaitong@chinamobile.com | 0.1 | 100% (+50%) | 100% (+50%) |  | 100% | 100%
16 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add test case applicability statements for the new test cases introduced in 38.523-1 | CMCC | RAN5#100 (Aug-23) | R5-230382, R5-231557 | hanaitong@chinamobile.com | 0.1 | 100% (+60%) | 100% (+60%) |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
17 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.