## Cover sheet
3GPP TSG RAN Meeting #101 | [10 empty] | RP-232258
Bangalore, India, Sep. 11th - 15th, 2023
Agenda Item: | 13.3.22
Source: | China Telecom
Title: | WP UE Conformance – Enhancement of Private Network Support for NG-RAN including CT aspects
Work item code: | NG_RAN_PRN_enh_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 45% (+37%) | 8 (+8) | 16 (-1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 44.6% (+36.9%) | 8 (+8) | 16 (-1)
FR1 |  | 44.6% (+36.9%) | 8 (+8) | 16 (-1)
FR2 |  | 44.6% (+36.9%) | 8 (+8) | 16 (-1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 95% (+5%) |  |  | 95% (+5%) |  |  | 95% (+5%)
Common ICS | 38.508-2 | 90% (+10%) |  |  | 90% (+10%) |  |  | 90% (+10%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 45.8% (+45.8%) | 8 (+8) | 16 (-1) | 45.8% (+45.8%) | 8 (+8) | 16 (-1) | 45.8% (+45.8%) | 8 (+8) | 16 (-1)
Applicability Protocol test cases | 38.523-2 | 40% (+40%) |  |  | 40% (+40%) |  |  | 40% (+40%)
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-221300 | New WID on UE Conformance – Enhancement of Private Network Support for NG-RAN including CT aspects, China Telecom, RAN#96, June 2022
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Enhancement of Private Network Support for NG-RAN including CT aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NG_RAN_PRN_enh_plus_CT-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Lei GAO |  |  | gaol8@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 44.6% (+36.9%) | 44.6% (+36.9%)
[14 empty] | 23 (-2) | 23 (-2)
[14 empty] | 26.2 (-4) | 26.2 (-4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4 | Introduction of General and Signaling Test Environment for Rel-17 eNPN Tests | ASN.1 updates (SIB1, SIB18, other messages) | China Telecom | RAN5#98 (Feb-23) | R5-231461 R5-231560 R5-233987 |  | 0.5 | 95% (+5%) | 95% (+5%) |  | 95% | 95%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.3.7 | Introduction of common implementation conformance statements for Rel-17 eNPN Tests Cases | eNPN PICS | China Telecom | RAN5#99 (May-23) | R5-233471 R5-235358 |  | 0.5 | 90% (+10%) | 90% (+10%) |  | 90% | 90%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Idle Mode
|  | 38.523-1 | 6.5.3 | SNPN Selection | New sub-clause header |  | TBD |  |  | 0
3 | Y | 38.523-1 | 6.5.3.1 | SNPN Selection in Manual Mode / Using credentials from a credentials holder | TS 23.122, cl 4.9.3.1.0 and 4.9.3.1.2 (1) with { UE in Manual network/SNPN selection mode and supports access to an SNPN using credentials from a credentials holder and an SNPN cell is available which does not support the access using credentials from a credentials holder } ensure that { when { UE is switched on or return to coverage } then { UE does not indicate to the user any available SNPNs } } (2) with { UE in Manual network/SNPN selection mode and supports access to an SNPN using credentials from a credentials holder } ensure that { when { an SNPN is available which broadcasts the indication that access using credentials from a credentials holder is supported } then { UE indicates to the user that an SNPN is available and user selects the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235359 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
4 | Y | 38.523-1 | 6.5.3.2 | SNPN Selection in Manual Mode / Onboarding services in SNPN | TS 23.122, cl 4.9.3.1.4 (1) with { UE in Manual network selection mode and an SNPN not supporting onboarding services is available } ensure that { when { UE is switched on or return to coverage } then { UE does not indicate to the user any available SNPN } } (2) with { UE in Manual network selection mode } ensure that { when { an SNPN indicating that onboarding is allowed is available and matches the onboarding SNPN selection information } then { UE indicates user the SNPN and user selects the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235360 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
5 | Y | 38.523-1 | 6.5.3.3 | SNPN Selection in Manual Mode / Switch to Automatic Mode | TS 23.122, cl 4.9.3.1.2 (1) with { UE in Manual network/SNPN selection mode and has registered on an SNPN cell which does not support emergency calls } ensure that { when { a different SNPN is available and user initiates an emergency call} then { UE automatically select the SNPN } } (2) with { UE in Manual network/SNPN selection mode and has registered on an SNPN cell } ensure that { when { a different SNPN is available and user initiates an emergency call and the registration request for emergency services is rejected by the network } then { UE automatically select the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235361 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
6 | Y | 38.523-1 | 6.5.3.4 | SNPN Selection in Automatic Mode / Onboarding services in SNPN | TS 23.122, cl 4.9.3.1.3 (1) with { UE in Automatic network selection mode and an SNPN supporting onboarding service is available which does not match the onboarding SNPN selection information } ensure that { when { UE is switched on or return to coverage } then { UE does not select the SNPN cell and continues searching for an allowable SNPN Cell } } (2) with { UE in Automatic network selection mode and Registration for onboarding services on an SNPN cell is unsuccessful } ensure that { when { an SNPN is available for which an entry exists in the "list of subscriber data" } then { UE performs SNPN selection not for onboarding services on the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235362 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
7 | Y | 38.523-1 | 6.5.3.5 | SNPN Selection in Automatic Mode / Using credentials from a credentials holder | TS 23.122, cl 4.9.3.1.1 (1) with { UE in Automatic network selection mode and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" } ensure that { when { SNPNs are available which broadcast the indication that access using credentials from a credentials holder is supported } then { UE selects a cell of the highest priority SNPN and UE attempts a registration on the selected cell } } (2) with { UE in Automatic network selection mode and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" } ensure that { when { SNPNs are available which broadcast the indication that access using credentials from a credentials holder is supported highest priority SNPN is not available} then { UE selects a cell of the next priority available SNPN and UE attempts a registration on the selected cell } } | Lenovo China Telecom | RAN5#100 (Aug-23) | R5-235364 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
8 | Y | 38.523-1 | 6.5.3.6 | SNPN / Limited service / No valid subscriber data | TS 23.122, cl 3.5 (1) with { UE in SNPN access mode and the "list of subscriber data" with no valid entry and UE is not configured with the default UE credentials } ensure that { when { an acceptable SNPN cell is available and UE needs to make a emergency call } then { UE selects the SNPN cell and attempts to camp on it } } (2) with { UE in SNPN access mode and the "list of subscriber data" with no valid entry and UE is configured with the default UE credentials } ensure that { when { an acceptable SNPN cell supporting onboarding services is available } then { UE selects the SNPN cell for onboardig services } } | Lenovo | RAN5#100 (Aug-23) | R5-235365 |  | 1 | 80% (+80%) | 80% (+80%) |  | 80% | 80%
9 | Y | 38.523-1 | 6.5.3.7 | SNPN / User Reselection in Automatic Mode / Using credentials from a credentials holder | TS 23.122, cl 4.9.3.2.1 (1) with { UE in Automatic SNPN selection mode and registered on an SNPN cell and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" or associated with the selected PLMN subscription } ensure that { when { another SNPN is available supporting access using credentials from a credentials holder or allow registration attempts from MSs that are not explicitly configured to select the SNPN and UE is requested to initiate reselection and registration onto an available SNPN } then { UE reselects the SNPN cell } } | Lenovo | RAN5#100 (Aug-23) | R5-235366 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
10 | Y | 38.523-1 | 6.5.3.8 | SNPN / cell reselection for IMS emergency services | TS 38.304, cl 5.2.8 (1) with { UE in SNPN access mode is in NR RRC_IDLE state and supports voice services } ensure that { when { UE receives SIB1 message indicating that the current cell does not support IMS voice calls for any SNPN(s) } then { UE perform cell selection/reselection to an acceptable cell of any available SNPN supporting emergency calls } } | Lenovo | RAN5#100 (Aug-23) | R5-235367 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
11 | Y | 38.523-1 | 6.5.3.9 | SNPN / cell reselection / SNPN to PLMN | TS 23.122, cl 3.5 (1) with { UE in SNPN access mode is in limited service state and supports accessing a PLMN } ensure that { when { UE needs to make an emergency call and there is no available SNPN supporting emergency services } then { UE stops operating in SNPN access mode and attempts to camp on a cell of a PLMN } } | Lenovo | RAN5#100 (Aug-23) | R5-235368 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TBD |  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 3 | 0% | 0% |  | 0% | 0%
RRC
|  | 38.523-1 | 8.1.7 | Non-public networks | Existing sub-clause header |  | RAN5#101 (Nov-23) |  |  | 0
13 |  | 38.523-1 | 8.1.7.2 | RRC connection establishment | New sub-clause header |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
14 | Y | 38.523-1 | 8.1.7.2.1 | RRC connection establishment / RRC setup complete with onboarding request | TS 38.331, cl 5.3.3.4 (1) with { UE is in SNPN access mode and receives SIB1 message } ensure that { when { UE upper layers provide onboarding request indication and SIB1 message indicating that registration for onboarding in the cell is supported } then { UE includes the onboardingRequest in RRCSetupComplete message upon reception of the RRCSetup message } } | China Telecom | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
15 |  | 38.523-1 | 8.1.7.3 | PWS notification | New sub-clause header |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
16 | Y | 38.523-1 | 8.1.7.3.1 | PWS notification / PWS reception in NR RRC_IDLE state / Accesses an SNPN using the PLMN subscription |  | China Telecom | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
17 | Y | 38.523-1 | 8.1.7.3.2 | PWS notification / PWS reception in NR RRC_IDLE state / Accesses an SNPN using entries in the "list of subscriber data" | Existing sub-clause header | China Telecom | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0% | 0%
NAS
TBD |  | 38.523-1 | 9.1.11 | SNPN / Mobility management aspects |  |  | TBD |  |  | 0
18 | Y | 38.523-1 | 9.1.11.4 | SNPN / Initial registration / Rejected / Temporarily not authorized for this SNPN / UE supporting using credentials from a credentials holder |  |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
19 | Y | 38.523-1 | 9.1.11.5 | SNPN / Initial registration / Rejected / Temporarily not authorized for this SNPN / UE supporting onboarding services in SNPN |  |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
21 | Y | 38.523-1 | 9.1.11.6 | SNPN / EAP based primary authentication and key agreement / EAP-AKA' related procedures / UE supporting using credentials from a credentials holder |  |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
22 | Y | 38.523-1 | 9.1.11.7 | SNPN / EAP based primary authentication and key agreement / EAP-AKA' related procedures / UE supporting onboarding services in SNPN |  |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | China Telecom | RAN5#100 (Aug-23) | R5-235363 |  | 3 | 40% (+40%) | 40% (+40%) |  | 40% | 40%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | TBD |  |  |  | 3 | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.