## Cover sheet
3GPP TSG-RAN5 Meeting #100 | [10 empty] | R5-235064
Toulouse, France, Aug. 21-25, 2023
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | UE Conformance - Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n257 and n258
Work item code: | NR_FR2_FWA_Bn257_Bn258-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID on Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n257 and n258 with Unique Identifier 870064, analysing the test case impact, applicability, test environment, and updating the relevant conformance specifications for the work item in Rel-17.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 30% (+6%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 30% (+6.2%)
FR1
FR2 |  | 30% (+6.2%)
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
LTE
FDD
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 50% | [5 empty] | 50%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx | 20% (+11.7%) | [5 empty] | 20% (+11.7%)
FR2 RF Rx test cases | 38.521-2 Rx | 100% | [5 empty] | 100%
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 0% | [5 empty] | 0%
RRM test cases | 38.533 | 0% | [5 empty] | 0%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% | [5 empty] | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 57.5% (+2.5%) | [5 empty] | 57.5% (+2.5%)
Test Point analysis receiver and transmitter test cases | 38.905 | 0% | [5 empty] | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n257 and n258 | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_FR2_FWA_Bn257_Bn258-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to WID on Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n257 and n258 with Unique Identifier 870064, analysing the test case impact, applicability, test environment, and updating the relevant conformance specifications for the work item in Rel-17. | [14 empty] | vs Area
WP Resp: |  | Yuxin Hao |  |  | haoyuxin<haoyuxin@huawei.com> | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  |  | 30% (+6.2%)
[14 empty] | Number of WP items |  | 0 | 47 (+1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Sum weight of WP items |  | 0 | 45.1 (+1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-2: Common ICS
|  | 38.508-2 | A.4.3 | Baseline Implementation Capabilities
1 |  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introducing PICS for PC5 for n257 and n258 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
42 |  | 38.508-2 | A.4.3.9 | RF Baseline Implementation Capabilities | Optional vendor declaration for PC5 antenna array configura |  | TBD |  |  | 1 | 100% | 100% |  |  |  |  | 100%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx | 6.2 | Transmit power
2 |  | 38.521-2 Tx | 6.2.1.0 | General | Updating Table 6.2.1.0-1 for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
3 |  | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | Updating minumum requirement and testing requirements for PC5 | Keysight | TBD | R5-233631 |  | 1 | 100% | 100% |  |  |  |  | 100%
4 |  | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | Updating test case for PC5 | Keysight | TBD | R5-233631 |  | 1 | 100% | 100% |  |  |  |  | 100%
5 |  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | Updating minumum requirement and testing requirements for PC5 | Keysight | TBD | R5-235746 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  |  | 100%
6 |  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | Updating minimum requirement and test requirement for PC5 for NS_202, NS_203 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.521-2 Tx | 6.2A | Transmit power for CA
7 |  | 38.521-2 Tx | 6.2A.2.0 | Minimum conformance requirements | Adding minimum requirements for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
8 |  | 38.521-2 Tx | 6.2A.2.1 | UE maximum output power reduction for CA (2UL CA) | Updating test configuration and test requriement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
9 |  | 38.521-2 Tx | 6.2A.3.0 | Minimum conformance requirements | Adding minimum requirements for PC5 for NS_202, NS_203 |  | TBD |  | FFS test case in 38521-2 | 1 | 0% | 0% |  |  |  |  | 0%
10 |  | 38.521-2 Tx | 6.2A.3.1 | UE maximum output power with additional requirements for CA (2UL CA) | Updating test case for PC5 for NS_202, NS_203 |  | TBD |  | FFS test case in 38521-2 | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.521-2 Tx | 6.2D | Transmit power for UL MIMO
11 |  | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP for UL MIMO | Updating minimum requirement and test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
12 |  | 38.521-2 Tx | 6.2D.1.2 | UE maximum output power - Spherical coverage for UL MIMO | Updating test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
13 |  | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
14 |  | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements for UL MIMO | Updating minimum requirements for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.521-2 Tx | 6.3 | Output power dynamics
15 |  | 38.521-2 Tx | 6.3.1 | Minimum output power | Updating minimum requirement and test requirement for PC5 | Keysight | TBD | R5-235746 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  |  | 100%
|  | 38.521-2 Tx | 6.3A | Output power dynamics for CA
16 |  | 38.521-2 Tx | 6.3A.1.0 | Minimum conformance requirements | Updating minimum requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
17 |  | 38.521-2 Tx | 6.3A.1.1 | Minimum output power for CA (2UL CA) | Updating test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.521-2 Tx | 6.4 | Transmit signal quality
18 |  | 38.521-2 Tx | 6.4.2.1 | Error vector magnitude | Updating minimum requirement and test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
19 |  | 38.521-2 Tx | 6.4.2.2 | Carrier leakage | Updating minimum requirement and test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
20 |  | 38.521-2 Tx | 6.4.2.3 | In-band emissions | Updating minimum requirement and test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.521-2 Tx | 6.4A | Transmit signal quality for CA
21 |  | 38.521-2 Tx | 6.4A.2.2.0 | Minimum conformance requirements | Updating minimum requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
22 |  | 38.521-2 Tx | 6.4A.2.2.1 | Carrier leakage for CA (2UL CA) | Updating test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
23 |  | 38.521-2 Tx | 6.4A.2.3.0 | Minimum conformance requirements | Updating minimum requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
24 |  | 38.521-2 Tx | 6.4A.2.3.1 | In-band emissions for CA (2UL CA) | Updating test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
24 |  | 38.521-2 Tx | 6.5.2.3 | Adjacent channel leakage ratio | Updating test case for PC5 | Keysight | TBD | R5-235746 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  |  | 100%
|  | 38.521-2 Tx | 6.6 | Beam correspondence
25 |  | 38.521-2 Tx | 6.6.1 | Beam correspondence - EIRP | Updating minimum requirement and test requirement for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx | 7.3 | Reference sensitivity
26 |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | Updating minimum requirement and test requirement for PC5 |  | TBD | R5-231775 |  | 1 | 100% | 100% |  |  |  |  | 100%
27 |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | Updating minimum requirement and test requirement for PC5 |  | TBD | R5-231775 |  | 1 | 100% | 100% |  |  |  |  | 100%
TS 38.521-2: FR2 RF test cases - Common clause
43 |  | 38.521-2 Annex | F.1.2/F.1.3 | Measurement of receiver | Updating MU/TT analysis for PC5 | Keysight | TBD | R5-231775 R5-235746 |  | 1 | 15% (+5%) | 15% (+5%) |  |  |  |  | 15%
44 |  | 38.521-2 Annex | F.3.2/F.3.3 | Measurement of receiver | Updating MU/TT analysis for PC5 | Keysight | TBD | R5-231775 R5-235746 |  | 1 | 15% (+5%) | 15% (+5%) |  |  |  |  | 15%
45 |  | 38.521-2 Annex | M.2 | Beam Peak Search Grid | Define PC5 measurement grids |  | TBD | R5-231776 |  | 1 | 100% | 100% |  |  |  |  | 100%
46 |  | 38.521-2 Annex | M.3 | Spherical Coverage Grid | Define PC5 measurement grids |  | TBD | R5-231776 |  | 1 | 100% | 100% |  |  |  |  | 100%
47 |  | 38.521-2 Annex | M.4 | TRP Measurement Grid | Define PC5 measurement grids |  | TBD | R5-231776 |  | 1 | 100% | 100% |  |  |  |  | 100%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 | 4.5.3 | Noc
28 |  | 38.521-4 | 4.5.3.2 | Noc for NR operating bands in FR2 | Updating Table 4.5.3.2-1 for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | 4 | Recommended test case applicability
29 |  | 38.522 | 4 | Test case conditions and selection criteria | Add new ICS statements for PC5 if needed |  | TBD |  |  | 0.1
30 |  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Updating testing selection criteria for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
31 |  | 38.522 | 4.2 | RRM conformance test cases | Updating testing selection criteria for PC5 |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 | 3A.4 | NR band groups
32 |  | 38.533 | 3A.4.2 | NR operating bands in FR2 | Updating for n257, n258 for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.533 | A.9 | Angle of Arrival (AoA) for FR2 RRM test cases
33 |  | 38.533 | A.9.3 | Setup 3: 2 AoAs | Updating Table A.9.3-1 for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.533 | B.1 | Conditions for NR RRC_IDLE state mobility
34 |  | 38.533 | B.1.2 | Conditions for measurements on NR intra-frequency cells for cell re-selection | Updating for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
|  | 38.533 | B.2 | Conditions for NR RRC_CONNECTED state
35 |  | 38.533 | B.2.2 | Conditions for NR intra-frequency measurements | Updating for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
36 |  | 38.533 | B.2.3 | Conditions for NR inter-frequency measurements | Updating for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
37 |  | 38.533 | B.2.4 | Conditions for NR L1-RSRP reporting | Updating for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
38 |  | 38.533 | B.2.5 | Conditions for RRC connection release with redirection to NR | Updating for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
39 |  | 38.533 | B.2.6.1 | Conditions for SSB based UE transmit timing | Updating for PC5 |  | TBD |  |  | 1 | 0% | 0% |  |  |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
40 |  | 38.903 | B.2 | Measurement error contribution descriptions | Updating FR2 MU calculating for PC5 | Keysight | TBD | R5-233639 | B.2.2.36 is not updated for PC5 yet | 0.5 | 90% | 90% |  |  |  |  | 90%
48 |  | 38.903 | B.x | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | Updating MU threshold for PC5 for test cases | Keysight | TBD | R5-230180 R5-233632 R5-233977 | This item is updated to include MU updating for bunch of test cases. | 0.5 | 25% (+5%) | 25% (+5%) |  |  |  |  | 25%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 | 4 | Test coverage analysis
41 |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-3 | Updating TP analysis for NS_202, NS_203 |  | TBD |  |  | 0.1 | 0% | 0% |  |  |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.