## Slide 1: NTN Testing work for NGSO deployments
Sateliot, Novamint, GateHouse

## Slide 2: Situation
NGSO support in NR NTN & IoT NTN
  Work conducted in Rel-17 and Rel-18 in RAN1/2/3 for NR NTN & IoT NTN includes explicitly both GSO and NGSO
  Corresponding work in RAN4/RAN5 for both NR NTN & IoT NTN include as well both GSO and NGSO
  LS between RAN5 & RAN4 in the last 2 meetings (May & Aug) identified that additional work is needed, first in RAN4 and then in RAN5, to support properly NGSO:
    In particular introducing new TE-emulated channel model with Doppler and delay shifts matching the satellite propagator model, ensuring that only the correctly-implemented UEs can pass the NGSO test cases
  NGSO support is a key requirement for inclusion of NR NTN & IoT NTN in satellite "IMT 2020"
Market situation
  Several Rel-17 based NGSO commercial deployments are ongoing (IoT & NR NTN)
  Non 3GPP based NGSO deployment are already there or moving fast
  For IoT NTN, the perspective is even more urgent:
    There is a market requiring both GSO and NGSO solutions from 3GPP - focus is NB-IoT
    Rel-17 based IoT NTN NGSO deployments are targeting to be commercial in first half 2024
  3GPP ecosystem is ready to push for both GSO and NGSO solutions
Therefore, it is urgent to address NTN Testing work for NGSO deployments in RAN4 & RAN5 within the current release

## Slide 3: Situation Assessment
 |  | WID completion date | Current situation (Sept 23)
Completion rate | GSO Support | NGSO support
RAN4 | Core + Perf | NR NTN Rel-17 | Mar-23 | 100% | Likely yes but FFS in RAN4 the applicability of Zero-Doppler in RRM TCs and Frequency Error TC | NO RAN4 recognized Zero-doppler conditions are not applicable for RRM TCs. Missing definition of TE-emulated channel model with Doppler/Delay shifts
IoT NTN Rel-18 (NOTE1) | Jun-23 | 100%
RAN5 | SIG | NR NTN Rel-17 | Dec-23 | 50% (Overall) | Yes (TBC) | Yes (TBC)
IoT NTN Rel-17 | Sep-23 -> Dec-23 | 98% | Yes | Yes
RF | NR NTN Rel-17 | Dec-23 | 50% (Overall) | Pending RAN4 addressing FFS issues (Dependency from RAN4) | NO (Dependency from RAN4)
IoT NTN Rel-18 (NOTE1) | Dec-23 | 46 % (62% for NB-IoT)
RAN5 SIG Test Specs
=> IoT NTN for both GSO and NGSO expected to be completed by Dec-23
(Delay of 3 months)
⇒ NR NTN for both GSO/NGSO expected to be completed by Dec-23 (No delay reported but completion is only at 50%)
RAN 5 RF/RRM/Demod Test Specs
=> Gaps detected in completed RAN4 work for testing NGSO cases. Applies to both NR and IoT NTN.
=>A few FFS detected in completed RAN4 work for testing GSO cases. Applies to both NR and IoT NTN.
⇒ Within IoT NTN, completion rate of NB-IoT test cases is 62%, while completion rate when considering eMTC is 46%.
=>RISK: Completion by Dec-23 for all the items (i.e. NR NTN and IoT NTN, including GSO and NGSO) is at stake
SITUATION ASSESSMENT
NOTE 1: Release-independent from Rel-17
RAN4&RAN5 interaction documents on NTN testing: R4-2314001, R5-235817
Notes: Rel-18 LTE_NBIOT_eMTC_NTN_req (RAN4-led)
(Release-independent from Rel-17)
-RAN4 Core part 100% completed in Dec-22
-RAN4 Perf part 100% completed in June-23
Rel-17 NR_NTN_solutions
-RAN4 NR_NTN_solutions-Core: 100% completed in Jun-22
-RAN4 NR_NTN_solutions-Perf: 100% completed in Mar-23

## Slide 4: Way Forward
RAN4 needs to work/complete work on identified missing points raised by RAN5 (e.g. TE-emulated channel model) to complete NTN testing specs within the current considered release and without long gap (one quarter) between GSO and NGSO support.
RAN5 and RAN4 should strengthen cooperation to complete all the work by Mar-24.
  There are 2 RAN4 meetings in Q4 23 (RAN4#108-bis, RAN4#109) and 1 RAN4 meeting in Q1 24 (RAN4#110)
  There are 1 RAN5 meeting in Q4 23 (RAN5#101) and 1 RAN5 meeting in Q1 24 (RAN5#102)
  If well coordinated, it should be possible to complete the remaining work for RAN4 in 3 meetings and for RAN5 in 2 meetings
    Coordination can be done before each meeting (RAN4 & RAN5) in order to bring consolidated work at the meetings
    Coordination in the form of joint sessions between RAN5 and RAN4 is also needed in November’s meeting (RAN4#109 & RAN5#101) and in February’ meeting (RAN4#110 & RAN5#102)
  Several satellite companies are already committed to put more resources in RAN4 & RAN5, in particular to support the work on NGSO testing issues

## Slide 5: Potential timelines
RAN
Sept 23 Oct 23 Nov 23 Dec 23 Jan 24 Feb 24 Mar 24 Apr 24 May 24 Jun 24
RAN#101
RAN#102
RAN#103
RAN#104
RAN4#110
RAN4#109
RAN4#108b
RAN5#102
RAN5#101
RAN4
RAN5
Joint Session
RAN4/RAN5
Joint Session
RAN4/RAN5
GSO support completed
for NR NTN & IoT NTN
NGSO support completed
for NR NTN & IoT NTN

## Slide 6: Proposals
RAN4
Proposal 1: RAN to mandate RAN4 to complete missing work (e.g. frequency error testing configurations, TE-emulated channel model with doppler/freq shifts) for IoT NTN & NR NTN by RAN#103 (Mar-24)
RAN4 & RAN 5 Nov 23 & Feb 24
Proposal 2: Coordination between RAN4 & RAN5 is needed in November 23 and in February 2024 - Joint sessions RAN4-RAN5 to be planned in Nov 23 and Feb 24 to provide status on each issue identified and define what is expected on both sides on NTN testing work
RAN5
Proposal 3: RAN to mandate RAN5 to complete work for IoT NTN & NR NTN on GSO by RAN#102 (Dec 23) and on NGSO by RAN#103 (Mar-24)
RAN
Proposal 4: Reassess the situation at RAN#102 and if timelines are at risk, prioritize technologies in line with respective technical completion rates and market needs
Notes: Expectation: endorsement from the plenary
P2 not clear how should be formulated (TBD). Clarify objectives of the joint sessions.
Warning: Agenda Item 13.4.1 is RAN5-related.

## Slide 7: Additional material

## Slide 8: Responses in the LS Replay
Source: R4-2314001