## Band combination table
Are there any change marks? (More explaination can be found in coversheet) | Band combination configuration | UpLink configuration | BCS | Subclass | Contact Name | Contact Company | Contact Email | Other supporting companies (min.3) | RAN Plenary in which the conbination was requested | Related WI (acronym) | Supported next level fallback modes including status (in DL and UL) | Status (New,Ongoing,Completed,Stopped) | TR# | TPs provided as input for TR | CRs provided to RAN | Core part Done? yes/no | Perf. part Done? yes/no | Open issues/Comments | Note
Unchange | CA_n66(2A) | CA_n66(2A) | 2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#89 | NR_CA_R17_intra-Core | (new) DL_n66(2A)_BCS2 | Ongoing |  |  |  | No | No
Unchange | CA_n66(3A) | CA_n66(2A) | 0 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#89 | NR_CA_R17_intra-Core | (new) DL_n66(3A)_BCS0 (new) DL_n66(2A)_UL_n66(2A)_BCS2 | Ongoing |  |  |  | No | No
Unchange | CA_n66(A-B) | CA_n66A CA_n66B | 0 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#89 | NR_CA_R18_Intra-Core | (Complete) DL_n66(2A)_UL_n66A (Complete) DL_n66(2A)_UL_n66A | Ongoing |  |  |  | No | No
Unchange | CA_n46C | CA_n46C | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n46C_UL_n46A_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n258(A-H) | - | 0 | Only FR2 | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n258H_BCS0 (New) DL_n258(A-G)_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n258(G-H) | - | 0 | Only FR2 | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n258(2G)_BCS0 (New) DL_n258(A-H)_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n66B | CA_n66B | 0 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#97 | NR_CA_R18_Intra | (Complete) DL_n66B_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n96B | CA_n96B | 0 | Only FR1 | Frank Azcuy | Charter Communications Inc. | Fank.Azcuy@charter.com | Qorvo, Cable Labs, Comcast | RAN#99 | NR_CA_R18_Intra | none | Ongoing |  |  |  | No | No
Unchange | CA_n96C | CA_n96C | 0 | Only FR1 | Frank Azcuy | Charter Communications Inc. | Fank.Azcuy@charter.com | Qorvo, Cable Labs, Comcast | RAN#99 | NR_CA_R18_Intra | none | Ongoing |  |  |  | No | No
Unchange | CA_n48(2A) | n48(2A) | 1 | Only FR1 | Yuanyuan Zhang | Samsung | tina55.zhang@samsung.com | Dish, Ericsson,Mediatek,OPPO, Fujitsu | RAN#100 | NR_CA_R18_intra | - | Ongoing |  |  |  | No | No
Unchange | CA_n48(3A) | n48(2A) | 1 | Only FR1 | Yuanyuan Zhang | Samsung | tina55.zhang@samsung.com | Dish, Ericsson,Mediatek,OPPO, Fujitsu | RAN#100 | NR_CA_R18_intra | (new)n48(2A) | Ongoing |  |  |  | No | No
Unchange | CA_n48(4A) | n48(2A) | 1 | Only FR1 | Yuanyuan Zhang | Samsung | tina55.zhang@samsung.com | Dish, Ericsson,Mediatek,OPPO, Fujitsu | RAN#100 | NR_CA_R18_intra | (new)CA_n48(3A) | Ongoing |  |  |  | No | No
Unchange | CA_n66(2A) | CA_n66(2A) | BCS1 | Only FR1 | Yuanyuan Zhang | Samsung | tina55.zhang@samsung.com | Dish, Fujitsu, Mediatek | RAN#101 | NR_CA_R18_intra | (completed) DL_n66(2A)_UL_n66A | Ongoing |  |  |  | No | No
Unchange | CA_n66(3A) | CA_n66(2A) | BCS1 | Only FR1 | Yuanyuan Zhang | Samsung | tina55.zhang@samsung.com | Dish, Fujitsu, Mediatek | RAN#101 | NR_CA_R18_intra | (completed) DL_n66(3A)_UL_n66A | Ongoing |  |  |  | No | No
New | CA_n3B | CA_n3B | 4 and 5 | Only FR1 | Charley Cao | Telstra | charley.cao@team.telstra.com | Ericsson, Nokia, LGE | RAN#102 | NR_CA_R18_intra | (completed) DL_n3B_UL_n3A | New
New | CA_n39(2A) | - | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | none | New
New | CA_n39(2A) | CA_n39(2A) | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | (new)DL CA_n39(2A) UL n39A | New
New | CA_n40(2A) | - | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | none | New
New | CA_n40(2A) | CA_n40(2A) | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | (new)DL CA_n40(2A) UL n40A | New
New | CA_n40C | - | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | none | New
New | CA_n40C | CA_n40C | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | (new)DL CA_n40C UL n40A | New
New | CA_n79(2A) | - | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | none | New
New | CA_n79(2A) | CA_n79(2A) | 4 and 5 | Only FR1 | Ziwei Chen | CMCC | chenziwei@chinamobile.com | Huawei, HiSilicon, ZTE Corporation, CATT | RAN#102 | NR_CA_R18_intra | (new)DL CA_n79(2A) UL n79A | New
New | CA_n257(A-G) | CA_n257(A-G) | 0 | Only FR2 | Wubin Zhou | ZTE | zhou.wubin@zte.com.cn | CKH IOD UK, Ericsson, Sanechips | RAN#102 | NR_CA_R18_intra-Core | (completed) DL_n257(A-G)_UL_n257G | New
New | CA_n258(A-G) | CA_n258(A-G) | 0 | Only FR2 | Wubin Zhou | ZTE | zhou.wubin@zte.com.cn | CKH IOD UK, Ericsson, Sanechips | RAN#102 | NR_CA_R18_intra-Core | (completed) DL_n258(A-G)_UL_n258G | New